## Central report
Last Update | 2026-09-12 | [47 empty] | IFERROR(VLOOKUP(B3,'[Finish Fabric Plan & Execution Status.xlsx]Tracking Sheet'!$B$4:$E$15000,2,0),0) | IFERROR(VLOOKUP(B3,'[Finish Fabric Plan & Execution Status.xlsx]Tracking Sheet'!$B$4:$E$15000,3,0),0) |  | IFERROR(VLOOKUP(B3,'[Cutting, Print & InpSummary.xls]Tracking Sheet'!$B$2:$G$10000,2,0),0) |  |  | IFERROR(VLOOKUP(B3,'[Cutting, Print & InpSummary.xls]Tracking Sheet'!$B$2:$G$10000,3,0),0) | IFERROR(VLOOKUP(B3,'[Cutting, Print & InpSummary.xls]Tracking Sheet'!$B$2:$G$10000,4,0),0) |  |  |  |  | IFERROR(VLOOKUP(B3,'\\192.168.100.54\mis\Report\Daily Report\Daily Production Summary\[Production Summary.xlsx]Tracking Sheet'!$B$2:$E$5000,3,0),0) |  | IFERROR(VLOOKUP(B3,'\\192.168.100.54\mis\Report\Daily Report\Daily Production Summary\[Production Summary.xlsx]Tracking Sheet'!$B$2:$E$5000,4,0),0)
Buyer | Job | Style | Order Qty | Fabric Req. (in Kg) | PO Received Date | T & A Plan Date | Item Description | Item | Yarn Dyeing T & A Start | Yarn Dyeing T & A End | Knitting T & A Start | Knitting T & A End | Dyeing -Finishing T & A Start | Dyeing-Finishing T & A End | All Over Print T & A Start | All Over Print T & A End | Trims & Accessories T & A End | Production & Other File Handover Date | PP Meeting Date | Cutting T & A Start | Cutting T & A End | Printing T & A Start | Printing T & A End | Stone/Parl Att. T & A Start | Stone/Parl Att. T & A Emd | Emb/Sequins/Arrey Emb T & A Start | Emb/Sequins/Arrey Emb T & A End | Sewing T & A Start | Sewing T & A End | Garments Washing/ Dyeing T & A Start | Garments Washing/ Dyeing T & A End | Iron, Folding,Packing & Finishing T & A End | Pre-final Inspection Date | Final Inspection | Ex-Factory Date | Cargo Closing Date | Total Lead Time (In Days) | Line | Merchandiser Name | Print Position | Embriodary Position | Print & Emb Description | Fabric Embllishment | Remarks | Floor | PP Status | PP sent date | PRESENT STATUS | Fabric Req. (in Kg) | Fabric Received | Fabric Balance | Cutting Qty | Cutting Balance | Print/Embr. Require | Print Send | Print rcvd | Recv balance | Ready for Input | Input Qty | Input Balance | Packing Qty | Packing Balance | Ship Qty | Ship Balance | Week | Slot | Sewing lead time | GMT Lead time | File Rcvd Date
BS-ONS | 26827 49th | 22029225 | 6000 | 5374 | 2025-11-27 | 2025-12-06 | MENS LS SWT HOODIE W KANGAROO PKT & ROUND STRING BTM CUFF | HOODY |  |  | 2026-01-25 | 2026-02-10 | 2026-02-20 | 2026-03-14 |  |  | 2026-05-02 | 2026-05-02 |  | 2026-05-14 | 2026-05-20 | [6 empty] | 2026-06-06 | 2026-06-13 |  |  | 2026-06-16 | 2026-06-18 | 2026-06-20 | 2026-06-29 | 2026-07-01 | 214 | R | Shakel | [5 empty] | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -6000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46073 | 0 | 27 | May'2 |  |  | 19.01.26
BS-ONS | 30730 3rd | 22030142 | 1733 | 1137 | 2025-12-10 | 2025-12-12 | Long pant w pkt string | Pant |  |  | 2026-02-02 | 2026-02-10 | 2026-02-20 | 2026-03-07 |  |  | 2026-03-13 | 2026-03-13 | 2026-03-30 | 2026-04-03 | 2026-04-04 | 2026-04-06 | 2026-04-08 |  |  | 2026-04-07 | 2026-04-10 | 2026-04-13 | 2026-04-16 |  |  | 2026-04-20 | 2026-04-22 | 2026-04-27 | 2026-07-20 | 2026-07-22 | 222 | B | Shakel | Thigh | Patch | spruce-1740 pcs 1 clr rub print & patch attach at emb |  |  | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1733 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46073 | 0 | 30 | Apr'1 |  |  | 07.03.26
BS-ONS | 45964 5th | 22039968 | 9000 | 6344 | 2026-01-20 | 2026-01-21 | LS High nk Haalf Zipp Swt shirt | Swt Shirt |  |  | 2026-02-18 | 2026-03-05 | 2026-03-12 | 2026-04-10 |  |  | 2026-04-18 | 2026-04-18 |  | 2026-04-24 | 2026-04-29 | [6 empty] | 2026-05-02 | 2026-05-12 |  |  | 2026-05-15 | 2026-05-18 | 2026-05-20 | 2026-07-06 | 2026-07-08 | 167 | C | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -9000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46093 | 0 | 28 | Apr'3 |  |  | 07.03.26
BS-NMT | 46724 | 13239294 | 5331 | 866 | 2026-01-07 | 2026-01-19 | LS o nk TS | TS |  |  | 2026-02-07 | 2026-02-15 | 2026-02-23 | 2026-03-09 |  |  | 2026-03-13 | 2026-03-13 | 2026-03-28 | 2026-04-01 | 2026-04-03 | 2026-04-04 | 2026-04-07 |  |  | 2026-04-04 | 2026-04-10 | 2026-04-13 | 2026-04-17 |  |  | 2026-04-20 | 2026-04-22 | 2026-04-25 | 2026-06-29 | 2026-07-01 | 173 | ZA1 | Sabikun | Nk | Chest | c.dancer-1785 pcs,,piroeute-1929 pcs,,black-1617 pcs all combo 1 clr flip sequin emb |  | Outlet | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -5331 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46076 | 0 | 27 | Apr'1 |  |  | 01.04.26
BS-NMT | 46725 | 13251383 | 2948 | 361 | 2026-01-07 | 2026-01-19 | LS o nk TS w shlder flounce | TS |  |  | 2026-02-04 | 2026-02-10 | 2026-02-23 | 2026-03-10 |  |  | 2026-03-13 | 2026-03-13 | 2026-03-30 | 2026-04-01 | 2026-04-02 | 2026-04-06 | 2026-04-10 |  |  |  |  | 2026-04-13 | 2026-04-16 |  |  | 2026-04-18 | 2026-04-21 | 2026-04-23 | 2026-06-29 | 2026-07-01 | 173 | T2 | Sabikun | Chest,Nk |  | c.dancer-1474 pcs,,Navy-1474 pcs both combo 1 clr gltr print |  | Outlet | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2948 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46076 | 0 | 27 | Apr'1 |  |  | 01.04.26
BS-NMT | 46726 | 13261163 | 1620 | 220 | 2026-01-07 | 2026-01-19 | LS o nk TS w shlder flounce | TS |  |  | 2026-02-14 | 2026-02-18 | 2026-03-01 | 2026-03-13 |  |  | 2026-03-27 | 2026-03-27 | 2026-04-02 | 2026-04-04 | 2026-04-06 | 2026-04-08 | 2026-04-10 |  |  |  |  | 2026-04-14 | 2026-04-15 |  |  | 2026-04-17 | 2026-04-20 | 2026-04-24 | 2026-06-29 | 2026-07-01 | 173 | T2 | Sabikun | Chest,Nk |  | c.dancer-810 pcs,,Navy-810 pcs both combo 1 clr gltr print |  | Outlet | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1620 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46082 | 0 | 27 | Apr'1 |  |  | 01.04.26
BS-ONL | 29402 41th | 15312874 | 6048 | 3425 | 2026-01-22 | 2026-01-28 | LS Swt hoodie w drawstring | Hoody |  |  | 2026-02-20 | 2026-03-03 | 2026-03-05 | 2026-03-31 |  |  | 2026-04-01 | 2026-04-01 |  | 2026-04-08 | 2026-04-11 |  |  |  |  | 2026-04-13 | 2026-04-16 | 2026-04-20 | 2026-04-23 |  |  | 2026-04-25 | 2026-04-29 | 2026-05-05 | 2026-06-29 | 2026-07-01 | 158 | E | Imran |  | Chest,Pkt | corntalk-3024 pcs,,laurel-3024 pcs both combo chest and btm side 1 CLR FLAT EMB |  |  | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -6048 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46086 | 0 | 27 | Apr'1 |  |  | 03.03.26
OVS SPA | 46758 | 262TRO046-222 | 6776 | 3557 | 2026-01-21 | 2026-02-02 | Legging w pleat and side pkt | Legging |  |  | 2026-04-20 | 2026-05-05 | 2026-05-05 | 2026-05-20 |  |  | 2026-06-10 | 2026-05-22 | 2026-06-08 | 2026-06-09 | 2026-06-11 |  |  | 2026-06-12 | 2026-06-16 | 2026-06-16 | 2026-06-22 | 2026-06-22 | 2026-06-30 |  |  | 2026-07-01 | 2026-07-03 | 2026-07-06 | 2026-07-13 | 2026-07-13 | 173 | H | Shaker | Stone | Thigh | Fig-6776 pcs applique emb at thigh and HP stone at thigh |  |  | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -6776 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46147 | 0 | 29 | Jun'1 |  |  | 25.05.26
OVS SPA | 46754 | 262SWT024-222 | 5746 | 2591 | 2026-01-21 | 2026-02-02 | LS drop shlder Swt hoody w kangaroo pkt | Hoody |  |  | 2026-04-01 | 2026-04-15 | 2026-04-16 | 2026-05-05 |  |  | 2026-06-10 | 2026-05-09 | 2026-05-20 | 2026-05-21 | 2026-05-23 | 2026-06-05 | 2026-06-11 | 2026-06-11 | 2026-06-15 | 2026-06-15 | 2026-06-20 | 2026-06-20 | 2026-06-30 |  |  | 2026-07-01 | 2026-07-03 | 2026-07-06 | 2026-07-13 | 2026-07-13 | 173 | N/2 | Shaker | Chest,Stone | Fr & Bk | Fig-5746 pcs frt 1 clr rub print back no print & frt back applique emb and frt back pkt Stone HP |  |  | NCL |  |  | Ready Test Cut | 1317 | 1317 | 0 | 0 | -5746 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46128 | 0 | 29 | May'3
OVS SPA | 46755 | 262SWT028-222 | 6501 | 2930 | 2026-01-21 | 2026-02-02 | LS Swt shirt w back pleat and slve frings | Swt Shirt |  |  | 2026-05-04 | 2026-05-15 | 2026-06-05 | 2026-06-20 |  |  | 2026-07-06 | 2026-07-04 | 2026-07-09 | 2026-07-10 | 2026-07-13 | [6 empty] | 2026-07-15 | 2026-07-24 |  |  | 2026-07-25 | 2026-07-27 | 2026-07-30 | 2026-08-05 | 2026-08-05 | 196 | N/3 | Shaker |  |  |  |  | Imp frings | NCL |  |  | Ready Test Cut | 2931 | 2931 | 0 | 0 | -6501 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46178 | 0 | 32 | Jul'1
BS-ONS | 45456 2nd | 22039477 | 2346 | 561 | 2026-02-14 | 2026-02-17 | SS o nk TS | TS |  |  | 2026-03-06 | 2026-03-12 | 2026-04-01 | 2026-04-13 |  |  | 2026-05-12 | 2026-05-12 | 2026-05-18 | 2026-05-20 | 2026-05-22 | 2026-06-08 | 2026-06-13 |  |  |  |  | 2026-06-17 | 2026-06-20 |  |  | 2026-06-23 | 2026-06-25 | 2026-06-29 | 2026-08-17 | 2026-08-19 | 184 | D1 | Shovon | FR,BK |  | Coconut spuce-1443 pcs frt back 8 clr pig print ,coconut pole-903 pcs frt back 2 clr pig print |  |  | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2346 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46113 | 0 | 34 | May'2 |  |  | 30.04.26
UTG-AF | 44278 3rd | BAD2916B | 1500 | 311 | 2026-02-09 | 2026-02-19 | LDS WIDE RIB TOP W FRILL | DRESS |  |  | 2026-06-05 | 2026-06-15 | 2026-06-16 | 2026-06-25 |  |  | 2026-07-10 | 2026-07-11 |  | 2026-07-16 | 2026-07-17 | [6 empty] | 2026-07-20 | 2026-07-23 |  |  | 2026-07-24 | 2026-07-27 | 2026-07-29 | 2026-08-08 | 2026-08-10 | 180 | N/3 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 311 | 311 | 0 | 0 | -1500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46189 | 0 | 33 | Jul'2
OVS SPA | 46880 | 262TSH320-227 | 34122 | 3697 | 2026-02-16 | 2026-02-23 | LS High nk TS w back nk Placket btn | TS |  |  | 2026-05-02 | 2026-05-20 | 2026-06-05 | 2026-06-20 |  |  | 2026-06-30 | 2026-06-25 | 2026-06-30 | 2026-07-01 | 2026-07-11 | [6 empty] | 2026-07-10 | 2026-07-27 |  |  | 2026-07-28 | 2026-07-30 | 2026-08-01 | 2026-08-05 | 2026-08-05 | 170 | E | Salam | [5 empty] | NFL1 |  |  | Cut Ok | 4010 | 4010 | 0 | 0 | -34122 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46178 | 0 | 32 | Jul'1 |  |  | 19.06.26
OVS SPA | 46881 | 262TSH321-227 | 30214 | 3273 | 2026-02-16 | 2026-02-23 | LS High nk TS w back nk Placket btn | TS |  |  | 2026-05-02 | 2026-05-20 | 2026-06-05 | 2026-06-20 |  |  | 2026-06-30 | 2026-06-17 | 2026-06-23 | 2026-06-24 | 2026-07-02 | 2026-07-01 | 2026-07-11 |  |  |  |  | 2026-07-10 | 2026-07-27 |  |  | 2026-07-28 | 2026-07-30 | 2026-08-01 | 2026-08-05 | 2026-08-05 | 170 | D1 | Salam | Chest |  | white 1-10128 pcs,,White 2-11051 pcs,,Haute red-9035 pcs all combo 4/5 color pig w gltr print |  | Artwork due | NFL1 |  |  | Cut Ok | 3273 | 3273 | 0 | 0 | -30214 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46178 | 0 | 32 | Jun'3 |  |  | 25.05.26
GBX-New Look | 47056 3rd | 9328950 | 4488 | 942 | 2026-02-24 | 2026-02-26 | Tank top | Tank Top |  |  | 2026-05-10 | 2026-05-16 | 2026-06-08 | 2026-06-22 |  |  | 2026-07-01 | 2026-07-01 |  | 2026-07-08 | 2026-07-09 | 2026-07-07 | 2026-07-10 |  |  |  |  | 2026-07-12 | 2026-07-16 |  |  | 2026-07-19 | 2026-07-20 | 2026-07-23 | 2026-08-01 | 2026-08-01 | 158 | N/1 | Morad | Nk |  | 3 combo nk size label print |  |  | NCL |  |  | Ready Test Cut | 943 | 943 | 0 | 0 | -4488 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 31 | Jul'1
BS-NMT | 46928 | 13260575 | 4123 | 1567 | 2026-02-18 | 2026-03-06 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-04-02 | 2026-04-08 | 2026-04-13 | 2026-04-28 |  |  | 2026-05-02 | 2026-05-02 | 2026-05-07 | 2026-05-09 | 2026-05-11 | 2026-05-12 | 2026-05-15 |  |  |  |  | 2026-05-18 | 2026-05-21 |  |  | 2026-05-23 | 2026-06-08 | 2026-06-12 | 2026-06-29 | 2026-07-01 | 131 | W2 | Kamruzzaman | Fr,Bk |  | grey-1546 pcs frt back 3 clr rub ,,lilas-1246 pcs frt 2 clr rub back 5 clr rub,,Navy-1331 pcs frt back 5 clr rub |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -4123 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46125 | 0 | 27 | May'1 |  |  | 05.05.26
BS-NMT | 46926 | 13260572/13261733 | 4458 | 892 | 2026-02-18 | 2026-03-06 | LS O nk TS | TS |  |  | 2026-04-02 | 2026-04-08 | 2026-04-12 | 2026-04-28 |  |  | 2026-04-28 | 2026-04-28 | 2026-05-05 | 2026-05-07 | 2026-05-09 | 2026-05-09 | 2026-05-13 |  |  |  |  | 2026-05-15 | 2026-05-19 |  |  | 2026-05-21 | 2026-05-23 | 2026-06-10 | 2026-06-29 | 2026-07-01 | 131 | ZA2 | Kamruzzaman | Chest,Nk |  | c.dan-936 pcs 3 clr pig,,lilac-1020 pcs 1 clr rub,,lilas-1077 pcs 4 clr rub,,navy-1425 pcs 3 clr rub |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -4458 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46124 | 0 | 27 | May'1 |  |  | 25.04.26
BS-NMT | 46925 | 13259688/13261406 | 6749 | 1445 | 2026-02-18 | 2026-03-06 | LS O nk TS | TS |  |  | 2026-03-28 | 2026-04-04 | 2026-04-08 | 2026-04-22 |  |  | 2026-04-24 | 2026-04-24 | 2026-04-29 | 2026-05-02 | 2026-05-05 | 2026-05-05 | 2026-05-09 |  |  |  |  | 2026-05-11 | 2026-05-14 |  |  | 2026-05-16 | 2026-05-18 | 2026-06-10 | 2026-06-29 | 2026-07-01 | 131 | ZA1 | Kamruzzaman | Chest,Nk |  | chocolate-876 pcs 5 clr rub,,c.dan-840 pcs 2 clr rub,,navy-2752 pcs 4 clr rub,,trade-2281 pcs 4 clr rub |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -6749 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46120 | 0 | 27 | May'1 |  |  | 21.04.26
BS-NMT | 46929 | 13234313 | 3291 | 1390 | 2026-02-18 | 2026-03-06 | LS Swt hoody | Hoody |  |  | 2026-04-03 | 2026-04-12 | 2026-04-18 | 2026-05-04 |  |  | 2026-05-07 | 2026-05-07 | 2026-05-13 | 2026-05-15 | 2026-05-16 | 2026-05-19 | 2026-05-22 |  |  |  |  | 2026-06-04 | 2026-06-06 |  |  | 2026-06-09 | 2026-06-12 | 2026-06-16 | 2026-06-29 | 2026-07-01 | 131 | V | Kamruzzaman | Chest |  | chocolate-1098 pcs 5 clr rub ,,mermaid-954 pcs 5 clr rub ,,Navy-1239 pcs 4 clr rub |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -3291 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46130 | 0 | 27 | May'2 |  |  | 25.04.26
BS-NMT | 46930 | 13249493 | 2340 | 1039 | 2026-02-18 | 2026-03-06 | LS swt full zipper hoody | Hoody |  |  | 2026-04-08 | 2026-04-16 | 2026-04-20 | 2026-05-05 |  |  | 2026-05-11 | 2026-05-11 | 2026-05-16 | 2026-05-19 | 2026-05-21 | 2026-06-15 | 2026-06-18 |  |  |  |  | 2026-06-18 | 2026-06-22 |  |  | 2026-06-23 | 2026-06-25 | 2026-06-26 | 2026-06-29 | 2026-07-01 | 131 | S | Kamruzzaman | Fr,Bk |  | Olive-1350 pcs frt 5 clr rub back no print ,,blue-990 pcs frt back 3 clr rub |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2340 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46132 | 0 | 27 | May'2 |  |  | 05.05.26
BS-ONL | 47045 | 15270956 | 7809 | 1245 | 2026-02-23 | 2026-03-04 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-04-03 | 2026-04-13 | 2026-04-15 | 2026-05-03 |  |  | 2026-05-06 | 2026-05-06 | 2026-05-13 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 2026-06-23 |  |  | 2026-06-05 | 2026-06-09 | 2026-06-11 | 2026-06-16 |  |  | 2026-06-19 | 2026-06-21 | 2026-06-25 | 2026-07-13 | 2026-07-15 | 140 | N2 | Jannati | Chest | Chest | c.dan-1950 pcs 6 clr rub 1 clr gltr ,,Fiji-807 pcs 3 clr rub 2 clr gltr ,,ponderosa-2028 pcs 9 clr rub 3 clr gltr ,,sky-1008 pcs,,bonbon-1008 pcs,,LGM-1008 pcs |  | 3 clr print artwork due | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -7809 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46127 | 0 | 29 | May'2 |  |  | 18.04.26
BS-ONL | 47044 | 15380932 | 1008 | 570 | 2026-02-23 | 2026-03-04 | AOP LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-04-08 | 2026-04-13 | 2026-04-17 | 2026-04-30 | 2026-05-06 | 2026-05-16 | 2026-05-20 | 2026-05-20 | 2026-06-09 | 2026-06-12 | 2026-06-13 | [6 empty] | 2026-06-15 | 2026-06-16 |  |  | 2026-06-19 | 2026-06-22 | 2026-06-25 | 2026-07-13 | 2026-07-15 | 140 | N2 | Jannati |  |  |  | AOP |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1008 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46129 | 0 | 29 | Jun'2 |  |  | 04.04.26
BS-ONL | 47043 | 15355780 | 2004 | 1261 | 2026-02-23 | 2026-03-04 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-04-12 | 2026-04-20 | 2026-04-24 | 2026-05-10 |  |  | 2026-05-16 | 2026-05-16 | 2026-05-22 | 2026-06-06 | 2026-06-07 | 2026-06-09 | 2026-06-13 |  |  |  |  | 2026-06-16 | 2026-06-18 |  |  | 2026-06-20 | 2026-06-22 | 2026-06-25 | 2026-07-13 | 2026-07-15 | 140 | N2 | Jannati | Fr,Bk |  | Birtch-696 pcs frt 5 clr rub 1 clr puff back no print ,,Fiji-1308 pcs frt back 1 clr rub 1 clr puff |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2004 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46136 | 0 | 29 | Jun'1 |  |  | 10.04.26
OVS SPA | 47186 | 262TSH301-227 | 21921 | 2430 | 2026-03-03 | 2026-03-06 | LS High nk TS w back nk Placket btn | TS |  |  | 2026-04-01 | 2026-04-18 | 2026-04-20 | 2026-05-09 |  |  | 2026-06-06 | 2026-05-09 | 2026-05-16 | 2026-05-18 | 2026-06-08 | 2026-06-08 | 2026-06-17 |  |  |  |  | 2026-06-15 | 2026-06-27 |  |  | 2026-06-29 | 2026-07-01 | 2026-07-03 | 2026-07-06 | 2026-07-06 | 125 | D1 | Salam | Chest | Chest | powder-9442 pcs 4 clr pig no emb ,,sugar-10009 pcs 4 clr pig no emb,,sugar set-2470 pcs 5 clr pig print and printed applque attach emb |  |  | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -21921 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46132 | 0 | 28 | May'2 |  |  | 19.05.26
UTG-(Even & Odd) | 41637 5th | BAD1502K | 1600 | 388 | 2026-02-26 | 2026-03-02 | LDS LS ROLL NK TS | TS |  |  | 2026-04-20 | 2026-04-28 | 2026-05-02 | 2026-05-14 |  |  | 2026-06-06 | 2026-06-08 |  | 2026-06-12 | 2026-06-13 | [6 empty] | 2026-06-15 | 2026-06-16 |  |  | 2026-06-17 | 2026-06-19 | 2026-06-22 | 2026-07-11 | 2026-07-13 | 135 | G1 | Rony | [5 empty] | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1600 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46144 | 0 | 29 | Jun'2 |  |  | 09.05.26
UTG-(Even & Odd) | 41637 6th | BAD1502L | 3000 | 720 | 2026-03-03 | 2026-03-04 | LDS LS ROLL NK TS | TS |  |  | 2026-05-10 | 2026-05-20 | 2026-06-06 | 2026-06-16 |  |  | 2026-06-23 | 2026-06-24 |  | 2026-06-29 | 2026-06-30 | [6 empty] | 2026-07-01 | 2026-07-04 |  |  | 2026-07-06 | 2026-07-08 | 2026-07-10 | 2026-07-17 | 2026-07-17 | 136 | G1 | Rony | [5 empty] | NFL1 |  |  | Cut Ok | 720 | 720 | 0 | 0 | -3000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 29 | Jun'3 |  |  | 09.05.26
GBX-Miss Shelfridge | 47243 2nd | INDOMS33582 | 1600 | 361 | 2026-03-13 | 2026-03-14 | LS V nk Cardigan w full placket btn | Cardigan |  |  | 2026-06-20 | 2026-06-30 | 2026-07-08 | 2026-07-23 |  |  | 2026-07-23 | 2026-07-23 | 2026-08-04 | 2026-08-08 | 2026-08-10 | [6 empty] | 2026-08-13 | 2026-08-18 |  |  | 2026-08-20 | 2026-08-22 | 2026-08-25 | 2026-09-15 | 2026-09-15 | 186 | N/3 | Morad | [5 empty] | NCL |  |  | Need Test Cut | 360 | 0 | -360 | 0 | -1600 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46211 | 0 | 38 | Aug'1
GBX-Miss Shelfridge | 47240 2nd | INDOMS33572 | 1700 | 378 | 2026-03-13 | 2026-03-14 | LS V nk TS w nk Lace | TS |  |  | 2026-05-10 | 2026-05-16 | 2026-06-05 | 2026-06-15 |  |  | 2026-06-18 | 2026-06-18 |  | 2026-06-25 | 2026-06-27 | [6 empty] | 2026-07-01 | 2026-07-03 |  |  | 2026-07-06 | 2026-07-07 | 2026-07-10 | 2026-07-15 | 2026-07-15 | 124 | N/1 | Morad |  |  |  |  | Lace | NCL |  |  | Need Test Cut | 378 | 0 | -378 | 0 | -1700 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46178 | 0 | 29 | Jun'3
GBX-Miss Shelfridge | 47242 3rd | INDOMS33594 | 2000 | 360 | 2026-03-13 | 2026-03-14 | LS v nk Half placket btn w nk Lace | TS |  |  | 2026-06-23 | 2026-06-30 | 2026-07-10 | 2026-07-27 |  |  | 2026-08-03 | 2026-08-03 |  | 2026-08-10 | 2026-08-12 | [6 empty] | 2026-08-15 | 2026-08-19 |  |  | 2026-08-21 | 2026-08-24 | 2026-08-27 | 2026-09-15 | 2026-09-15 | 186 | N/2 | Morad |  |  |  |  | Lace | NCL |  |  | Need Test Cut | 360 | 0 | -360 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 38 | Aug'1
GBX-Miss Shelfridge | 47250 2nd | INDOMS33574 | 2200 | 721 | 2026-03-13 | 2026-03-14 | Lace trim LS wrap top | TS |  |  | 2026-05-02 | 2026-05-09 | 2026-05-15 | 2026-05-30 |  |  | 2026-06-10 | 2026-06-10 |  | 2026-06-19 | 2026-06-22 | [6 empty] | 2026-06-23 | 2026-06-27 |  |  | 2026-06-30 | 2026-07-03 | 2026-07-06 | 2026-07-15 | 2026-07-15 | 124 | N/1 | Morad |  |  |  |  | Lace | NCL |  |  | Ready Test Cut | 0 | 0 | 0 | 0 | -2200 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 29 | Jun'3
GBX-Miss Shelfridge | 47250 3rd | INDOMS33574 | 2000 | 656 | 2026-03-13 | 2026-03-14 | Lace trim LS wrap top | TS |  |  | 2026-06-20 | 2026-06-30 | 2026-07-14 | 2026-07-30 |  |  | 2026-08-08 | 2026-08-08 |  | 2026-08-15 | 2026-08-17 | [6 empty] | 2026-08-20 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-28 | 2026-08-30 | 2026-09-15 | 2026-09-15 | 186 | N/1 | Morad |  |  |  |  | Lace | NCL |  |  | Need Test Cut | 657 | 0 | -657 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46217 | 0 | 38 | Aug'2
GBX-Miss Shelfridge | 47245 2nd | INDOMS33661 | 2000 | 467 | 2026-03-13 | 2026-03-14 | LS TS w nk picoting | TS |  |  | 2026-06-15 | 2026-06-25 | 2026-07-05 | 2026-07-20 |  |  | 2026-07-25 | 2026-07-25 | 2026-08-03 | 2026-08-06 | 2026-08-07 | [6 empty] | 2026-08-10 | 2026-08-12 |  |  | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-09-15 | 2026-09-15 | 186 | N/1 | Morad | [5 empty] | NCL |  |  | Need Test Cut | 388 | 0 | -388 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46208 | 0 | 38 | Aug'1
BS-NMT | 47229 | 13260350 | 1648 | 755 | 2026-02-18 | 2026-03-13 | LS Swt hoody w cuff btm rib | Hoody |  |  | 2026-04-01 | 2026-04-07 | 2026-04-15 | 2026-04-30 |  |  | 2026-05-06 | 2026-05-06 | 2026-05-12 | 2026-05-14 | 2026-05-15 | 2026-05-18 | 2026-05-22 |  |  |  |  | 2026-06-06 | 2026-06-08 |  |  | 2026-06-10 | 2026-06-12 | 2026-06-15 | 2026-06-29 | 2026-07-01 | 131 | V | Tomal | Fr,Bk |  | black-824 pcs frt 4 clr photo print back no print ,,mermaid-824 pcs frt 3 clr photo back 4 clr photo |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1648 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46127 | 0 | 27 | May'2 |  |  | 11.05.26
BS-NMT | 47142 | 13260331 | 2364 | 368 | 2026-02-18 | 2026-03-10 | LS boat nk TS | TS |  |  | 2026-04-05 | 2026-04-10 | 2026-04-15 | 2026-04-30 |  |  | 2026-05-09 | 2026-05-09 | 2026-05-14 | 2026-05-16 | 2026-05-18 |  |  | 2026-05-18 | 2026-05-22 |  |  | 2026-06-04 | 2026-06-06 |  |  | 2026-06-09 | 2026-06-11 | 2026-06-16 | 2026-06-29 | 2026-07-01 | 131 | ZA1 | Haider | Stone |  | c.dan-807 pcs 1 size all over stone at chest,,black-1557 pcs 1 size stone HP at chest |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2364 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46127 | 0 | 27 | May'2 |  |  | 09.05.26
BS-NMT | 47147 | 13260339 | 1661 | 764 | 2026-02-18 | 2026-03-12 | LS Swt shirt w cuff btm rib w gmts dye acid wash | Swt Shirt |  |  | 2026-04-08 | 2026-04-14 | 2026-04-18 | 2026-04-25 |  |  | 2026-05-02 | 2026-05-02 | 2026-05-12 | 2026-05-16 | 2026-05-18 |  |  | 2026-06-15 | 2026-06-17 |  |  | 2026-05-21 | 2026-05-23 | 2026-06-06 | 2026-06-11 | 2026-06-19 | 2026-06-20 | 2026-06-23 | 2026-06-29 | 2026-07-01 | 131 | Z | Haider | Stone |  | plum-1058 pcs,,lilac-603 pcs both combo 1 size stone HP at chest |  | Gmts dye acid wash | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1661 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46130 | 0 | 27 | May'2 |  |  | 09.05.26
BS-NMT | 43143 3rd | 13231114 | 6090 | 812 | 2026-02-20 | 2026-03-11 | LS dress btm mesh | Dress |  |  | 2026-04-20 | 2026-04-28 | 2026-05-05 | 2026-05-20 |  |  | 2026-06-05 | 2026-06-05 | 2026-06-12 | 2026-06-15 | 2026-06-18 | 2026-06-18 | 2026-06-22 |  |  |  |  | 2026-06-24 | 2026-06-30 |  |  | 2026-07-04 | 2026-07-06 | 2026-07-11 | 2026-07-22 | 2026-07-24 | 152 | S | Shamoly | Chest,Nk |  | Navy-3330 pcs,,lavender-2760 pcs both combo 1 clr puff gltr print |  | Imp mesh | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -6090 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46147 | 0 | 30 | Jun'3 |  |  | 13.06.26
BS-ONS | 47318 | 22030844 | 2019 | 45 | 2026-03-06 | 2026-03-07 | SS o nk TS | TS |  |  | 2026-04-05 | 2026-04-10 | 2026-04-15 | 2026-04-30 |  |  | 2026-05-08 | 2026-05-08 | 2026-05-14 | 2026-05-16 | 2026-05-18 | 2026-05-20 | 2026-05-23 |  |  |  |  | 2026-06-08 | 2026-06-09 |  |  | 2026-06-11 | 2026-06-14 | 2026-06-15 | 2026-06-29 | 2026-07-01 | 115 | G1 | Shakel | Chest,Nk |  | black-1266 pcs photo print ,,white-801 pcs 1 clr rub |  | License order | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2019 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46127 | 0 | 27 | May'2 |  |  | 25.04.26
BS-ONL | 47036 | 15380813 | 510 | 78 | 2026-02-23 | 2026-03-07 | SS o nk TS | TS |  |  | 2026-04-10 | 2026-04-15 | 2026-04-20 | 2026-04-30 |  |  | 2026-05-11 | 2026-05-11 | 2026-05-16 | 2026-05-18 | 2026-05-18 | 2026-05-20 | 2026-05-22 | 2026-06-05 | 2026-06-08 |  |  | 2026-06-10 | 2026-06-11 |  |  | 2026-06-13 | 2026-06-15 | 2026-06-20 | 2026-07-13 | 2026-07-15 | 140 | O1 | Jannati | Chest,Stone |  | c.dan-510 pcs 1 clr gltr print and 3 clr rine stone HP |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -510 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46132 | 0 | 29 | May'2 |  |  | 28.03.26
BS-ONL | 47159 | 15356524 | 1407 | 1020 | 2026-02-20 | 2026-03-14 | LS Swt Shirt long dress w cuff btm rib | Dress |  |  | 2026-04-12 | 2026-04-18 | 2026-04-22 | 2026-05-05 |  |  | 2026-05-08 | 2026-05-08 | 2026-05-14 | 2026-05-16 | 2026-05-18 | 2026-05-20 | 2026-06-05 |  |  | 2026-06-08 | 2026-06-12 | 2026-06-15 | 2026-06-17 |  |  | 2026-06-19 | 2026-06-20 | 2026-06-23 | 2026-07-20 | 2026-07-22 | 150 | K | Zahirul | Chest | Chest | black tree-897 pcs ,,black crismas-510 pcs both combo 1 clr mettalic 1 clr gltr and 1 clr seq emb |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1407 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46134 | 0 | 30 | May'2 |  |  | 05.06.26
BS-ONL | 47160 | 15282179 | 2124 | 490 | 2026-02-20 | 2026-03-14 | SS o nk long TS | TS |  |  | 2026-04-13 | 2026-04-18 | 2026-04-25 | 2026-05-08 |  |  | 2026-05-13 | 2026-05-13 | 2026-05-19 | 2026-05-21 | 2026-05-22 | 2026-06-06 | 2026-06-10 |  |  | 2026-06-10 | 2026-06-15 | 2026-06-18 | 2026-06-20 |  |  | 2026-06-23 | 2026-06-25 | 2026-06-28 | 2026-07-20 | 2026-07-22 | 150 | O1 | Zahirul | Chest | Chest | black crismas-600 pcs 1 clr mettalic 1 clr gltr and 1 clr seq emb ,,black tree-972 pcs 1 clr mettalic 1 clr gltr and 1 clr seq emb ,,black spice-552 pcs 5 clr rub 1 clr foil and 1 clr seq emb |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2124 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46137 | 0 | 30 | May'3 |  |  | 22.05.26
BS-ONL | 47158 | 15381538 | 2376 | 545 | 2026-02-20 | 2026-03-14 | SS o nk TS | TS |  |  | 2026-04-07 | 2026-04-14 | 2026-04-20 | 2026-05-08 |  |  | 2026-05-12 | 2026-05-12 | 2026-05-18 | 2026-05-20 | 2026-05-22 | 2026-06-04 | 2026-06-08 |  |  | 2026-06-09 | 2026-06-15 | 2026-06-18 | 2026-06-20 |  |  | 2026-06-23 | 2026-06-25 | 2026-06-30 | 2026-07-13 | 2026-07-15 | 143 | N1 | Zahirul | Chest | Chest | black-1076 pcs 5 clr rub 2 clr gltr and 1 clr seq emb ,,sky-788 pcs 6 clr rub 2 clr gltr and 1 clr seq emb ,,red-512 pcs 5 clr rub 3 clr gltr and 1 clr seq emb |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2376 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46132 | 0 | 29 | May'2 |  |  | 22.05.26
BS-ONL | 47157 | 15356872 | 2628 | 1569 | 2026-02-20 | 2026-03-14 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-04-10 | 2026-04-20 | 2026-04-23 | 2026-05-10 |  |  | 2026-05-14 | 2026-05-14 | 2026-05-21 | 2026-06-05 | 2026-06-06 | 2026-06-08 | 2026-06-13 |  |  |  |  | 2026-06-17 | 2026-06-20 |  |  | 2026-06-23 | 2026-06-25 | 2026-06-30 | 2026-07-20 | 2026-07-22 | 150 | K | Zahirul | Chest |  | pink-796 pcs,,sky-312 pcs ,,black tree-979 pcs 3 clr rub 2 clr gltr ,,black cookie-541 pcs 6 clr rub 1 clr gltr |  | Artwork due | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2628 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46135 | 0 | 30 | Jun'3 |  |  | 05.06.26
BS-ONL | 46902 | 15313972 | 540 | 275 | 2026-02-20 | 2026-03-07 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-04-10 | 2026-04-15 | 2026-04-20 | 2026-05-05 |  |  | 2026-05-12 | 2026-05-12 | 2026-05-19 | 2026-05-21 | 2026-05-21 |  |  |  |  | 2026-06-05 | 2026-06-12 | 2026-06-15 | 2026-06-16 |  |  | 2026-06-18 | 2026-06-20 | 2026-06-24 | 2026-07-13 | 2026-07-15 | 143 | N2 | Zahirul |  | Slv | black-540 pcs both slve cut out emb |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -540 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46132 | 0 | 29 | May'3 |  |  | 22.05.26
OVS SPA | 46828 | 262JOG030-230 | 14502 | 3660 | 2026-03-02 | 2026-03-09 | LS swt hoody and elasted legging | Top & BTM |  |  | 2026-04-01 | 2026-04-18 | 2026-04-18 | 2026-05-13 |  |  | 2026-05-23 | 2026-05-11 | 2026-05-19 | 2026-05-20 | 2026-05-25 | 2026-06-06 | 2026-06-13 |  |  | 2026-06-13 | 2026-06-20 | 2026-06-20 | 2026-06-30 |  |  | 2026-07-01 | 2026-07-02 | 2026-07-04 | 2026-07-06 | 2026-07-06 | 126 | N/3 | Khairul | Chest | Chest | bitter top-7251 pcs 2 clr rub print 1 clr flat 2 clr seq emb ,,rose btm-7251 pcs no print emb |  |  | NCL |  |  | Ready Test Cut | 0 | 0 | 0 | 0 | -14502 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46130 | 0 | 28 | May'2
OVS SPA | 46829 | 262JOG032-230 | 21116 | 5250 | 2026-03-02 | 2026-03-09 | LS swt shirt and elasted legging | Top & BTM |  |  | 2026-04-01 | 2026-04-18 | 2026-04-18 | 2026-05-11 |  |  | 2026-06-05 | 2026-05-09 | 2026-05-18 | 2026-05-19 | 2026-05-25 | 2026-06-05 | 2026-06-12 |  |  | 2026-06-11 | 2026-06-18 | 2026-06-18 | 2026-07-01 |  |  | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-06 | 2026-07-06 | 126 | A+C | Khairul | Chest | Chest | egret top-10558 pcs 6 clr pig 2 clr flat 7 clr lurex 8 clr seq emb ,,black btm-10558 pcs no print emb |  |  | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -21116 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46130 | 0 | 28 | May'2 |  |  | 16.05.26
OVS SPA | 46834 | 262JOG031-230 | 17078 | 3865 | 2026-03-02 | 2026-03-09 | LS swt shirt and elasted legging | Top & BTM |  |  | 2026-04-01 | 2026-04-18 | 2026-04-20 | 2026-05-09 |  |  | 2026-06-06 | 2026-05-12 | 2026-05-19 | 2026-05-20 | 2026-05-25 | 2026-06-06 | 2026-06-13 | 2026-06-13 | 2026-06-18 |  |  | 2026-06-18 | 2026-06-27 |  |  | 2026-06-29 | 2026-07-01 | 2026-07-03 | 2026-07-06 | 2026-07-06 | 126 | Q+P | Khairul | Chest,Stone |  | pink top-8539 pcs 5 clr pig 2 clr gltr print 5 size stone HP ,,black btm-8539 pcs no print stone |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -17078 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46132 | 0 | 28 | May'2 |  |  | 16.05.26
GBX-New Look | 47403 1st | 91533449 | 1275 | 166 | 2026-03-30 | 2026-03-30 | YD SL TS w full placket btn | TS | 2026-05-22 | 2026-05-25 | 2026-06-06 | 2026-06-10 | 2026-06-11 | 2026-06-15 |  |  | 2026-06-15 | 2026-06-15 | 2026-06-20 | 2026-06-22 | 2026-06-22 | [6 empty] | 2026-06-24 | 2026-06-25 |  |  | 2026-06-27 | 2026-06-29 | 2026-06-30 | 2026-07-04 | 2026-07-05 | 96 | N/3 | Shofi |  |  |  | YD |  | NCL |  |  | Ready Test Cut | 30 | 30 | 0 | 0 | -1275 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46184 | 0 | 28 | May'1
BS-NMT | 47227 | 13260081 | 645 | 274 | 2026-02-18 | 2026-03-16 | LS o nk TS w side waist gathering | TS |  |  | 2026-05-15 | 2026-05-24 | 2026-05-06 | 2026-05-15 |  |  | 2026-05-20 | 2026-05-20 | 2026-06-08 | 2026-06-11 | 2026-06-12 | [6 empty] | 2026-06-15 | 2026-06-16 |  |  | 2026-06-18 | 2026-06-20 | 2026-06-23 | 2026-06-29 | 2026-07-01 | 131 | Z | Tomal | [5 empty] | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -645 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46148 | 0 | 27 | Jun'2 |  |  | 18.05.26
BS-NMT | 47228 | 13260093 | 1200 | 290 | 2026-02-18 | 2026-03-16 | LS boat Nk TS | TS |  |  | 2026-04-13 | 2026-04-18 | 2026-04-22 | 2026-05-05 |  |  | 2026-05-12 | 2026-05-12 | 2026-05-18 | 2026-05-21 | 2026-05-22 | [6 empty] | 2026-06-06 | 2026-06-08 |  |  | 2026-06-10 | 2026-06-13 | 2026-06-18 | 2026-06-29 | 2026-07-01 | 131 | ZA1 | Tomal | [5 empty] | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1200 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46134 | 0 | 27 | May'3 |  |  | 10.06.26
BS-NMT | 47353 | 13263336 | 4048 | 917 | 2026-03-02 | 2026-03-16 | AOP LS Swt shirt w rib | Swt Shirt |  |  | 2026-04-04 | 2026-04-12 | 2026-04-15 | 2026-05-02 | 2026-05-05 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 2026-06-04 | 2026-06-06 | 2026-06-10 | [6 empty] | 2026-06-10 | 2026-06-16 |  |  | 2026-06-17 | 2026-06-18 | 2026-06-20 | 2026-06-29 | 2026-07-01 | 119 | W2 | Sanaul |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -4048 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46127 | 0 | 27 | Jun'1 |  |  | 16.06.26
BS-NMT | 47231 | 13260352 | 1656 | 396 | 2026-02-18 | 2026-03-16 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-04-10 | 2026-04-16 | 2026-04-20 | 2026-05-05 |  |  | 2026-05-11 | 2026-05-11 | 2026-05-18 | 2026-05-21 | 2026-05-22 |  |  |  |  | 2026-06-06 | 2026-06-13 | 2026-06-17 | 2026-06-18 |  |  | 2026-06-20 | 2026-06-23 | 2026-06-25 | 2026-06-29 | 2026-07-01 | 131 | W2 | Tomal | Chest,Nk |  | plive-828 pcs,,black-828 pcs both combo 2 clr flat 4 clr terry emb |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1656 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46132 | 0 | 27 | May'3 |  |  | 11.05.26
BS-NMT | 47226 | 13260551 | 4524 | 1727 | 2026-02-18 | 2026-03-16 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-04-07 | 2026-04-15 | 2026-04-23 | 2026-05-08 |  |  | 2026-05-13 | 2026-05-13 | 2026-05-21 | 2026-06-06 | 2026-06-08 | [6 empty] | 2026-06-10 | 2026-06-13 |  |  | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-29 | 2026-07-01 | 131 | V | Tomal |  |  |  |  | badge label | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -4524 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46135 | 0 | 27 | Jun'1 |  |  | 11.05.26
BS-NMT | 47230 | 13260351 | 1788 | 842 | 2026-02-18 | 2026-03-16 | LS Swt Hoody w kangaro pkt & drawstring | Hoody |  |  | 2026-04-08 | 2026-04-15 | 2026-04-20 | 2026-05-05 |  |  | 2026-05-09 | 2026-05-09 | 2026-05-16 | 2026-05-20 | 2026-05-22 |  |  |  |  | 2026-06-05 | 2026-06-12 | 2026-06-15 | 2026-06-18 |  |  | 2026-06-20 | 2026-06-22 | 2026-06-23 | 2026-06-29 | 2026-07-01 | 131 | S | Tomal |  | Chest | grey-984 pcs,,sesame-804 pcs both combo 2 clr flat 4 clr terry emb |  |  | NFL3 |  |  | Cut Ok | 378 | 378 | 0 | 0 | -1788 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46132 | 0 | 27 | May'2 |  |  | 13.06.26
BS-NMT | 47232 | 13260356 | 1410 | 343 | 2026-02-18 | 2026-03-16 | LS cut & Sew swt Pant w side & back bon pkt drawstrig | Pant |  |  | 2026-04-08 | 2026-05-04 | 2026-04-23 | 2026-05-17 |  |  | 2026-05-17 | 2026-05-17 | 2026-05-25 | 2026-06-05 | 2026-06-06 | 2026-06-08 | 2026-06-12 |  |  |  |  | 2026-06-15 | 2026-06-17 |  |  | 2026-06-18 | 2026-06-20 | 2026-06-22 | 2026-06-29 | 2026-07-01 | 131 | X | Tomal | Thigh |  | olive-810 pcs,,black-600 pcs both combo 1 clr HD rubber print |  |  | NFL3 |  |  | Cut Ok | 515 | 515 | 0 | 0 | -1410 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46135 | 0 | 27 | Jun'1 |  |  | 20.06.26
BS-ONL | 30708 14th | 15201465 | 10980 | 1716 | 2026-03-27 | 2026-03-28 | Long Tank Top | Tank top |  |  | 2026-04-12 | 2026-04-20 | 2026-05-02 | 2026-05-14 |  |  | 2026-05-13 | 2026-05-13 |  | 2026-05-18 | 2026-05-21 | [6 empty] | 2026-06-05 | 2026-06-09 |  |  | 2026-06-11 | 2026-06-12 | 2026-06-16 | 2026-06-29 | 2026-07-01 | 94 | D1 | Mainul | [5 empty] | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -10980 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46144 | 0 | 27 | May'2 |  |  | 22.04.26
OVS SPA | 47053 | 262JOG020-230 | 62416 | 13170 | 2026-03-11 | 2026-03-16 | LS Swt Shirt and Swt legging set | Top & Btm |  |  | 2026-03-28 | 2026-04-18 | 2026-04-14 | 2026-05-09 |  |  | 2026-05-18 | 2026-04-29 | 2026-05-04 | 2026-05-05 | 2026-05-20 | 2026-05-14 | 2026-06-10 |  |  |  |  | 2026-06-10 | 2026-06-24 |  |  | 2026-06-25 | 2026-06-26 | 2026-06-29 | 2026-07-10 | 2026-07-10 | 121 | NFL3 | Khairul | Chest |  | allysum top-9850 pcs 5 clr rub 1 clr gltr ,,blues btm-9850 pcs no print ,,pink top-12776 pcs 6 clr rub 1 clr gltr print ,,pig pant -12776 pcs no print ,,dusty top-8582 pcs 6 clr rub 1 clr gltr print ,,dusty btm-8582 pcs no print |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -62416 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46126 | 0 | 28 | May'1 |  |  | 05.06.26
BS-ONL | 27204 42th | 15323159 | 13436 | 3247 | 2026-03-13 | 2026-03-16 | LS o nk TS | TS |  |  | 2026-04-13 | 2026-04-24 | 2026-04-25 | 2026-05-10 |  |  | 2026-05-12 | 2026-05-12 |  | 2026-05-16 | 2026-05-19 | [6 empty] | 2026-06-04 | 2026-06-08 |  |  | 2026-06-10 | 2026-06-12 | 2026-06-15 | 2026-07-20 | 2026-07-22 | 129 | D1 | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -13436 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46137 | 0 | 30 | May'2 |  |  | 04.04.26
OVS SPA | 47257 | 262PJA040-228 | 12936 | 2715 | 2026-03-04 | 2026-03-16 | AOP LS shirt w front pkt placket btn and AOP trouser w drawsring | Top & Btm |  |  | 2026-04-01 | 2026-05-05 | 2026-04-15 | 2026-05-11 | 2026-05-02 | 2026-05-18 | 2026-06-06 | 2026-06-04 | 2026-06-09 | 2026-06-10 | 2026-06-17 | [6 empty] | 2026-06-16 | 2026-06-27 |  |  | 2026-06-29 | 2026-07-01 | 2026-07-03 | 2026-07-10 | 2026-07-10 | 128 | N/3 | Khairul |  |  |  | AOP |  | NCL |  |  | Ready Test Cut | 0 | 0 | 0 | 0 | -12936 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46127 | 0 | 28 | Jun'1
OVS SPA | 47234 | 262PJA622-224 | 10100 | 2980 | 2026-03-04 | 2026-03-16 | AOP LS shirt w front pkt placket btn and AOP trouser w drawsring | Top & Btm |  |  | 2026-04-01 | 2026-06-15 | 2026-04-15 | 2026-06-25 | 2026-06-24 | 2026-07-03 | 2026-06-30 | 2026-07-03 | 2026-07-08 | 2026-07-09 | 2026-07-13 | [6 empty] | 2026-07-10 | 2026-07-20 |  |  | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-22 | 140 | B+F | Khairul |  |  |  | AOP |  | NFL1 |  |  | Cut Ok | 2980 | 2980 | 0 | 0 | -10100 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46127 | 0 | 30 | Jul'1 |  |  | 11.07.26
OVS SPA | 47233 | 262PJA524-224 | 13612 | 2645 | 2026-03-04 | 2026-03-16 | AOP LS shirt w front pkt placket btn and AOP trouser w drawsring | Top & Btm |  |  | 2026-04-01 | 2026-05-05 | 2026-04-15 | 2026-05-11 | 2026-05-02 | 2026-05-18 | 2026-06-06 | 2026-06-04 | 2026-06-09 | 2026-06-10 | 2026-06-17 | [6 empty] | 2026-06-16 | 2026-06-27 |  |  | 2026-06-29 | 2026-07-01 | 2026-07-03 | 2026-07-10 | 2026-07-10 | 128 | B+F | Khairul |  |  |  | AOP |  | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -13612 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46127 | 0 | 28 | Jun'1 |  |  | 19.06.26
OVS SPA | 46273 | 262PJA028PRCM-6111 | 8452 | 3212 | 2026-03-13 | 2026-03-16 | AOP LS Shirt w full placket brn and trouser w drawstring | Top & BTM |  |  | 2026-04-15 | 2026-04-30 | 2026-05-02 | 2026-05-14 | 2026-05-15 | 2026-06-10 | 2026-06-19 | 2026-06-20 | 2026-06-25 | 2026-06-26 | 2026-06-27 | [6 empty] | 2026-06-19 | 2026-07-04 |  |  | 2026-07-06 | 2026-07-08 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 122 | N/3 | Basir |  |  |  | AOP |  | NCL |  |  | Ready Test Cut | 0 | 0 | 0 | 0 | -8452 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46144 | 0 | 29 | Jun'3
GBX-Miss Shelfridge | 47246 2nd | INDOMS33618 | 1500 | 438 | 2026-03-13 | 2026-03-17 | LS Corset Top | TS |  |  | 2026-04-20 | 2026-04-25 | 2026-05-05 | 2026-05-15 |  |  | 2026-05-20 | 2026-05-20 |  | 2026-06-05 | 2026-06-06 | [6 empty] | 2026-06-09 | 2026-06-11 |  |  | 2026-06-13 | 2026-06-16 | 2026-06-20 | 2026-07-15 | 2026-07-15 | 124 | N/2 | Morad | [5 empty] | NCL |  |  | Ready Test Cut | 30 | 30 | 0 | 0 | -1500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46147 | 0 | 29 | Jun'1
GBX-Miss Shelfridge | 47253 | INDOMS33578 | 2500 | 720 | 2026-03-13 | 2026-03-17 | LS Twist TS w cut&sew | TS |  |  | 2026-05-02 | 2026-05-10 | 2026-05-15 | 2026-06-10 |  |  | 2026-06-16 | 2026-06-16 | 2026-06-23 | 2026-06-26 | 2026-06-27 | [6 empty] | 2026-07-01 | 2026-07-04 |  |  | 2026-07-06 | 2026-07-07 | 2026-07-09 | 2026-07-13 | 2026-07-15 | 122 | N/3 | Morad | [5 empty] | NCL |  |  | Ready Test Cut | 0 | 0 | 0 | 0 | -2500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 29 | Jun'3
GBX-Miss Shelfridge | 47319 2nd | CDIJB17353 | 1000 | 201 | 2026-03-13 | 2026-03-17 | LS Square nk TS w nk lace | TS |  |  | 2026-05-05 | 2026-05-15 | 2026-06-04 | 2026-06-16 |  |  | 2026-06-20 | 2026-06-20 |  | 2026-06-26 | 2026-06-27 | [6 empty] | 2026-07-03 | 2026-07-06 |  |  | 2026-07-08 | 2026-07-10 | 2026-07-13 | 2026-07-15 | 2026-07-15 | 124 | N/1 | Morad | [5 empty] | NCL |  |  | Ready Test Cut | 201 | 201 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46177 | 0 | 29 | Jun'3
GBX-Miss Shelfridge | 47252 | INDOMS33576 | 3700 | 1085 | 2026-03-13 | 2026-03-17 | LS open back Nk twist Body suit | Body |  |  | 2026-04-20 | 2026-04-30 | 2026-05-07 | 2026-05-23 |  |  | 2026-06-10 | 2026-06-10 | 2026-06-17 | 2026-06-20 | 2026-06-23 | [6 empty] | 2026-06-25 | 2026-06-30 |  |  | 2026-07-03 | 2026-07-04 | 2026-07-06 | 2026-07-15 | 2026-07-15 | 124 | N/3 | Morad | [5 empty] | NCL |  |  | Ready Test Cut | 0 | 0 | 0 | 0 | -3700 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46149 | 0 | 29 | Jun'2
BS-ONL | 47179 | 15366576 | 1956 | 186 | 2026-02-20 | 2026-03-16 | LS v nk Cut & sew mesh TS | TS |  |  | 2026-04-25 | 2026-04-30 | 2026-05-07 | 2026-05-18 |  |  | 2026-06-21 | 2026-06-21 | 2026-06-30 | 2026-07-08 | 2026-07-13 | [6 empty] | 2026-07-10 | 2026-07-20 |  |  | 2026-07-22 | 2026-07-25 | 2026-07-30 | 2026-08-10 | 2026-08-12 | 171 | Q | Mainul |  |  |  |  | Mesh | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1956 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46149 | 0 | 33 | Jul'1 |  |  | 18.06.26
GBX-Miss Shelfridge | 47246 3rd | INDOMS33618 | 1000 | 297 | 2026-03-13 | 2026-03-17 | LS Corset Top | TS |  |  | 2026-07-01 | 2026-07-06 | 2026-07-17 | 2026-07-30 |  |  | 2026-08-07 | 2026-08-07 |  | 2026-08-13 | 2026-08-14 | [6 empty] | 2026-08-17 | 2026-08-19 |  |  | 2026-08-21 | 2026-08-24 | 2026-08-30 | 2026-09-13 | 2026-09-15 | 184 | N/2 | Morad | [5 empty] | NCL |  |  | Need Test Cut | 0 | 0 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46220 | 0 | 38 | Aug'2
GBX-Miss Shelfridge | 47320 2nd | CDIJB11029 | 2000 | 467 | 2026-03-13 | 2026-03-17 | LS crew nk body suit | Body |  |  | 2026-06-15 | 2026-06-22 | 2026-07-01 | 2026-07-15 |  |  | 2026-07-20 | 2026-07-20 |  | 2026-07-27 | 2026-07-28 | [6 empty] | 2026-08-01 | 2026-08-04 |  |  | 2026-08-06 | 2026-08-08 | 2026-08-10 | 2026-08-15 | 2026-08-15 | 155 | N/3 | Morad | [5 empty] | NCL |  |  | Ready Test Cut | 466 | 466 | 0 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 33 | Jul'3
GBX-Miss Shelfridge | 47320 3rd | CDIJB11029 | 2000 | 467 | 2026-03-13 | 2026-03-17 | LS crew nk body suit | Body |  |  | 2026-06-16 | 2026-06-25 | 2026-07-01 | 2026-07-15 |  |  | 2026-07-20 | 2026-07-20 |  | 2026-07-27 | 2026-07-28 | [6 empty] | 2026-08-04 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-12 | 2026-08-15 | 2026-09-15 | 2026-09-15 | 186 | N/3 | Morad | [5 empty] | NCL |  |  | Ready Test Cut | 466 | 444 | -22 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 38 | Jul'3
GBX-Miss Shelfridge | 47319 3rd | CDIJB17353 | 2000 | 402 | 2026-03-13 | 2026-03-17 | LS Square nk TS w nk lace | TS |  |  | 2026-07-15 | 2026-06-25 | 2026-07-07 | 2026-07-22 |  |  | 2026-08-01 | 2026-08-01 |  | 2026-08-08 | 2026-08-10 | [6 empty] | 2026-08-13 | 2026-08-17 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-22 | 2026-09-15 | 2026-09-15 | 186 | N/1 | Morad | [5 empty] | NCL |  |  | Need Test Cut | 402 | 0 | -402 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46210 | 0 | 38 | Aug'1
GBX-Miss Shelfridge | 47247 2nd | INDOMS33634 | 2000 | 443 | 2026-03-13 | 2026-03-17 | LS Square nk Shirt w frt lace | Shirt |  |  | 2026-07-01 | 2026-07-07 | 2026-07-14 | 2026-07-28 |  |  | 2026-08-04 | 2026-08-04 |  | 2026-08-12 | 2026-08-13 | [6 empty] | 2026-08-17 | 2026-08-21 |  |  | 2026-08-25 | 2026-08-28 | 2026-09-03 | 2026-09-15 | 2026-09-15 | 186 | N/2 | Morad |  |  |  |  | Lace | NCL |  |  | Need Test Cut | 444 | 0 | -444 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46217 | 0 | 38 | Aug'2
GBX-Miss Shelfridge | 47254 2nd | INDOMS33640 | 1000 | 233 | 2026-03-13 | 2026-03-17 | LS TS w btm lace and nk picoting | TS |  |  | 2026-06-15 | 2026-06-20 | 2026-07-01 | 2026-07-12 |  |  | 2026-07-18 | 2026-07-18 |  | 2026-07-25 | 2026-07-27 | [6 empty] | 2026-08-01 | 2026-08-03 |  |  | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-15 | 2026-08-15 | 155 | N/1 | Morad | [5 empty] | NCL |  |  | Ready Test Cut | 233 | 233 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 33 | Jul'3
GBX-Miss Shelfridge | 47254 3rd | INDOMS33640 | 2000 | 477 | 2026-03-13 | 2026-03-17 | LS TS w btm lace and nk picoting | TS |  |  | 2026-06-08 | 2026-06-17 | 2026-07-05 | 2026-07-17 |  |  | 2026-07-22 | 2026-07-22 |  | 2026-07-28 | 2026-07-30 | [6 empty] | 2026-08-04 | 2026-08-07 |  |  | 2026-08-10 | 2026-08-12 | 2026-08-15 | 2026-09-15 | 2026-09-15 | 186 | N/1 | Morad | [5 empty] | NCL |  |  | Need Test Cut | 476 | 0 | -476 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46208 | 0 | 38 | Jul'3
BS-ONL | 27204 43th | 15323159 | 7040 | 1701 | 2026-03-30 | 2026-04-01 | LS o nk TS | TS |  |  | 2026-04-10 | 2026-04-20 | 2026-04-25 | 2026-05-07 |  |  | 2026-05-13 | 2026-05-13 |  | 2026-05-18 | 2026-05-22 | [6 empty] | 2026-06-08 | 2026-06-12 |  |  | 2026-06-15 | 2026-06-17 | 2026-06-20 | 2026-06-29 | 2026-07-01 | 91 | D1 | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -7040 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46137 | 0 | 27 | May'2 |  |  | 04.04.26
BS-ONL | 26766 19th | 15316135 | 3000 | 1452 | 2026-03-29 | 2026-04-02 | LDS PANT W PKT drawstring | PANT |  |  | 2026-04-08 | 2026-04-20 | 2026-04-24 | 2026-05-08 |  |  | 2026-05-08 | 2026-05-08 |  | 2026-05-14 | 2026-05-18 |  |  |  |  | 2026-05-16 | 2026-05-19 | 2026-05-21 | 2026-05-25 |  |  | 2026-06-05 | 2026-06-06 | 2026-06-08 | 2026-07-06 | 2026-07-08 | 71 | P | Imran |  | Thigh | black-3000 pcs 1 clr flat emb |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -3000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46136 | 0 | 28 | May'2 |  |  | 02.05.26
BS-NMT | 47299 | 13265872 | 1035 | 109 | 2026-03-23 | 2026-04-07 | Swt pant w side seam contrast fab horn | Pant |  |  | 2026-04-25 | 2026-04-30 | 2026-05-03 | 2026-05-20 |  |  | 2026-05-22 | 2026-05-22 | 2026-06-10 | 2026-06-13 | 2026-06-13 | [6 empty] | 2026-06-15 | 2026-06-20 |  |  | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-29 | 2026-07-01 | 98 | Y | Shamoly | [5 empty] | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1035 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46145 | 0 | 27 | Jun'2 |  |  | 08.05.26
BS-NMT | 47298 | 13265870 | 1230 | 178 | 2026-03-23 | 2026-04-07 | LS Swt shirt w cuff btm rib and side contrast horn attach | Swt Shirt |  |  | 2026-04-25 | 2026-04-30 | 2026-05-05 | 2026-05-18 |  |  | 2026-05-19 | 2026-05-19 | 2026-06-06 | 2026-06-08 | 2026-06-09 | 2026-06-11 | 2026-06-13 |  |  |  |  | 2026-06-16 | 2026-06-17 |  |  | 2026-06-18 | 2026-06-20 | 2026-06-23 | 2026-06-29 | 2026-07-01 | 98 | T2 | Shamoly | Chest |  | peyote mellange-1230 pcs 3 clr rub print |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1230 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46147 | 0 | 27 | Jun'1 |  |  | 19.06.26
BS-ONS | 47414 | 22040041 | 2097 | 1587 | 2026-03-25 | 2026-04-02 | LS Half zipper Swt Shirt | Swt Shirt |  |  | 2026-04-22 | 2026-05-02 | 2026-05-05 | 2026-05-23 |  |  | 2026-06-06 | 2026-06-06 | 2026-06-15 | 2026-06-18 | 2026-06-19 |  |  |  |  | 2026-06-22 | 2026-06-27 | 2026-07-01 | 2026-07-04 |  |  | 2026-07-07 | 2026-07-10 | 2026-07-13 | 2026-07-20 | 2026-07-22 | 117 | C | Shovon |  | Chest | black-543 pcs,,pine-1098 pcs,,coffe-456 pcs all combo 1 clr flat 1 clr terry emb |  |  | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2097 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46147 | 0 | 30 | Jun'2 |  |  | 25.05.26
BS-ONL | 47413 | 15389044 | 300 | 110 | 2026-03-27 | 2026-04-04 | AOP SS o nk Long Dress | Dress |  |  | 2026-04-25 | 2026-04-28 | 2026-05-06 | 2026-05-16 | 2026-05-19 | 2026-05-25 | 2026-06-08 | 2026-06-08 | 2026-06-15 | 2026-06-17 | 2026-06-17 | [6 empty] | 2026-06-20 | 2026-06-20 |  |  | 2026-06-23 | 2026-06-25 | 2026-06-30 | 2026-07-13 | 2026-07-15 | 108 | K | Zahirul |  |  |  | AOP |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -300 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46148 | 0 | 29 | Jun'2 |  |  | 23.05.23
BS-ONL | 47419 | 15390471 | 600 | 220 | 2026-03-27 | 2026-04-06 | LS contrast piping shirt w btn and legging set | Top & BTM |  |  | 2026-05-02 | 2026-05-08 | 2026-05-11 | 2026-05-23 |  |  | 2026-06-09 | 2026-06-09 | 2026-06-15 | 2026-06-18 | 2026-06-19 | [6 empty] | 2026-06-22 | 2026-06-24 |  |  | 2026-06-26 | 2026-06-29 | 2026-07-05 | 2026-07-13 | 2026-07-15 | 108 | J+P | Zahirul | [5 empty] | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -600 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46153 | 0 | 29 | Jun'2 |  |  | 25.06.26
BS-ONL | 47412 | 15390465 | 600 | 235 | 2026-03-27 | 2026-04-06 | AOP LS o nk TS and Legging w self drawstring | Top & BTM |  |  | 2026-04-24 | 2026-04-28 | 2026-05-05 | 2026-05-16 | 2026-05-18 | 2026-05-25 | 2026-06-09 | 2026-06-09 | 2026-06-15 | 2026-06-17 | 2026-06-18 | [6 empty] | 2026-06-22 | 2026-06-23 |  |  | 2026-06-25 | 2026-06-27 | 2026-06-30 | 2026-07-13 | 2026-07-15 | 108 | P+O1 | Zahirul |  |  |  | AOP |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -600 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46147 | 0 | 29 | Jun'2 |  |  | 23.05.26
OVS SPA | 47421 | 262TSH209-6140 | 9276 | 1040 | 2026-03-30 | 2026-04-06 | LS High nk TS w back nk Placket btn | TS |  |  | 2026-04-20 | 2026-04-30 | 2026-05-02 | 2026-05-14 |  |  | 2026-06-06 | 2026-05-23 | 2026-06-09 | 2026-06-10 | 2026-06-13 | 2026-06-13 | 2026-06-18 | 2026-06-15 | 2026-06-23 |  |  | 2026-06-18 | 2026-06-26 |  |  | 2026-06-27 | 2026-06-30 | 2026-07-02 | 2026-07-06 | 2026-07-06 | 98 | NCL | Basir | Chest,Stone |  | white-4638 pcs 5 clr pig 1 size HP stone,,red-4638 pcs 5 clr rub 1 size HP stone |  |  | NCL |  |  | Ready Test Cut | 0 | 0 | 0 | 0 | -9276 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46144 | 0 | 28 | Jun'1
OVS SPA | 47422 | 262TSH210-6140 | 9030 | 1005 | 2026-03-30 | 2026-04-06 | LS High nk TS w back nk Placket btn | TS |  |  | 2026-04-20 | 2026-04-30 | 2026-05-02 | 2026-05-15 |  |  | 2026-06-08 | 2026-06-19 | 2026-06-25 | 2026-06-27 | 2026-06-30 | [6 empty] | 2026-07-01 | 2026-07-07 |  |  | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 102 | Q | Basir | [5 empty] | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -9030 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46144 | 0 | 28 | Jun'2 |  |  | 10.06.26
OVS SPA | 47423 | 262TSH317-227 | 7788 | 850 | 2026-03-30 | 2026-04-06 | LS High nk TS w back nk Placket btn | TS |  |  | 2026-05-02 | 2026-05-14 | 2026-05-15 | 2026-06-15 |  |  | 2026-06-25 | 2026-06-22 | 2026-06-27 | 2026-06-29 | 2026-07-02 | 2026-07-02 | 2026-07-07 |  |  |  |  | 2026-07-07 | 2026-07-14 |  |  | 2026-07-15 | 2026-07-16 | 2026-07-18 | 2026-07-20 | 2026-07-20 | 112 | E | Salam | Chest |  | Sugar-3978 pcs 4 clr or 2 clr rub 1 clr trasparent gltr ,,Purple-3810 pcs 5 clr rub or 3 clr rub |  | Need merchandiser artwork confirmation | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -7788 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 30 | Jun'3 |  |  | 25.05.26
GBX-New Look | 47409 | TBC | 1832 | 1132 | 2026-04-02 | 2026-04-04 | LS YD polo w collar placket btn and cuff rib | Polo | 2026-04-23 | 2026-04-30 | 2026-05-05 | 2026-05-18 | 2026-05-22 | 2026-06-10 |  |  | 2026-06-13 | 2026-06-13 | 2026-06-20 | 2026-06-24 | 2026-06-27 | [6 empty] | 2026-07-01 | 2026-07-06 |  |  | 2026-07-08 | 2026-07-10 | 2026-07-13 | 2026-07-18 | 2026-07-19 | 107 | J | Morad |  |  |  | YD |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1832 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46164 | 0 | 30 | Jun'3 |  |  | 03.07.26
GBX-New Look | 47407 | TBC | 4810 | 1800 | 2026-04-02 | 2026-04-04 | SS TS w frt falf placket btn | TS |  |  | 2026-04-22 | 2026-05-05 | 2026-05-09 | 2026-05-26 |  |  | 2026-06-09 | 2026-06-09 | 2026-06-15 | 2026-06-17 | 2026-06-20 | [6 empty] | 2026-06-22 | 2026-06-27 |  |  | 2026-06-30 | 2026-07-03 | 2026-07-07 | 2026-07-18 | 2026-07-19 | 107 | K | Morad | [5 empty] | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -4810 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46151 | 0 | 30 | Jun'2 |  |  | 25.05.26
GBX-New Look | 47408 | MF Rib Henley SS Tee | 1480 | 463 | 2026-04-02 | 2026-04-04 | SS TS w frt falf placket btn | TS |  |  | 2026-05-02 | 2026-05-09 | 2026-05-18 | 2026-06-09 |  |  | 2026-06-13 | 2026-06-13 | 2026-06-20 | 2026-06-23 | 2026-06-25 | [6 empty] | 2026-06-27 | 2026-06-30 |  |  | 2026-07-03 | 2026-07-06 | 2026-07-10 | 2026-07-18 | 2026-07-19 | 107 | K | Morad | [5 empty] | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1480 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46160 | 0 | 30 | Jun'3 |  |  | 25.05.26
OVS SPA | 47420 | 262TSH322-227 | 22999 | 2549 | 2026-04-01 | 2026-04-06 | LS High nk TS w back nk Placket btn | TS |  |  | 2026-05-02 | 2026-05-18 | 2026-05-20 | 2026-06-15 |  |  | 2026-07-02 | 2026-06-27 | 2026-07-04 | 2026-07-06 | 2026-07-11 | 2026-07-09 | 2026-07-15 | 2026-07-13 | 2026-07-20 |  |  | 2026-07-14 | 2026-07-28 |  |  | 2026-07-29 | 2026-07-31 | 2026-08-03 | 2026-08-05 | 2026-08-05 | 126 | E | Salam | Chest,Stone |  | white--9941 pcs 6 clr pig and 1 size HP stone,,red-7105 pcs 2 clr puff print no stone or 5 clr rub 1 clr gltr (need merchant confirmation ,,white another-5953 pcs 4 clr pig 1 clr gltr print no stone |  | Need merchandiser artwork confirmation | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -22999 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46162 | 0 | 32 | Jul'1 |  |  | 19.06.26
BS-ONL | 27204 48th | 15323159 | 19120 | 4582 | 2026-04-07 | 2026-04-09 | LS o nk TS | TS |  |  | 2026-04-22 | 2026-05-03 | 2026-05-03 | 2026-05-23 |  |  | 2026-05-18 | 2026-05-18 |  | 2026-05-25 | 2026-06-08 | [6 empty] | 2026-06-08 | 2026-06-15 |  |  | 2026-06-17 | 2026-06-18 | 2026-06-20 | 2026-07-27 | 2026-07-29 | 76 | F | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -19120 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46145 | 0 | 31 | May'3 |  |  | 25.04.26
BS-ONS | 47418 | 22039832 | 555 | 179 | 2026-03-25 | 2026-04-08 | SS o nk TS | TS |  |  | 2026-04-28 | 2026-05-03 | 2026-05-08 | 2026-05-20 |  |  | 2026-05-23 | 2026-05-23 | 2026-06-08 | 2026-06-10 | 2026-06-10 | 2026-06-13 | 2026-06-16 |  |  |  |  | 2026-06-18 | 2026-06-19 |  |  | 2026-06-20 | 2026-06-23 | 2026-06-26 | 2026-07-05 | 2026-07-07 | 102 | F | Shakel | Fr & Bk & Nk |  | Jet black-579 pcs frt 2 clr rub back photo print |  | License order | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -555 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46150 | 0 | 28 | Jun'1 |  |  | 19.06.26
BS-ONS | 47417 | 22039852 | 880 | 546 | 2026-03-30 | 2026-04-08 | LS o nk Swt Shirt | Swt Shirt |  |  | 2026-05-02 | 2026-05-07 | 2026-05-18 | 2026-06-08 |  |  | 2026-06-12 | 2026-06-12 | 2026-06-17 | 2026-06-20 | 2026-06-20 | 2026-06-24 | 2026-06-25 |  |  | 2026-06-24 | 2026-06-27 | 2026-07-01 | 2026-07-02 |  |  | 2026-07-04 | 2026-07-07 | 2026-07-10 | 2026-07-20 | 2026-07-22 | 112 | A | Shakel | Nk | Chest | LGM-859 pcs,,black-69 pcs both combo nk 1 clr rub print and chest 4 clr flat emb |  | License order | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -880 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46160 | 0 | 30 | Jun'2 |  |  | 16.06.26
BS-ONS | 47416 | 22039851 | 1752 | 555 | 2026-03-27 | 2026-04-08 | SS o nk TS | TS |  |  | 2026-05-02 | 2026-05-07 | 2026-05-12 | 2026-06-06 |  |  | 2026-06-10 | 2026-06-10 | 2026-06-16 | 2026-06-18 | 2026-06-19 | 2026-06-22 | 2026-06-23 |  |  | 2026-06-23 | 2026-06-25 | 2026-06-27 | 2026-06-29 |  |  | 2026-06-30 | 2026-07-02 | 2026-07-04 | 2026-07-18 | 2026-07-20 | 113 | D1 | Shakel | Nk | Chest | black-720 pcs,,c. dancer-1080 pcs both combo nk 1 clr rub print and chest 4 clr flat emb |  |  | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1752 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46154 | 0 | 30 | Jun'2 |  |  | 16.06.26
BS-ONS | 41626 24th | 22031973 | 3000 | 1935 | 2026-04-09 | 2026-04-11 | MENS LONG SWT PANT W SIDE & BK PKT | PANT |  |  | 2026-04-23 | 2026-05-02 | 2026-05-06 | 2026-05-20 |  |  | 2026-05-20 | 2026-05-20 |  | 2026-06-05 | 2026-06-06 | [6 empty] | 2026-06-08 | 2026-06-12 |  |  | 2026-06-15 | 2026-06-16 | 2026-06-18 | 2026-07-27 | 2026-07-29 | 109 | B | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -3000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46148 | 0 | 31 | Jun'1 |  |  | 22.04.26
BS-ONS | 47415 | 22040202 | 516 | 328 | 2026-03-31 | 2026-04-09 | LS swt hoody w cuff btm rib | Swt Shirt |  |  | 2026-05-03 | 2026-05-10 | 2026-05-15 | 2026-06-06 |  |  | 2026-06-10 | 2026-06-10 | 2026-06-17 | 2026-06-19 | 2026-06-19 |  |  |  |  | 2026-06-22 | 2026-06-27 | 2026-07-01 | 2026-07-02 |  |  | 2026-07-04 | 2026-07-07 | 2026-07-10 | 2026-07-20 | 2026-07-22 | 111 | A | Shovon |  | Chest | LGM-516 pcs contrast applique fab attach emb |  | ONS-Junior | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -516 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 30 | Jun'2 |  |  | 13.06.26
BS-ONS | 47439 | 22040115 | 513 | 81 | 2026-03-31 | 2026-04-09 | SS o nk TS | TS |  |  | 2026-05-06 | 2026-05-10 | 2026-05-22 | 2026-06-08 |  |  | 2026-06-11 | 2026-06-11 | 2026-06-17 | 2026-06-20 | 2026-06-20 | 2026-06-23 | 2026-06-26 |  |  |  |  | 2026-07-01 | 2026-07-01 |  |  | 2026-07-03 | 2026-07-06 | 2026-07-09 | 2026-07-20 | 2026-07-22 | 111 | G2 | Shovon | Fr,Bk |  | c.dan-513 pcs frt back 1 clr rub print |  | ONS-Junior | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -513 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46164 | 0 | 30 | Jun'2 |  |  | 13.06.26
BS-ONL | 47460 | 15383814 | 1808 | 475 | 2026-04-09 | 2026-04-09 | SS o nk TS | TS |  |  | 2026-05-02 | 2026-05-08 | 2026-05-12 | 2026-05-25 |  |  | 2026-06-08 | 2026-06-08 | 2026-06-15 | 2026-06-17 | 2026-06-18 |  |  |  |  | 2026-06-20 | 2026-06-27 | 2026-07-01 | 2026-07-03 |  |  | 2026-07-04 | 2026-07-06 | 2026-07-07 | 2026-07-12 | 2026-07-14 | 94 | O1 | Jannati |  | Fr & Bk | N sky-624 pcs,,c.dan-1184 pcs both combo frt back 1 clr flat and Applique attach emb |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1808 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46154 | 0 | 29 | Jun'2 |  |  | 05.06.26
BS-ONL | 47453 | 15333887 | 2565 | 1142 | 2026-04-07 | 2026-04-11 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-04-22 | 2026-05-02 | 2026-05-06 | 2026-05-25 |  |  | 2026-05-22 | 2026-05-22 | 2026-06-08 | 2026-06-11 | 2026-06-15 |  |  | 2026-06-15 | 2026-06-23 |  |  | 2026-06-25 | 2026-06-29 |  |  | 2026-07-01 | 2026-07-03 | 2026-07-06 | 2026-07-13 | 2026-07-15 | 97 | N2 | Jannati | Stone |  | black-1350 pcs,,fig-1215 pcs both combo ffrt both slve all over stone HP |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2565 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46148 | 0 | 29 | Jun'2 |  |  | 05.06.26
BS-ONL | 47041 2nd | 15355912 | 1464 | 1295 | 2026-04-07 | 2026-04-11 | LS Swt shirt w hand sewn nk lace attach | Swt Shirt |  |  | 2026-05-02 | 2026-05-10 | 2026-05-15 | 2026-06-06 |  |  | 2026-06-06 | 2026-06-06 |  | 2026-06-13 | 2026-06-15 |  |  | 2026-06-20 | 2026-06-26 |  |  | 2026-06-17 | 2026-06-19 |  |  | 2026-06-29 | 2026-06-30 | 2026-07-05 | 2026-07-13 | 2026-07-15 | 97 | K | Jannati |  |  | 2 combo hand sewn lace hand sewn at collar |  | Hand sewn stone lace | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1464 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 29 | Jun'2 |  |  | 05.05.26
BS-ONL | 47486 | 15390965 | 800 | 172 | 2026-04-01 | 2026-04-15 | AOP LS U nk TS w nk Lace | TS |  |  | 2026-05-06 | 2026-05-12 | 2026-05-18 | 2026-06-06 | 2026-06-10 | 2026-06-16 | 2026-06-18 | 2026-06-18 | 2026-06-24 | 2026-06-26 | 2026-06-27 | [6 empty] | 2026-07-01 | 2026-07-02 |  |  | 2026-07-04 | 2026-07-07 | 2026-07-08 | 2026-07-13 | 2026-07-15 | 103 | N1 | Mainul |  |  |  | AOP |  | NFL2 |  |  | Cut Ok | 172 | 172 | 0 | 0 | -800 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46160 | 0 | 29 | Jun'3 |  |  | 08.07.26
BS-ONL | 47487 | 15390966 | 800 | 286 | 2026-04-01 | 2026-04-15 | AOP Long Plazo w waist picoting | Legging |  |  | 2026-05-06 | 2026-05-13 | 2026-05-18 | 2026-06-06 | 2026-06-09 | 2026-06-15 | 2026-06-17 | 2026-06-17 | 2026-06-23 | 2026-06-26 | 2026-06-27 | [6 empty] | 2026-07-01 | 2026-07-02 |  |  | 2026-07-03 | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-15 | 103 | L2 | Mainul |  |  |  | AOP |  | NFL2 |  |  | Cut Ok | 330 | 330 | 0 | 0 | -800 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46160 | 0 | 29 | Jun'3 |  |  | 08.07.26
BS-ONL | 47485 | 15248240 | 2430 | 380 | 2026-04-07 | 2026-04-15 | SS o nk TS | TS |  |  | 2026-05-02 | 2026-05-07 | 2026-05-12 | 2026-05-24 |  |  | 2026-05-24 | 2026-05-24 | 2026-06-09 | 2026-06-11 | 2026-06-12 | [6 empty] | 2026-06-15 | 2026-06-18 |  |  | 2026-06-20 | 2026-06-22 | 2026-06-24 | 2026-06-29 | 2026-07-01 | 83 | O1 | Mainul | [5 empty] | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2430 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46154 | 0 | 27 | Jun'2 |  |  | 22.04.26
BS-ONL | 47436 | 15389237 | 1893 | 965 | 2026-03-31 | 2026-04-08 | LS reglan Slve Swt shirt | Swt Shirt |  |  | 2026-04-23 | 2026-04-30 | 2026-05-05 | 2026-05-18 |  |  | 2026-05-20 | 2026-05-20 | 2026-06-08 | 2026-06-11 | 2026-06-12 |  |  | 2026-06-15 | 2026-06-19 |  |  | 2026-06-22 | 2026-06-24 |  |  | 2026-06-26 | 2026-06-29 | 2026-07-03 | 2026-07-20 | 2026-07-22 | 111 | N2 | Zahirul | Stone |  | black-1107 pcs,,coffe-786 pcs both combo both slve HP stone |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1893 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46147 | 0 | 30 | Jun'2 |  |  | 05.06.26
BS-ONL | 47434 | 15358644 | 2022 | 1340 | 2026-03-31 | 2026-04-08 | LS reglan Slve Swt shirt dress | Swt Shirt |  |  | 2026-04-24 | 2026-05-04 | 2026-05-12 | 2026-06-06 |  |  | 2026-06-09 | 2026-06-09 | 2026-06-16 | 2026-06-19 | 2026-06-20 |  |  | 2026-06-23 | 2026-06-27 |  |  | 2026-07-01 | 2026-07-04 |  |  | 2026-07-06 | 2026-07-08 | 2026-07-10 | 2026-07-20 | 2026-07-22 | 111 | K | Zahirul | Stone |  | black-861 pcs,,coffe-1161 pcs both combo both slve HP stone |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2022 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46154 | 0 | 30 | Jun'2 |  |  | 22.05.26
BS-ONL | 24475 13th | 15188036 | 504 | 105 | 2026-03-31 | 2026-04-08 | Tank Top | Tank Top |  |  | 2026-05-02 | 2026-05-06 | 2026-05-12 | 2026-05-22 |  |  | 2026-06-06 | 2026-06-06 |  | 2026-06-12 | 2026-06-12 | [6 empty] | 2026-06-15 | 2026-06-16 |  |  | 2026-06-18 | 2026-06-20 | 2026-06-25 | 2026-07-20 | 2026-07-22 | 111 | O2 | Zahirul | [5 empty] | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 535 | 31 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46154 | 0 | 30 | Jun'2 |  |  | 22.05.26
BS-ONL | 47435 | 15384316 | 2280 | 1125 | 2026-03-31 | 2026-04-08 | LS Swt shirt w cuff btm rib and V shape rib panel | Swt Shirt |  |  | 2026-04-20 | 2026-04-26 | 2026-05-02 | 2026-05-13 |  |  | 2026-05-13 | 2026-05-13 | 2026-05-18 | 2026-05-20 | 2026-05-21 | 2026-05-23 | 2026-06-05 |  |  | 2026-06-05 | 2026-06-08 | 2026-06-08 | 2026-06-11 |  |  | 2026-06-12 | 2026-06-13 | 2026-06-15 | 2026-06-15 | 2026-07-17 | 76 | K | Zahirul | Chest | Chest | kalamata-1374 pcs 1 clr rub 1 clr lurex emb,,LGM-906 pcs 1 clr 1 clr flat emb |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2280 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46144 | 0 | 29 | May'2 |  |  | 07.05.26
BS-ONL | 47430 | 15384235 | 504 | 110 | 2026-03-31 | 2026-04-09 | SS o nk TS | TS |  |  | 2026-05-02 | 2026-05-06 | 2026-05-10 | 2026-05-22 |  |  | 2026-06-08 | 2026-06-08 | 2026-06-13 | 2026-06-15 | 2026-06-15 | 2026-06-17 | 2026-06-19 |  |  |  |  | 2026-06-22 | 2026-06-23 |  |  | 2026-06-25 | 2026-06-27 | 2026-06-30 | 2026-07-20 | 2026-07-22 | 111 | O1 | Zahirul | Chest |  | black-504 pcs photo print w 1 clr foil print |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -504 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46152 | 0 | 30 | Jun'2 |  |  | 23.05.26
BS-ONL | 47426 | 15384275 | 504 | 115 | 2026-03-31 | 2026-04-09 | SS o nk TS | TS |  |  | 2026-05-02 | 2026-05-06 | 2026-05-12 | 2026-05-22 |  |  | 2026-06-06 | 2026-06-06 | 2026-06-11 | 2026-06-13 | 2026-06-13 | 2026-06-16 | 2026-06-19 |  |  |  |  | 2026-06-22 | 2026-06-23 |  |  | 2026-06-25 | 2026-06-27 | 2026-06-30 | 2026-07-20 | 2026-07-22 | 111 | O1 | Zahirul | Fr,Bk |  | coffee-504 pcs frt back 1 clr rub print |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -504 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46154 | 0 | 30 | Jun'2 |  |  | 23.05.26
BS-ONL | 27204 50th | 15323159 | 5040 | 1208 | 2026-04-14 | 2026-04-15 | LS o nk TS | TS |  |  | 2026-05-03 | 2026-05-12 | 2026-05-15 | 2026-05-25 |  |  | 2026-06-06 | 2026-06-06 |  | 2026-06-12 | 2026-06-15 | [6 empty] | 2026-06-17 | 2026-06-20 |  |  | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-29 | 2026-07-01 | 76 | F | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -5040 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 27 | Jun'2 |  |  | 25.04.26
BS-ONL | 43969 36th | 15270390 | 6080 | 1009 | 2026-04-09 | 2026-04-10 | SS o nk TS | TS |  |  | 2026-05-03 | 2026-05-10 | 2026-05-15 | 2026-06-06 |  |  | 2026-06-05 | 2026-06-05 |  | 2026-06-10 | 2026-06-11 | [6 empty] | 2026-06-13 | 2026-06-16 |  |  | 2026-06-18 | 2026-06-20 | 2026-06-23 | 2026-06-29 | 2026-07-01 | 81 | ZA1 | Dalim | [5 empty] | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -6080 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 27 | Jun'1 |  |  | 25.04.26
OVS SPA | 47443 | 262PJA1118-903 | 15674 | 4519 | 2026-04-02 | 2026-04-11 | LS TS and AOP Pant w self drawstring | Top & BTM |  |  | 2026-05-02 | 2026-05-14 | 2026-05-14 | 2026-06-08 | 2026-06-09 | 2026-06-20 | 2026-06-27 | 2026-06-13 | 2026-06-19 | 2026-06-20 | 2026-06-26 | 2026-06-25 | 2026-07-02 |  |  | 2026-07-02 | 2026-07-08 | 2026-07-07 | 2026-07-16 |  |  | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-22 | 2026-07-22 | 111 | A+D | Salam | Chest,HP | Chest | jet stream top-7837 pcs 6 clr pig and 1 clr flat emb ,,melang btm-7837 pcs no print emb | AOP |  | NFL1 |  |  | Cut Ok | 4656 | 4656 | 0 | 0 | -15674 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46156 | 0 | 30 | Jun'2 |  |  | 10.06.26
OVS SPA | 47441 | 262PJA1114-903 | 7932 | 2320 | 2026-04-02 | 2026-04-11 | LS TS and AOP Pant w self drawstring | Top & BTM |  |  | 2026-05-02 | 2026-05-13 | 2026-05-14 | 2026-06-08 | 2026-06-09 | 2026-06-22 | 2026-06-30 | 2026-06-23 | 2026-06-30 | 2026-07-01 | 2026-07-06 | 2026-07-04 | 2026-07-11 |  |  |  |  | 2026-07-10 | 2026-07-15 |  |  | 2026-07-16 | 2026-07-17 | 2026-07-20 | 2026-07-22 | 2026-07-22 | 111 | N/2 | Salam | Chest,HP |  | June bug top-3966 pcs 1 cl flock 1 clr gltr print ,,grey btm-3966 pcs no print | AOP |  | NCL |  |  | Ready Test Cut | 2357 | 2357 | 0 | 0 | -7932 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46156 | 0 | 30 | Jul'1
OVS SPA | 47442 | 262PJA1116-903 | 15674 | 5035 | 2026-04-02 | 2026-04-11 | LS TS w pkt & front half placke btn and AOP Pant w self drawstring | Top & BTM |  |  | 2026-05-02 | 2026-05-14 | 2026-05-14 | 2026-06-08 | 2026-06-09 | 2026-06-20 | 2026-06-27 | 2026-06-18 | 2026-06-25 | 2026-06-26 | 2026-07-02 | 2026-07-02 | 2026-07-08 |  |  |  |  | 2026-07-07 | 2026-07-16 |  |  | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-22 | 2026-07-22 | 111 | A+D | Salam | Chest,Pkt |  | Jet stream top-7837 pcs chest 5 clr pig pkt 1 clr puff print and nk HP ,,embold btm-7837 pcs no print | AOP |  | NFL1 |  |  | Cut Ok | 5035 | 5035 | 0 | 0 | -15674 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46156 | 0 | 30 | Jun'3 |  |  | 12.06.26
OVS SPA | 47444 | 262GOW1020-903 | 2244 | 1290 | 2026-03-30 | 2026-04-11 | LS night wear w velvet attach at slve hem | Cardigan |  |  | 2026-05-02 | 2026-05-13 | 2026-05-15 | 2026-06-15 |  |  | 2026-06-27 | 2026-06-26 | 2026-07-02 | 2026-07-03 | 2026-07-04 | [6 empty] | 2026-07-06 | 2026-07-09 |  |  | 2026-07-10 | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-15 | 107 | N/3 | Salam | [5 empty] | NCL |  |  | Ready Test Cut | 0 | 0 | 0 | 0 | -2244 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 29 | Jul'1
OVS SPA | 47469 | 262LEG249-6140 | 3785 | 536 | 2026-04-02 | 2026-04-11 | AOP elasted legging w fake fly and pkt | Legging |  |  | 2026-05-02 | 2026-05-13 | 2026-05-14 | 2026-06-08 | 2026-06-10 | 2026-06-20 | 2026-07-03 | 2026-07-04 | 2026-07-09 | 2026-07-10 | 2026-07-11 | [6 empty] | 2026-07-13 | 2026-07-17 |  |  | 2026-07-18 | 2026-07-20 | 2026-07-22 | 2026-07-25 | 2026-07-25 | 114 | G1 | Basir |  |  |  | AOP |  | NFL1 |  |  | Cut Ok | 536 | 536 | 0 | 0 | -3785 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46156 | 0 | 30 | Jul'1 |  |  | 01.07.26
OVS SPA | 47470 | 262JOG251-6140 | 4040 | 768 | 2026-04-02 | 2026-04-11 | LS Swt shirt w contrast collar and bk placket btn and AOP legging | Top & BTM |  |  | 2026-05-02 | 2026-05-13 | 2026-05-14 | 2026-06-08 | 2026-06-10 | 2026-06-20 | 2026-07-03 | 2026-06-29 | 2026-07-04 | 2026-07-06 | 2026-07-09 |  |  |  |  | 2026-07-09 | 2026-07-13 | 2026-07-13 | 2026-07-16 |  |  | 2026-07-17 | 2026-07-20 | 2026-07-22 | 2026-07-25 | 2026-07-25 | 114 | A+D | Basir |  | Chest | white top-2020 pcs 5 clr flat 1 clr lurex emb ,,Red btm-2020 pcs no emb | AOP |  | NFL1 |  |  | Cut Ok | 784 | 773 | -11 | 0 | -4040 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46156 | 0 | 30 | Jul'1 |  |  | 03.07.26
OVS SPA | 47471 | 262JOG252-6140 | 7700 | 1216 | 2026-04-02 | 2026-04-11 | LS Swt shirt w collar frill and bk placket btn and legging | Top & BTM |  |  | 2026-05-11 | 2026-05-22 | 2026-06-08 | 2026-06-20 |  |  | 2026-07-02 | 2026-06-24 | 2026-06-30 | 2026-07-01 | 2026-07-04 |  |  |  |  | 2026-07-04 | 2026-07-12 | 2026-07-11 | 2026-07-18 |  |  | 2026-07-20 | 2026-07-22 | 2026-07-24 | 2026-07-25 | 2026-07-25 | 114 | A+D | Basir |  | Chest | red top-3850 pcs 4 clr flat 1 clr lurex 1 clr terry emb and bow attach ,,blue btm-3850 pcs no emb |  |  | NFL1 |  |  | Cut Ok | 1298 | 1297 | -1 | 0 | -7700 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 30 | Jul'1 |  |  | 03.07.26
OVS SPA | 47481 | 262JOG315-227 | 25236 | 3628 | 2026-04-10 | 2026-04-11 | LS Swt shirt and leggin | Top & BTM |  |  | 2026-04-25 | 2026-05-08 | 2026-05-09 | 2026-06-10 |  |  | 2026-06-25 | 2026-06-13 | 2026-06-19 | 2026-06-20 | 2026-06-27 |  |  | 2026-06-26 | 2026-07-06 |  |  | 2026-07-04 | 2026-07-15 |  |  | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-20 | 101 | N/3 | Salam | Chest |  | Salsa top-12618 pcs 1 clr gltr print ,,salsa btm-12618 pcs no no stone |  | merchant confirm no print only stone | NCL |  |  | Ready Test Cut | 0 | 0 | 0 | 0 | -25236 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46151 | 0 | 30 | Jun'2
OVS SPA | 47468 | 262PJA1117-903 | 8384 | 2962 | 2026-04-09 | 2026-04-11 | LS boat nk TS and AOP trouser w self drawstring | Top & BTM |  |  | 2026-04-25 | 2026-05-08 | 2026-05-09 | 2026-05-22 | 2026-06-06 | 2026-06-16 | 2026-06-30 | 2026-06-24 | 2026-06-30 | 2026-07-01 | 2026-07-04 | 2026-07-04 | 2026-07-11 |  |  |  |  | 2026-07-10 | 2026-07-16 |  |  | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-22 | 2026-07-22 | 104 | N/2 | Salam | Chest,HP |  | blue top-4192 pcs 5 clr rub 2 clr puff print ,,grey btm-4192 pcs no print | AOP |  | NCL |  |  | Ready Test Cut | 2931 | 2931 | 0 | 0 | -8384 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46151 | 0 | 30 | Jul'1
OVS SPA | 47445 | 262NDG1019-903 | 4168 | 1667 | 2026-04-09 | 2026-04-17 | LS TS dress | Dress |  |  | 2026-05-02 | 2026-05-14 | 2026-05-15 | 2026-06-10 |  |  | 2026-06-20 | 2026-06-16 | 2026-06-22 | 2026-06-23 | 2026-06-25 | 2026-06-25 | 2026-07-01 |  |  |  |  | 2026-07-01 | 2026-07-06 |  |  | 2026-07-07 | 2026-07-09 | 2026-07-11 | 2026-07-15 | 2026-07-15 | 97 | N/2 | Salam | Chest,HP |  | potpouri-4168 pcs Digital photo print w 1 clr flock print |  |  | NCL |  |  | Ready Test Cut | 0 | 0 | 0 | 0 | -4168 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 29 | Jun'3
OVS SPA | 47503 | 262PJA1111-903 | 15990 | 4997 | 2026-04-13 | 2026-04-17 | LS o nk TS and AOP Elasted legging w self drawstring | Top & BTM |  |  | 2026-05-02 | 2026-05-13 | 2026-05-13 | 2026-05-25 | 2026-05-25 | 2026-06-15 | 2026-06-20 | 2026-06-06 | 2026-06-13 | 2026-06-15 | 2026-06-20 | 2026-06-20 | 2026-06-30 |  |  |  |  | 2026-07-01 | 2026-07-13 |  |  | 2026-07-14 | 2026-07-16 | 2026-07-18 | 2026-07-22 | 2026-07-22 | 100 | N/3 | Salam | Chest,HP |  | melange top-7995 pcs digital photo print w 1 clr puff print ,,June btm-7995 pcs no print | AOP |  | NCL |  |  | Ready Test Cut | 0 | 0 | 0 | 0 | -15990 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46155 | 0 | 30 | Jun'2
GBX-New Look | 47404 2nd | 9328960 | 908 | 300 | 2026-04-01 | 2026-04-10 | SS oversized fit SS TS | TS |  |  | 2026-05-10 | 2026-05-15 | 2026-06-05 | 2026-06-16 |  |  | 2026-06-18 | 2026-06-18 |  | 2026-06-24 | 2026-06-24 | 2026-06-27 | 2026-06-27 |  |  |  |  | 2026-07-01 | 2026-07-02 |  |  | 2026-07-04 | 2026-07-08 | 2026-07-10 | 2026-07-18 | 2026-07-18 | 108 | N/2 | Morad | Nk |  | 2 combo nk size label print |  |  | NCL |  |  | Ready Test Cut | 480 | 480 | 0 | 0 | -908 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46178 | 0 | 29 | Jun'3
BS-ONS | 47440 | 22040200 | 519 | 265 | 2026-03-31 | 2026-04-09 | LS Swt shirt w high nk half zipper | Swt Shirt |  |  | 2026-05-03 | 2026-05-10 | 2026-05-18 | 2026-06-13 |  |  | 2026-06-18 | 2026-06-18 | 2026-06-25 | 2026-06-27 | 2026-06-27 |  |  |  |  | 2026-07-01 | 2026-07-04 | 2026-07-08 | 2026-07-09 |  |  | 2026-07-11 | 2026-07-14 | 2026-07-20 | 2026-08-17 | 2026-08-19 | 139 | C | Shovon |  | Chest | black-519 pcs 1 clr flat 1 clr terry emb |  | ONS-Junior | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -519 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46160 | 0 | 34 | Jun'3 |  |  | 13.06.26
BS-ONL | 27204 51th | 15323159 | 10080 | 2419 | 2026-04-22 | 2026-04-23 | LS o nk TS | TS |  |  | 2026-05-05 | 2026-05-15 | 2026-06-05 | 2026-06-15 |  |  | 2026-06-10 | 2026-06-10 |  | 2026-06-15 | 2026-06-18 | [6 empty] | 2026-06-18 | 2026-06-23 |  |  | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-29 | 2026-07-01 | 68 | D2 | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 2419 | 2419 | 0 | 0 | -10080 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46178 | 0 | 27 | Jun'2 |  |  | 25.04.26
BS-NMT | 47517 | 13224978/13229864 | 5889 | 820 | 2026-04-16 | 2026-04-25 | LS O nk TS | TS |  |  | 2026-05-06 | 2026-05-13 | 2026-05-17 | 2026-06-13 |  |  | 2026-06-15 | 2026-06-15 | 2026-06-20 | 2026-06-23 | 2026-06-26 | 2026-06-25 | 2026-06-30 |  |  |  |  | 2026-07-02 | 2026-07-06 |  |  | 2026-07-08 | 2026-07-10 | 2026-07-14 | 2026-07-27 | 2026-07-29 | 102 | ZA1 | Kamruzzaman | Chest,Nk |  | white polar-798 pcs 5 clr pig ,,Island dog-801 pcs 5 clr pig ,,Navy Dino-816 pcs 5 clr pig ,,mosstone truckin-1737 pcs 5 clr rub ,,surf vroom-1737 pcs 3 clr rub |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -5889 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46159 | 0 | 31 | Jun'3 |  |  | 13.06.26
BS-NMT | 47518 | 13224969/13229841 | 8126 | 1659 | 2026-04-16 | 2026-04-25 | LS O nk TS | TS |  |  | 2026-05-07 | 2026-05-13 | 2026-05-17 | 2026-06-13 |  |  | 2026-06-15 | 2026-06-15 | 2026-06-20 | 2026-06-23 | 2026-06-26 | 2026-06-25 | 2026-06-29 |  |  |  |  | 2026-07-01 | 2026-07-04 |  |  | 2026-07-07 | 2026-07-10 | 2026-07-13 | 2026-07-20 | 2026-07-22 | 95 | ZA1 | Kamruzzaman | Chest,Nk |  | white sppeed-1587 pcs 5 clr pig ,,surf red-1587 pcs 4 clr pig ,,andora loading-1001 pcs 1 clr rub ,,white basket-794 pcs 5 clr pig ,,Island Dog-1511 pcs 5 clr pig ,,Navy Game-1646 pcs 5 clr rub |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -8126 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46159 | 0 | 30 | Jun'3 |  |  | 13.06.26
BS-NMT | 47519 | 13224952 | 1944 | 405 | 2026-04-16 | 2026-04-25 | LS O nk TS | TS |  |  | 2026-05-10 | 2026-05-15 | 2026-05-20 | 2026-06-14 |  |  | 2026-06-15 | 2026-06-15 | 2026-06-20 | 2026-06-22 | 2026-06-23 | 2026-06-25 | 2026-06-27 |  |  |  |  | 2026-07-01 | 2026-07-02 |  |  | 2026-07-04 | 2026-07-06 | 2026-07-09 | 2026-07-20 | 2026-07-22 | 95 | ZA2 | Kamruzzaman | Chest,Nk |  | grape-1032 pcs,,Navy-912 pcs both combo 2 clr rub |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1944 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46162 | 0 | 30 | Jun'3 |  |  | 20.06.26
BS-NMT | 47520 | 13229879 | 2010 | 273 | 2026-04-16 | 2026-04-25 | LS O nk TS | TS |  |  | 2026-05-10 | 2026-05-15 | 2026-06-05 | 2026-06-15 |  |  | 2026-06-15 | 2026-06-15 | 2026-06-20 | 2026-06-22 | 2026-06-23 | 2026-06-25 | 2026-06-27 |  |  |  |  | 2026-07-03 | 2026-07-04 |  |  | 2026-07-07 | 2026-07-09 | 2026-07-11 | 2026-07-27 | 2026-07-29 | 102 | ZA2 | Kamruzzaman | Chest,Nk |  | pink-1005 pcs,,Navy-1005 pcs |  | Artwork due | NFL3 |  |  | Cut Ok | 274 | 274 | 0 | 0 | -2010 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46178 | 0 | 31 | Jun'3 |  |  | 19.06.26
BS-NMT | 47521 | 13235107/13240391 | 3770 | 669 | 2026-04-16 | 2026-04-25 | LS O nk TS | TS |  |  | 2026-05-10 | 2026-05-15 | 2026-05-20 | 2026-06-10 |  |  | 2026-06-12 | 2026-06-12 | 2026-06-16 | 2026-06-18 | 2026-06-20 | 2026-06-20 | 2026-06-24 |  |  |  |  | 2026-06-25 | 2026-06-29 |  |  | 2026-07-02 | 2026-07-03 | 2026-07-08 | 2026-07-20 | 2026-07-22 | 95 | ZA2 | Kamruzzaman | Chest,Nk |  | Grape-2068 pcs,,Navy-2068 pcs both combo 1 clr gltr |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -3770 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46162 | 0 | 30 | Jun'1 |  |  | 20.06.26
BS-NMT | 47522 | 13225108/13255214 | 2408 | 305 | 2026-04-16 | 2026-04-25 | LS O nk TS | TS |  |  | 2026-05-10 | 2026-05-15 | 2026-06-05 | 2026-06-15 |  |  | 2026-06-17 | 2026-06-17 | 2026-06-23 | 2026-06-25 | 2026-06-26 | 2026-06-29 | 2026-06-30 |  |  |  |  | 2026-07-06 | 2026-07-08 |  |  | 2026-07-10 | 2026-07-13 | 2026-07-15 | 2026-07-27 | 2026-07-29 | 102 | ZA1 | Kamruzzaman | Chest,Nk |  | Grape-1604 pcs,,Navy-804 pcs both combo 1 clr gltr |  |  | NFL3 |  |  | Cut Ok | 305 | 305 | 0 | 0 | -2408 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46178 | 0 | 31 | Jun'3 |  |  | 19.06.26
BS-NMT | 47523 | 13262446 | 810 | 147 | 2026-04-16 | 2026-04-25 | LS Capsl dress | Dress |  |  | 2026-05-18 | 2026-05-23 | 2026-06-12 | 2026-06-22 |  |  | 2026-06-26 | 2026-06-26 | 2026-07-02 | 2026-07-04 | 2026-07-04 | 2026-07-07 | 2026-07-07 |  |  |  |  | 2026-07-09 | 2026-07-10 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-27 | 2026-07-29 | 102 | Y | Kamruzzaman | Chest,Nk |  | blooming-810 pcs 1 clr gltr print |  |  | NFL3 |  |  | Cut Ok | 146 | 146 | 0 | 0 | -810 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 31 | Jul'1 |  |  | 09.07.26
BS-NMT | 47524 | 13260598 | 1744 | 639 | 2026-04-16 | 2026-04-25 | AOP Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-05-07 | 2026-05-12 | 2026-05-16 | 2026-06-06 | 2026-06-06 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-17 | 2026-06-19 | 2026-06-20 | [6 empty] | 2026-06-23 | 2026-06-24 |  |  | 2026-06-26 | 2026-06-27 | 2026-06-30 | 2026-07-06 | 2026-07-08 | 81 | T1 | Kamruzzaman |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 640 | 640 | 0 | 0 | -1744 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46158 | 0 | 28 | Jun'1 |  |  | 26.06.26
BS-NMT | 47525 | 13260594 | 4146 | 967 | 2026-04-16 | 2026-04-25 | AOP Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-05-05 | 2026-05-13 | 2026-05-15 | 2026-06-08 | 2026-06-08 | 2026-06-16 | 2026-06-15 | 2026-06-15 | 2026-06-20 | 2026-06-22 | 2026-06-24 | [6 empty] | 2026-06-25 | 2026-06-27 |  |  | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-06 | 2026-07-08 | 81 | W2 | Kamruzzaman |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 967 | 942 | -25 | 0 | -4146 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 28 | Jun'3 |  |  | 26.06.26
BS-NMT | 47526 | 13235162 | 6264 | 1132 | 2026-04-16 | 2026-04-25 | AOP YD and solid LS TS w letus | TS | 2026-05-05 | 2026-05-12 | 2026-05-07 | 2026-05-20 | 2026-05-21 | 2026-06-16 | 2026-06-15 | 2026-06-20 | 2026-06-22 | 2026-06-22 | 2026-06-27 | 2026-06-29 | 2026-07-02 | 2026-07-02 | 2026-07-06 |  |  | 2026-07-02 | 2026-07-06 | 2026-07-07 | 2026-07-13 |  |  | 2026-07-15 | 2026-07-16 | 2026-07-18 | 2026-07-20 | 2026-07-22 | 95 | Z | Kamruzzaman | Nk | Chest | white bow-1320 pcs 1 clr lurex emb ,,Grap YD- no emb,,grap solid -1320 pcs no emb ,,pink Aop-1320 pcs no emb ,,pink YD-1152 pcs no emb | YD & AOP |  | NFL3 |  |  | Cut Ok | 1133 | 1133 | 0 | 0 | -6264 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46163 | 0 | 30 | Jun'3 |  |  | 26.06.26
BS-NMT | 47527 | 13235163 | 3612 | 474 | 2026-04-16 | 2026-04-25 | AOP YD and solid LS TS w letus | TS | 2026-05-15 | 2026-05-20 | 2026-05-20 | 2026-06-06 | 2026-06-09 | 2026-06-18 | 2026-06-20 | 2026-06-25 | 2026-06-26 | 2026-06-26 | 2026-07-02 | 2026-07-04 | 2026-07-07 | 2026-07-07 | 2026-07-08 |  |  |  |  | 2026-07-10 | 2026-07-13 |  |  | 2026-07-15 | 2026-07-17 | 2026-07-18 | 2026-07-27 | 2026-07-29 | 102 | Z | Kamruzzaman | Nk |  | 3 combo label print | YD & AOP |  | NFL3 |  |  | Cut Ok | 483 | 483 | 0 | 0 | -3612 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46182 | 0 | 31 | Jul'1 |  |  | 26.06.26
BS-NMT | 47528 | 13260622 | 3218 | 389 | 2026-04-16 | 2026-04-25 | LS o nk TS w letus | TS |  |  | 2026-05-07 | 2026-05-12 | 2026-05-18 | 2026-06-12 |  |  | 2026-06-12 | 2026-06-12 | 2026-06-17 | 2026-06-19 | 2026-06-20 | 2026-06-22 | 2026-06-24 |  |  | 2026-06-22 | 2026-06-25 | 2026-06-26 | 2026-06-29 |  |  | 2026-06-30 | 2026-07-02 | 2026-07-03 | 2026-07-06 | 2026-07-08 | 81 | ZA1 | Kamruzzaman | Nk | Chest | Navy-916 pcs 1 clr flat emb ,,red-1501 pcs 4 clr flat emb ,,Wild-801 pcs 2 clr flat emb |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -3218 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46160 | 0 | 28 | Jun'1 |  |  | 25.06.26
BS-NMT | 47529 | 13249494 | 2406 | 726 | 2026-04-16 | 2026-04-25 | LS full zipper Swt hoody | Hoody |  |  | 2026-05-06 | 2026-05-13 | 2026-05-16 | 2026-06-12 |  |  | 2026-06-13 | 2026-06-13 | 2026-06-19 | 2026-06-22 | 2026-06-24 | 2026-06-25 | 2026-06-29 |  |  |  |  | 2026-07-01 | 2026-07-04 |  |  | 2026-07-07 | 2026-07-09 | 2026-07-13 | 2026-07-27 | 2026-07-29 | 102 | S | Kamruzzaman | Chest |  | Abyss-786 pcs one part 5 clr rub ,,chocolate-786 pcs two part 6 clr rub,,Navy-834 pcs 2 part 6 clr rub |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2406 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46158 | 0 | 31 | Jun'3 |  |  | 01.07.26
BS-NMT | 47530 | 13250549 | 2979 | 670 | 2026-04-16 | 2026-04-25 | Swt Pant w drawstring | Pant |  |  | 2026-05-10 | 2026-05-16 | 2026-06-06 | 2026-06-18 |  |  | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-06-27 | 2026-06-29 | [6 empty] | 2026-07-01 | 2026-07-03 |  |  | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-27 | 2026-07-29 | 102 | U | Kamruzzaman | [5 empty] | NFL3 |  |  | Cut Ok | 670 | 670 | 0 | 0 | -2979 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 31 | Jun'3 |  |  | 26.06.26
BS-NMT | 47531 | 13260641 | 6865 | 2185 | 2026-04-16 | 2026-04-25 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-05-06 | 2026-05-13 | 2026-05-15 | 2026-06-09 |  |  | 2026-06-09 | 2026-06-09 | 2026-06-13 | 2026-06-15 | 2026-06-17 | 2026-06-16 | 2026-06-20 |  |  |  |  | 2026-06-20 | 2026-06-24 |  |  | 2026-06-26 | 2026-06-27 | 2026-06-30 | 2026-07-06 | 2026-07-08 | 81 | W2 | Kamruzzaman | Chest |  | botania-2533 pcs 5 clr rub print ,,Island-1983 pcs 6 clr rub print ,,Navy-2349 pcs 5 clr rub print |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -6865 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 28 | Jun'1 |  |  | 20.06.26
BS-NMT | 47532 | 13260636 | 3964 | 889 | 2026-04-16 | 2026-04-25 | AOP & Solid LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-05-05 | 2026-05-13 | 2026-05-15 | 2026-06-10 | 2026-06-06 | 2026-06-12 | 2026-06-10 | 2026-06-10 | 2026-06-16 | 2026-06-18 | 2026-06-20 | 2026-06-20 | 2026-06-22 |  |  |  |  | 2026-06-24 | 2026-06-26 |  |  | 2026-06-27 | 2026-06-29 | 2026-06-30 | 2026-07-06 | 2026-07-08 | 81 | W2 | Kamruzzaman | Chest |  | botania-763 pcs 6 clr rub print ,,Island AOP-784 pcs no print ,,Navy-1588 pcs 6 clr rub print ,,red dhalia AOP-829 pcs no print | AOP |  | NFL3 |  |  | Cut Ok | 887 | 887 | 0 | 0 | -3964 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 28 | Jun'1 |  |  | 26.06.26
BS-NMT | 47533 | 13260621 | 5898 | 1853 | 2026-04-16 | 2026-04-25 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-05-03 | 2026-05-13 | 2026-05-15 | 2026-06-10 |  |  | 2026-06-10 | 2026-06-10 | 2026-06-15 | 2026-06-16 | 2026-06-19 | 2026-06-18 | 2026-06-22 |  |  |  |  | 2026-06-22 | 2026-06-26 |  |  | 2026-06-27 | 2026-06-30 | 2026-07-02 | 2026-07-06 | 2026-07-08 | 81 | T1 | Kamruzzaman | Chest |  | Peyote-1576 pcs 2 clr rub 3 clr gltr ,,red-2176 pcs 1 clr rub 3 clr gltr ,,wild-2146 pcs 6 clr rub |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -5898 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 28 | Jun'1 |  |  | 26.06.26
BS-NMT | 47534 | 13260623 | 7909 | 1468 | 2026-04-16 | 2026-04-25 | AOP & Solid LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-05-05 | 2026-05-13 | 2026-05-15 | 2026-06-08 | 2026-06-05 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-15 | 2026-06-16 | 2026-06-19 | 2026-06-18 | 2026-06-22 |  |  |  |  | 2026-06-22 | 2026-06-25 |  |  | 2026-06-27 | 2026-06-29 | 2026-06-30 | 2026-07-06 | 2026-07-08 | 81 | W2 | Kamruzzaman | Fr,Bk |  | Navy-2370 pcs frt 6 clr rub back 1 clr rub,,peyote AOP-1218 pcs no print ,,red-3463 pcs frt 7 clr rub back no print ,,wild AOP-858 pcs no print |  |  | NFL3 |  |  | Cut Ok | 1670 | 1632 | -38 | 0 | -7909 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 28 | Jun'1 |  |  | 26.06.26
BS-NMT | 47535 | 13235095 | 2781 | 1187 | 2026-04-16 | 2026-04-25 | LS Swt hoody | Hoody |  |  | 2026-05-08 | 2026-05-15 | 2026-05-20 | 2026-06-15 |  |  | 2026-06-17 | 2026-06-17 | 2026-06-22 | 2026-06-24 | 2026-06-25 | [6 empty] | 2026-07-01 | 2026-07-04 |  |  | 2026-07-07 | 2026-07-09 | 2026-07-13 | 2026-07-20 | 2026-07-22 | 95 | T2 | Kamruzzaman | [5 empty] | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2781 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46162 | 0 | 30 | Jun'3 |  |  | 26.06.26
BS-NMT | 47681 | 13262049 | 810 | 170 | 2026-04-15 | 2026-04-28 | LS boat nk TS w nk Lace | TS |  |  | 2026-05-13 | 2026-05-17 | 2026-06-08 | 2026-06-18 |  |  | 2026-06-20 | 2026-06-20 | 2026-06-25 | 2026-06-27 | 2026-06-27 | [6 empty] | 2026-07-01 | 2026-07-02 |  |  | 2026-07-04 | 2026-07-08 | 2026-07-10 | 2026-07-20 | 2026-07-22 | 96 | Z | Tomal |  |  |  |  | Lace | NFL3 |  |  | Cut Ok | 170 | 170 | 0 | 0 | -810 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 30 | Jun'3 |  |  | 27.06.26
BS-NMT | 47660 | 13258653 | 3288 | 725 | 2026-04-14 | 2026-04-24 | AOP Swt pant w rib | Pant |  |  | 2026-05-04 | 2026-05-10 | 2026-05-15 | 2026-06-05 | 2026-06-06 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-17 | 2026-06-19 | 2026-06-20 | [6 empty] | 2026-06-22 | 2026-06-25 |  |  | 2026-06-26 | 2026-06-27 | 2026-06-29 | 2026-06-29 | 2026-07-01 | 76 | Z | Shamoly |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 725 | 725 | 0 | 0 | -3288 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 27 | Jun'1 |  |  | 25.05.26
BS-NMT | 47658 | 13258646 | 1606 | 240 | 2026-04-14 | 2026-04-24 | YD LS o nk TS | TS | 2026-05-07 | 2026-05-13 | 2026-05-16 | 2026-05-22 | 2026-06-05 | 2026-06-10 |  |  | 2026-06-09 | 2026-06-09 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 |  |  |  |  | 2026-06-22 | 2026-06-23 |  |  | 2026-06-24 | 2026-06-25 | 2026-06-27 | 2026-06-29 | 2026-07-01 | 76 | T1 | Shamoly | Chest,Nk |  | LGM-803 pcs,,c.dan-803 pcs both combo 2 clr rub print | YD |  | NFL3 |  |  | Cut Ok | 240 | 240 | 0 | 0 | -1606 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46178 | 0 | 27 | Jun'1 |  |  | 13.06.26
BS-NMT | 47659 | 13258652 | 4221 | 1161 | 2026-04-14 | 2026-04-24 | AOP LS SWt hoodie w full zipper | Hoody |  |  | 2026-05-02 | 2026-05-10 | 2026-05-12 | 2026-05-25 | 2026-05-25 | 2026-06-10 | 2026-06-09 | 2026-06-09 | 2026-06-15 | 2026-06-17 | 2026-06-20 | [6 empty] | 2026-06-20 | 2026-06-25 |  |  | 2026-06-26 | 2026-06-27 | 2026-06-29 | 2026-06-29 | 2026-07-01 | 76 | S | Shamoly |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -4221 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46154 | 0 | 27 | Jun'1 |  |  | 26.06.26
BS-NMT | 47665 | 13258661 | 2724 | 429 | 2026-04-14 | 2026-04-24 | SS o nk TS | TS |  |  | 2026-05-08 | 2026-05-12 | 2026-05-16 | 2026-06-08 |  |  | 2026-06-08 | 2026-06-08 | 2026-06-13 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 2026-06-18 |  |  |  |  | 2026-06-20 | 2026-06-23 |  |  | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-29 | 2026-07-01 | 76 | ZA1 | Shamoly | Fr & Bk & Nk |  | c.dan-908 pcs frt 1 clr rub back 5 clr rub,,pine-908 pcs frt back 1 clr rub,,blue-908 pcs frt back 2 clr rub |  |  | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2724 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46158 | 0 | 27 | Jun'1 |  |  | 25.05.26
BS-NMT | 47661 | 13258654 | 1600 | 457 | 2026-04-14 | 2026-04-24 | LS Swt Shirt w rib | Swt Shirt |  |  | 2026-05-06 | 2026-05-12 | 2026-05-18 | 2026-06-10 |  |  | 2026-06-10 | 2026-06-10 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 |  |  |  |  | 2026-06-22 | 2026-06-23 |  |  | 2026-06-24 | 2026-06-25 | 2026-06-27 | 2026-06-29 | 2026-07-01 | 76 | T2 | Shamoly | Chest |  | pine-800 pcs,,Navy-800 pcs both combo 1 clr puff print |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1600 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46160 | 0 | 27 | Jun'1 |  |  | 25.05.26
BS-NMT | 47662 | 13258657 | 2691 | 1150 | 2026-04-14 | 2026-04-29 | LS Swt shirt w vuff rib | Swt Shirt |  |  | 2026-05-07 | 2026-05-13 | 2026-05-16 | 2026-06-10 |  |  | 2026-06-08 | 2026-06-08 | 2026-06-13 | 2026-06-15 | 2026-06-16 | 2026-06-18 | 2026-06-20 |  |  |  |  | 2026-06-23 | 2026-06-24 |  |  | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-29 | 2026-07-01 | 76 | F | Shamoly | Fr,Bk |  | LGM-787 pcs frt 1 clr rub back no print ,,Pinre-952 pcs frt back 2 clr rub ,,black-952 pcs frt back 2 clr rub |  |  | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2691 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46158 | 0 | 27 | Jun'1 |  |  | 25.05.26
BS-NMT | 47663 | 13258658 | 1626 | 790 | 2026-04-14 | 2026-04-29 | Swt pant w waist belt | Pant |  |  | 2026-05-08 | 2026-05-14 | 2026-05-18 | 2026-06-10 |  |  | 2026-06-10 | 2026-06-10 | 2026-06-16 | 2026-06-18 | 2026-06-19 | [6 empty] | 2026-06-22 | 2026-06-24 |  |  | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-29 | 2026-07-01 | 76 | X | Shamoly | [5 empty] | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1626 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46160 | 0 | 27 | Jun'1 |  |  | 25.05.26
BS-NMT | 47664 | 13258659 | 3215 | 1608 | 2026-04-14 | 2026-04-29 | LS swt hoody w rib | Hoody |  |  | 2026-05-04 | 2026-05-13 | 2026-05-15 | 2026-06-08 |  |  | 2026-06-06 | 2026-06-06 | 2026-06-13 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-20 |  |  |  |  | 2026-06-22 | 2026-06-24 |  |  | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-29 | 2026-07-01 | 76 | V | Shamoly | slv,Chest |  | pine- 1630 pcs chest 3 clr rub slve no print ,,blue-1585 pcs chest one slve 2 clr rub |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -3215 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 27 | Jun'1 |  |  | 25.05.26
BS-NMT | 47666 | 13258665 | 5126 | 2520 | 2026-04-14 | 2026-04-29 | LS swt hoody w rib | Hoody |  |  | 2026-05-06 | 2026-05-15 | 2026-05-16 | 2026-06-10 |  |  | 2026-06-08 | 2026-06-08 | 2026-06-13 | 2026-06-15 | 2026-06-17 | 2026-06-17 | 2026-06-20 |  |  |  |  | 2026-06-22 | 2026-06-25 |  |  | 2026-06-26 | 2026-06-27 | 2026-06-29 | 2026-06-29 | 2026-07-01 | 76 | V | Shamoly | Fr,Bk |  | LGm-1292 pcs frt 2 clr rub back no print ,,pine-1849 pcs frt back 2 clr rub ,,Navy-1985 pcs frt back 1 clr rub |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -5126 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46158 | 0 | 27 | Jun'1 |  |  | 25.05.26
BS-NMT | 47667 | 13258669 | 5935 | 1588 | 2026-04-14 | 2026-04-29 | Swt pant w waist belt | Pant |  |  | 2026-05-17 | 2026-05-16 | 2026-05-16 | 2026-06-10 |  |  | 2026-06-09 | 2026-06-09 | 2026-06-15 | 2026-06-17 | 2026-06-20 | [6 empty] | 2026-06-20 | 2026-06-26 |  |  | 2026-06-27 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-07-01 | 76 | X | Shamoly | [5 empty] | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -5935 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46158 | 0 | 27 | Jun'1 |  |  | 25.05.26
BS-NMT | 47542 | 13261843 | 6165 | 804 | 2026-04-15 | 2026-04-27 | Pant w cargo pkt and drawstring | Pant |  |  | 2026-05-12 | 2026-05-18 | 2026-06-10 | 2026-06-17 |  |  | 2026-06-18 | 2026-06-18 | 2026-06-25 | 2026-06-27 | 2026-06-30 | [6 empty] | 2026-07-01 | 2026-07-06 |  |  | 2026-07-08 | 2026-07-10 | 2026-07-14 | 2026-07-27 | 2026-07-29 | 103 | X | Mosaddik |  |  |  |  | Imp fab on 07/06 | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -6165 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 31 | Jun'3 |  |  | 30.06.26
BS-NMT | 47541 | 13261845 | 1140 | 165 | 2026-04-15 | 2026-04-27 | Swt Shirt w shlder snap btn and kangaro pkt | Swt Shirt |  |  | 2026-05-15 | 2026-05-17 | 110/6 | 2026-06-18 |  |  | 2026-06-23 | 2026-06-23 | 2026-06-29 | 2026-07-01 | 2026-07-02 | [6 empty] | 2026-07-06 | 2026-07-08 |  |  | 2026-07-10 | 2026-07-13 | 2026-07-15 | 2026-07-27 | 2026-07-29 | 103 | S | Mosaddik |  |  |  |  | Imp fab on 07/06 | NFL3 |  |  | Cut Ok | 3 | 3 | 0 | 0 | -1140 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | #VALUE! | 0 | 31 | Jul'1 |  |  | 30.06.26
BS-NMT | 47558 | 13258871 | 1626 | 133 | 2026-04-15 | 2026-04-27 | LS o nk TS w shlder snap btn | TS |  |  | 2026-05-09 | 2026-05-14 | 2026-05-18 | 2026-06-10 |  |  | 2026-06-10 | 2026-06-10 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-22 |  |  |  |  | 2026-06-24 | 2026-06-26 |  |  | 2026-06-29 | 2026-06-30 | 2026-07-02 | 2026-07-05 | 2026-07-07 | 81 | T1 | Mosaddik | Chest,Nk |  | Lotus-813 pcs 4 clr rub 1 clr gltr ,,white-813 pcs 2 clr rub 1 clr gltr |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1626 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46160 | 0 | 28 | Jun'1 |  |  | 06.06.26
BS-NMT | 47561 | 13261553 | 2993 | 163 | 2026-04-15 | 2026-04-27 | AOP Elsated Legging | Legging |  |  | 2026-05-18 | 2026-05-22 | 2026-06-08 | 2026-06-17 | 2026-06-20 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-30 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-06 |  |  |  |  | 2026-07-08 | 2026-07-09 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-27 | 2026-07-29 | 103 | W1 | Mosaddik | Waist |  | 2 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 163 | 163 | 0 | 0 | -2993 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 31 | Jul'1 |  |  | 09.06.26
BS-NMT | 47546 | 13265448 | 3018 | 286 | 2026-04-15 | 2026-04-27 | LS dress w collar and bow | Dress |  |  | 2026-07-03: 2026-06-24; 2026-07-04: 2026-06-24; 2026-07-09: 2026-06-30; 2026-07-10: 2026-07-03; 2026-07-11: 2026-07-06 | 2026-07-06 | 2026-07-08 |  |  |  |  | 2026-07-10 | 2026-07-15 |  |  | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-27 | 2026-07-29 | 103 | S | Mosaddik | Nk |  | 2 combo label print |  | Imp fab on 07/06 | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -3018 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 31 | Jul'1 |  |  | 13.07.26
BS-NMT | 47543 | 13249242 | 6983 | 344 | 2026-04-15 | 2026-04-27 | Elsated Legging | Legging |  |  | 2026-07-03: 2026-06-20; 2026-07-04: 2026-06-20; 2026-07-09: 2026-06-26; 2026-07-10: 2026-06-29; 2026-07-11: 2026-06-30 | 2026-07-02 | 2026-07-04 |  |  |  |  | 2026-07-06 | 2026-07-09 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-16 | 2026-07-27 | 2026-07-29 | 103 | W1 | Mosaddik | Waist |  | 4 combo label print |  | Imp fab on 07/06 | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -6983 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 31 | Jun'3 |  |  | 30.06.26
BS-NMT | 47544 | 13249241 | 6757 | 459 | 2026-04-15 | 2026-04-27 | LS Body w nk picot and btm snap btn | Body |  |  | 2026-07-03: 2026-06-16; 2026-07-04: 2026-06-16; 2026-07-09: 2026-06-22; 2026-07-10: 2026-06-24; 2026-07-11: 2026-06-27 | 2026-06-27 | 2026-06-30 |  |  |  |  | 2026-07-01 | 2026-07-06 |  |  | 2026-07-08 | 2026-07-10 | 2026-07-13 | 2026-07-27 | 2026-07-29 | 103 | Y | Mosaddik | Nk |  | 4 combo label print |  | Imp fab on 07/06 | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -6757 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 31 | Jun'3 |  |  | 30.06.26
BS-NMT | 47569 | 13262050 | 1215 | 186 | 2026-04-15 | 2026-04-27 | AOP LS romper w shlder btm snap btn | Romper |  |  | 2026-05-12 | 2026-05-15 | 2026-06-06 | 2026-06-16 | 2026-06-18 | 2026-06-24 | 2026-06-25 | 2026-06-25 | 2026-07-01 | 2026-07-03 | 2026-07-04 | 2026-07-07 | 2026-07-08 |  |  |  |  | 2026-07-10 | 2026-07-13 |  |  | 2026-07-15 | 2026-07-17 | 2026-07-20 | 2026-07-27 | 2026-07-29 | 103 | S | Mosaddik | Nk |  | 1 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 186 | 186 | 0 | 0 | -1215 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 31 | Jul'1 |  |  | 06.06.26
BS-NMT | 47553 | 13258874 | 2178 | 231 | 2026-04-15 | 2026-04-27 | LS Dress w mesh and shlder snap btn | Dress |  |  | 2026-05-08 | 2026-05-13 | 2026-05-20 | 2026-06-09 | 2026-06-10 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-20 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 |  |  |  |  | 2026-06-27 | 2026-06-30 |  |  | 2026-07-01 | 2026-07-02 | 2026-07-04 | 2026-07-06 | 2026-07-08 | 82 | S | Mosaddik | Nk |  | 1 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 231 | 231 | 0 | 0 | -2178 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46162 | 0 | 28 | Jun'3 |  |  | 06.06.26
BS-NMT | 47545 | 13249243 | 5409 | 583 | 2026-04-15 | 2026-04-27 | LS Dress w mesh and shlder snap btn nk pickoting | Dress |  |  | 2026-05-09 | 2026-05-15 | 2026-06-09 | 2026-06-17 |  |  | 2026-06-16 | 2026-06-16 | 2026-06-22 | 2026-06-24 | 2026-06-27 | 2026-06-27 | 2026-06-30 |  |  |  |  | 2026-07-01 | 2026-07-06 |  |  | 2026-07-08 | 2026-07-10 | 2026-07-14 | 2026-07-27 | 2026-07-29 | 103 | S | Mosaddik | Nk |  | 3 combo label print |  | Imp fab on 07/06 | NFL3 |  |  | Cut Ok | 241 | 241 | 0 | 0 | -5409 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46182 | 0 | 31 | Jun'3 |  |  | 01.07.26
BS-NMT | 47547 | 13261839 | 4908 | 482 | 2026-04-15 | 2026-04-27 | LS Dress w mesh and shlder snap btn nk pickoting | Dress |  |  | 2026-05-02 | 2026-05-17 | 2026-06-08 | 2026-06-18 |  |  | 2026-06-18 | 2026-06-18 | 2026-06-24 | 2026-06-26 | 2026-06-30 | 2026-06-29 | 2026-07-01 |  |  |  |  | 2026-07-03 | 2026-07-09 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-27 | 2026-07-29 | 103 | S | Mosaddik | Nk |  | 3 combo label print |  | Imp fab on 07/06 | NFL3 |  |  | Cut Ok | 209 | 209 | 0 | 0 | -4908 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 31 | Jun'3 |  |  | 13.07.26
BS-NMT | 47551 | 13258872 | 1725 | 162 | 2026-04-15 | 2026-04-27 | AOP LS romper w shlder btm snap btn | Romper |  |  | 2026-05-09 | 2026-05-14 | 2026-05-20 | 2026-06-09 | 2026-06-12 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 |  |  |  |  | 2026-06-27 | 2026-06-30 |  |  | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-06 | 2026-07-08 | 82 | Y | Mosaddik | Nk |  | 1 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 162 | 162 | 0 | 0 | -1725 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46162 | 0 | 28 | Jun'3 |  |  | 06.06.26
BS-NMT | 47550 | 13258875 | 855 | 65 | 2026-04-15 | 2026-04-27 | AOP Legging w waist herringbone tape bow | Legging |  |  | 2026-05-11 | 2026-05-14 | 2026-05-20 | 2026-06-08 | 2026-06-10 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 2026-06-23 | 2026-06-25 | 2026-06-25 | 2026-06-27 | 2026-06-27 |  |  |  |  | 2026-06-29 | 2026-06-30 |  |  | 2026-07-01 | 2026-07-02 | 2026-07-04 | 2026-07-04 | 2026-07-06 | 80 | T2 | Mosaddik | Waist |  | 1 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 65 | 65 | 0 | 0 | -855 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46162 | 0 | 28 | Jun'3 |  |  | 06.06.26
BS-NMT | 47575 | 13261569 | 1005 | 147 | 2026-04-15 | 2026-04-27 | LS SWt shirt e front cargo pkt and shlder snap btn | Swt Shirt |  |  | 2026-05-15 | 2026-05-20 | 2026-06-10 | 2026-06-23 |  |  | 2026-06-25 | 2026-06-25 | 2026-07-02 | 2026-07-04 | 2026-07-06 | [6 empty] | 2026-07-08 | 2026-07-10 |  |  | 2026-07-13 | 2026-07-15 | 2026-07-18 | 2026-07-27 | 2026-07-29 | 103 | S | Mosaddik | [5 empty] | NFL3 |  |  | Cut Ok | 147 | 147 | 0 | 0 | -1005 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 31 | Jul'1 |  |  | 20.06.26
BS-NMT | 47562 | 13246830 | 3380 | 286 | 2026-04-15 | 2026-04-27 | LS body w btm snap btn and front woven collar placket btn and bow attach | Body |  |  | 2026-05-11 | 2026-05-17 | 2026-06-10 | 2026-06-22 |  |  | 2026-06-25 | 2026-06-25 | 2026-07-01 | 2026-07-03 | 2026-07-06 | 2026-07-06 | 2026-07-08 |  |  |  |  | 2026-07-10 | 2026-07-16 |  |  | 2026-07-18 | 2026-07-20 | 2026-07-22 | 2026-07-27 | 2026-07-29 | 103 | X+Y | Mosaddik | Nk |  | 1 combo label print |  |  | NFL3 |  |  | Cut Ok | 285 | 285 | 0 | 0 | -3380 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 31 | Jul'1 |  |  | 06.06.26
BS-NMT | 47566 | 13249501 | 1605 | 137 | 2026-04-15 | 2026-04-27 | LS TS w chest tape pannel and nk bow and shlder snap btn | TS |  |  | 2026-05-15 | 2026-05-18 | 2026-06-12 | 2026-06-22 |  |  | 2026-06-25 | 2026-06-25 | 2026-07-01 | 2026-07-03 | 2026-07-04 | 2026-07-07 | 2026-07-08 |  |  |  |  | 2026-07-10 | 2026-07-13 |  |  | 2026-07-15 | 2026-07-16 | 2026-07-20 | 2026-07-27 | 2026-07-29 | 103 | S | Mosaddik | Nk |  | 1 combo label print |  |  | NFL3 |  |  | Cut Ok | 138 | 138 | 0 | 0 | -1605 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 31 | Jul'1 |  |  | 06.06.26
BS-NMT | 47567 | 13261576 | 3722 | 412 | 2026-04-15 | 2026-04-27 | AOP LS romper w w front placket btn and shlder btm snap btn | Romper |  |  | 2026-05-16 | 2026-05-22 | 2026-06-08 | 2026-06-18 | 2026-06-20 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-07-01 | 2026-07-03 | 2026-07-06 | 2026-07-06 | 2026-07-09 |  |  |  |  | 2026-07-10 | 2026-07-15 |  |  | 2026-07-17 | 2026-07-18 | 2026-07-22 | 2026-07-27 | 2026-07-29 | 103 | Y | Mosaddik | Nk |  | 2 combo Label print | AOP |  | NFL3 |  |  | Cut Ok | 413 | 413 | 0 | 0 | -3722 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 31 | Jul'1 |  |  | 09.06.26
BS-NMT | 47576 | 13261570 | 1065 | 138 | 2026-04-15 | 2026-04-27 | Swt pant w 2 cargo pkt | Pant |  |  | 2026-05-14 | 2026-05-18 | 2026-06-10 | 2026-06-20 |  |  | 2026-06-23 | 2026-06-23 | 2026-06-29 | 2026-07-02 | 2026-07-03 | [6 empty] | 2026-07-06 | 2026-07-08 |  |  | 2026-07-10 | 2026-07-11 | 2026-07-15 | 2026-07-27 | 2026-07-29 | 103 | X | Mosaddik | [5 empty] | NFL3 |  |  | Cut Ok | 138 | 138 | 0 | 0 | -1065 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 31 | Jul'1 |  |  | 20.06.26
BS-NMT | 47560 | 13261551 | 3112 | 311 | 2026-04-15 | 2026-04-27 | AOP LS romper w shlder btm snap btn | Romper |  |  | 2026-05-15 | 2026-05-20 | 2026-06-06 | 2026-06-14 | 2026-06-15 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-24 | 2026-06-26 | 2026-06-27 | 2026-06-30 | 2026-07-01 |  |  |  |  | 2026-07-03 | 2026-07-07 |  |  | 2026-07-09 | 2026-07-11 | 2026-07-14 | 2026-07-27 | 2026-07-29 | 103 | Y | Mosaddik | Nk |  | 2 combo Label print | AOP |  | NFL3 |  |  | Cut Ok | 312 | 312 | 0 | 0 | -3112 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 31 | Jun'3 |  |  | 20.06.26
BS-NMT | 47573 | 13261567 | 2584 | 319 | 2026-04-15 | 2026-04-27 | Waist fold YD Swt Pant | Pant | 2026-05-16 | 2026-05-22 | 2026-06-08 | 2026-06-16 | 2026-06-18 | 2026-06-27 |  |  | 2026-07-01 | 2026-07-01 | 2026-07-07 | 2026-07-09 | 2026-07-10 | [6 empty] | 2026-07-13 | 2026-07-16 |  |  | 2026-07-18 | 2026-07-20 | 2026-07-22 | 2026-07-27 | 2026-07-29 | 103 | Z | Mosaddik |  |  |  | YD |  | NFL3 |  |  | Cut Ok | 319 | 319 | 0 | 0 | -2584 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46191 | 0 | 31 | Jul'1 |  |  | 27.06.26
BS-NMT | 47572 | 13261566 | 6118 | 919 | 2026-04-15 | 2026-04-27 | YD LS Swt shirt w shlder snap btn | Swt Shirt | 2026-05-14 | 2026-05-20 | 2026-05-22 | 2026-06-10 | 2026-06-14 | 2026-06-20 |  |  | 2026-06-20 | 2026-06-20 | 2026-06-27 | 2026-06-29 | 2026-07-01 |  |  |  |  | 2026-06-29 | 2026-07-08 | 2026-07-11 | 2026-07-16 |  |  | 2026-07-18 | 2026-07-21 | 2026-07-23 | 2026-07-27 | 2026-07-29 | 103 | T2 | Mosaddik |  | Chest | Sepia-3719 pcs,,Navy-2399 pcs both combo 4 clr terry emb | YD |  | NFL3 |  |  | Cut Ok | 919 | 908 | -11 | 0 | -6118 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46187 | 0 | 31 | Jun'3 |  |  | 20.06.26
BS-NMT | 47548 | 13224060 | 3292 | 315 | 2026-04-15 | 2026-04-27 | LS Body w shlder and btm snap btn | Body |  |  | 2026-05-08 | 2026-05-13 | 2026-05-20 | 2026-06-10 |  |  | 2026-06-12 | 2026-06-12 | 2026-06-17 | 2026-06-19 | 2026-06-20 | 2026-06-22 | 2026-06-24 |  |  |  |  | 2026-06-26 | 2026-06-30 |  |  | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-06 | 2026-07-08 | 82 | Y | Mosaddik | Chest,Nk |  | Red-2481 pcs,,Navy-811 pcs both combo 1 clr rub print |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -3292 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46162 | 0 | 28 | Jun'1 |  |  | 06.06.26
BS-NMT | 47578 | 13261451 | 2644 | 211 | 2026-04-15 | 2026-04-27 | LS o nk TS w shlder snap btn | TS |  |  | 2026-05-11 | 2026-05-17 | 2026-06-06 | 2026-06-16 |  |  | 2026-06-17 | 2026-06-17 | 2026-06-22 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-29 |  |  |  |  | 2026-07-01 | 2026-07-03 |  |  | 2026-07-06 | 2026-07-08 | 2026-07-11 | 2026-07-27 | 2026-07-29 | 103 | T1 | Mosaddik | Chest,Nk |  | Mauve-1697 pcs 4 clr rub,,birch-947 pcs 3 clr rub |  |  | NFL3 |  |  | Cut Ok | 211 | 211 | 0 | 0 | -2644 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 31 | Jun'3 |  |  | 20.06.26
BS-NMT | 47571 | 13261605 | 1689 | 152 | 2026-04-15 | 2026-04-27 | LS o nk TS w shlder snap btn | TS |  |  | 2026-05-12 | 2026-05-14 | 2026-06-06 | 2026-06-15 |  |  | 2026-06-15 | 2026-06-15 | 2026-06-20 | 2026-06-23 | 2026-06-24 | 2026-06-26 | 2026-06-29 |  |  |  |  | 2026-07-02 | 2026-07-04 |  |  | 2026-07-07 | 2026-07-08 | 2026-07-11 | 2026-07-27 | 2026-07-29 | 103 | T1 | Mosaddik | Chest,Nk |  | Sepia-882 pcs,,Abyss-807 pcs both combo 1 clr flock print |  |  | NFL3 |  |  | Cut Ok | 152 | 152 | 0 | 0 | -1689 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 31 | Jun'3 |  |  | 27.06.26
BS-NMT | 47568 | 13261578 | 2220 | 121 | 2026-04-15 | 2026-04-27 | AOP Legging w front fake fly and btn | Legging |  |  | 2026-05-12 | 2026-05-17 | 2026-06-06 | 2026-06-16 | 2026-06-18 | 2026-06-24 | 2026-06-26 | 2026-06-26 | 2026-07-02 | 2026-07-04 | 2026-07-06 | 2026-07-07 | 2026-07-08 |  |  |  |  | 2026-07-10 | 2026-07-13 |  |  | 2026-07-15 | 2026-07-16 | 2026-07-18 | 2026-07-27 | 2026-07-29 | 103 | T1 | Mosaddik | Waist |  | 1 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 121 | 121 | 0 | 0 | -2220 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 31 | Jul'1 |  |  | 27.06.26
BS-NMT | 47552 | 13265099 | 810 | 46 | 2026-04-15 | 2026-04-29 | AOP Elsated Legging | Legging |  |  | 2026-05-12 | 2026-05-15 | 2026-05-20 | 2026-06-08 | 2026-06-10 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 2026-06-20 | 2026-06-23 | 2026-06-23 | 2026-06-25 | 2026-06-25 |  |  |  |  | 2026-06-27 | 2026-06-27 |  |  | 2026-06-29 | 2026-06-30 | 2026-07-02 | 2026-07-06 | 2026-07-08 | 82 | W1 | Mosaddik | Nk |  | 1 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 46 | 46 | 0 | 0 | -810 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46162 | 0 | 28 | Jun'3 |  |  | 20.06.26
BS-NMT | 47559 | 13261607 | 1332 | 201 | 2026-04-15 | 2026-04-29 | LS body suit w snap btn contrast btm side w shoulder tape | Body |  |  | 2026-05-22 | 2026-06-06 | 2026-06-10 | 2026-06-24 |  |  | 2026-06-26 | 2026-06-26 | 2026-07-02 | 2026-07-04 | 2026-07-06 | 2026-07-07 | 2026-07-08 |  |  |  |  | 2026-07-10 | 2026-07-13 |  |  | 2026-07-14 | 2026-07-15 | 2026-07-17 | 2026-07-20 | 2026-07-22 | 96 | X | Mosaddik | Nk |  | 1 combo label print |  |  | NFL3 |  |  | Cut Ok | 200 | 200 | 0 | 0 | -1332 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 30 | Jul'1 |  |  | 01.07.26
BS-NMT | 47557 | 13262902 | 810 | 70 | 2026-04-15 | 2026-04-29 | LS o nk TS w shlder snap btn | TS |  |  | 2026-05-12 | 2026-05-16 | 2026-06-06 | 2026-06-12 |  |  | 2026-06-13 | 2026-06-13 | 2026-06-18 | 2026-06-20 | 2026-06-22 | 2026-06-23 | 2026-06-25 |  |  |  |  | 2026-06-27 | 2026-06-29 |  |  | 2026-06-30 | 2026-07-02 | 2026-07-04 | 2026-07-06 | 2026-07-08 | 82 | T1 | Mosaddik | Chest,Nk |  | red-810 pcs 3 clr rub 1 clr puff |  |  | NFL3 |  |  | Cut Ok | 69 | 69 | 0 | 0 | -810 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 28 | Jun'1 |  |  | 06.06.26
BS-NMT | 47554 | 13264588 | 1460 | 42 | 2026-04-15 | 2026-04-29 | Bib w snap btn | Bib |  |  | 2026-05-12 | 2026-05-15 | 2026-06-06 | 2026-06-16 |  |  | 2026-06-17 | 2026-06-17 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 2026-06-25 | 2026-06-26 |  |  |  |  | 2026-06-29 | 2026-06-30 |  |  | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-06 | 2026-07-08 | 82 | T1 | Mosaddik | Chest |  | red-1460 pcs 1 clr rub |  |  | NFL3 |  |  | Cut Ok | 42 | 42 | 0 | 0 | -1460 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 28 | Jun'3 |  |  | 06.06.26
BS-NMT | 47593 | 13251906 | 1526 | 177 | 2026-04-15 | 2026-04-24 | AOP Waist fold Swt pant w rib | Pant |  |  | 2026-05-07 | 2026-05-13 | 2026-05-16 | 2026-06-10 | 2026-06-10 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-24 | 2026-06-26 | 2026-06-27 | [6 empty] | 2026-07-02 | 2026-07-04 |  |  | 2026-07-07 | 2026-07-09 | 2026-07-13 | 2026-07-27 | 2026-07-29 | 103 | T1 | Sabikun |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 184 | 177 | -7 | 0 | -1526 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46158 | 0 | 31 | Jun'3 |  |  | 23.05.26
BS-NMT | 47590 | 13251953 | 2628 | 314 | 2026-04-15 | 2026-04-24 | AOP & Solid Waist fold Swt pant w rib | Pant |  |  | 2026-05-07 | 2026-05-13 | 2026-05-18 | 2026-06-10 | 2026-06-10 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 2026-06-23 | 2026-06-25 | 2026-06-26 | 2026-06-29 | 2026-07-02 |  |  |  |  | 2026-07-04 | 2026-07-08 |  |  | 2026-07-10 | 2026-07-11 | 2026-07-14 | 2026-07-27 | 2026-07-29 | 103 | T1 | Sabikun | Thigh |  | Sepia-801 pcs 2 clr rub 1 clr puff,,abyss-906 pcs 2 clr rub 1 clr puff,,island AOP-921 pcs no print | AOP |  | NFL3 |  |  | Cut Ok | 314 | 314 | 0 | 0 | -2628 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46160 | 0 | 31 | Jun'3 |  |  | 23.05.26
BS-NMT | 47594 | 13255270 | 1380 | 180 | 2026-04-15 | 2026-04-24 | AOP Swt shirt w shoulder snap btn and Waist fold Swt pant w rib | Top & BTM |  |  | 2026-05-10 | 2026-05-15 | 2026-05-18 | 2026-06-10 | 2026-06-12 | 2026-06-18 | 2026-06-20 | 2026-06-20 | 2026-06-26 | 2026-06-29 | 2026-06-30 | [6 empty] | 2026-07-03 | 2026-07-06 |  |  | 2026-07-08 | 2026-07-10 | 2026-07-15 | 2026-07-27 | 2026-07-29 | 103 | T1+Z | Sabikun |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 180 | 180 | 0 | 0 | -1380 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46160 | 0 | 31 | Jun'3 |  |  | 23.05.26
BS-NMT | 47591 | 13255268 | 1746 | 237 | 2026-04-15 | 2026-04-24 | AOP Swt shirt w shoulder snap btn and Waist fold Swt pant w rib | Top & BTM |  |  | 2026-05-07 | 2026-05-13 | 2026-05-16 | 2026-06-11 | 2026-06-13 | 2026-06-20 | 2026-06-20 | 2026-06-20 | 2026-06-26 | 2026-06-29 | 2026-06-30 | [6 empty] | 2026-07-04 | 2026-07-07 |  |  | 2026-07-09 | 2026-07-10 | 2026-07-14 | 2026-07-27 | 2026-07-29 | 103 | T1+Z | Sabikun |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 237 | 237 | 0 | 0 | -1746 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46158 | 0 | 31 | Jun'3 |  |  | 23.05.26
BS-NMT | 47589 | 13251951 | 1630 | 237 | 2026-04-15 | 2026-04-24 | AOP Swt shirt w shoulder snap btn | Swt Shirt |  |  | 2026-05-07 | 2026-05-13 | 2026-05-15 | 2026-06-10 | 2026-06-12 | 2026-06-18 | 2026-06-19 | 2026-06-19 | 2026-06-25 | 2026-06-27 | 2026-06-29 | [6 empty] | 2026-07-03 | 2026-07-04 |  |  | 2026-07-07 | 2026-07-09 | 2026-07-13 | 2026-07-27 | 2026-07-29 | 103 | T2 | Sabikun |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 238 | 238 | 0 | 0 | -1630 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 31 | Jun'3 |  |  | 23.05.26
BS-NMT | 47592 | 13251904 | 2024 | 292 | 2026-04-15 | 2026-04-24 | AOP Swt shirt w shoulder snap btn | Swt Shirt |  |  | 2026-05-07 | 2026-05-13 | 2026-05-15 | 2026-06-10 | 2026-06-11 | 2026-06-18 | 2026-06-17 | 2026-06-17 | 2026-06-25 | 2026-06-27 | 2026-06-29 | [6 empty] | 2026-07-01 | 2026-07-03 |  |  | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-27 | 2026-07-29 | 103 | T2 | Sabikun |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 292 | 292 | 0 | 0 | -2024 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 31 | Jun'3 |  |  | 23.05.26
BS-NMT | 44025 4th | 13251205 | 3000 | 543 | 2026-04-15 | 2026-04-18 | AOP Legging | Legging |  |  | 2026-05-02 | 2026-05-07 | 2026-05-10 | 2026-05-23 | 2026-06-05 | 2026-06-11 | 2026-06-10 | 2026-06-10 |  | 2026-06-15 | 2026-06-16 | [6 empty] | 2026-06-18 | 2026-06-20 |  |  | 2026-06-23 | 2026-06-25 | 2026-06-27 | 2026-07-06 | 2026-07-08 | 82 | W1 | Jafar |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 542 | 523 | -19 | 0 | -3000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46152 | 0 | 28 | Jun'1 |  |  | 25.05.26
BS-NMT | 47669 | 13249975 | 1608 | 862 | 2026-04-15 | 2026-04-28 | LS High nk Half zipper Swt shirt w side pkt | Swt Shirt |  |  | 2026-05-13 | 2026-05-25 | 2026-06-10 | 2026-06-23 |  |  | 2026-06-25 | 2026-06-25 | 2026-07-01 | 2026-07-03 | 2026-07-04 |  |  |  |  | 2026-07-06 | 2026-07-07 | 2026-07-09 | 2026-07-11 |  |  | 2026-07-14 | 2026-07-15 | 2026-07-17 | 2026-07-20 | 2026-07-22 | 96 | S+T1 | Tomal |  | Chest | chocolate-801 pcs,,black-807 pcs both combo 1 clr flat emb |  |  | NFL3 |  |  | Cut Ok | 861 | 861 | 0 | 0 | -1608 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 30 | Jul'1 |  |  | 27.06.26
BS-NMT | 47671 | 13261383 | 1699 | 835 | 2026-04-15 | 2026-04-28 | Swt pant w side pkt and drawstring | Pant |  |  | 2026-05-15 | 2026-06-06 | 2026-06-10 | 2026-06-23 |  |  | 2026-06-24 | 2026-06-24 | 2026-07-01 | 2026-07-03 | 2026-07-04 | [6 empty] | 2026-07-06 | 2026-07-09 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-20 | 2026-07-22 | 96 | X | Tomal | [5 empty] | NFL3 |  |  | Cut Ok | 836 | 836 | 0 | 0 | -1699 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 30 | Jul'1 |  |  | 08.07.26
BS-NMT | 47675 | 13261590 | 3597 | 890 | 2026-04-15 | 2026-04-28 | Swt pant w side and back pkt | Pant |  |  | 2026-05-12 | 2026-05-20 | 2026-06-08 | 2026-06-23 |  |  | 2026-06-25 | 2026-06-25 | 2026-07-03 | 2026-07-06 | 2026-07-09 | [6 empty] | 2026-07-10 | 2026-07-15 |  |  | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-27 | 2026-07-29 | 103 | X | Tomal | [5 empty] | NFL3 |  |  | Cut Ok | 890 | 890 | 0 | 3660 | 63 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 31 | Jul'1 |  |  | 27.06.26
BS-NMT | 47670 | 13261382 | 810 | 320 | 2026-04-15 | 2026-04-28 | SS cut & sew TS w nk btm rib | TS |  |  | 2026-05-23 | 2026-06-08 | 2026-06-12 | 2026-06-24 |  |  | 2026-06-26 | 2026-06-26 | 2026-07-02 | 2026-07-04 | 2026-07-06 | [6 empty] | 2026-07-08 | 2026-07-09 |  |  | 2026-07-10 | 2026-07-13 | 2026-07-15 | 2026-07-20 | 2026-07-22 | 96 | Z | Tomal | [5 empty] | NFL3 |  |  | Cut Ok | 320 | 320 | 0 | 0 | -810 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 30 | Jul'1 |  |  | 27.06.26
BS-NMT | 47672 | 13261489 | 3728 | 981 | 2026-04-15 | 2026-04-28 | AOP & Solid LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-05-11 | 2026-05-17 | 2026-05-20 | 2026-06-15 | 2026-06-16 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 2026-06-27 | 2026-06-30 | 2026-07-02 | 2026-07-02 | 2026-07-06 |  |  |  |  | 2026-07-07 | 2026-07-10 |  |  | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-27 | 2026-07-29 | 103 | W2 | Tomal | Chest |  | abyss AOP-2464 pcs no print ,,olive night-1264 pcs 8 clr rub | AOP |  | NFL3 |  |  | Cut Ok | 980 | 980 | 0 | 0 | -3728 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46162 | 0 | 31 | Jun'3 |  |  | 27.06.26
BS-NMT | 47676 | 13261969 | 1624 | 618 | 2026-04-15 | 2026-04-28 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-05-12 | 2026-05-18 | 2026-06-06 | 2026-06-18 |  |  | 2026-06-20 | 2026-06-20 | 2026-06-26 | 2026-06-29 | 2026-06-30 | 2026-07-02 | 2026-07-04 |  |  |  |  | 2026-07-07 | 2026-07-08 |  |  | 2026-07-10 | 2026-07-13 | 2026-07-15 | 2026-07-20 | 2026-07-22 | 96 | W2 | Tomal | Chest |  | Island-824 pcs 9 clr rub print ,,Navy-800 pcs 6 clr rub |  |  | NFL3 |  |  | Cut Ok | 619 | 619 | 0 | 0 | -1624 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 30 | Jun'3 |  |  | 07.07.26
BS-NMT | 47673 | 13261493 | 1602 | 219 | 2026-04-15 | 2026-04-28 | LS o nk TS | TS |  |  | 2026-05-14 | 2026-05-18 | 2026-06-07 | 2026-06-18 |  |  | 2026-06-20 | 2026-06-20 | 2026-06-25 | 2026-06-27 | 2026-06-29 | 2026-07-02 | 2026-07-04 |  |  |  |  | 2026-07-07 | 2026-07-08 |  |  | 2026-07-10 | 2026-07-13 | 2026-07-16 | 2026-07-27 | 2026-07-29 | 103 | ZA1 | Tomal | Chest,Nk |  | mosstone-801 pcs 5 clr rub 1 clr flock print ,,sepia-801 pcs 6 clr rub 1 clr flock print |  |  | NFL3 |  |  | Cut Ok | 218 | 218 | 0 | 0 | -1602 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46180 | 0 | 31 | Jun'3 |  |  | 10.07.26
BS-NMT | 47680 | 13262049 | 1641 | 313 | 2026-04-15 | 2026-04-28 | SS o nk TS | TS |  |  | 2026-05-12 | 2026-05-15 | 2026-05-22 | 2026-06-13 |  |  | 2026-06-15 | 2026-06-15 | 2026-06-20 | 2026-06-23 | 2026-06-24 | 2026-06-26 | 2026-06-27 |  |  |  |  | 2026-07-01 | 2026-07-02 |  |  | 2026-07-04 | 2026-07-07 | 2026-07-10 | 2026-07-20 | 2026-07-22 | 96 | Z | Tomal | Chest,Nk |  | island-813 pcs,,sepia-828 pcs both combo 1 clr rub |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1641 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46164 | 0 | 30 | Jun'3 |  |  | 27.06.26
BS-NMT | 47677 | 13262037/13265612 | 2640 | 325 | 2026-04-15 | 2026-04-28 | LS o nk TS | TS |  |  | 2026-05-12 | 2026-05-18 | 2026-06-06 | 2026-06-17 |  |  | 2026-06-18 | 2026-06-18 | 2026-06-24 | 2026-06-26 | 2026-06-27 | 2026-07-01 | 2026-07-03 |  |  |  |  | 2026-07-07 | 2026-07-09 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-27 | 2026-07-29 | 103 | ZA1 | Tomal | Chest,Nk |  | island-1320 pcs,,abyss-1320 pcs both combo 6 clr rub |  |  | NFL3 |  |  | Cut Ok | 324 | 324 | 0 | 0 | -2640 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 31 | Jun'3 |  |  | 27.06.26
BS-NMT | 47678 | 13262044 | 6006 | 731 | 2026-04-15 | 2026-04-28 | LS TS w contrast slve w apllique wings and elasted legging | Top & BTM |  |  | 2026-05-07 | 2026-05-13 | 2026-05-18 | 2026-06-10 |  |  | 2026-06-11 | 2026-06-11 | 2026-06-16 | 2026-06-18 | 2026-06-21 | 2026-06-22 | 2026-06-24 |  |  |  |  | 2026-06-27 | 2026-06-30 |  |  | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-06 | 2026-07-08 | 82 | ZA1+W1 | Tomal | Chest,Nk |  | abyss top-3003 pcs 3 clr rub print ,,abyss btm-3003 pcs no print |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -6006 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46160 | 0 | 28 | Jun'1 |  |  | 20.06.26
BS-NMT | 47679 | 13262045 | 5898 | 683 | 2026-04-15 | 2026-04-28 | LS o nk TS and elasted legging | Top & BTM |  |  | 2026-05-08 | 2026-05-13 | 2026-05-18 | 2026-06-09 |  |  | 2026-06-10 | 2026-06-10 | 2026-06-16 | 2026-06-18 | 2026-06-20 | 2026-06-20 | 2026-06-23 |  |  |  |  | 2026-06-25 | 2026-06-27 |  |  | 2026-06-29 | 2026-06-30 | 2026-07-02 | 2026-07-06 | 2026-07-08 | 82 | ZA1+W1 | Tomal | Chest,Nk |  | Navy top-2949 pcs 6 clr rub ,,Navy btm-2949 pcs no print |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -5898 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46160 | 0 | 28 | Jun'1 |  |  | 20.06.26
BS-NMT | 47674 | 13261588 | 5372 | 1464 | 2026-04-15 | 2026-04-28 | LS YD Swt shirt w cuff btm rib | Swt Shirt | 2026-05-10 | 2026-05-17 | 2026-05-20 | 2026-06-11 | 2026-06-15 | 2026-06-25 |  |  | 2026-06-26 | 2026-06-26 | 2026-07-02 | 2026-07-04 | 2026-07-07 |  |  |  |  | 2026-07-06 | 2026-07-10 | 2026-07-10 | 2026-07-14 |  |  | 2026-07-16 | 2026-07-18 | 2026-07-20 | 2026-07-27 | 2026-07-29 | 103 | W2 | Tomal |  | Chest | Sepia-3016 pcs 3 clr flat emb ,,navy-2356 pcs 4 clr flat emb | YD |  | NFL3 |  |  | Cut Ok | 1465 | 1438 | -27 | 0 | -5372 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 31 | Jul'1 |  |  | 27.06.26
BS-NMT | 47613 | 13265387 | 4889 | 546 | 2026-04-15 | 2026-04-28 | LS o nk TS w nk picoting | TS | [8 empty] | 2026-06-25 | 2026-06-25 | 2026-07-02 | 2026-07-04 | 2026-07-07 | 2026-07-07 | 2026-07-09 |  |  |  |  | 2026-07-10 | 2026-07-15 |  |  | 2026-07-17 | 2026-07-18 | 2026-07-21 | 2026-07-27 | 2026-07-29 | 103 | Z | Haider | Nk |  | 4 combo label print |  | Imp fab on 25/06 | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -4889 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 31 | Jul'1 |  |  | 27.06.26
BS-NMT | 47612 | 13265388 | 4754 | 452 | 2026-04-15 | 2026-04-28 | Elasted Legging | Legging | [8 empty] | 2026-06-20 | 2026-06-20 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-04 |  |  |  |  | 2026-07-06 | 2026-07-09 |  |  | 2026-07-11 | 2026-07-14 | 2026-07-15 | 2026-07-27 | 2026-07-29 | 103 | W1 | Haider | Waist |  | 4 combo label print |  | Imp fab on 25/06 | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -4754 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 31 | Jun'3 |  |  | 27.06.26
BS-NMT | 47599 | 13262039 | 5334 | 618 | 2026-04-15 | 2026-04-28 | LS TS w contrast slve w apllique letus frill and elasted legging | Top & BTM |  |  | 2026-05-09 | 2026-05-15 | 2026-05-20 | 2026-06-10 |  |  | 2026-06-12 | 2026-06-12 | 2026-06-16 | 2026-06-18 | 2026-06-20 | 2026-06-20 | 2026-06-23 |  |  |  |  | 2026-06-25 | 2026-06-27 |  |  | 2026-06-30 | 2026-07-02 | 2026-07-03 | 2026-07-06 | 2026-07-08 | 82 | W1+T1 | Haider | Chest,Nk |  | pink top-2667 pcs 4 clr rub ,,pink btm -2667 pcs no print |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -5334 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46162 | 0 | 28 | Jun'1 |  |  | 11.06.26
BS-NMT | 47598 | 13262041 | 7844 | 869 | 2026-04-15 | 2026-04-28 | LS o Nk TS and Elasted Legging | Top & BTM |  |  | 2026-05-08 | 2026-05-14 | 2026-05-20 | 2026-06-08 |  |  | 2026-06-10 | 2026-06-10 | 2026-06-16 | 2026-06-18 | 2026-06-20 | 2026-06-20 | 2026-06-25 |  |  |  |  | 2026-06-25 | 2026-06-29 |  |  | 2026-06-30 | 2026-07-02 | 2026-07-03 | 2026-07-06 | 2026-07-08 | 82 | Z+ZA1 | Haider | Fr,bk,Nk,Leg & waist |  | ballerina top-3922 pcs4 clr pig at chest ,,ballerina btm-3922 pcs 2 part 3 clr pig |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -7844 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46162 | 0 | 28 | Jun'1 |  |  | 11.06.26
BS-NMT | 47595 | 13251455 | 2514 | 348 | 2026-04-15 | 2026-04-28 | LS AOP Dress w mesh at btm | Dress |  |  | 2026-05-05 | 2026-05-12 | 2026-05-17 | 2026-06-08 | 2026-06-09 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-20 | 2026-06-22 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  |  |  |  | 2026-06-26 | 2026-06-30 |  |  | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-06 | 2026-07-08 | 82 | S | Haider | Nk |  | 1 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 348 | 327 | -21 | 0 | -2514 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46159 | 0 | 28 | Jun'3 |  |  | 23.05.26
BS-NMT | 47596 | 13251461 | 1365 | 171 | 2026-04-15 | 2026-04-28 | AOP LS o nk TS | TS |  |  | 2026-05-09 | 2026-05-14 | 2026-05-20 | 2026-06-08 | 2026-06-10 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 2026-06-22 | 2026-06-24 | 2026-06-24 | 2026-06-26 | 2026-06-26 |  |  |  |  | 2026-06-29 | 2026-06-30 |  |  | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-06 | 2026-07-08 | 82 | W2 | Haider | Nk |  | 1 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 171 | 171 | 0 | 0 | -1365 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46162 | 0 | 28 | Jun'3 |  |  | 23.05.26
BS-NMT | 47597 | 13251459 | 1260 | 131 | 2026-04-15 | 2026-04-28 | AOP elasted Legging | Legging |  |  | 2026-05-09 | 2026-05-13 | 2026-05-20 | 2026-06-08 | 2026-06-10 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-20 | 2026-06-23 | 2026-06-23 | 2026-06-25 | 2026-06-25 |  |  |  |  | 2026-06-27 | 2026-06-29 |  |  | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-06 | 2026-07-08 | 82 | Z | Haider | Waist |  | 1 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 131 | 131 | 0 | 0 | -1260 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46162 | 0 | 28 | Jun'3 |  |  | 23.05.26
BS-NMT | 47610 | 13252965 | 6501 | 368 | 2026-04-15 | 2026-04-28 | Skirt w AOP mesh | Skirt |  |  | 2026-05-11 | 2026-05-18 | 2026-06-10 | 2026-06-22 |  |  | 2026-06-25 | 2026-06-25 | 2026-07-01 | 2026-07-03 | 2026-07-06 | 2026-07-06 | 2026-07-09 |  |  |  |  | 2026-07-10 | 2026-07-15 |  |  | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-27 | 2026-07-29 | 103 | T1 | Haider | Waist |  | 4 combo label print |  |  | NFL3 |  |  | Cut Ok | 368 | 368 | 0 | 0 | -6501 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 31 | Jul'1 |  |  | 23.05.26
BS-NMT | 47601 | 13265660 | 1011 | 381 | 2026-04-15 | 2026-04-28 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-05-12 | 2026-05-17 | 2026-06-08 | 2026-06-20 |  |  | 2026-06-22 | 2026-06-22 | 2026-06-27 | 2026-06-30 | 2026-06-30 | 2026-07-02 | 2026-07-06 |  |  |  |  | 2026-07-08 | 2026-07-09 |  |  | 2026-07-11 | 2026-07-14 | 2026-07-16 | 2026-07-20 | 2026-07-22 | 96 | W2 | Haider | slv,Chest |  | pink-1011 pcs frt both slve 2 clr puff print |  |  | NFL3 |  |  | Cut Ok | 381 | 381 | 0 | 0 | -1011 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 30 | Jun'3 |  |  | 11.06.26
BS-NMT | 47600 | 13262047 | 1005 | 152 | 2026-04-15 | 2026-04-28 | SS o nk TS | TS |  |  | 2026-05-11 | 2026-05-17 | 2026-06-06 | 2026-06-16 |  |  | 2026-06-18 | 2026-06-18 | 2026-06-24 | 2026-06-26 | 2026-06-26 | 2026-06-29 | 2026-06-30 |  |  |  |  | 2026-07-04 | 2026-07-06 |  |  | 2026-07-08 | 2026-07-10 | 2026-07-15 | 2026-07-20 | 2026-07-22 | 96 | Z | Haider | Chest,Nk |  | white-1005 pcs 1 clr rub print |  |  | NFL3 |  |  | Cut Ok | 152 | 152 | 0 | 0 | -1005 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 30 | Jun'3 |  |  | 23.05.26
BS-NMT | 47602 | 13266114 | 1005 | 152 | 2026-04-15 | 2026-04-28 | LS o nk TS | TS |  |  | 2026-05-11 | 2026-05-16 | 2026-06-06 | 2026-06-15 |  |  | 2026-06-17 | 2026-06-17 | 2026-06-23 | 2026-06-25 | 2026-06-26 | 2026-06-29 | 2026-06-30 |  |  | 2026-06-30 | 2026-07-02 | 2026-07-06 | 2026-07-07 |  |  | 2026-07-09 | 2026-07-11 | 2026-07-13 | 2026-07-20 | 2026-07-22 | 96 | ZA1 | Haider | Nk | Chest | black-1005 pcs 3 clr seq emb |  |  | NFL3 |  |  | Cut Ok | 192 | 192 | 0 | 0 | -1005 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 30 | Jun'3 |  |  | 11.06.26
BS-NMT | 47614 | 13261649 | 5043 | 672 | 2026-04-15 | 2026-04-28 | LS Dress w btm mesh | Dress |  |  | 2026-06-06 | 2026-06-10 | 2026-06-22 | 2026-06-26 |  |  | 2026-06-25 | 2026-06-25 | 2026-07-01 | 2026-07-03 | 2026-07-07 | 2026-07-06 | 2026-07-09 |  |  |  |  | 2026-07-10 | 2026-07-16 |  |  | 2026-07-18 | 2026-07-20 | 2026-07-22 | 2026-07-27 | 2026-07-29 | 103 | V | Haider | Nk |  | 3 combo label print |  | Imp fab on 20/06 | NFL3 |  |  | Cut Ok | 256 | 256 | 0 | 0 | -5043 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46195 | 0 | 31 | Jul'1 |  |  | 23.05.26
BS-NMT | 47611 | 13252963 | 11203 | 1708 | 2026-04-15 | 2026-04-28 | LS Dress w btm mesh w nk picot | Dress |  |  | 2026-06-06 | 2026-06-12 | 2026-06-20 | 2026-06-28 |  |  | 2026-06-26 | 2026-06-26 | 2026-07-02 | 2026-07-04 | 2026-07-10 | 2026-07-07 | 2026-07-10 |  |  |  |  | 2026-07-10 | 2026-07-17 |  |  | 2026-07-20 | 2026-07-22 | 2026-07-23 | 2026-07-27 | 2026-07-29 | 103 | V | Haider | Nk |  | 4 combo label print |  | Imp fab on 20/06 | NFL3 |  |  | Cut Ok | 700 | 700 | 0 | 0 | -11203 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46193 | 0 | 31 | Jul'1 |  |  | 23.05.26
BS-ONL | 47457 | 15384402 | 1188 | 210 | 2026-04-12 | 2026-04-20 | Tank Top w chest heart shape stone patch hand sewing | Tank Top |  |  | 2026-05-04 | 2026-05-10 | 2026-05-15 | 2026-06-06 |  |  | 2026-06-06 | 2026-06-06 | 2026-06-13 | 2026-06-16 | 2026-06-17 |  |  | 2026-06-22 | 2026-06-26 |  |  | 2026-06-19 | 2026-06-20 |  |  | 2026-06-27 | 2026-06-29 | 2026-07-03 | 2026-07-13 | 2026-07-15 | 92 | O2 | Jannati |  |  | c.dan-594 pcs,,black-594 pcs both combo hand sewn heart shape patch |  | Hand sewn stone patch | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1188 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 29 | Jun'1 |  |  | 13.05.26
BS-ONL | 47459 | 15388212 | 1014 | 154 | 2026-04-12 | 2026-04-20 | SS o nk TS | TS |  |  | 2026-05-02 | 2026-05-06 | 2026-05-10 | 2026-05-22 |  |  | 2026-05-20 | 2026-05-20 | 2026-06-08 | 2026-06-10 | 2026-06-11 | 2026-06-13 | 2026-06-15 |  |  | 2026-06-17 | 2026-06-19 | 2026-06-22 | 2026-06-23 |  |  | 2026-06-25 | 2026-06-27 | 2026-06-30 | 2026-07-13 | 2026-07-15 | 92 | N1 | Jannati | Chest | Chest | c.dan-507 pcs 1 clr pig print 1 clr seq emb ,,black-507 pcs 1 clr rub print 1 clr seq emb |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1014 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46152 | 0 | 29 | Jun'1 |  |  | 18.05.26
BS-ONL | 30711 6th | 15209156 | 6210 | 1217 | 2026-04-23 | 2026-04-25 | LS o nk TS | TS |  |  | 2026-05-10 | 2026-05-15 | 2026-06-05 | 2026-06-11 |  |  | 2026-06-10 | 2026-06-10 | 2026-06-15 | 2026-06-17 | 2026-06-18 | [6 empty] | 2026-06-20 | 2026-06-23 |  |  | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-29 | 2026-07-01 | 67 | ZA1 | Mainul | [5 empty] | NFL3 |  |  | Cut Ok | 1217 | 1217 | 0 | 0 | -6210 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46178 | 0 | 27 | Jun'1 |  |  | 11.06.26
BS-ONL | 47514 | 15381873 | 1908 | 946 | 2026-04-16 | 2026-04-22 | Waist belt swt pant w side pkt drawstring | Pant |  |  | 2026-05-03 | 2026-05-10 | 2026-05-13 | 2026-06-09 |  |  | 2026-06-12 | 2026-06-12 | 2026-06-19 | 2026-06-22 | 2026-06-24 |  |  |  |  | 2026-06-25 | 2026-06-27 | 2026-07-01 | 2026-07-04 |  |  | 2026-07-07 | 2026-07-08 | 2026-07-11 | 2026-07-20 | 2026-07-22 | 95 | P | Khalid |  | Thigh | pumic-600 pcs,,wine-696 pcs,,dress-612 pcs all combo 1 clr lurex emb |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1908 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46155 | 0 | 30 | Jun'3 |  |  | 09.06.26
BS-ONL | 47515 | 15381739 | 810 | 141 | 2026-04-16 | 2026-04-22 | SS o nk TS | TS |  |  | 2026-05-06 | 2026-05-11 | 2026-05-14 | 2026-05-25 |  |  | 2026-06-06 | 2026-06-06 | 2026-06-10 | 2026-06-12 | 2026-06-13 | 2026-06-15 | 2026-06-16 |  |  |  |  | 2026-06-18 | 2026-06-19 |  |  | 2026-06-20 | 2026-06-23 | 2026-06-24 | 2026-06-29 | 2026-07-01 | 74 | O1 | Khalid | Chest |  | dress-810 pcs 2 clr rub 1 clr mettalic print |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -810 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46156 | 0 | 27 | Jun'1 |  |  | 16.05.26
BS-ONL | 40864 2nd | 15333392 | 2748 | 682 | 2026-04-16 | 2026-04-22 | High Waist legging | Legging |  |  | 2026-05-05 | 2026-05-10 | 2026-05-15 | 2026-06-08 |  |  | 2026-06-10 | 2026-06-10 | 2026-06-15 | 2026-06-17 | 2026-06-18 |  |  |  |  | 2026-06-20 | 2026-06-23 | 2026-06-25 | 2026-06-27 |  |  | 2026-06-29 | 2026-07-02 | 2026-07-04 | 2026-07-13 | 2026-07-15 | 88 | O1 | Khalid |  | Thigh | black-2748 pcs 1 clr lurex emb |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2748 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 29 | Jun'1 |  |  | 16.05.26
BS-ONL | 47511 | 15381726 | 1256 | 852 | 2026-04-16 | 2026-04-22 | Swt Pant w side contrast piping bon pkt and drawstring | Pant |  |  | 2026-05-04 | 2026-05-10 | 2026-05-15 | 2026-06-06 |  |  | 2026-06-09 | 2026-06-09 | 2026-06-15 | 2026-06-17 | 2026-06-18 | [6 empty] | 2026-06-20 | 2026-06-23 |  |  | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-29 | 2026-07-01 | 74 | R | Khalid | [5 empty] | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1256 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 27 | Jun'1 |  |  | 16.05.26
BS-ONL | 47510 | 15381877 | 5964 | 2748 | 2026-04-16 | 2026-04-22 | Swt pant w side pkt | Pant |  |  | 2026-05-02 | 2026-05-12 | 2026-05-14 | 2026-06-10 |  |  | 2026-06-10 | 2026-06-10 | 2026-06-15 | 2026-06-17 | 2026-06-20 |  |  |  |  | 2026-06-20 | 2026-06-24 | 2026-06-25 | 2026-06-30 |  |  | 2026-07-02 | 2026-07-04 | 2026-07-10 | 2026-07-20 | 2026-07-22 | 95 | R | Khalid |  | Thigh | pumic-1600 pcs,,winetasting-2128 pcs,,dress-2236 pcs all combo 1 clr lurex emb |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -5964 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46156 | 0 | 30 | Jun'1 |  |  | 09.06.26
BS-ONL | 40866 2nd | 15333403 | 6252 | 922 | 2026-04-16 | 2026-04-22 | LS v nk TS | TS |  |  | 2026-05-04 | 2026-05-11 | 2026-05-15 | 2026-06-08 |  |  | 2026-06-10 | 2026-06-10 | 2026-06-16 | 2026-06-18 | 2026-06-20 |  |  |  |  | 2026-06-20 | 2026-06-24 | 2026-06-25 | 2026-06-30 |  |  | 2026-07-02 | 2026-07-04 | 2026-07-07 | 2026-07-20 | 2026-07-22 | 95 | N1 | Khalid |  | Chest | black-1542 pcs,,wine-2160 pcs,,dress-2550 pcs all combo 1 clr lurex emb |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -6252 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 30 | Jun'1 |  |  | 16.05.26
BS-ONL | 44329 2nd | 15359041 | 2948 | 1142 | 2026-04-16 | 2026-04-22 | HW legging | Legging |  |  | 2026-05-06 | 2026-05-11 | 2026-05-15 | 2026-06-08 |  |  | 2026-06-08 | 2026-06-08 | 2026-06-13 | 2026-06-15 | 2026-06-17 | 2026-06-17 | 2026-06-19 |  |  |  |  | 2026-06-22 | 2026-06-25 |  |  | 2026-06-27 | 2026-06-29 | 2026-07-03 | 2026-07-13 | 2026-07-15 | 88 | P | Khalid | Waist |  | 1 combo label print |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2948 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 29 | Jun'1 |  |  | 20.05.26
BS-ONL | 47508 | 15381811 | 1280 | 593 | 2026-04-16 | 2026-04-22 | LS Hoodie w full zipper pkt zipper and drawstring | Hoody |  |  | 2026-05-05 | 2026-05-11 | 2026-05-15 | 2026-06-10 |  |  | 2026-06-13 | 2026-06-13 | 2026-06-19 | 2026-06-22 | 2026-06-23 | [6 empty] | 2026-06-25 | 2026-06-29 |  |  | 2026-07-02 | 2026-07-03 | 2026-07-06 | 2026-07-13 | 2026-07-15 | 88 | R | Khalid | [5 empty] | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1280 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 29 | Jun'3 |  |  | 27.06.26
BS-ONL | 47512 | 15381723 | 1176 | 754 | 2026-04-16 | 2026-04-23 | LS high nk half zipper Swt shirt w slve contrast piping | Swt Shirt |  |  | 2026-05-04 | 2026-05-11 | 2026-05-15 | 2026-06-08 |  |  | 2026-06-09 | 2026-06-09 | 2026-06-15 | 2026-06-17 | 2026-06-18 | [6 empty] | 2026-06-20 | 2026-06-23 |  |  | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-29 | 2026-07-01 | 74 | R | Khalid | [5 empty] | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1176 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 27 | Jun'1 |  |  | 16.05.26
BS-ONL | 47513 | 15381876 | 1860 | 873 | 2026-04-16 | 2026-04-23 | LS o nk Swt shirt w rib | Swt Shirt |  |  | 2026-05-04 | 2026-05-12 | 2026-05-15 | 2026-06-13 |  |  | 2026-06-15 | 2026-06-15 | 2026-06-20 | 2026-06-23 | 2026-06-25 |  |  |  |  | 2026-06-26 | 2026-06-29 | 2026-07-02 | 2026-07-06 |  |  | 2026-07-08 | 2026-07-10 | 2026-07-13 | 2026-07-20 | 2026-07-22 | 95 | K | Khalid |  | Chest | pumic-600 pcs,,wine-600 pcs,,dress-660 pcs all combo 1 clr lurex emb |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1860 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 30 | Jun'3 |  |  | 09.06.26
BS-ONL | 47509 | 15381995 | 5352 | 2468 | 2026-04-16 | 2026-04-23 | LS Reglan High nk full zipper jacket w side bon pkt | Jacket |  |  | 2026-05-03 | 2026-05-14 | 2026-05-13 | 2026-06-08 |  |  | 2026-06-06 | 2026-06-06 | 2026-06-13 | 2026-06-16 | 2026-06-20 |  |  |  |  | 2026-06-19 | 2026-06-22 | 2026-06-22 | 2026-06-29 |  |  | 2026-07-03 | 2026-07-04 | 2026-07-06 | 2026-07-13 | 2026-07-15 | 88 | R | Khalid |  | Chest | pumic-1588 pcs,,wine-1804 pcs,,dress-1960 pcs all combo 1 clr lurex emb |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -5352 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46155 | 0 | 29 | Jun'1 |  |  | 20.05.26
BS-ONL | 47507 | 15381872 | 2024 | 1091 | 2026-04-16 | 2026-04-23 | LS full zipper Swt hoody w drawstring | Hoody |  |  | 2026-05-04 | 2026-05-13 | 2026-05-15 | 2026-06-10 |  |  | 2026-06-13 | 2026-06-13 | 2026-06-19 | 2026-06-22 | 2026-06-24 |  |  |  |  | 2026-06-24 | 2026-06-27 | 2026-07-01 | 2026-07-04 |  |  | 2026-07-06 | 2026-07-08 | 2026-07-10 | 2026-07-20 | 2026-07-22 | 95 | R | Khalid |  | Chest | pumic-616 pcs,,wine-804 pcs,,dress-604 pcs all combo 1 clr lurex emb |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2024 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 30 | Jun'3 |  |  | 20.05.26
BS-ONL | 47064 3rd | 15381536 | 1000 | 522 | 2026-04-16 | 2026-04-18 | SS o nk TS | TS |  |  | 2026-04-08 | 2026-04-14 | 2026-05-20 | 2026-06-10 |  |  | 2026-06-10 | 2026-06-10 |  | 2026-06-15 | 2026-06-16 | 2026-06-18 | 2026-06-22 |  |  |  |  | 2026-06-25 | 2026-06-26 |  |  | 2026-06-29 | 2026-06-30 | 2026-07-06 | 2026-07-20 | 2026-07-22 | 95 | N1 | Zahirul | Chest |  | black-1000 pcs 1 clr rub 1 clr foil |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46162 | 0 | 30 | Jun'1 |  |  | 04.05.26
BS-ONL | 29253 9th | 15247220 | 1600 | 350 | 2026-04-16 | 2026-04-18 | TANK TOP | Tank Top |  |  | 2026-05-03 | 2026-05-09 | 2026-05-17 | 2026-06-06 |  |  | 2026-06-09 | 2026-06-09 |  | 2026-06-13 | 2026-06-15 | [6 empty] | 2026-06-17 | 2026-06-18 |  |  | 2026-06-20 | 2026-06-22 | 2026-06-23 | 2026-06-29 | 2026-07-01 | 74 | K | Zahirul | [5 empty] | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1600 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46159 | 0 | 27 | Jun'1 |  |  | 22.05.26
BS-ONL | 47316 | 15360701 | 396 | 72 | 2026-04-04 | 2026-04-22 | Lurex YD LS o nk TS w letus stitch and nk picoting | TS | 2026-05-14 | 2026-05-20 | 2026-06-05 | 2026-06-10 | 2026-06-12 | 2026-06-18 |  |  | 2026-06-20 | 2026-06-20 | 2026-06-26 | 2026-06-29 | 2026-06-29 | [6 empty] | 2026-07-02 | 2026-07-02 |  |  | 2026-07-04 | 2026-07-06 | 2026-07-08 | 2026-07-20 | 2026-07-22 | 107 | N1 | Abid |  |  |  | YD |  | NFL2 |  |  | Cut Ok | 72 | 72 | 0 | 421 | 25 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 30 | Jun'3 |  |  | 24.06.26
BS-ONL | 47315 | 15387209 | 336 | 88 | 2026-04-10 | 2026-04-22 | LS o nk TS w blind stitch | TS |  |  | 2026-05-06 | 2026-05-09 | 2026-05-18 | 2026-06-10 |  |  | 2026-06-12 | 2026-06-12 | 2026-06-18 | 2026-06-20 | 2026-06-20 | 2026-06-23 | 2026-06-26 |  |  |  |  | 2026-07-01 | 2026-07-01 |  |  | 2026-07-03 | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-15 | 94 | N2 | Abid | Fr,Bk |  | tofu-170 pcs frt 1 clr pig 1 clr puff back 1 clr pig 4 clr puff,,blue-170 pcs frt 3 clr rub 3 clr puff print back no print |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -336 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46160 | 0 | 29 | Jun'1 |  |  | 02.07.26
BS-ONL | 47317 | 15364584 | 3948 | 1262 | 2026-04-04 | 2026-04-22 | LS Swt shirt w rib | Swt Shirt |  |  | 2026-05-04 | 2026-05-12 | 2026-05-13 | 2026-06-08 |  |  | 2026-06-06 | 2026-06-06 | 2026-06-13 | 2026-06-15 | 2026-06-18 |  |  |  |  | 2026-06-17 | 2026-06-29 | 2026-07-02 | 2026-07-08 |  |  | 2026-07-10 | 2026-07-11 | 2026-07-13 | 2026-07-20 | 2026-07-22 | 107 | N2 | Abid |  | AOE | wine-1314 pcs,,bracken-1482 pcs,,pink lady-1158 pcs all combo frt back both slve all over 1 clr flat emb |  |  | NFL2 |  |  | Cut Ok | 40 | 40 | 0 | 0 | -3948 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46155 | 0 | 30 | Jun'1 |  |  | 02.07.26
BS-ONL | 47634 | 15366853 | 1476 | 341 | 2026-04-04 | 2026-04-22 | Lurex YD LS o nk TS | TS | 2026-05-12 | 2026-05-18 | 2026-05-22 | 2026-06-08 | 2026-06-12 | 2026-06-18 |  |  | 2026-06-20 | 2026-06-20 | 2026-06-25 | 2026-06-27 | 2026-06-29 | [6 empty] | 2026-07-03 | 2026-07-06 |  |  | 2026-07-08 | 2026-07-10 | 2026-07-13 | 2026-07-20 | 2026-07-22 | 107 | N1 | Abid |  |  |  | YD |  | NFL2 |  |  | Cut Ok | 386 | 386 | 0 | 0 | -1476 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 30 | Jun'3 |  |  | 24.06.26
BS-ONL | 47635 | 15380610 | 312 | 72 | 2026-04-04 | 2026-04-23 | Lurex YD Elasted legging w letus stitich | Legging | 2026-05-15 | 2026-05-20 | 2026-06-08 | 2026-06-12 | 2026-06-17 | 2026-06-22 |  |  | 2026-06-24 | 2026-06-24 | 2026-06-30 | 2026-07-03 | 2026-07-03 | [6 empty] | 2026-07-06 | 2026-07-07 |  |  | 2026-07-09 | 2026-07-13 | 2026-07-14 | 2026-07-20 | 2026-07-22 | 107 | P | Abid |  |  |  | YD |  | NFL2 |  |  | Cut Ok | 72 | 72 | 0 | 0 | -312 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46190 | 0 | 30 | Jul'1 |  |  | 02.07.26
BS-ONL | 47636 | 15380611 | 456 | 102 | 2026-04-04 | 2026-04-23 | Lurex YD LS dress w btm double layer woven | Dress | 2026-05-10 | 2026-05-15 | 2026-06-06 | 2026-06-10 | 2026-06-12 | 2026-06-17 |  |  | 2026-06-18 | 2026-06-18 | 2026-06-25 | 2026-06-27 | 2026-06-27 | [6 empty] | 2026-07-02 | 2026-07-03 |  |  | 2026-07-07 | 2026-07-08 | 2026-07-13 | 2026-07-20 | 2026-07-22 | 107 | Q | Abid |  |  |  | YD |  | NFL2 |  |  | Cut Ok | 102 | 102 | 0 | 0 | -456 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 30 | Jun'3 |  |  | 07.07.26
BS-ONL | 47644 | 15384571 | 1296 | 163 | 2026-04-04 | 2026-04-23 | LS o nk TS w blind stitch two combo bow aattach | TS |  |  | 2026-05-12 | 2026-06-16 | 2026-06-05 | 2026-06-17 |  |  | 2026-06-17 | 2026-06-17 | 2026-06-23 | 2026-06-25 | 2026-06-26 | 2026-06-29 | 2026-06-30 |  |  | 2026-07-01 | 2026-07-04 | 2026-07-06 | 2026-07-07 |  |  | 2026-07-09 | 2026-07-13 | 2026-07-15 | 2026-07-20 | 2026-07-22 | 107 | N1 | Abid | Chest | Chest | wine tasting-402 pcs no print mesh fabric applique attach emb,,pink-474 pcs no print 1 clr lurex emb and satin fab bow attach ,,c.dan-424 pcs 1 clr rub 1 clr HD and tuffle fabric bow attach no emb |  |  | NFL2 |  |  | Cut Ok | 163 | 163 | 0 | 0 | -1296 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46178 | 0 | 30 | Jun'3 |  |  | 04.07.26
BS-ONL | 46770 2nd | 15374735 | 3040 | 576 | 2026-04-24 | 2026-04-27 | LS AOP O nk TS | TS |  |  | 2026-05-05 | 2026-05-15 | 2026-05-18 | 2026-06-10 | 2026-06-12 | 2026-06-19 | 2026-06-17 | 2026-06-17 |  | 2026-06-22 | 2026-06-24 | [6 empty] | 2026-06-25 | 2026-06-29 |  |  | 2026-07-02 | 2026-07-04 | 2026-07-07 | 2026-07-13 | 2026-07-15 | 80 | L1 | Abid |  |  |  | AOP |  | NFL2 |  |  | Cut Ok | 576 | 576 | 0 | 0 | -3040 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46160 | 0 | 29 | Jun'3 |  |  | 02.07.26
BS-ONL | 47645 | 15384584 | 1716 | 195 | 2026-04-04 | 2026-04-27 | LS o nk TS w blind stitch | TS |  |  | 2026-05-08 | 2026-05-12 | 2026-05-17 | 2026-06-13 |  |  | 2026-06-16 | 2026-06-16 | 2026-06-26 | 2026-06-22 | 2026-06-24 | 2026-06-24 | 2026-06-27 |  |  | 2026-06-27 | 2026-07-06 | 2026-07-09 | 2026-07-11 |  |  | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-20 | 2026-07-22 | 107 | N1 | Abid | Chest | Chest | c.dan-890 pcs 1 clr pig print and 3 clr tapping emb,,pink-830 pcs 1 clr rub print and 1 clr tapping emb |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1716 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46159 | 0 | 30 | Jun'3 |  |  | 07.07.26
BS-ONL | 47641 | 15383292 | 410 | 101 | 2026-04-04 | 2026-04-27 | LS TS w front nk cut out w bow | TS |  |  | 2026-05-12 | 2026-05-16 | 2026-06-06 | 2026-06-16 |  |  | 2026-06-18 | 2026-06-18 | 2026-06-24 | 2026-06-26 | 2026-06-26 | [6 empty] | 2026-06-29 | 2026-06-30 |  |  | 2026-07-03 | 2026-07-06 | 2026-07-08 | 2026-07-20 | 2026-07-22 | 107 | O1 | Abid | [5 empty] | NFL2 |  |  | Cut Ok | 101 | 101 | 0 | 0 | -410 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 30 | Jun'3 |  |  | 07.07.26
BS-ONL | 47640 | 15382572 | 3444 | 1168 | 2026-04-04 | 2026-04-27 | LS Swt shirt w rib | Swt Shirt |  |  | 2026-05-06 | 2026-05-13 | 2026-05-18 | 2026-06-13 |  |  | 2026-06-16 | 2026-06-16 | 2026-06-23 | 2026-06-25 | 2026-06-27 | 2026-06-27 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-03 | 2026-07-08 | 2026-07-10 | 2026-07-13 |  |  | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-20 | 2026-07-22 | 107 | N2 | Abid | Chest,Stone | Chest | fudge-2190 pcs 1 clr rub 1 clr flock print and HP stone no emb ,,bel-594 pcs no print stone and 2 clr flat 1 clr terry emb ,,wood-666 pcs 1 clr rub 1 clr flock print and HP stone no emb |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -3444 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46160 | 0 | 30 | Jun'3 |  |  | 07.07.26
BS-ONL | 47639 | 15382571 | 1800 | 624 | 2026-04-04 | 2026-04-27 | Elataed Legging w side contrast piping | Legging |  |  | 2026-05-05 | 2026-05-16 | 2026-06-06 | 2026-06-18 |  |  | 2026-06-20 | 2026-06-20 | 2026-06-26 | 2026-06-29 | 2026-06-30 | [6 empty] | 2026-07-03 | 2026-07-04 |  |  | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-20 | 2026-07-22 | 107 | P | Abid | [5 empty] | NFL2 |  |  | Cut Ok | 625 | 625 | 0 | 0 | -1800 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 30 | Jun'3 |  |  | 22.06.26
BS-ONL | 47642 | 15384328 | 405 | 69 | 2026-04-04 | 2026-04-27 | LS o nk TS w blind stitch | TS |  |  | 2026-05-12 | 2026-05-15 | 2026-06-06 | 2026-06-15 |  |  | 2026-06-17 | 2026-06-17 | 2026-06-22 | 2026-06-24 | 2026-06-24 | 2026-06-26 | 2026-06-27 |  |  |  |  | 2026-07-01 | 2026-07-01 |  |  | 2026-07-03 | 2026-07-06 | 2026-07-08 | 2026-07-20 | 2026-07-22 | 107 | O1 | Abid | slv,Chest |  | c.dan-407 pcs chest 1 clr pig 3 clr gltr and one slve 1 clr pig |  |  | NFL2 |  |  | Cut Ok | 69 | 69 | 0 | 0 | -405 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 30 | Jun'3 |  |  | 20.06.26
BS-ONL | 47637 | 15382404 | 528 | 120 | 2026-04-04 | 2026-04-27 | LS Swt shirt w rib | Swt Shirt |  |  | 2026-05-09 | 2026-05-14 | 2026-05-20 | 2026-06-13 |  |  | 2026-06-15 | 2026-06-15 | 2026-06-20 | 2026-06-23 | 2026-06-23 | 2026-06-25 | 2026-06-26 |  |  | 2026-06-29 | 2026-07-02 | 2026-07-04 | 2026-07-06 |  |  | 2026-07-08 | 2026-07-09 | 2026-07-11 | 2026-07-20 | 2026-07-22 | 107 | N2 | Abid | Chest | Chest | n. sky-530 pcs 1 clr rub print and chochet fabric applique emb |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 575 | 47 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46162 | 0 | 30 | Jun'3 |  |  | 06.07.26
BS-ONL | 47638 | 15382405 | 492 | 121 | 2026-04-04 | 2026-04-27 | Swt pant w side pkt and rib | Pant |  |  | 2026-05-11 | 2026-05-15 | 2026-06-06 | 2026-06-17 |  |  | 2026-06-18 | 2026-06-18 | 2026-06-25 | 2026-06-27 | 2026-06-27 |  |  |  |  | 2026-06-30 | 2026-07-02 | 2026-07-06 | 2026-07-07 |  |  | 2026-07-09 | 2026-07-11 | 2026-07-13 | 2026-07-20 | 2026-07-22 | 107 | P | Abid |  | Thigh | N.sky-494 pcs chochet fabric applique emb |  |  | NFL2 |  |  | Cut Ok | 121 | 121 | 0 | 0 | -492 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 30 | Jun'3 |  |  | 06.07.26
BS-ONL | 47643 | 15384337 | 3117 | 1054 | 2026-04-04 | 2026-04-27 | LS Swt shirt w rib | Swt Shirt |  |  | 2026-05-05 | 2026-05-13 | 2026-05-17 | 2026-06-13 |  |  | 2026-06-15 | 2026-06-15 | 2026-06-20 | 2026-06-23 | 2026-06-25 | 2026-06-25 | 2026-06-30 |  |  | 2026-06-27 | 2026-07-03 | 2026-07-06 | 2026-07-09 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-20 | 2026-07-22 | 107 | N2 | Abid | Fr & Bk & Slv | Chest | Tofu-626 pcs frt 1 clr pig 1 clr gltr and HP stone no emb both slve 1 clr pig ,,blue XOXO-338 pcs no print chest 1 clr flat 1 clr terry emb ,,blue bracken-602 pcs no print chest 1 clr flat 1 clr terry emb,,grape -527 pcs frt back 1 clr rub 1 clr gltr both slve 1 clr rub,,true-434 pcs frt back 1 clr rub 1 clr gltr both slve 1 clr rub,,bracken-602 pcs |  | one combo artwork due | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -3117 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46159 | 0 | 30 | Jun'3 |  |  | 02.07.26
BS-ONL | 47647 | 15384635 | 588 | 185 | 2026-04-04 | 2026-04-27 | LS Swt shirt dress w rib btm mesh | Dress |  |  | 2026-05-09 | 2026-05-14 | 2026-05-18 | 2026-06-13 |  |  | 2026-06-15 | 2026-06-15 | 2026-06-20 | 2026-06-22 | 2026-06-23 | 2026-06-25 | 2026-06-27 |  |  |  |  | 2026-07-02 | 2026-07-04 |  |  | 2026-07-07 | 2026-07-08 | 2026-07-13 | 2026-07-20 | 2026-07-22 | 107 | J | Abid | Fr,Bk |  | pink-362 pcs frt 2 clr rub 2 clr puff back 2 clr puff,,phanthom-230 pcs frt 1 clr rub 1 clr puff back no print |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -588 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46160 | 0 | 30 | Jun'3 |  |  | 09.07.26
BS-ONL | 47646 | 15384633 | 948 | 205 | 2026-04-04 | 2026-04-27 | LS Swt shirt w rib | Swt Shirt |  |  | 2026-05-09 | 2026-05-15 | 2026-05-18 | 2026-06-10 |  |  | 2026-06-12 | 2026-06-12 | 2026-06-18 | 2026-06-20 | 2026-06-20 | 2026-06-22 | 2026-06-23 |  |  | 2026-06-25 | 2026-06-30 | 2026-07-04 | 2026-07-06 |  |  | 2026-07-08 | 2026-07-10 | 2026-07-13 | 2026-07-20 | 2026-07-22 | 107 | N2 | Abid | Chest | Chest | pink-950 pcs 1 clr rub print and 1 clr tapping emb |  |  | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -948 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46160 | 0 | 30 | Jun'1 |  |  | 07.07.26
OVS SPA | 47396 | 262TSH063-223 | 3335 | 1139 | 2026-04-15 | 2026-04-25 | YD SS o nk TS | TS | 2026-05-09 | 2026-05-18 | 2026-05-20 | 2026-06-13 | 2026-06-15 | 2026-06-27 |  |  | 2026-07-10 | 2026-06-27 | 2026-07-04 | 2026-07-06 | 2026-07-08 | 2026-07-09 | 2026-07-13 |  |  | 2026-07-13 | 2026-07-17 | 2026-07-17 | 2026-07-20 |  |  | 2026-07-21 | 2026-07-23 | 2026-07-25 | 2026-07-27 | 2026-07-27 | 103 | G2 | Sirajul | Chest | Chest | multicolor-3335 pcs 1 clr rub and 3 clr flat emb |  |  | NFL1 |  |  | Cut Ok | 1139 | 1139 | 0 | 0 | -3335 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 31 | Jul'1 |  |  | 06.07.26
OVS SPA | 47505 | 262JOG015-226 | 10290 | 3290 | 2026-04-15 | 2026-04-25 | LS Swt shirt w rib and Swt pant w pkt and drawstring | Top & BTM |  |  | 2026-05-11 | 2026-05-25 | 2026-06-06 | 2026-06-20 |  |  | 2026-06-25 | 2026-06-17 | 2026-06-23 | 2026-06-24 | 2026-06-29 | 2026-06-27 | 2026-07-04 |  |  |  |  | 2026-07-04 | 2026-07-10 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-15 | 91 | N/2 | Sirajul | Fr,Bk |  | summer top-5145 pcs frt back 4 clr rub 1 clr flock print ,,toffeee btm-5145 pcs bo print |  |  | NCL |  |  | Ready Test Cut | 3247 | 3247 | 0 | 0 | -10290 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 29 | Jun'3
OVS SPA | 47399 | 262TRO086PF-223 | 3155 | 1420 | 2026-04-15 | 2026-04-25 | Trouser w drawstring and both leg Rib tape | Trouser |  |  | 2026-05-11 | 2026-05-25 | 2026-06-08 | 2026-06-20 |  |  | 2026-07-07 | 2026-07-02 | 2026-07-07 | 2026-07-08 | 2026-07-10 |  |  |  |  | 2026-07-10 | 2026-07-15 | 2026-07-15 | 2026-07-20 |  |  | 2026-07-21 | 2026-07-23 | 2026-07-25 | 2026-07-27 | 2026-07-27 | 103 | H | Sirajul |  | Thigh | chocolate-3155 pcs 3 clr flat emb |  |  | NFL1 |  |  | Cut Ok | 1420 | 1420 | 0 | 0 | -3155 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 31 | Jul'1 |  |  | 01.07.26
OVS SPA | 47398 | 262TRO085PF-223 | 11910 | 6203 | 2026-04-15 | 2026-04-25 | Trouser w drawstring and both leg contrast tape | Trouser |  |  | 2026-05-08 | 2026-05-25 | 2026-06-06 | 2026-06-22 |  |  | 2026-06-24 | 2026-06-25 | 2026-06-30 | 2026-07-01 | 2026-07-04 | [6 empty] | 2026-07-04 | 2026-07-13 |  |  | 2026-07-14 | 2026-07-16 | 2026-07-18 | 2026-07-20 | 2026-07-20 | 96 | H | Sirajul | [5 empty] | NFL1 |  |  | Cut Ok | 5013 | 5013 | 0 | 0 | -11910 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 30 | Jul'1 |  |  | 27.06.26
OVS SPA | 47397 | 262SWT052-223 | 3135 | 1680 | 2026-04-23 | 2026-04-27 | LS SWT hoody w front nk placket and kangaroo pkt | Hoody | 2026-05-08 | 2026-05-18 | 2026-05-18 | 2026-06-13 | 2026-06-15 | 2026-06-27 |  |  | 2026-07-08 | 2026-06-25 | 2026-07-03 | 2026-07-04 | 2026-07-06 | 2026-07-07 | 2026-07-11 |  |  | 2026-07-10 | 2026-07-15 | 2026-07-15 | 2026-07-21 |  |  | 2026-07-22 | 2026-07-23 | 2026-07-25 | 2026-07-27 | 2026-07-27 | 95 | N/2 | Sirajul | Bk | BK | Pale khaki-3135 pcs 1 clr pig and 1 clr flat 1 clr terry emb |  |  | NCL |  |  | Cut Ok | 1680 | 1680 | 0 | 0 | -3135 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 31 | Jul'1
OVS SPA | 47668 | 262TSH321W-227 | 2761 | 299 | 2026-04-22 | 2026-04-25 | LS ST w back nk Placket btn | TS |  |  | 2026-06-08 | 2026-06-17 | 2026-06-18 | 2026-07-02 |  |  | 2026-07-10 | 2026-07-04 | 2026-07-10 | 2026-07-11 | 2026-07-13 | 2026-07-14 | 2026-07-20 |  |  |  |  | 2026-07-20 | 2026-07-24 |  |  | 2026-07-24 | 2026-07-25 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 96 | A | Salam | Chest |  | White-1518 pcs 6 clr pig 1 clr gltr ,,red-1243 pcs 5 clr rub 1 clr gltr |  |  | NFL1 |  |  | Cut Ok | 299 | 299 | 0 | 0 | -2761 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46191 | 0 | 31 | Jul'2 |  |  | 01.07.26
OVS SPA | 47500 | 262PJA071-228 | 20108 | 4370 | 2026-04-13 | 2026-04-21 | AOP LS Swt shirt w rib and AOP Swt pant | Top & Btm |  |  | 2026-05-02 | 2026-06-10 | 2026-05-16 | 2026-06-15 | 2026-06-10 | 2026-06-27 | 2026-06-29 | 2026-06-27 | 2026-07-03 | 2026-07-04 | 2026-07-09 | 2026-07-07 | 2026-07-13 |  |  |  |  | 2026-07-08 | 2026-07-17 |  |  | 2026-07-18 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-22 | 100 | V+U | Khairul | Heat Press/Heat Seal |  | 1 combo nk HP sticker | AOP |  | NFL3 |  |  | Cut Ok | 4170 | 4170 | 0 | 0 | -20108 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46158 | 0 | 30 | Jul'1 |  |  | 04.07.26
OVS SPA | 47501 | 262PJA072-228 | 5598 | 1280 | 2026-04-13 | 2026-04-21 | LS Swt shirt w rib and AOP Swt pant | Top & Btm |  |  | 2026-05-02 | 2026-06-10 | 2026-05-15 | 2026-06-15 | 2026-06-10 | 2026-06-22 | 2026-07-03 | 2026-07-02 | 2026-07-06 | 2026-07-07 | 2026-07-09 | 2026-07-09 | 2026-07-13 |  |  |  |  | 2026-07-13 | 2026-07-17 |  |  | 2026-07-18 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-22 | 100 | N/3 | Khairul | Chest,HP |  | red top-2799 pcs 4 clr rub 1 clr puff print ,,red AOP btm-2799 pcs no print | AOP |  | NCL |  |  | Ready Test Cut | 1280 | 1280 | 0 | 0 | -5598 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46157 | 0 | 30 | Jul'1
OVS SPA | 47502 | 262PJA171-228 | 14430 | 4955 | 2026-04-13 | 2026-04-21 | LS Swt shirt w rib and AOP Swt pant | Top & Btm |  |  | 2026-05-02 | 2026-06-10 | 2026-05-16 | 2026-06-16 | 2026-06-10 | 2026-06-22 | 2026-06-30 | 2026-06-18 | 2026-06-24 | 2026-06-25 | 2026-06-30 | 2026-07-01 | 2026-07-07 |  |  | 2026-07-06 | 2026-07-11 | 2026-07-10 | 2026-07-17 |  |  | 2026-07-18 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-22 | 100 | U+V | Khairul | Chest,HP | Chest | salute top-7215 pcs 1 clr rub print and 5 clr flat emb ,,red Aop btm-7215 pcs no print emb | AOP |  | NFL3 |  |  | Cut Ok | 4955 | 4947 | -8 | 0 | -14430 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46158 | 0 | 30 | Jun'3 |  |  | 04.07.26
OVS SPA | 47491 | 262TSH247-6154 | 1795 | 875 | 2026-04-16 | 2026-04-29 | LS double slve TS w YD nk rib | TS | 2026-05-05 | 2026-05-15 | 2026-05-15 | 2026-05-26 | 2026-06-06 | 2026-06-20 |  |  | 2026-06-29 | 2026-06-26 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-06 | 2026-07-09 |  |  | 2026-07-08 | 2026-07-10 | 2026-07-09 | 2026-07-11 |  |  | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 95 | N/1 | Khairul | Fr,Bk | Chest | zifandel-1795 pcs frt 2 clr rub and applique emb back 3 clr rub print | YD |  | NCL |  |  | Ready Test Cut | 875 | 875 | 0 | 0 | -1795 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 30 | Jul'1
OVS SPA | 47492 | 262SWT358-6154 | 1565 | 975 | 2026-04-16 | 2026-04-29 | LS Swt hoody w kangaro pkt | Hoody |  |  | 2026-05-13 | 2026-05-25 | 2026-05-26 | 2026-06-20 |  |  | 2026-06-29 | 2026-06-24 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 2026-07-06 |  |  | 2026-07-06 | 2026-07-09 | 2026-07-09 | 2026-07-13 |  |  | 2026-07-14 | 2026-07-16 | 2026-07-18 | 2026-07-20 | 2026-07-20 | 95 | B | Khairul | Chest | Chest | sand-1565 pcs 2 clr rub 1 clr flat emb |  |  | NFL1 |  |  | Cut Ok | 80 | 80 | 0 | 0 | -1565 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46168 | 0 | 30 | Jul'1 |  |  | 06.07.26
OVS SPA | 47493 | 262SWT374-6156 | 3955 | 1540 | 2026-04-16 | 2026-04-29 | LS swt hoody w contrast hood and kangro pkt | Hoody |  |  | 2026-05-13 | 2026-05-25 | 2026-05-26 | 2026-06-18 |  |  | 2026-06-27 | 2026-06-20 | 2026-06-27 | 2026-06-29 | 2026-07-01 | 2026-07-02 | 2026-07-08 |  |  |  |  | 2026-07-07 | 2026-07-13 |  |  | 2026-07-15 | 2026-07-16 | 2026-07-18 | 2026-07-20 | 2026-07-20 | 95 | B | Khairul | Chest |  | tofu-3955 pcs 5 clr rub and embossed print |  |  | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -3955 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46168 | 0 | 30 | Jun'3 |  |  | 15.07.26
OVS SPA | 47497 | 262TSH383-6156 | 4235 | 740 | 2026-04-16 | 2026-04-29 | LS high nk TS | TS |  |  | 2026-05-13 | 2026-05-26 | 2026-06-06 | 2026-06-24 |  |  | 2026-06-27 | 2026-06-24 | 2026-06-30 | 2026-07-01 | 2026-07-04 | 2026-07-04 | 2026-07-09 |  |  |  |  | 2026-07-08 | 2026-07-14 |  |  | 2026-07-15 | 2026-07-16 | 2026-07-18 | 2026-07-20 | 2026-07-20 | 95 | E | Khairul | Fr,Bk |  | tofu-4235 pcs frt 1 clr rub back 5 clr rub |  |  | NFL1 |  |  | Cut Ok | 740 | 740 | 0 | 0 | -4235 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 30 | Jul'1 |  |  | 29.06.26
OVS SPA | 47498 | 262SWT385-6156 | 3955 | 1180 | 2026-04-16 | 2026-04-29 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-05-11 | 2026-05-23 | 2026-05-25 | 2026-06-22 |  |  | 2026-06-27 | 2026-06-24 | 2026-06-30 | 2026-07-01 | 2026-07-03 | 2026-07-03 | 2026-07-08 |  |  |  |  | 2026-07-08 | 2026-07-11 |  |  | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 95 | A | Khairul | Chest |  | blue-3955 pcs 1 clr rub print |  |  | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -3955 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46167 | 0 | 30 | Jul'1 |  |  | 29.06.26
BS-NMT | 47536 | 13262473 | 1600 | 540 | 2026-04-16 | 2026-04-25 | Swt Pant w side pkt drawstring | Pant |  |  | 2026-05-15 | 2026-05-20 | 2026-06-10 | 2026-06-26 |  |  | 2026-07-01 | 2026-07-01 | 2026-07-07 | 2026-07-10 | 2026-07-11 | [6 empty] | 2026-07-15 | 2026-07-17 |  |  | 2026-07-20 | 2026-07-22 | 2026-07-25 | 2026-08-17 | 2026-08-19 | 123 | X | Kamruzzaman | [5 empty] | NFL3 |  |  | Cut Ok | 540 | 540 | 0 | 1680 | 80 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 34 | Jul'1 |  |  | 20.06.26
BS-NMT | 47537 | 13262474 | 3018 | 1233 | 2026-04-16 | 2026-04-25 | LS Swt hoody w kangaro pkt | Hoody |  |  | 2026-05-13 | 2026-05-20 | 2026-06-08 | 2026-06-24 |  |  | 2026-06-27 | 2026-06-27 | 2026-07-03 | 2026-07-06 | 2026-07-08 | 2026-07-09 | 2026-07-13 |  |  |  |  | 2026-07-15 | 2026-07-18 |  |  | 2026-07-21 | 2026-07-23 | 2026-07-25 | 2026-08-17 | 2026-08-19 | 123 | T2 | Kamruzzaman | Chest |  | Navy-1114 pcs 4 clr rub,,gray-1108 pcs 3 clr rub,,olive-796 pcs 3 clr rub |  |  | NFL3 |  |  | Cut Ok | 1232 | 1232 | 0 | 3155 | 137 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 34 | Jul'1 |  |  | 19.06.26
BS-NMT | 47538 | 13235128 | 801 | 170 | 2026-04-16 | 2026-04-25 | AOP LS Swt shirt w bm rib | Swt Shirt |  |  | 2026-05-15 | 2026-05-20 | 2026-06-10 | 2026-06-22 | 2026-06-25 | 2026-06-30 | 2026-07-04 | 2026-07-04 | 2026-07-10 | 2026-07-13 | 2026-07-13 | [6 empty] | 2026-07-15 | 2026-07-16 |  |  | 2026-07-18 | 2026-07-21 | 2026-07-25 | 2026-08-24 | 2026-08-26 | 130 | Z | Kamruzzaman |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 170 | 170 | 0 | 820 | 19 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 35 | Jul'2 |  |  | 01.07.26
BS-NMT | 47539 | 13235130 | 1608 | 454 | 2026-04-16 | 2026-04-25 | AOP & Solid AOP Swt dress | Dress |  |  | 2026-05-15 | 2026-05-20 | 2026-06-10 | 2026-06-23 | 2026-06-25 | 2026-06-30 | 2026-07-06 | 2026-07-06 | 2026-07-11 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 2026-07-16 |  |  |  |  | 2026-07-16 | 2026-07-17 |  |  | 2026-07-20 | 2026-07-22 | 2026-07-25 | 2026-08-24 | 2026-08-26 | 130 | Y | Kamruzzaman | Chest |  | grape AOP-804 pcs no print ,,blue-804 pcs 1 clr rub 1 clr gltr | AOP |  | NFL3 |  |  | Cut Ok | 454 | 435 | -19 | 1699 | 91 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 35 | Jul'2 |  |  | 01.07.26
BS-NMT | 47540 | 13234338 | 2682 | 710 | 2026-04-16 | 2026-04-25 | AOP & Solid LS Swt shirt | Swt Shirt |  |  | 2026-05-12 | 2026-05-18 | 2026-06-06 | 2026-06-20 | 2026-06-22 | 2026-06-27 | 2026-06-29 | 2026-06-29 | 2026-07-04 | 2026-07-07 | 2026-07-08 | 2026-07-10 | 2026-07-14 |  |  |  |  | 2026-07-16 | 2026-07-18 |  |  | 2026-07-20 | 2026-07-22 | 2026-07-27 | 2026-08-24 | 2026-08-26 | 130 | Z | Kamruzzaman | Chest |  | Navy -803 pcs 5 clr rub ,,Olive AOP-959 pcs no print ,,sepia-920 pcs 6 clr rub | AOP |  | NFL3 |  |  | Cut Ok | 593 | 593 | 0 | 2804 | 122 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 35 | Jul'1 |  |  | 01.07.26
BS-NMT | 47587 | 13262630 | 1860 | 191 | 2026-04-15 | 2026-04-27 | LS Dress w btm double layer mesh and shlder snap btn | Dress |  |  | 2026-06-17 | 2026-05-20 | 2026-06-20 | 2026-06-30 |  |  | 2026-07-07 | 2026-07-07 | 2026-07-15 | 2026-07-18 | 2026-07-20 | 2026-07-22 | 2026-07-23 |  |  |  |  | 2026-07-25 | 2026-07-28 |  |  | 2026-07-30 | 2026-08-01 | 2026-08-03 | 2026-08-24 | 2026-08-26 | 131 | S+T | Mosaddik | Nk |  | 1 combo label print |  |  | NFL3 |  |  | Cut Ok | 192 | 192 | 0 | 0 | -1860 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46193 | 0 | 35 | Jul'2 |  |  | 01.08.26
BS-NMT | 47588 | 13262631 | 1005 | 43 | 2026-04-15 | 2026-04-27 | Skirt w double layer mesh | Skirt |  |  | 2026-05-15 | 2026-05-17 | 2026-06-20 | 2026-06-27 |  |  | 2026-07-06 | 2026-07-06 | 2026-07-13 | 2026-07-15 | 2026-07-16 | 2026-07-20 | 2026-07-21 |  |  |  |  | 2026-07-23 | 2026-07-27 |  |  | 2026-07-29 | 2026-07-30 | 2026-08-06 | 2026-08-24 | 2026-08-26 | 131 | X | Mosaddik | Waist |  | 1 combo label print |  |  | NFL3 |  |  | Cut Ok | 43 | 43 | 0 | 0 | -1005 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46193 | 0 | 35 | Jul'2 |  |  | 07.08.26
BS-NMT | 47621 | 13262658 | 1654 | 544 | 2026-04-15 | 2026-04-28 | LS full zipper hoody w kangaroo pkt | Hoody |  |  | 2026-06-06 | 2026-06-10 | 2026-06-22 | 2026-06-30 |  |  | 2026-07-04 | 2026-07-04 | 2026-07-11 | 2026-07-14 | 2026-07-15 |  |  |  |  | 2026-07-17 | 2026-07-20 | 2026-07-23 | 2026-07-27 |  |  | 2026-07-29 | 2026-07-31 | 2026-08-03 | 2026-08-24 | 2026-08-26 | 131 | S | Haider |  | Chest | mauve-812 pcs,,blue-842 pcs both combo 1 clr lurex emb |  | Imp fab on 20/06 | NFL3 |  |  | Cut Ok | 142 | 142 | 0 | 1733 | 79 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46195 | 0 | 35 | Jul'2 |  |  | 04.07.26
BS-NMT | 47620 | 13262657 | 1815 | 363 | 2026-04-15 | 2026-04-28 | Swt elasted pant | Pant | [8 empty] | 2026-07-10 | 2026-07-10 | 2026-07-18 | 2026-07-21 | 2026-07-22 | [6 empty] | 2026-07-24 | 2026-07-28 |  |  | 2026-07-30 | 2026-08-01 | 2026-08-05 | 2026-08-24 | 2026-08-26 | 131 | Z | Haider |  |  |  |  | Imp fab on 25/06 | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 1895 | 80 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 35 | Jul'3 |  |  | 04.07.26
BS-ONL | 47649 | 15384289 | 996 | 143 | 2026-04-04 | 2026-04-23 | LS o nk TS w blind stitch one combo bow aattach | TS |  |  | 2026-05-15 | 2026-05-20 | 2026-06-10 | 2026-06-23 |  |  | 2026-06-26 | 2026-06-26 | 2026-07-04 | 2026-07-07 | 2026-07-07 | 2026-07-10 | 2026-07-11 |  |  | 2026-07-13 | 2026-07-17 | 2026-07-20 | 2026-07-21 |  |  | 2026-07-23 | 2026-07-25 | 2026-07-28 | 2026-08-22 | 2026-08-24 | 140 | O1 | Abid | Chest | Chest | winetasting-518 pcs no print mesh fabric applique attach emb ,,c.dan-482 pcs 1 clr rub 1 clr HD and tuffle fabric bow attach no emb |  |  | NFL2 |  |  | Cut Ok | 143 | 143 | 0 | 0 | -996 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 35 | Jul'1 |  |  | 24.06.26
BS-ONL | 47648 | 15383418 | 1684 | 377 | 2026-04-04 | 2026-04-28 | LS TS w full placket frill and btn | TS |  |  | 2026-06-06 | 2026-06-10 | 2026-06-16 | 2026-06-30 |  |  | 2026-07-07 | 2026-07-07 | 2026-07-13 | 2026-07-16 | 2026-07-17 | [6 empty] | 2026-07-20 | 2026-07-24 |  |  | 2026-07-27 | 2026-07-29 | 2026-08-07 | 2026-08-22 | 2026-08-24 | 140 | J | Abid | [5 empty] | NFL2 |  |  | Cut Ok | 377 | 377 | 0 | 0 | -1684 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46189 | 0 | 35 | Jul'2 |  |  | 24.07.26
BS-ONL | 47651 | 15384621/15392611 | 945 | 291 | 2026-04-04 | 2026-04-28 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-05-13 | 2026-05-18 | 2026-06-10 | 2026-06-24 |  |  | 2026-06-26 | 2026-06-26 | 2026-07-04 | 2026-07-07 | 2026-07-08 | 2026-07-10 | 2026-07-18 |  |  |  |  | 2026-07-22 | 2026-07-23 |  |  | 2026-07-25 | 2026-07-28 | 2026-07-30 | 2026-08-10 | 2026-08-12 | 128 | N2 | Abid | Fr & Bk & Slv |  | red-347 pcs,,pansy-602 pcs both combo frt back both slve all over 1 clr flock print |  |  | NFL2 |  |  | Cut Ok | 291 | 291 | 0 | 0 | -945 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 33 | Jul'1 |  |  | 02.07.26
BS-ONL | 47650 | 15384295 | 876 | 329 | 2026-04-04 | 2026-04-28 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-05-17 | 2026-05-22 | 2026-06-12 | 2026-06-27 |  |  | 2026-07-01 | 2026-07-01 | 2026-07-09 | 2026-07-11 | 2026-07-11 | 2026-07-14 | 2026-07-18 |  |  |  |  | 2026-07-22 | 2026-07-23 |  |  | 2026-07-25 | 2026-07-28 | 2026-07-30 | 2026-08-24 | 2026-08-26 | 142 | N2 | Abid | Fr,Bk |  | wine-878 pcs frt back 1 clr mettalic puff 1 clr puff print |  |  | NFL2 |  |  | Cut Ok | 328 | 328 | 0 | 917 | 41 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 35 | Jul'2 |  |  | 06.07.26
BS-ONL | 47654 | 15385290 | 828 | 323 | 2026-04-04 | 2026-04-28 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-06-06 | 2026-06-10 | 2026-06-15 | 2026-06-30 |  |  | 2026-07-06 | 2026-07-06 | 2026-07-13 | 2026-07-15 | 2026-07-16 | 2026-07-20 | 2026-07-24 |  |  |  |  | 2026-07-28 | 2026-07-29 |  |  | 2026-07-31 | 2026-08-05 | 2026-08-10 | 2026-09-21 | 2026-09-23 | 170 | N2 | Abid | Fr,Bk |  | blue-830 pcs frt back 3 clr HD rub print |  |  | NFL2 |  |  | Cut Ok | 323 | 323 | 0 | 946 | 118 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 39 | Jul'2 |  |  | 06.07.26
BS-ONL | 47653 | 15384868 | 420 | 102 | 2026-04-04 | 2026-04-28 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-06-06 | 2026-06-10 | 2026-06-15 | 2026-06-30 |  |  | 2026-07-09 | 2026-07-09 | 2026-07-16 | 2026-07-20 | 2026-07-20 | 2026-07-23 | 2026-07-25 |  |  |  |  | 2026-07-28 | 2026-07-29 |  |  | 2026-07-31 | 2026-08-05 | 2026-08-10 | 2026-09-21 | 2026-09-23 | 170 | N2 | Abid | Chest |  | tofu-422 pcs 4 clr rub 1 clr gltr |  |  | NFL2 |  |  | Cut Ok | 102 | 102 | 0 | 450 | 30 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 39 | Jul'2 |  |  | 02.07.26
BS-ONL | 47652 | 15384864 | 786 | 122 | 2026-04-04 | 2026-04-28 | LS o nk TS w blind stitch | TS |  |  | 2026-06-06 | 2026-06-10 | 2026-06-15 | 2026-06-30 |  |  | 2026-07-10 | 2026-07-10 | 2026-07-16 | 2026-07-18 | 2026-07-18 | 2026-07-21 | 2026-07-23 |  |  |  |  | 2026-07-25 | 2026-07-27 |  |  | 2026-07-29 | 2026-07-31 | 2026-08-05 | 2026-09-21 | 2026-09-23 | 170 | O1 | Abid | Chest |  | c.dan-230 pcs 4 clr pig 1 clr gltr ,,dutch-242 pcs 3 clr rub ,,pink-314 pcs 5 clr rub 1 clr gltr |  |  | NFL2 |  |  | Cut Ok | 103 | 103 | 0 | 864 | 78 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 39 | Jul'2 |  |  | 20.06.26
BS-NMT | 47682 | 13262049 | 2098 | 465 | 2026-04-17 | 2026-05-08 | LS TS w front full placket btn and lace | TS |  |  | 2026-05-16 | 2026-05-22 | 2026-06-10 | 2026-06-23 |  |  | 2026-06-25 | 2026-06-25 | 2026-07-01 | 2026-07-03 | 2026-07-04 | [6 empty] | 2026-07-07 | 2026-07-10 |  |  | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-20 | 2026-07-22 | 94 | Y | Tomal |  |  |  |  | Lace | NFL3 |  |  | Cut Ok | 465 | 465 | 0 | 0 | -2098 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 30 | Jul'1 |  |  | 15.07.26
BS-NMT | 47564 | 13261430 | 900 | 92 | 2026-04-15 | 2026-05-08 | Slipper w fab ear | Slipper |  |  | 2026-05-20 | 2026-05-25 | 2026-06-15 | 2026-06-25 |  |  | 2026-07-01 | 2026-07-01 | 2026-07-07 | 2026-07-09 | 2026-07-10 | 2026-07-13 | 2026-07-14 |  |  |  |  | 2026-07-16 | 2026-07-18 |  |  | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-27 | 2026-07-29 | 103 | T2 | Mosaddik | leg |  | birch-900 pcs 3 clr rub print |  |  | NFL3 |  |  | Cut Ok | 92 | 92 | 0 | 0 | -900 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 31 | Jul'1 |  |  | 02.07.26
BS-NMT | 47563 | 13261571 | 1290 | 132 | 2026-04-15 | 2026-05-08 | Slipper w fab ear | Slipper |  |  | 2026-05-17 | 2026-05-22 | 2026-06-12 | 2026-06-24 |  |  | 2026-06-27 | 2026-06-27 | 2026-07-04 | 2026-07-07 | 2026-07-08 | 2026-07-10 | 2026-07-13 |  |  |  |  | 2026-07-16 | 2026-07-18 |  |  | 2026-07-20 | 2026-07-22 | 2026-07-23 | 2026-07-27 | 2026-07-29 | 103 | T2 | Mosaddik | leg |  | birch-1290 pcs 3 clr rub print |  |  | NFL3 |  |  | Cut Ok | 131 | 131 | 0 | 0 | -1290 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 31 | Jul'1 |  |  | 02.07.26
BS-NMT | 47565 | 13246585 | 1245 | 175 | 2026-04-15 | 2026-05-08 | YD Polo Shirt w front pkt placket btn and cuff btm collar rib | Polo | 2026-06-06 | 2026-06-11 | 2026-06-13 | 2026-06-19 | 2026-06-22 | 2026-06-27 |  |  | 2026-07-02 | 2026-07-02 | 2026-07-08 | 2026-07-10 | 2026-07-11 | [6 empty] | 2026-07-14 | 2026-07-17 |  |  | 2026-07-18 | 2026-07-20 | 2026-07-22 | 2026-07-27 | 2026-07-29 | 103 | X | Mosaddik |  |  |  | YD |  | NFL3 |  |  | Cut Ok | 175 | 175 | 0 | 0 | -1245 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46195 | 0 | 31 | Jul'1 |  |  | 06.06.26
BS-NMT | 47556 | 13258863 | 2394 | 363 | 2026-04-15 | 2026-05-08 | LS body w shoulder and btm snap btn | Body |  |  | 2026-05-15 | 2026-05-20 | 2026-06-06 | 2026-06-13 |  |  | 2026-06-12 | 2026-06-12 | 2026-06-18 | 2026-06-19 | 2026-06-22 | 2026-06-22 | 2026-06-24 |  |  | 2026-06-24 | 2026-06-29 | 2026-07-01 | 2026-07-03 |  |  | 2026-07-04 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 82 | Y | Mosaddik | Chest,Nk | Chest | red-1452 pcs,,Navy-942 pcs both combo 3 clr rub 1 clr terry emb |  |  | NFL3 |  |  | Cut Ok | 363 | 363 | 0 | 0 | -2394 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 28 | Jun'2 |  |  | 06.06.26
BS-NMT | 47574 | 13261609 | 5894 | 629 | 2026-04-15 | 2026-05-08 | LS ronper w collar placket btn and snap btn | Romper |  |  | 2026-05-15 | 2026-06-08 | 2026-06-10 | 2026-06-23 |  |  | 2026-06-25 | 2026-06-25 | 2026-07-01 | 2026-07-03 | 2026-07-06 | 2026-07-06 | 2026-07-09 |  |  |  |  | 2026-07-10 | 2026-07-16 |  |  | 2026-07-18 | 2026-07-20 | 2026-07-22 | 2026-07-27 | 2026-07-29 | 103 | X | Mosaddik | Nk |  | 2 combo label print |  |  | NFL3 |  |  | Cut Ok | 629 | 629 | 0 | 0 | -5894 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 31 | Jul'1 |  |  | 13.07.26
BS-NMT | 47570 | 13262051 | 1200 | 203 | 2026-04-15 | 2026-05-08 | AOP LS body w sanp btn | Body |  |  | 2026-05-15 | 2026-05-20 | 2026-06-10 | 2026-06-22 | 2026-06-24 | 2026-06-30 | 2026-07-03 | 2026-07-03 | 2026-07-09 | 2026-07-11 | 2026-07-11 | 2026-07-14 | 2026-07-15 |  |  |  |  | 2026-07-17 | 2026-07-18 |  |  | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-27 | 2026-07-29 | 103 | S | Mosaddik | Nk |  | 1 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 203 | 203 | 0 | 0 | -1200 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 31 | Jul'2 |  |  | 27.06.26
BS-NMT | 47577 | 13261558 | 3525 | 323 | 2026-04-15 | 2026-05-08 | LS body w bk nk key hole cuff frill and snap btn | Body |  |  | 2026-05-20 | 2026-06-08 | 2026-06-15 | 2026-06-25 |  |  | 2026-06-27 | 2026-06-27 | 2026-07-03 | 2026-07-06 | 2026-07-08 | 2026-07-08 | 2026-07-10 |  |  |  |  | 2026-07-13 | 2026-07-17 |  |  | 2026-07-18 | 2026-07-20 | 2026-07-22 | 2026-07-27 | 2026-07-29 | 103 | T2 | Mosaddik | Nk |  | 1 combo label print |  |  | NFL3 |  |  | Cut Ok | 323 | 323 | 0 | 0 | -3525 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 31 | Jul'1 |  |  | 20.06.26
BS-NMT | 47555 | 13258864 | 1848 | 54 | 2026-04-15 | 2026-05-08 | Bib w snap btn | Bib |  |  | 2026-05-12 | 2026-05-15 | 2026-05-20 | 2026-06-11 |  |  | 2026-06-13 | 2026-06-13 | 2026-06-18 | 2026-06-20 | 2026-06-22 | 2026-06-23 | 2026-06-24 |  |  |  |  | 2026-06-27 | 2026-06-29 |  |  | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-06 | 2026-07-08 | 82 | T1 | Mosaddik | Chest |  | red-924 pcs,,navy-924 pcs both combo 3 clr rub print |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1848 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46162 | 0 | 28 | Jun'2 |  |  | 06.06.26
BS-NMT | 47549 | 13258865 | 825 | 24 | 2026-04-15 | 2026-05-08 | Bib w snap btn | Bib |  |  | 2026-05-14 | 2026-05-16 | 2026-06-06 | 2026-06-11 |  |  | 2026-06-13 | 2026-06-13 | 2026-06-18 | 2026-06-20 | 2026-06-20 | 2026-06-23 | 2026-06-24 |  |  |  |  | 2026-06-26 | 2026-06-26 |  |  | 2026-06-27 | 2026-06-30 | 2026-07-02 | 2026-07-06 | 2026-07-08 | 82 | T1 | Mosaddik | Chest |  | red-825 pcs 1 clr rub print |  |  | NFL3 |  |  | Cut Ok | 24 | 24 | 0 | 0 | -825 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 28 | Jun'2 |  |  | 06.06.26
BS-NMT | 44024 10th | 13235553 | 2000 | 206 | 2026-04-29 | 2026-05-06 | LS body w cotty and bow + Pant | Top & BTM |  |  | 2026-05-06 | 2026-05-11 | 2026-05-13 | 2026-05-23 |  |  | 2026-05-20 | 2026-05-20 |  | 2026-05-25 | 2026-05-26 | 2026-06-05 | 2026-06-05 |  |  |  |  | 2026-06-08 | 2026-06-10 |  |  | 2026-06-12 | 2026-06-15 | 2026-06-18 | 2026-06-29 | 2026-07-01 | 61 | X+W1 | Jafar | Waist & Nk |  | 2 combo Waist nk logo print |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46155 | 0 | 27 | May'3 |  |  | 16.05.26
BS-NMT | 43320 17th | 13216876 | 1040 | 94 | 2026-05-06 | 2026-05-08 | LS collar body w snap btn | Body |  |  | 2026-05-15 | 2026-05-20 | 2026-06-10 | 2026-06-20 |  |  | 2026-06-18 | 2026-06-18 |  | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-26 |  |  |  |  | 2026-06-29 | 2026-06-30 |  |  | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-06 | 2026-07-08 | 61 | Y | Jafar | Nk |  | 1 combo label print |  |  | NFL3 |  |  | Cut Ok | 94 | 94 | 0 | 0 | -1040 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 28 | Jun'3 |  |  | 25.05.26
BS-NMT | 44026 14th | 13195885 | 16680 | 2942 | 2026-05-06 | 2026-05-08 | Weist belt legging | Legging |  |  | 2026-05-15 | 2026-05-22 | 2026-06-05 | 2026-06-15 |  |  | 2026-06-17 | 2026-06-17 |  | 2026-06-23 | 2026-06-26 | [6 empty] | 2026-06-26 | 2026-06-30 |  |  | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-06 | 2026-07-08 | 61 | W1 | Jafar | [5 empty] | NFL3 |  |  | Cut Ok | 2943 | 2943 | 0 | 0 | -16680 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46178 | 0 | 28 | Jun'3 |  |  | 25.05.26
BS-NMT | 47603 | 13261625 | 2655 | 378 | 2026-04-15 | 2026-05-08 | AOP LS o nk TS w shlder frill | TS |  |  | 2026-05-20 | 2026-05-25 | 2026-06-08 | 2026-06-20 | 2026-06-23 | 2026-06-28 | 2026-07-02 | 2026-07-02 | 2026-07-08 | 2026-07-10 | 2026-07-11 | 2026-07-13 | 2026-07-14 |  |  |  |  | 2026-07-16 | 2026-07-18 |  |  | 2026-07-20 | 2026-07-22 | 2026-07-25 | 2026-07-27 | 2026-07-29 | 103 | Z | Haider | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 378 | 378 | 0 | 0 | -2655 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 31 | Jul'1 |  |  | 27.06.26
BS-NMT | 47604 | 13262218 | 1614 | 317 | 2026-04-15 | 2026-05-08 | AOP LS Dress w shlder frill | Dress |  |  | 2026-05-20 | 2026-05-25 | 2026-06-08 | 2026-06-19 | 2026-06-22 | 2026-06-27 | 2026-06-29 | 2026-06-29 | 2026-07-04 | 2026-07-06 | 2026-07-07 | 2026-07-09 | 2026-07-10 |  |  |  |  | 2026-07-13 | 2026-07-16 |  |  | 2026-07-18 | 2026-07-21 | 2026-07-22 | 2026-07-27 | 2026-07-29 | 103 | T2 | Haider | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 318 | 308 | -10 | 0 | -1614 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 31 | Jul'1 |  |  | 23.05.26
BS-NMT | 47605 | 13261626 | 2817 | 345 | 2026-04-15 | 2026-05-08 | AOP elasted Legging | Legging |  |  | 2026-05-20 | 2026-05-25 | 2026-06-09 | 2026-06-18 | 2026-06-22 | 2026-06-27 | 2026-06-29 | 2026-06-29 | 2026-07-03 | 2026-07-06 | 2026-07-07 | 2026-07-09 | 2026-07-10 |  |  |  |  | 2026-07-13 | 2026-07-15 |  |  | 2026-07-17 | 2026-07-20 | 2026-07-23 | 2026-07-27 | 2026-07-29 | 103 | W1 | Haider | Waist |  | 2 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 345 | 345 | 0 | 2910 | 93 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46182 | 0 | 31 | Jul'1 |  |  | 27.06.26
BS-NMT | 47606 | 13261639 | 1210 | 288 | 2026-04-15 | 2026-05-08 | AOP LS Swt shirt | Swt Shirt |  |  | 2026-05-11 | 2026-05-18 | 2026-06-08 | 2026-06-20 | 2026-06-23 | 2026-06-29 | 2026-07-01 | 2026-07-01 | 2026-07-07 | 2026-07-10 | 2026-07-10 | [6 empty] | 2026-07-13 | 2026-07-14 |  |  | 2026-07-16 | 2026-07-18 | 2026-07-20 | 2026-07-27 | 2026-07-29 | 103 | W2 | Haider |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 289 | 289 | 0 | 0 | -1210 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 31 | Jul'1 |  |  | 10.07.26
BS-NMT | 47607 | 13261635 | 3535 | 784 | 2026-04-15 | 2026-05-08 | AOP Pant w waist frill | Pant |  |  | 2026-05-13 | 2026-05-20 | 2026-06-08 | 2026-06-20 | 2026-06-23 | 2026-06-29 | 2026-07-01 | 2026-07-01 | 2026-07-07 | 2026-07-09 | 2026-07-10 | [6 empty] | 2026-07-13 | 2026-07-16 |  |  | 2026-07-18 | 2026-07-20 | 2026-07-22 | 2026-07-26 | 2026-07-28 | 102 | U | Haider |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 784 | 784 | 0 | 0 | -3535 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 31 | Jul'1 |  |  | 27.06.26
BS-NMT | 47608 | 13261653 | 3155 | 329 | 2026-04-15 | 2026-05-08 | LS o nk TS w front bow attach | TS |  |  | 2026-05-15 | 2026-05-20 | 2026-06-10 | 2026-06-22 |  |  | 2026-06-24 | 2026-06-24 | 2026-06-29 | 2026-07-01 | 2026-07-03 | 2026-07-03 | 2026-07-04 |  |  |  |  | 2026-07-06 | 2026-07-09 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-16 | 2026-07-27 | 2026-07-29 | 103 | Z | Haider | Nk |  | 2 combo label print |  |  | NFL3 |  |  | Cut Ok | 329 | 329 | 0 | 0 | -3155 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 31 | Jul'1 |  |  | 23.05.26
BS-NMT | 47609 | 13261606 | 885 | 103 | 2026-04-15 | 2026-05-08 | LS O nk TS w letus stich at nk slve | TS |  |  | 2026-06-06 | 2026-06-10 | 2026-06-16 | 2026-06-27 |  |  | 2026-07-01 | 2026-07-01 | 2026-07-06 | 2026-07-08 | 2026-07-09 | 2026-07-11 | 2026-07-11 |  |  | 2026-07-11 | 2026-07-14 | 2026-07-16 | 2026-07-17 |  |  | 2026-07-20 | 2026-07-22 | 2026-07-24 | 2026-07-27 | 2026-07-29 | 103 | Z | Haider | Nk | Chest | grape-885 pcs 2 clr flat applique emb |  |  | NFL3 |  |  | Cut Ok | 103 | 103 | 0 | 0 | -885 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46189 | 0 | 31 | Jul'1 |  |  | 27.06.26
BS-ONS | 44076 16th | 22013782 | 3900 | 842 | 2026-05-02 | 2026-05-04 | SS T Shirt | TS |  |  | 2026-05-16 | 2026-05-22 | 2026-06-06 | 2026-06-18 |  |  | 2026-06-17 | 2026-06-17 |  | 2026-06-22 | 2026-06-23 | [6 empty] | 2026-06-25 | 2026-06-26 |  |  | 2026-07-02 | 2026-07-03 | 2026-07-07 | 2026-07-13 | 2026-07-15 | 72 | D2 | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 841 | 841 | 0 | 0 | -3900 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 29 | Jun'3 |  |  | 11.05.26
BS-ONL | 47698 | 15387396 | 2304 | 347 | 2026-04-26 | 2026-04-30 | SS o nk TS | TS | [8 empty] | 2026-06-15 | 2026-06-15 | 2026-06-19 | 2026-06-20 | 2026-06-22 | 2026-06-23 | 2026-06-24 |  |  |  |  | 2026-06-25 | 2026-06-27 |  |  | 2026-06-30 | 2026-07-02 | 2026-07-03 | 2026-07-13 | 2026-07-15 | 78 | N1 | Imran | Chest,Nk |  | white-1152 pcs,,white flower-1152 pcs both combo 2 clr pig print |  | licence order/stock fab from 41787 27th | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -2304 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 29 | Jun'1 |  |  | 23.06.26
BS-ONL | 47700 | 15388197 | 1272 | 569 | 2026-04-30 | 2026-05-06 | LS o nk Swt shirt w rib | Swt Shirt |  |  | 2026-05-13 | 2026-05-20 | 2026-06-06 | 2026-06-18 |  |  | 2026-06-16 | 2026-06-16 | 2026-06-22 | 2026-06-24 | 2026-06-25 | 2026-06-27 | 2026-06-30 |  |  |  |  | 2026-07-02 | 2026-07-04 |  |  | 2026-07-07 | 2026-07-08 | 2026-07-10 | 2026-07-13 | 2026-07-15 | 74 | N2 | Imran | Chest,Nk |  | birtch-636 pcs 9 clr rub ,,red-636 pcs 5 clr rub |  | licence order | NFL2 |  |  | Cut Ok | 568 | 568 | 0 | 0 | -1272 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 29 | Jun'3 |  |  | 23.06.26
BS-ONL | 47697 | 15387403 | 3276 | 1450 | 2026-04-30 | 2026-05-06 | LS o nk Swt shirt w rib | Swt Shirt |  |  | 2026-05-09 | 2026-05-18 | 2026-05-20 | 2026-06-13 |  |  | 2026-06-15 | 2026-06-15 | 2026-06-20 | 2026-06-23 | 2026-06-25 | 2026-06-25 | 2026-06-29 |  |  |  |  | 2026-07-01 | 2026-07-04 |  |  | 2026-07-06 | 2026-07-08 | 2026-07-10 | 2026-07-13 | 2026-07-15 | 74 | N2 | Imran | Chest,Nk |  | LGM-1638 pcs 6 clr rubv ,,brown-1638 pcs 3 clr rub |  | licence order | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -3276 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46162 | 0 | 29 | Jun'3 |  |  | 23.06.26
BS-ONL | 22041 60th | 15204712 | 3708 | 773 | 2026-05-05 | 2026-05-06 | LDS LS TS | TS |  |  | 2026-05-12 | 2026-05-18 | 2026-06-08 | 2026-06-18 |  |  | 2026-06-17 | 2026-06-17 |  | 2026-06-23 | 2026-06-24 | [6 empty] | 2026-06-26 | 2026-06-29 |  |  | 2026-06-30 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-06 | 60 | D2 | Imran | [5 empty] | NFL1 |  |  | Cut Ok | 774 | 774 | 0 | 0 | -3708 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 28 | Jun'3 |  |  | 06.06.26
BS-ONL | 22035 69th | 15095808 | 3672 | 812 | 2026-05-05 | 2026-05-06 | LDS TANK TOP | TANK TOP |  |  | 2026-05-12 | 2026-05-20 | 2026-06-08 | 2026-06-20 |  |  | 2026-06-20 | 2026-06-20 |  | 2026-06-26 | 2026-06-27 | [6 empty] | 2026-07-01 | 2026-07-03 |  |  | 2026-07-06 | 2026-07-08 | 2026-07-10 | 2026-07-13 | 2026-07-15 | 69 | ZA2 | Imran | [5 empty] | NFL3 |  |  | Cut Ok | 525 | 525 | 0 | 0 | -3672 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 29 | Jun'3 |  |  | 06.06.26
BS-ONL | 29402 42th | 15312874 | 3024 | 1712 | 2026-05-08 | 2026-05-08 | LS Swt hoodie w drawstring | Hoody |  |  | 2026-05-13 | 2026-05-23 | 2026-06-10 | 2026-06-23 |  |  | 2026-06-25 | 2026-06-25 |  | 2026-07-01 | 2026-07-02 |  |  |  |  | 2026-07-04 | 2026-07-06 | 2026-07-08 | 2026-07-09 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-27 | 2026-07-29 | 80 | E | Imran |  | Chest,Pkt | n. sky-3024 pcs chest and btm side 1 CLR FLAT EMB |  |  | NFL1 |  |  | Cut Ok | 1712 | 1712 | 0 | 0 | -3024 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 31 | Jul'1 |  |  | 06.06.26
BS-ONL | 47705 | 15393197 | 1296 | 483 | 2026-04-25 | 2026-05-02 | Elasted Pant | Pant |  |  | 2026-07-02 | 2026-07-08 | 2026-07-08 | 2026-07-13 |  |  | 2026-06-24 | 2026-06-24 | 2026-07-15 | 2026-07-16 | 2026-07-17 | [6 empty] | 2026-07-18 | 2026-07-20 |  |  | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-20 | 2026-07-22 | 86 | P | Abid | [5 empty] | NFL2 |  |  | Cut Ok | 530 | 530 | 0 | 0 | -1296 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46211 | 0 | 30 | Jul'1 |  |  | 09.07.26
BS-ONL | 47706 | 15382406 | 996 | 165 | 2026-04-20 | 2026-05-08 | LS YD O nk TS | TS | 2026-06-06 | 2026-06-10 | 2026-06-12 | 2026-06-17 | 2026-06-19 | 2026-06-23 |  |  | 2026-06-25 | 2026-06-25 | 2026-06-30 | 2026-07-02 | 2026-07-03 |  |  |  |  | 2026-07-06 | 2026-07-08 | 2026-07-10 | 2026-07-11 |  |  | 2026-07-13 | 2026-07-15 | 2026-07-16 | 2026-07-20 | 2026-07-22 | 91 | M | Abid |  | Chest | c.dan-350 pcs,,fiji-650 pcs both combo 2 clr flat emb | YD |  | NFL2 |  |  | Cut Ok | 166 | 166 | 0 | 0 | -996 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46192 | 0 | 30 | Jul'1 |  |  | 07.07.26
OVS SPA | 47494 | 262TRO378-6154 | 2448 | 1235 | 2026-04-29 | 2026-05-08 | Swt Joggers w side pkt drawstring | Pant |  |  | 2026-05-15 | 2026-05-25 | 2026-06-06 | 2026-06-20 |  |  | 2026-06-29 | 2026-06-24 | 2026-07-01 | 2026-07-02 | 2026-07-04 | 2026-07-06 | 2026-07-09 |  |  |  |  | 2026-07-09 | 2026-07-13 |  |  | 2026-07-14 | 2026-07-16 | 2026-07-18 | 2026-07-20 | 2026-07-20 | 82 | H | Khairul | leg |  | black-2448 pcs one leg 1 clr rub print |  |  | NFL1 |  |  | Cut Ok | 1235 | 1235 | 0 | 0 | -2448 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 30 | Jul'1 |  |  | 29.06.26
OVS SPA | 47448 | 262TRO376-6154 | 2448 | 995 | 2026-04-29 | 2026-05-08 | Swt pant w side piping and drawstring back yoke | Pant |  |  | 2026-05-15 | 2026-05-25 | 2026-06-06 | 2026-06-18 |  |  | 2026-07-01 | 2026-07-04 | 2026-07-08 | 2026-07-09 | 2026-07-10 | [6 empty] | 2026-07-11 | 2026-07-15 |  |  | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-20 | 82 | H | Khairul | [5 empty] | NFL1 |  |  | Cut Ok | 995 | 995 | 0 | 0 | -2448 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 30 | Jul'1 |  |  | 01.07.26
OVS SPA | 47496 | 262SWT380-6154 | 2448 | 1055 | 2026-04-29 | 2026-05-08 | LS SWt shirt w front yoke piping and cuff btm rib | Swt Shirt |  |  | 2026-06-06 | 2026-06-15 | 2026-06-15 | 2026-06-27 |  |  | 2026-06-30 | 2026-06-26 | 2026-07-03 | 2026-07-04 | 2026-07-06 | 2026-07-07 | 2026-07-11 |  |  |  |  | 2026-07-11 | 2026-07-15 |  |  | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-20 | 82 | N/2 | Khairul | Fr,Bk |  | black-2448 pcs frt back 1 clr rub print |  |  | NCL |  |  | Ready Test Cut | 1055 | 1055 | 0 | 0 | -2448 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 30 | Jul'1
OVS SPA | 47495 | 262TSH379-6154 | 2448 | 1085 | 2026-04-29 | 2026-05-08 | LS double slve TS w YD nk rib | TS | 2026-05-15 | 2026-05-25 | 2026-06-06 | 2026-06-15 | 2026-06-16 | 2026-06-25 |  |  | 2026-06-30 | 2026-06-26 | 2026-07-03 | 2026-07-04 | 2026-07-06 | 2026-07-07 | 2026-07-11 |  |  |  |  | 2026-07-11 | 2026-07-15 |  |  | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-20 | 82 | N/2 | Khairul | Chest |  | black-2448 pcs digital photo print w 2 clr rub |  |  | NCL |  |  | Ready Test Cut | 1085 | 1085 | 0 | 0 | -2448 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46189 | 0 | 30 | Jul'1
GBX-New Look | 47738 | RW915-2518 | 4120 | 1425 | 2026-05-10 | 2026-05-06 | Dress w inner shorts | Dress |  |  | 2026-05-13 | 2026-05-20 | 2026-06-06 | 2026-05-15 |  |  | 2026-06-13 | 2026-06-13 | 2026-06-18 | 2026-06-20 | 2026-06-23 | [6 empty] | 2026-06-24 | 2026-06-30 |  |  | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-04 | 2026-07-05 | 55 | N/2 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 1425 | 1425 | 0 | 0 | -4120 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 28 | Jun'2
GBX-New Look | 47403 2nd | 91533449 | 3805 | 476 | 2026-05-07 | 2026-05-08 | YD SL TS w full placket btn | TS | 2026-05-22 | 2026-06-05 | 2026-06-06 | 2026-06-15 | 2026-06-15 | 2026-06-20 |  |  | 2026-06-17 | 2026-06-17 |  | 2026-06-22 | 2026-06-24 | [6 empty] | 2026-06-24 | 2026-06-29 |  |  | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-04 | 2026-07-05 | 58 | N/3 | Shofi |  |  |  | YD |  | NCL |  |  | Ready Test Cut | 476 | 460 | -16 | 0 | -3805 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 28 | Jun'3
GBX-TM Lewin | 47717 | 68313/68163/68164/68165 | 2670 | 1848 | 2026-05-04 | 2026-05-07 | LS Polo Shirt w Placket btn | Polo |  |  | 2026-05-15 | 2026-06-13 | 2026-06-09 | 2026-06-23 |  |  | 2026-06-23 | 2026-06-23 | 2026-06-29 | 2026-07-01 | 2026-07-03 | [6 empty] | 2026-07-04 | 2026-07-09 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-20 | 2026-07-20 | 77 | N/3 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 1855 | 1855 | 0 | 0 | -2670 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46182 | 0 | 30 | Jul'1
GBX-TM Lewin | 47725 | 68666/68667/68668/68669 | 2310 | 1708 | 2026-05-05 | 2026-05-08 | LS Swt shirt | Swt Shirt |  |  | 2026-08-01 | 2026-08-04 | 2026-08-07 | 2026-08-13 |  |  | 2026-08-04 | 2026-08-04 | 2026-08-12 | 2026-08-14 | 2026-08-15 | [6 empty] | 2026-08-17 | 2026-08-20 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 112 | N/2 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 1710 | 1623 | -87 | 0 | -2310 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46241 | 0 | 35 | Aug'2
GBX-TM Lewin | 47720 | 68660/68661/68662 | 1275 | 865 | 2026-05-05 | 2026-05-08 | LS Polo Shirt w Placket btn | Polo |  |  | 2026-05-20 | 2026-06-08 | 2026-06-10 | 2026-06-24 |  |  | 2026-06-24 | 2026-06-24 | 2026-07-01 | 2026-07-03 | 2026-07-04 | [6 empty] | 2026-07-07 | 2026-07-10 |  |  | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 76 | N/3 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 864 | 864 | 0 | 0 | -1275 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 30 | Jul'1
GBX-TM Lewin | 47719 | 68659 | 430 | 304 | 2026-05-05 | 2026-05-08 | LS Polo Shirt w Placket btn | Polo |  |  | 2026-05-25 | 2026-06-10 | 2026-06-14 | 2026-06-24 |  |  | 2026-06-26 | 2026-06-26 | 2026-07-02 | 2026-07-04 | 2026-07-04 | [6 empty] | 2026-07-08 | 2026-07-09 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-20 | 2026-07-20 | 76 | N/3 | Shofi | [5 empty] | NFL2 |  |  | Cut Ok | 304 | 304 | 0 | 448 | 18 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46187 | 0 | 30 | Jul'1
GBX-TM Lewin | 47724 | 68161/68162/68181/68182 | 2530 | 1868 | 2026-05-05 | 2026-05-08 | LS Swt shirt | Swt Shirt |  |  | 2026-05-17 | 2026-06-08 | 2026-06-12 | 2026-06-27 |  |  | 2026-06-29 | 2026-06-29 | 2026-07-04 | 2026-07-07 | 2026-07-08 | [6 empty] | 2026-07-10 | 2026-07-14 |  |  | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-20 | 76 | N/2 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 1871 | 1871 | 0 | 0 | -2530 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 30 | Jul'1
GBX-TM Lewin | 47721 | 68663/68664/68665 | 1590 | 1282 | 2026-05-05 | 2026-05-08 | LS Polo Shirt w zipper | Polo |  |  | 2026-05-22 | 2026-06-10 | 2026-06-10 | 2026-06-25 |  |  | 2026-06-25 | 2026-06-25 | 2026-07-01 | 2026-07-03 | 2026-07-04 | [6 empty] | 2026-07-06 | 2026-07-10 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-20 | 2026-07-20 | 76 | N/2 | Shofi | [5 empty] | NFL2 |  |  | Cut Ok | 1282 | 1282 | 0 | 1652 | 62 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 30 | Jul'1
BS-NMT | 47683 | 13262445 | 600 | 126 | 2026-04-17 | 2026-05-08 | LS o nk TS | TS |  |  | 2026-05-08 | 2026-06-12 | 2026-06-16 | 2026-06-30 |  |  | 2026-07-06 | 2026-07-06 | 2026-07-13 | 2026-07-15 | 2026-07-15 |  |  | 2026-07-17 | 2026-07-18 |  |  | 2026-07-21 | 2026-07-22 |  |  | 2026-07-24 | 2026-07-28 | 2026-07-30 | 2026-08-17 | 2026-08-19 | 122 | Z | Tomal | Stone |  | white-600 pcs both slve All over stone attach |  |  | NFL3 |  |  | Cut Ok | 126 | 126 | 0 | 0 | -600 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46189 | 0 | 34 | Jul'2 |  |  | 25.07.26
BS-NMT | 47584 | 13262617 | 1910 | 152 | 2026-04-15 | 2026-04-30 | Elasted Legging | Legging |  |  | 2026-06-06 | 2026-06-10 | 2026-06-15 | 2026-06-27 |  |  | 2026-07-01 | 2026-07-01 | 2026-07-08 | 2026-07-10 | 2026-07-10 |  |  |  |  | 2026-07-13 | 2026-07-17 | 2026-07-20 | 2026-07-21 |  |  | 2026-07-23 | 2026-07-25 | 2026-07-28 | 2026-08-24 | 2026-08-26 | 131 | W1 | Mosaddik |  | Leg | peyote-1000 pcs,,mauve-910 pcs both combo 2 leg 1 clr terry emb |  |  | NFL3 |  |  | Cut Ok | 151 | 151 | 0 | 1981 | 71 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 35 | Jul'1 |  |  | 23.07.26
BS-NMT | 47583 | 13262616 | 2493 | 341 | 2026-04-15 | 2026-04-30 | LS SWt shirt w slder snap btn | Swt Shirt |  |  | 2026-05-16 | 2026-06-25 | 2026-06-10 | 2026-06-25 |  |  | 2026-06-29 | 2026-06-29 | 2026-07-06 | 2026-07-08 | 2026-07-09 | 2026-07-11 | 2026-07-13 |  |  | 2026-07-15 | 2026-07-24 | 2026-07-27 | 2026-07-30 |  |  | 2026-08-03 | 2026-08-05 | 2026-08-10 | 2026-08-24 | 2026-08-26 | 131 | T2 | Mosaddik | Chest | Front,Slv | maove-1335 pcs,,peyote-1158 pcs both combo 1 clr rub print at chest and front both slve 1 clr terry emb |  |  | NFL3 |  |  | Cut Ok | 341 | 341 | 0 | 2622 | 129 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 35 | Jul'1 |  |  | 14.07.26
BS-NMT | 47582 | 13265643 | 1200 | 105 | 2026-04-15 | 2026-04-30 | AOP Body w snap btn and legging | Top & BTM |  |  | 2026-05-13 | 2026-05-16 | 2026-06-10 | 2026-06-23 | 2026-06-25 | 2026-06-30 | 2026-07-06 | 2026-07-06 | 2026-07-11 | 2026-07-13 | 2026-07-14 | 2026-07-16 | 2026-07-17 |  |  |  |  | 2026-07-20 | 2026-07-27 |  |  | 2026-07-23 | 2026-07-27 | 2026-07-29 | 2026-08-24 | 2026-08-26 | 131 | Y+W1 | Mosaddik | Waist & Nk |  | 2 combo label print |  |  | NFL3 |  |  | Cut Ok | 105 | 105 | 0 | 1250 | 50 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 35 | Jul'2 |  |  | 16.07.26
BS-NMT | 47581 | 13262614 | 1608 | 55 | 2026-04-15 | 2026-04-30 | AOP bib w snap btn | Bib |  |  | 2026-06-06 | 2026-06-10 | 2026-06-13 | 2026-06-23 | 2026-07-01 | 2026-07-05 | 2026-07-10 | 2026-07-10 | 2026-07-17 | 2026-07-20 | 2026-07-20 | [6 empty] | 2026-07-23 | 2026-07-24 |  |  | 2026-07-27 | 2026-07-29 | 2026-08-05 | 2026-08-24 | 2026-08-26 | 131 | T1 | Mosaddik |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 56 | 56 | 0 | 1700 | 92 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46186 | 0 | 35 | Jul'2 |  |  | 23.07.26
BS-NMT | 47586 | 13250320 | 2191 | 214 | 2026-04-15 | 2026-04-30 | Swt pant w drawstring | Pant |  |  | 2026-06-10 | 2026-06-16 | 2026-07-01 | 2026-07-10 |  |  | 2026-07-14 | 2026-07-14 | 2026-07-20 | 2026-07-23 | 2026-07-24 | [6 empty] | 2026-07-27 | 2026-07-29 |  |  | 2026-07-30 | 2026-08-03 | 2026-08-06 | 2026-08-24 | 2026-08-26 | 131 | Z | Mosaddik | [5 empty] | NFL3 |  |  | Cut Ok | 215 | 215 | 0 | 2312 | 121 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 35 | Jul'3 |  |  | 14.07.26
BS-NMT | 47580 | 13262613 | 4505 | 488 | 2026-04-15 | 2026-05-08 | AOP Elasted Legging | Legging |  |  | 2026-05-22 | 2026-06-06 | 2026-06-10 | 2026-06-22 | 2026-06-24 | 2026-06-30 | 2026-07-03 | 2026-07-03 | 2026-07-10 | 2026-07-13 | 2026-07-14 | 2026-07-16 | 2026-07-17 |  |  |  |  | 2026-07-20 | 2026-07-23 |  |  | 2026-07-25 | 2026-07-28 | 2026-07-30 | 2026-08-24 | 2026-08-26 | 131 | W1 | Mosaddik | Waist |  | 2 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 488 | 488 | 0 | 4628 | 123 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 35 | Jul'2 |  |  | 16.07.26
BS-NMT | 47579 | 13262612 | 4834 | 524 | 2026-04-15 | 2026-05-08 | LS AOP Body w snap btn | Body |  |  | 2026-05-20 | 2026-05-25 | 2026-06-08 | 2026-06-20 | 2026-06-23 | 2026-06-30 | 2026-07-06 | 2026-07-06 | 2026-07-13 | 2026-07-15 | 2026-07-18 | 2026-07-20 | 2026-07-22 |  |  |  |  | 2026-07-24 | 2026-07-29 |  |  | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-24 | 2026-08-26 | 131 | Y | Mosaddik | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 524 | 524 | 0 | 4925 | 91 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 35 | Jul'2 |  |  | 16.07.26
BS-NMT | 47585 | 13262898 | 1335 | 151 | 2026-04-15 | 2026-05-08 | YD LS reglan Swt shirt w full zipper and YD rib and snap btn | Swt Shirt | 2026-06-07 | 2026-06-12 | 2026-06-15 | 2026-06-20 | 2026-06-26 | 2026-07-08 |  |  | 2026-07-14 | 2026-07-14 | 2026-07-20 | 2026-07-22 | 2026-07-23 |  |  |  |  | 2026-07-25 | 2026-07-29 | 2026-08-01 | 2026-08-04 |  |  | 2026-08-06 | 2026-08-08 | 2026-08-11 | 2026-08-24 | 2026-08-26 | 131 | S | Mosaddik |  | Chest | peyote -1335 pcs 4 clr terry emb |  |  | NFL3 |  |  | Cut Ok | 209 | 209 | 0 | 1381 | 46 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46199 | 0 | 35 | Jul'3 |  |  | 14.07.26
BS-NMT | 47684 | 13262778 | 1608 | 381 | 2026-04-17 | 2026-05-08 | LS o nk TS | TS |  |  | 2026-05-15 | 2026-05-22 | 2026-06-12 | 2026-06-27 |  |  | 2026-07-01 | 2026-07-01 | 2026-07-07 | 2026-07-09 | 2026-07-10 | 2026-07-13 | 2026-07-17 |  |  |  |  | 2026-07-20 | 2026-07-22 |  |  | 2026-07-24 | 2026-07-27 | 2026-07-30 | 2026-08-17 | 2026-08-19 | 122 | Z | Tomal | Fr & Bk & Nk |  | plum-804 pcs,,white-804 pcs both combo frt back 1 clr HD print |  |  | NFL3 |  |  | Cut Ok | 382 | 382 | 0 | 0 | -1608 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 34 | Jul'1 |  |  | 15.07.26
BS-NMT | 47685 | 13262862 | 4523 | 1119 | 2026-04-17 | 2026-05-08 | LS Swt shirt w rib | Swt Shirt |  |  | 2026-05-15 | 2026-05-22 | 2026-06-10 | 2026-06-22 |  |  | 2026-06-24 | 2026-06-24 | 2026-07-01 | 2026-07-03 | 2026-07-06 |  |  |  |  | 2026-07-06 | 2026-07-15 | 2026-07-18 | 2026-07-22 |  |  | 2026-07-24 | 2026-07-28 | 2026-07-30 | 2026-08-17 | 2026-08-19 | 122 | W2 | Tomal |  | Chest | island-2764 pcs,,Navy-1759 pcs both combo 5 clr terry emb |  |  | NFL3 |  |  | Cut Ok | 1119 | 1119 | 0 | 4707 | 184 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 34 | Jul'1 |  |  | 15.07.26
BS-NMT | 47686 | 13262865 | 3310 | 877 | 2026-04-17 | 2026-05-08 | Swt pant w side bk pkt and drawstring | Pant |  |  | 2026-06-13 | 2026-06-20 | 2026-06-27 | 2026-07-12 |  |  | 2026-07-17 | 2026-07-17 | 2026-07-24 | 2026-07-27 | 2026-07-29 | [6 empty] | 2026-08-01 | 2026-08-07 |  |  | 2026-08-09 | 2026-08-10 | 2026-08-12 | 2026-08-24 | 2026-08-26 | 129 | X+Y | Tomal | [5 empty] | NFL3 |  |  | Cut Ok | 877 | 877 | 0 | 3410 | 100 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46200 | 0 | 35 | Jul'3 |  |  | 15.07.26
BS-NMT | 47615 | 13262764 | 1000 | 183 | 2026-04-15 | 2026-05-08 | SS o nk TS w gmts dye acid wash | TS |  |  | 2026-06-08 | 2026-06-13 | 2026-06-18 | 2026-06-24 |  |  | 2026-07-02 | 2026-07-02 | 2026-07-11 | 2026-07-14 | 2026-07-15 | 2026-07-29 | 2026-07-31 |  |  |  |  | 2026-07-17 | 2026-07-18 | 2026-07-22 | 2026-07-27 | 2026-08-04 | 2026-08-07 | 2026-08-10 | 2026-08-15 | 2026-08-17 | 122 | T1 | Haider | Chest,Nk |  | black-1000 pcs 1 clr gltr print all over at chest |  | Gmts dye acid wash | NFL3 |  |  | Cut Ok | 185 | 185 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46191 | 0 | 34 | Jul'2 |  |  | 04.07.26
BS-NMT | 47616 | 13262761 | 1737 | 307 | 2026-04-15 | 2026-05-08 | LS o nk TS | TS |  |  | 2026-06-06 | 2026-06-11 | 2026-06-15 | 2026-06-30 |  |  | 2026-07-04 | 2026-07-04 | 2026-07-11 | 2026-07-15 | 2026-07-16 | 2026-07-18 | 2026-07-20 |  |  | 2026-07-18 | 2026-07-22 | 2026-07-24 | 2026-07-25 |  |  | 2026-07-28 | 2026-07-30 | 2026-08-08 | 2026-08-17 | 2026-08-19 | 124 | ZA1 | Haider | Nk | Chest | grey-930 pcs,,white-807 pcs both combo 3 clr seq emb |  |  | NFL3 |  |  | Cut Ok | 307 | 307 | 0 | 1806 | 69 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 34 | Jul'2 |  |  | 04.07.26
BS-NMT | 47617 | 13265471 | 2395 | 369 | 2026-04-15 | 2026-05-08 | AOP LS o nk TS | TS |  |  | 2026-05-20 | 2026-06-06 | 2026-06-10 | 2026-06-23 | 2026-06-27 | 2026-07-04 | 2026-07-09 | 2026-07-09 | 2026-07-15 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-22 |  |  |  |  | 2026-07-24 | 2026-07-27 |  |  | 2026-07-29 | 2026-07-31 | 2026-08-08 | 2026-08-24 | 2026-08-26 | 131 | ZA1 | Haider | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 369 | 369 | 0 | 2465 | 70 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 35 | Jul'2 |  |  | 04.07.26
BS-NMT | 47618 | 13262680 | 2634 | 601 | 2026-04-15 | 2026-05-08 | AOP LS O nk dress w shlder frill | Dress |  |  | 2026-05-20 | 2026-06-06 | 2026-06-12 | 2026-06-24 | 2026-06-27 | 2026-07-04 | 2026-07-07 | 2026-07-07 | 2026-07-13 | 2026-07-15 | 2026-07-16 | 2026-07-18 | 2026-07-20 |  |  |  |  | 2026-07-22 | 2026-07-25 |  |  | 2026-07-27 | 2026-07-29 | 2026-07-31 | 2026-08-24 | 2026-08-26 | 131 | V | Haider | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 602 | 602 | 0 | 2731 | 97 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 35 | Jul'2 |  |  | 04.07.26
BS-NMT | 47619 | 13262679 | 2851 | 309 | 2026-04-15 | 2026-05-08 | AOP Elasted legging | Legging |  |  | 2026-05-20 | 2026-06-06 | 2026-06-12 | 2026-06-24 | 2026-06-27 | 2026-07-04 | 2026-07-07 | 2026-07-07 | 2026-07-13 | 2026-07-15 | 2026-07-16 | 2026-07-18 | 2026-07-20 |  |  |  |  | 2026-07-22 | 2026-07-24 |  |  | 2026-07-27 | 2026-07-29 | 2026-07-31 | 2026-08-24 | 2026-08-26 | 131 | W1 | Haider | Waist |  | 2 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 318 | 308 | -10 | 2933 | 82 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 35 | Jul'2 |  |  | 04.07.26
BS-NMT | 47622 | 13263242 | 2193 | 333 | 2026-04-15 | 2026-05-08 | LS o nk Dress w btm mesh | Dress |  |  | 2026-06-05 | 2026-06-11 | 2026-06-15 | 2026-06-30 |  |  | 2026-07-08 | 2026-07-08 | 2026-07-15 | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-21 |  |  |  |  | 2026-07-24 | 2026-07-28 |  |  | 2026-07-30 | 2026-07-31 | 2026-08-06 | 2026-08-24 | 2026-08-26 | 131 | S+T1 | Haider | Nk |  | 2 combo label print |  |  | NFL3 |  |  | Cut Ok | 333 | 333 | 0 | 2280 | 87 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 35 | Jul'2 |  |  | 11.07.26
BS-NMT | 47623 | 13263243 | 2022 | 101 | 2026-04-15 | 2026-05-08 | Elasted skirt w mesh | Skirt |  |  | 2026-06-06 | 2026-06-13 | 2026-06-15 | 2026-06-30 |  |  | 2026-07-09 | 2026-07-09 | 2026-07-16 | 2026-07-18 | 2026-07-20 | 2026-07-21 | 2026-07-22 |  |  |  |  | 2026-07-24 | 2026-07-27 |  |  | 2026-07-29 | 2026-07-31 | 2026-08-07 | 2026-08-24 | 2026-08-26 | 131 | X | Haider | Waist |  | 2 combo label print |  |  | NFL3 |  |  | Cut Ok | 101 | 101 | 0 | 2164 | 142 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 35 | Jul'2 |  |  | 04.07.26
BS-ONL | 47707 | 15384287 | 1536 | 322 | 2026-04-26 | 2026-05-08 | LS o nk TS | TS |  |  | 2026-06-05 | 2026-06-10 | 2026-06-15 | 2026-06-30 |  |  | 2026-07-06 | 2026-07-06 | 2026-07-11 | 2026-07-13 | 2026-07-14 | 2026-07-16 | 2026-07-17 |  |  |  |  | 2026-07-20 | 2026-07-22 |  |  | 2026-07-24 | 2026-07-28 | 2026-07-31 | 2026-08-24 | 2026-08-26 | 120 | O1 | Abid | Fr,Bk |  | c.dan-590 pcs frt back 1 clr pig 2 clr puff ,,phanthom-950 pcs ftr 1 clr rub 1 clr puff back no print |  |  | NFL2 |  |  | Cut Ok | 323 | 323 | 0 | 0 | -1536 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 35 | Jul'2 |  |  | 24.06.26
BS-ONL | 47708 | 15384867 | 216 | 43 | 2026-04-26 | 2026-05-08 | LS o nk TS | TS |  |  | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-30 |  |  | 2026-07-09 | 2026-07-09 | 2026-07-15 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-24 |  |  |  |  | 2026-07-28 | 2026-07-28 |  |  | 2026-07-30 | 2026-08-04 | 2026-08-07 | 2026-08-21 | 2026-08-23 | 117 | O1 | Abid | Chest |  | pink-218 pcs 6 clr pi print |  |  | NFL2 |  |  | Cut Ok | 42 | 41 | -1 | 0 | -216 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46191 | 0 | 35 | Jul'2 |  |  | 25.07.26
OVS SPA | 47693 | 271PJA5006-6150 | 4440 | 970 | 2026-04-24 | 2026-04-30 | LS o nk TS and Aop Legging | Top & BTM |  |  | 2026-06-15 | 2026-06-25 | 2026-07-01 | 2026-07-13 | 2026-07-14 | 2026-07-21 | 2026-07-28 | 2026-07-24 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-04 |  |  |  |  | 2026-08-06 | 2026-08-11 |  |  | 2026-08-12 | 2026-08-14 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 115 | A+D1 | Hadia | Chest,Nk |  | blac top-2220 pcs 7 clr rub ,,blac btm-2220 pcs no print | AOP |  | NFL1 |  |  | Cut Ok | 970 | 970 | 0 | 0 | -4440 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 34 | Jul'3 |  |  | 23.07.26
OVS SPA | 47694 | 271TSH5107-6151 | 11403 | 1200 | 2026-04-24 | 2026-04-30 | SS o nk TS | TS |  |  | 2026-06-25 | 2026-07-08 | 2026-07-09 | 2026-07-20 |  |  | 2026-07-25 | 2026-07-25 | 2026-07-31 | 2026-08-01 | 2026-08-06 | 2026-08-05 | 2026-08-10 |  |  |  |  | 2026-08-05 | 2026-08-13 |  |  | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-17 | 2026-08-17 | 115 | G2 | Hadia | Heat Press/Heat Seal |  | 3 combo nk HP |  |  | NFL1 |  |  | Cut Ok | 1200 | 1200 | 0 | 0 | -11403 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46212 | 0 | 34 | Aug'1 |  |  | 25.07.26
OVS SPA | 47695 | 271TSH5111-6151 | 6816 | 1020 | 2026-04-24 | 2026-04-30 | SS o nk TS | TS |  |  | 2026-06-25 | 2026-07-08 | 2026-07-09 | 2026-07-20 |  |  | 2026-07-25 | 2026-07-29 | 2026-08-03 | 2026-08-04 | 2026-08-06 | 2026-08-03 | 2026-08-07 |  |  |  |  | 2026-08-06 | 2026-08-11 |  |  | 2026-08-12 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 2026-08-17 | 115 | G1 | Hadia | Heat Press/Heat Seal |  | 3 combo nk HP |  |  | NFL1 |  |  | Cut Ok | 1020 | 1020 | 0 | 0 | -6816 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46212 | 0 | 34 | Aug'1 |  |  | 23.07.26
OVS SPA | 47691 | 271PJA5004-6150 | 6456 | 1320 | 2026-04-24 | 2026-05-08 | LS o nk TS and Aop Legging | Top & BTM |  |  | 2026-06-06 | 2026-06-15 | 2026-06-16 | 2026-06-27 | 2026-07-01 | 2026-07-08 | 2026-07-24 | 2026-07-16 | 2026-07-22 | 2026-07-23 | 2026-07-25 | 2026-07-27 | 2026-08-03 |  |  |  |  | 2026-08-03 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-12 | 2026-08-14 | 2026-08-17 | 2026-08-17 | 115 | N/2 | Hadia | Chest,Nk |  | breeze top-3228 pcs 7 clr rub print ,,blance btm-3228 pcs no print | AOP |  | NCL |  |  | Ready Test Cut | 1320 | 1320 | 0 | 0 | -6456 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46189 | 0 | 34 | Jul'3
OVS SPA | 47689 | 271PJA5002-6150 | 11606 | 1655 | 2026-04-24 | 2026-05-08 | LS o nk TS and Aop Swt pant | Top & BTM |  |  | 2026-06-06 | 2026-06-15 | 2026-06-16 | 2026-06-27 | 2026-07-01 | 2026-07-11 | 2026-07-20 | 2026-07-14 | 2026-07-20 | 2026-07-21 | 2026-07-25 | 2026-07-27 | 2026-08-01 |  |  |  |  | 2026-08-01 | 2026-08-07 |  |  | 2026-08-08 | 2026-08-10 | 2026-08-12 | 2026-08-17 | 2026-08-17 | 115 | A+E | Hadia | Chest,Nk |  | blanc top-5803 pcs 7 clr rub print ,,blanc btm-5803 pcs no print | AOP |  | NFL1 |  |  | Cut Ok | 1655 | 1655 | 0 | 0 | -11606 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46189 | 0 | 34 | Jul'3 |  |  | 20.07.26
OVS SPA | 47690 | 271PJA5003-6150 | 7728 | 1110 | 2026-04-24 | 2026-05-08 | LS o nk TS and Aop Swt pant | Top & BTM |  |  | 2026-06-06 | 2026-06-15 | 2026-06-15 | 2026-06-27 | 2026-07-01 | 2026-07-08 | 2026-07-22 | 2026-07-15 | 2026-07-21 | 2026-07-22 | 2026-07-25 | 2026-07-25 | 2026-07-31 |  |  |  |  | 2026-08-03 | 2026-08-10 |  |  | 2026-08-11 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 2026-08-17 | 115 | A+E | Hadia | Chest,Nk |  | white top-3864 pcs 4 clr rub 1 clr puff ,,white btm-3864 pcs no print | AOP |  | NFL1 |  |  | Cut Ok | 1110 | 1110 | 0 | 0 | -7728 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 34 | Jul'3 |  |  | 23.07.26
OVS SPA | 47688 | 271PJA5001-6150 | 5110 | 740 | 2026-04-24 | 2026-05-08 | LS o nk TS and Aop Swt pant | Top & BTM |  |  | 2026-06-06 | 2026-06-15 | 2026-06-15 | 2026-06-27 | 2026-07-01 | 2026-07-11 | 2026-07-28 | 2026-07-25 | 2026-07-31 | 2026-08-01 | 2026-08-03 | 2026-08-04 | 2026-08-08 |  |  |  |  | 2026-08-08 | 2026-08-13 |  |  | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-17 | 2026-08-17 | 115 | N/2 | Hadia | Chest,Nk |  | breeze top-2555 pcs 7 clr rub print ,,blance btm-2555 pcs no print | AOP | same print as 47691 | NCL |  |  | Ready Test Cut | 740 | 740 | 0 | 0 | -5110 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 34 | Aug'1
OVS SPA | 47692 | 271PJA5005-6150 | 4144 | 910 | 2026-04-24 | 2026-05-08 | LS o nk TS w cuff rib and Aop Swt pant | Top & BTM |  |  | 2026-06-06 | 2026-06-15 | 2026-06-15 | 2026-06-27 | 2026-07-01 | 2026-07-11 | 2026-07-28 | 2026-07-25 | 2026-07-31 | 2026-08-01 | 2026-08-03 | 2026-08-04 | 2026-08-08 |  |  |  |  | 2026-08-08 | 2026-08-13 |  |  | 2026-08-14 | 2026-08-15 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 115 | N/2 | Hadia | Chest,Nk |  | pink top-2072 pcs 4 clr rub 1 clr puff,,pink btm-2072 pcs no print | AOP | same print as 47690 | NCL |  |  | Ready Test Cut | 890 | 890 | 0 | 0 | -4144 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 34 | Aug'1
OVS SPA | 47696 | 271VST5108-6151 | 63025 | 5385 | 2026-04-24 | 2026-05-08 | AOP and Solid Tank top | Tank Top |  |  | 2026-05-15 | 2026-06-10 | 2026-06-10 | 2026-06-25 | 2026-06-23 | 2026-07-10 | 2026-07-10 | 2026-07-01 | 2026-07-06 | 2026-07-07 | 2026-07-20 | 2026-07-14 | 2026-07-25 |  |  |  |  | 2026-07-20 | 2026-08-12 |  |  | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-17 | 2026-08-17 | 115 | D1+D2 | Hadia | Nk |  | 5 combo label print | AOP |  | NFL1 |  |  | Cut Ok | 5385 | 5385 | 0 | 0 | -63025 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 34 | Jul'1 |  |  | 20.07.26
BS-ONS | 45750 2nd | 22037659 | 4252 | 1341 | 2026-04-30 | 2026-05-07 | SS o nk TS w nk rib | TS |  |  | 2026-06-15 | 2026-06-25 | 2026-07-06 | 2026-07-20 |  |  | 2026-07-25 | 2026-07-25 | 2026-08-03 | 2026-08-06 | 2026-08-08 | 2026-08-10 | 2026-08-12 |  |  | 2026-08-10 | 2026-08-13 | 2026-08-17 | 2026-08-20 |  |  | 2026-08-22 | 2026-08-24 | 2026-08-31 | 2026-10-19 | 2026-10-21 | 172 | D1 | Shakel | Nk | Chest | white blue-1272 pcs 7 clr flat emb,,,white yellow-480 pcs 7 clr flat emb, ,,white green-1274 pcs 7 clr flat emb,,white red-1322 pcs 9 clr flat emb |  | License order | NFL1 |  |  | Cut Ok | 1344 | 1344 | 0 | 4534 | 282 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46209 | 0 | 43 | Aug'1 |  |  | 27.07.26
OVS SPA | 47699 | 271BLZFTT528-6172 | 2630 | 1622 | 2026-04-27 | 2026-05-08 | LS blazer w frob pkt and btn | Blazer |  |  | 2026-07-01 | 2026-07-11 | 2026-07-13 | 2026-07-24 |  |  | 2026-08-08 | 2026-08-07 | 2026-08-12 | 2026-08-13 | 2026-08-14 | [6 empty] | 2026-08-15 | 2026-08-21 |  |  | 2026-08-22 | 2026-08-24 | 2026-08-26 | 2026-09-07 | 2026-09-07 | 133 | N/3 | Shaker | [5 empty] | NCL |  |  | Ready Test Cut | 1622 | 1622 | 0 | 0 | -2630 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46216 | 0 | 37 | Aug'2
OVS SPA | 47506 | 271TROFTB114-6172 | 10800 | 3294 | 2026-04-27 | 2026-05-08 | Trouser w side pkt and drawstring | Trouser |  |  | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-09-28 |  |  | 2026-10-03 | 2026-10-05 | 2026-10-09 | 2026-10-10 | 2026-10-14 | [6 empty] | 2026-10-15 | 2026-10-26 |  |  | 2026-10-27 | 2026-10-28 | 2026-10-30 | 2026-11-09 | 2026-11-09 | 196 | H | Shaker | [5 empty] | NFL1 |  |  | File Due | 3522 | 1132 | -2390 | 0 | -10800 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46279 | 0 | 46 | Oct'1
BS-ONS | 30588 18th | 22031724 | 3000 | 1255 | 2026-05-08 | 2026-05-09 | SS o nk TS | TS |  |  | 2026-05-15 | 2026-05-25 | 2026-06-08 | 2026-06-13 |  |  | 2026-06-13 | 2026-06-13 |  | 2026-06-17 | 2026-06-18 | [6 empty] | 2026-06-20 | 2026-06-23 |  |  | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-29 | 2026-07-01 | 52 | D1 | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 1256 | 1256 | 0 | 0 | -3000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 27 | Jun'2 |  |  | 12.05.26
BS-NMT | 44019 15th | 13247093 | 1500 | 228 | 2026-05-13 | 2026-05-15 | Weist belt legging | Legging |  |  | 2026-06-05 | 2026-06-10 | 2026-06-12 | 2026-06-22 |  |  | 2026-06-22 | 2026-06-22 |  | 2026-06-26 | 2026-06-27 | 2026-06-27 | 2026-06-29 |  |  |  |  | 2026-06-29 | 2026-06-30 |  |  | 2026-07-01 | 2026-07-02 | 2026-07-04 | 2026-07-06 | 2026-07-08 | 54 | Z | Jafar | WAIST |  | 1 combo label print |  |  | NFL3 |  |  | Cut Ok | 228 | 228 | 0 | 0 | -1500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 28 | Jun'3 |  |  | 08.06.26
BS-NMT | 43316 24th | 13234729 | 4560 | 782 | 2026-05-13 | 2026-05-15 | LS o nk TS | TS |  |  | 2026-05-20 | 2026-05-26 | 2026-06-06 | 2026-06-19 |  |  | 2026-06-18 | 2026-06-18 |  | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 |  |  |  |  | 2026-06-27 | 2026-06-30 |  |  | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-06 | 2026-07-08 | 54 | ZA2 | Jafar | Nk |  | 4 combo label print |  |  | NFL3 |  |  | Cut Ok | 781 | 781 | 0 | 0 | -4560 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 28 | Jun'3 |  |  | 25.05.26
BS-ONS | 26828 66th | 22029226 | 1550 | 1039 | 2026-05-12 | 2026-05-15 | LS Swt shirt | Swt Shirt |  |  | 2026-05-18 | 2026-05-22 | 2026-06-06 | 2026-06-13 |  |  | 2026-06-13 | 2026-06-13 |  | 2026-06-17 | 2026-06-18 | [6 empty] | 2026-06-22 | 2026-06-25 |  |  | 2026-06-26 | 2026-06-27 | 2026-06-30 | 2026-07-06 | 2026-07-08 | 55 | T2 | Shakel |  |  |  |  | stock fab from 26827 43th & 44th | NFL3 |  |  | Cut Ok | 1053 | 1053 | 0 | 0 | -1550 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46179 | 0 | 28 | Jun'2 |  |  | 18.05.26
BS-ONL | 45380 15th | 15346761 | 1155 | 253 | 2026-05-12 | 2026-05-13 | SS o nk TS | TS |  |  | 2026-06-06 | 2026-06-10 | 2026-06-12 | 2026-06-25 |  |  | 2026-06-25 | 2026-06-25 |  | 2026-06-30 | 2026-06-30 | 2026-07-02 | 2026-07-04 |  |  |  |  | 2026-07-07 | 2026-07-08 |  |  | 2026-07-10 | 2026-07-13 | 2026-07-15 | 2026-07-18 | 2026-07-20 | 67 | N1 | Jannati | Chest |  | Phanthom-585 pcs 2 clr pig ,,c.dancer-570 pcs 1 clr high rub print |  |  | NFL2 |  |  | Cut Ok | 253 | 253 | 0 | 0 | -1155 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 30 | Jun'3 |  |  | 20.06.26
BS-ONL | 47761 | 15386899 | 2387 | 507 | 2026-05-12 | 2026-05-15 | AOP LS O nk TS w nk Lace | TS |  |  | 2026-05-20 | 2026-06-08 | 2026-06-08 | 2026-06-20 | 2026-06-20 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-07-01 | 2026-07-03 | 2026-07-04 | [6 empty] | 2026-07-06 | 2026-07-09 |  |  | 2026-07-10 | 2026-07-11 | 2026-07-13 | 2026-07-13 | 2026-07-15 | 62 | N1 | Jannati |  |  |  | AOP |  | NFL2 |  |  | Cut Ok | 507 | 484 | -23 | 0 | -2387 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 29 | Jul'1 |  |  | 20.06.26
BS-ONL | 47764 | 15368612 | 1560 | 476 | 2026-05-12 | 2026-05-15 | SS o nk TS | TS |  |  | 2026-05-20 | 2026-06-06 | 2026-06-08 | 2026-06-20 |  |  | 2026-06-19 | 2026-06-19 | 2026-06-24 | 2026-06-26 | 2026-06-27 | 2026-06-29 | 2026-07-02 | 2026-07-08 | 2026-07-10 | 2026-07-02 | 2026-07-03 | 2026-07-06 | 2026-07-07 |  |  | 2026-07-10 | 2026-07-11 | 2026-07-13 | 2026-07-13 | 2026-07-15 | 62 | O1 | Jannati | Chest | Chest | black-780 pcs 1 clr rub 1 clr glte print and 1 size pearl attach,,white-780 pcs 1 clr pig print and 1 clr seq emb |  | 1 combo pearl attach | NFL2 |  |  | Cut Ok | 476 | 466 | -10 | 0 | -1560 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 29 | Jun'3 |  |  | 22.06.26
BS-ONL | 47769 | 15387784 | 3488 | 1191 | 2026-05-12 | 2026-05-15 | AOP & solid Loose elasted legging w waist woven label | Legging |  |  | 2026-05-22 | 2026-06-10 | 2026-06-09 | 2026-06-20 | 2026-06-19 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-07-01 | 2026-07-02 | 2026-07-04 | [6 empty] | 2026-07-04 | 2026-07-08 |  |  | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-13 | 2026-07-15 | 62 | K | Jannati |  |  |  | AOP |  | NFL2 |  |  | Cut Ok | 1191 | 1191 | 0 | 0 | -3488 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46182 | 0 | 29 | Jul'1 |  |  | 02.07.26
BS-ONL | 45320 5th | 15303954 | 800 | 401 | 2026-05-13 | 2026-05-14 | Swt pant w side pkt drawstring | PANT |  |  | 2026-06-06 | 2026-06-10 | 2026-06-15 | 2026-06-27 |  |  | 2026-07-01 | 2026-07-01 |  | 2026-07-04 | 2026-07-04 |  |  |  |  | 2026-07-08 | 2026-07-08 | 2026-07-10 | 2026-07-11 |  |  | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-27 | 2026-07-29 | 75 | P | Khalid |  | Thigh | black-800 pcs 1 clr flat emb |  |  | NFL2 |  |  | Cut Ok | 401 | 401 | 0 | 0 | -800 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 31 | Jul'1 |  |  | 20.06.26
BS-ONL | 47753 | 15392578 | 504 | 240 | 2026-05-06 | 2026-05-11 | LS Swt shirt w nk btm rib and slve woven fabric | Swt Shirt |  |  | 2026-06-06 | 2026-06-10 | 2026-06-16 | 2026-06-27 |  |  | 2026-07-01 | 2026-07-01 | 2026-07-07 | 2026-07-09 | 2026-07-09 | [6 empty] | 2026-07-11 | 2026-07-13 |  |  | 2026-07-15 | 2026-07-15 | 2026-07-16 | 2026-07-20 | 2026-07-22 | 75 | K | Zahirul | [5 empty] | NFL2 |  |  | Cut Ok | 240 | 240 | 0 | 0 | -504 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46189 | 0 | 30 | Jul'1 |  |  | 05.06.26
BS-ONL | 47752 | 15388675 | 504 | 505 | 2026-05-06 | 2026-05-11 | LS oversizes Hoody w kangaro pkt and drawstring | Hoody |  |  | 2026-06-05 | 2026-06-10 | 2026-06-12 | 2026-06-24 |  |  | 2026-06-24 | 2026-06-24 | 2026-07-01 | 2026-07-03 | 2026-07-03 |  |  |  |  | 2026-07-06 | 2026-07-10 | 2026-07-13 | 2026-07-14 |  |  | 2026-07-15 | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-22 | 75 | R | Zahirul |  | Front,Slv | coffe -504 pcs frt both slve applique emb w twill fabric |  |  | NFL2 |  |  | Cut Ok | 505 | 505 | 0 | 0 | -504 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 30 | Jul'1 |  |  | 23.05.26
BS-ONL | 27204 52th | 15323159 | 13040 | 3130 | 2026-05-13 | 2026-05-14 | LS o nk TS | TS |  |  | 2026-06-05 | 2026-06-13 | 2026-06-15 | 2026-06-28 |  |  | 2026-06-27 | 2026-06-27 |  | 2026-07-04 | 2026-07-07 | [6 empty] | 2026-07-08 | 2026-07-13 |  |  | 2026-07-15 | 2026-07-17 | 2026-07-18 | 2026-07-27 | 2026-07-29 | 75 | D2 | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 3130 | 3130 | 0 | 0 | -13040 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 31 | Jul'1 |  |  | 16.06.26
BS-ONL | 29254 15th | 15247221 | 2040 | 389 | 2026-05-15 | 2026-05-16 | SS o nk TS | TS |  |  | 2026-06-05 | 2026-06-10 | 2026-06-15 | 2026-06-26 |  |  | 2026-06-26 | 2026-06-26 |  | 2026-07-03 | 2026-07-04 | [6 empty] | 2026-07-08 | 2026-07-11 |  |  | 2026-07-14 | 2026-07-16 | 2026-07-18 | 2026-07-27 | 2026-07-29 | 73 | M | Zahirul | [5 empty] | NFL2 |  |  | Cut Ok | 389 | 389 | 0 | 0 | -2040 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 31 | Jul'1 |  |  | 23.05.26
BS-ONL | 29251 13th | 15247223 | 2080 | 511 | 2026-05-15 | 2026-05-16 | MATERNITY CUT & SEW LEGGING | LEGGING |  |  | 2026-05-20 | 2026-05-25 | 2026-06-08 | 2026-06-15 |  |  | 2026-06-15 | 2026-06-15 |  | 2026-06-19 | 2026-06-20 | [6 empty] | 2026-06-22 | 2026-06-24 |  |  | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-29 | 2026-07-01 | 45 | H | Zahirul | [5 empty] | NFL1 |  |  | Cut Ok | 511 | 511 | 0 | 0 | -2080 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 27 | Jun'2 |  |  | 22.05.26
GBX-Anthony's | 47726 | SP-ASWT-001 | 660 | 533 | 2026-05-07 | 2026-05-09 | Swt shirt w zipper | Swt Shirt |  |  | 2026-06-06 | 2026-06-13 | 2026-06-15 | 2026-06-30 |  |  | 2026-07-01 | 2026-07-01 | 2026-07-06 | 2026-07-08 | 2026-07-09 | [6 empty] | 2026-07-11 | 2026-07-13 |  |  | 2026-07-15 | 2026-07-17 | 2026-07-22 | 2026-07-30 | 2026-07-30 | 84 | N/2 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 534 | 524 | -10 | 0 | -660 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 31 | Jul'1
GBX-Anthony's | 47722 | SPAJKT-038 | 275 | 230 | 2026-05-07 | 2026-05-09 | LS Jacket w full zipper | Jacket |  |  | 2026-06-08 | 2026-06-13 | 2026-06-17 | 2026-06-29 |  |  | 2026-07-01 | 2026-07-01 | 2026-07-07 | 2026-07-09 | 2026-07-09 | [6 empty] | 2026-07-13 | 2026-07-15 |  |  | 2026-07-17 | 2026-07-20 | 2026-07-22 | 2026-07-30 | 2026-07-30 | 84 | N/2 | Shofi | [5 empty] | NFL2 |  |  | Cut Ok | 230 | 230 | 0 | 287 | 12 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46190 | 0 | 31 | Jul'1
GBX-TM Lewin | 47740 | 68670/68671/68672/68673/68674 | 3990 | 1010 | 2026-05-07 | 2026-05-09 | SS crew nk TS | TS |  |  | 2026-05-20 | 2026-05-25 | 2026-06-10 | 2026-06-22 |  |  | 2026-06-20 | 2026-06-20 | 2026-06-25 | 2026-06-27 | 2026-06-29 | [6 empty] | 2026-07-01 | 2026-07-04 |  |  | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-20 | 2026-07-20 | 74 | N/1 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 1008 | 1008 | 0 | 0 | -3990 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 30 | Jun'3
UTG-AF | 43663 7th | BAD1634S | 13500 | 3210 | 2026-05-14 | 2026-05-16 | LS o nk TS | TS |  |  | 2026-06-06 | 2026-06-15 | 2026-06-15 | 2026-06-30 |  |  | 2026-07-02 | 2026-07-04 |  | 2026-07-07 | 2026-07-11 | [6 empty] | 2026-07-09 | 2026-07-18 |  |  | 2026-07-20 | 2026-07-21 | 2026-07-23 | 2026-07-25 | 2026-07-27 | 72 | G2 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 3210 | 3210 | 0 | 0 | -13500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 31 | Jul'1 |  |  | 29.06.26
UTG-AF | 43306 18th | BAD1369BV | 1500 | 265 | 2026-05-14 | 2026-05-16 | LDS V NK TS | TS |  |  | 2026-06-06 | 2026-06-13 | 2026-06-15 | 2026-06-27 |  |  | 2026-07-06 | 2026-07-08 |  | 2026-07-10 | 2026-07-11 | [6 empty] | 2026-07-13 | 2026-07-15 |  |  | 2026-07-16 | 2026-07-20 | 2026-07-22 | 2026-07-25 | 2026-07-27 | 72 | G2 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 265 | 265 | 0 | 0 | -1500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 31 | Jul'1 |  |  | 06.06.26
UTG-AF | 40665 7th | BAD1123T | 2500 | 586 | 2026-05-14 | 2026-05-16 | LDS LS WRAP TS W LACE | TS |  |  | 2026-06-06 | 2026-06-15 | 2026-06-15 | 2026-06-27 |  |  | 2026-07-07 | 2026-07-09 |  | 2026-07-11 | 2026-07-13 | [6 empty] | 2026-07-14 | 2026-07-18 |  |  | 2026-07-20 | 2026-07-22 | 2026-07-23 | 2026-07-25 | 2026-07-27 | 72 | N/1 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 586 | 586 | 0 | 0 | -2500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 31 | Jul'2
UTG-AF | 41947 26th | BAD1101AS/984CE/2554AQ | 15400 | 2709 | 2026-05-14 | 2026-05-16 | LDS O NK SS TS | TS |  |  | 2026-06-05 | 2026-06-15 | 2026-06-15 | 2026-06-30 |  |  | 2026-07-02 | 2026-07-04 |  | 2026-07-06 | 2026-07-11 | [6 empty] | 2026-07-09 | 2026-07-17 |  |  | 2026-07-18 | 2026-07-20 | 2026-07-22 | 2026-07-25 | 2026-07-27 | 72 | W1 | Rana | [5 empty] | NFL3 |  |  | Cut Ok | 2745 | 2675 | -70 | 0 | -15400 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 31 | Jul'1 |  |  | 06.06.26
UTG-AF | 45883 3rd | BAD2602J | 2000 | 280 | 2026-05-14 | 2026-05-16 | Scallop Nk Tank top | Tank Top |  |  | 2026-06-09 | 2026-06-13 | 2026-06-15 | 2026-06-27 |  |  | 2026-07-06 | 2026-07-08 |  | 2026-07-10 | 2026-07-11 | [6 empty] | 2026-07-13 | 2026-07-16 |  |  | 2026-07-17 | 2026-07-20 | 2026-07-22 | 2026-07-25 | 2026-07-27 | 72 | W1 | Rana | [5 empty] | NFL3 |  |  | Cut Ok | 280 | 280 | 0 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 31 | Jul'1 |  |  | 29.06.26
UTG-AF | 40668 7th | BAD1630R | 4000 | 780 | 2026-05-14 | 2026-05-16 | LS o nk TS | TS |  |  | 2026-06-06 | 2026-06-15 | 2026-06-16 | 2026-06-29 |  |  | 2026-07-04 | 2026-07-06 |  | 2026-07-08 | 2026-07-09 | [6 empty] | 2026-07-10 | 2026-07-14 |  |  | 2026-07-15 | 2026-07-17 | 2026-07-20 | 2026-07-25 | 2026-07-27 | 72 | D1 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 762 | 762 | 0 | 0 | -4000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46189 | 0 | 31 | Jul'1 |  |  | 29.06.26
UTG-AF | 46152 5th | BAD0985AJ | 9000 | 2070 | 2026-05-14 | 2026-05-16 | LDS O NK LS TS | TS |  |  | 2026-06-06 | 2026-06-15 | 2026-06-15 | 2026-06-29 |  |  | 2026-07-02 | 2026-07-04 |  | 2026-07-08 | 2026-07-11 | [6 empty] | 2026-07-10 | 2026-07-17 |  |  | 2026-07-18 | 2026-07-20 | 2026-07-22 | 2026-07-25 | 2026-07-27 | 72 | D1 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 1994 | 1994 | 0 | 9289 | 289 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 31 | Jul'1 |  |  | 06.06.26
UTG-AF | 40675 9th | BAD1546mamaX | 3000 | 732 | 2026-05-14 | 2026-05-16 | LDS BOAT NK LS TS | TS |  |  | 2026-06-06 | 2026-06-15 | 2026-06-16 | 2026-06-29 |  |  | 2026-07-06 | 2026-07-08 |  | 2026-07-11 | 2026-07-13 | [6 empty] | 2026-07-14 | 2026-07-16 |  |  | 2026-07-17 | 2026-07-20 | 2026-07-22 | 2026-07-25 | 2026-07-27 | 72 | ZA2 | Rana | [5 empty] | NFL3 |  |  | Cut Ok | 732 | 732 | 0 | 0 | -3000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46189 | 0 | 31 | Jul'2 |  |  | 06.06.26
UTG-AF | 44587 7th | BAD2548R | 18000 | 4018 | 2026-05-14 | 2026-05-16 | LDS LS V NK TS | TS |  |  | 2026-06-06 | 2026-06-16 | 2026-06-15 | 2026-07-02 |  |  | 2026-07-01 | 2026-07-02 |  | 2026-07-04 | 2026-07-10 | [6 empty] | 2026-07-08 | 2026-07-17 |  |  | 2026-07-18 | 2026-07-20 | 2026-07-23 | 2026-07-25 | 2026-07-27 | 72 | W2 | Rana | [5 empty] | NFL3 |  |  | Cut Ok | 4020 | 4020 | 0 | 0 | -18000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 31 | Jul'1 |  |  | 06.06.26
UTG-AF | 42965 15th | BAD2530mamaAC | 18000 | 7198 | 2026-05-14 | 2026-05-16 | Long Plazoo | Plazo |  |  | 2026-06-06 | 2026-06-20 | 2026-06-18 | 2026-07-03 |  |  | 2026-07-04 | 2026-07-06 |  | 2026-07-08 | 2026-07-14 | [6 empty] | 2026-07-11 | 2026-07-20 |  |  | 2026-07-21 | 2026-07-22 | 2026-07-24 | 2026-07-25 | 2026-07-27 | 72 | U | Rana | [5 empty] | NFL3 |  |  | Cut Ok | 7197 | 7197 | 0 | 0 | -18000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46191 | 0 | 31 | Jul'1 |  |  | 29.06.26
UTG-AF | 44613 5th | BAD2908mamaE | 6000 | 1475 | 2026-05-14 | 2026-05-16 | LDS O NK TS TS | TS |  |  | 2026-06-06 | 2026-06-15 | 2026-06-16 | 2026-06-29 |  |  | 2026-07-04 | 2026-07-06 |  | 2026-07-09 | 2026-07-11 | [6 empty] | 2026-07-13 | 2026-07-16 |  |  | 2026-07-17 | 2026-07-20 | 2026-07-22 | 2026-07-25 | 2026-07-27 | 72 | ZA2 | Rana | [5 empty] | NFL3 |  |  | Cut Ok | 1474 | 1474 | 0 | 0 | -6000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46189 | 0 | 31 | Jul'1 |  |  | 29.06.26
UTG-AF | 45092 7th | BAD1058mBQ/1468mamaAH | 13600 | 3356 | 2026-05-14 | 2026-05-16 | AOP Long legging | Legging |  |  | 2026-06-06 | 2026-06-20 | 2026-06-18 | 2026-07-03 |  |  | 2026-07-04 | 2026-07-06 |  | 2026-07-08 | 2026-07-11 | [6 empty] | 2026-07-10 | 2026-07-18 |  |  | 2026-07-20 | 2026-07-21 | 2026-07-23 | 2026-07-25 | 2026-07-27 | 72 | V1 | Rana | [5 empty] | NFL3 |  |  | Cut Ok | 3290 | 3265 | -25 | 0 | -13600 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46191 | 0 | 31 | Jul'1 |  |  | 06.06.26
UTG-AF | 46885 4th | BAD3195mamaC | 2000 | 660 | 2026-05-14 | 2026-05-16 | Long legging | Legging |  |  | 2026-06-06 | 2026-06-15 | 2026-06-16 | 2026-06-30 |  |  | 2026-07-10 | 2026-07-11 |  | 2026-07-14 | 2026-07-15 | [6 empty] | 2026-07-16 | 2026-07-18 |  |  | 2026-07-20 | 2026-07-21 | 2026-07-23 | 2026-07-25 | 2026-07-27 | 72 | V1 | Rana | [5 empty] | NFL3 |  |  | Cut Ok | 660 | 660 | 0 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46189 | 0 | 31 | Jul'2 |  |  | 06.06.26
UTG-AF | 40671 10th | BAD1298AI | 14000 | 3519 | 2026-05-14 | 2026-05-16 | YD LS boat nk TS | TS | 2026-06-06 | 2026-06-13 | 2026-06-13 | 2026-06-22 | 2026-06-22 | 2026-07-02 |  |  | 2026-07-02 | 2026-07-04 |  | 2026-07-07 | 2026-07-11 | [6 empty] | 2026-07-10 | 2026-07-20 |  |  | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-25 | 2026-07-27 | 72 | D2 | Rana |  |  |  | YD |  | NFL1 |  |  | Cut Ok | 3500 | 3500 | 0 | 0 | -14000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46195 | 0 | 31 | Jul'1 |  |  | 29.06.26
UTG-AF | 41712 13th | BAD2323mamaY | 9000 | 2315 | 2026-05-14 | 2026-05-16 | LDS LONG LEGGINGS | LEGGING |  |  | 2026-06-06 | 2026-06-15 | 2026-06-15 | 2026-06-29 |  |  | 2026-07-01 | 2026-07-03 |  | 2026-07-06 | 2026-07-11 | [6 empty] | 2026-07-08 | 2026-07-17 |  |  | 2026-07-18 | 2026-07-20 | 2026-07-22 | 2026-07-25 | 2026-07-27 | 72 | K1 | Rana | [5 empty] | NFL2 |  |  | Cut Ok | 2314 | 2314 | 0 | 0 | -9000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 31 | Jul'1 |  |  | 06.06.26
UTG-AF | 43305 2nd | BAD0954S | 2200 | 850 | 2026-05-14 | 2026-05-16 | LDS 3/4 SLV DRESS | Dress |  |  | 2026-06-06 | 2026-06-15 | 2026-06-16 | 2026-06-27 |  |  | 2026-07-06 | 2026-07-07 |  | 2026-07-10 | 2026-07-11 | [6 empty] | 2026-07-14 | 2026-07-17 |  |  | 2026-07-18 | 2026-07-20 | 2026-07-22 | 2026-07-25 | 2026-07-27 | 72 | N/3 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 850 | 850 | 0 | 0 | -2200 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46189 | 0 | 31 | Jul'1
UTG-AF | 30405 6th | BAD2498mamaH | 4000 | 1566 | 2026-05-14 | 2026-05-16 | HW Long plazo | Plazo |  |  | 2026-06-09 | 2026-06-16 | 2026-06-17 | 2026-06-29 |  |  | 2026-07-06 | 2026-07-07 |  | 2026-07-09 | 2026-07-10 | [6 empty] | 2026-07-13 | 2026-07-18 |  |  | 2026-07-20 | 2026-07-21 | 2026-07-23 | 2026-07-25 | 2026-07-27 | 72 | N/2 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 1581 | 1581 | 0 | 0 | -4000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46190 | 0 | 31 | Jul'1
UTG-AF | 41713 6th | BAD1395mamaQ | 2000 | 661 | 2026-05-14 | 2026-05-16 | LDS MAMA PLAZO | PLAZO |  |  | 2026-06-08 | 2026-06-17 | 2026-06-18 | 2026-06-29 |  |  | 2026-07-06 | 2026-07-07 |  | 2026-07-10 | 2026-07-11 | [6 empty] | 2026-07-13 | 2026-07-16 |  |  | 2026-07-17 | 2026-07-20 | 2026-07-22 | 2026-07-25 | 2026-07-27 | 72 | N/2 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 661 | 661 | 0 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46191 | 0 | 31 | Jul'1
UTG-(Even & Odd) | 41318 15th | BAD1571AD | 1500 | 380 | 2026-05-13 | 2026-05-16 | LDS CROPPED WRAP OVERLAP LS TS | TS |  |  | 2026-06-06 | 2026-06-12 | 2026-06-13 | 2026-06-24 |  |  | 2026-06-30 | 2026-07-01 |  | 2026-07-03 | 2026-07-04 | [6 empty] | 2026-07-06 | 2026-07-09 |  |  | 2026-07-10 | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-18 | 65 | N/1 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 380 | 380 | 0 | 0 | -1500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46186 | 0 | 29 | Jul'1
UTG-(Even & Odd) | 46615 6th | BAD1318Z | 2000 | 600 | 2026-05-13 | 2026-05-16 | AOP SKIRT W SIDE SLIT | Skirt |  |  | 2026-05-21 | 2026-06-12 | 2026-06-13 | 2026-06-23 | 2026-06-24 | 2026-07-02 | 2026-07-03 | 2026-07-04 |  | 2026-07-07 | 2026-07-08 | [6 empty] | 2026-07-09 | 2026-07-11 |  |  | 2026-07-13 | 2026-07-14 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 65 | D2 | Rony |  |  |  | AOP |  | NFL1 |  |  | Cut Ok | 600 | 600 | 0 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46186 | 0 | 29 | Jul'1 |  |  | 01.07.26
UTG-(Even & Odd) | 24297 11th | BAD1112T | 2500 | 586 | 2026-05-13 | 2026-05-16 | LDS LS TS | TS |  |  | 2026-06-05 | 2026-06-13 | 2026-06-15 | 2026-06-26 |  |  | 2026-07-01 | 2026-07-02 |  | 2026-07-04 | 2026-07-06 | [6 empty] | 2026-07-06 | 2026-07-10 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-18 | 65 | N/3 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 586 | 586 | 0 | 0 | -2500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 29 | Jul'1
UTG-(Even & Odd) | 22738 9th | BAD1131R | 1500 | 358 | 2026-05-13 | 2026-05-16 | LDS LS BODYSUIT | SUIT |  |  | 2026-06-05 | 2026-06-13 | 2026-06-15 | 2026-06-26 |  |  | 2026-07-01 | 2026-07-02 |  | 2026-07-04 | 2026-07-06 | [6 empty] | 2026-07-07 | 2026-07-10 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-18 | 65 | N/3 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 358 | 358 | 0 | 0 | -1500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 29 | Jul'1
UTG-(Even & Odd) | 24231 15th | BAD0967AB | 2500 | 365 | 2026-05-13 | 2026-05-16 | LDS LS TS W LACE | TS |  |  | 2026-06-05 | 2026-06-13 | 2026-06-15 | 2026-06-26 |  |  | 2026-07-01 | 2026-07-02 |  | 2026-07-04 | 2026-07-06 | [6 empty] | 2026-07-06 | 2026-07-10 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-18 | 65 | N/1 | Rony |  |  |  |  | Lace | NCL |  |  | Ready Test Cut | 365 | 365 | 0 | 0 | -2500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 29 | Jul'1
UTG-(Even & Odd) | 44047 10th | BAD0982AL | 11000 | 2630 | 2026-05-13 | 2026-05-16 | LDS LS BODYSUIT | SUIT |  |  | 2026-05-20 | 2026-06-10 | 2026-06-11 | 2026-06-23 |  |  | 2026-06-23 | 2026-06-24 |  | 2026-06-27 | 2026-07-02 | [6 empty] | 2026-07-01 | 2026-07-10 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-18 | 65 | N/1 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 2630 | 2630 | 0 | 0 | -11000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46184 | 0 | 29 | Jun'3
UTG-(Even & Odd) | 41645 8th | BAD2681G | 8000 | 1790 | 2026-05-13 | 2026-05-16 | Cropped LS TS w placket | TS |  |  | 2026-05-20 | 2026-06-10 | 2026-06-11 | 2026-06-23 |  |  | 2026-06-23 | 2026-06-24 |  | 2026-06-27 | 2026-07-02 | [6 empty] | 2026-07-01 | 2026-07-10 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-18 | 65 | C | Rony | [5 empty] | NFL1 |  |  | Cut Ok | 1790 | 1790 | 0 | 0 | -8000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46184 | 0 | 29 | Jun'3 |  |  | 29.06.26
UTG-(Even & Odd) | 30703 10th | BAD2640J | 2000 | 420 | 2026-05-13 | 2026-05-16 | LDS BODYSUIT W ZIPPER | SUIT |  |  | 2026-06-05 | 2026-06-13 | 2026-06-15 | 2026-06-26 |  |  | 2026-07-01 | 2026-07-02 |  | 2026-07-04 | 2026-07-06 | [6 empty] | 2026-07-07 | 2026-07-10 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-18 | 65 | N/3 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 420 | 420 | 0 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 29 | Jul'1
UTG-(Even & Odd) | 23325 14th | BAD0960BB | 10500 | 2505 | 2026-05-13 | 2026-05-16 | LDS LS HIGH NK TS | TS |  |  | 2026-05-22 | 2026-06-12 | 2026-06-13 | 2026-06-25 |  |  | 2026-06-27 | 2026-06-29 |  | 2026-07-01 | 2026-07-06 | [6 empty] | 2026-07-04 | 2026-07-11 |  |  | 2026-07-13 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 65 | G2 | Rony | [5 empty] | NFL1 |  |  | Cut Ok | 2505 | 2505 | 0 | 0 | -10500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46186 | 0 | 29 | Jul'1 |  |  | 29.06.26
UTG-(Even & Odd) | 24230 19th | BAD0966AC | 4000 | 870 | 2026-05-13 | 2026-05-16 | LDS LS TS W LETTUCE | TS |  |  | 2026-06-06 | 2026-06-15 | 2026-06-16 | 2026-06-25 |  |  | 2026-07-01 | 2026-07-02 |  | 2026-07-04 | 2026-07-06 | [6 empty] | 2026-07-07 | 2026-07-10 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-18 | 65 | G2 | Rony | [5 empty] | NFL1 |  |  | Cut Ok | 870 | 870 | 0 | 0 | -4000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46189 | 0 | 29 | Jul'1 |  |  | 06.06.26
UTG-(Even & Odd) | 45963 9th | BAD0962BO | 4500 | 1030 | 2026-05-13 | 2026-05-16 | LDS LS R NK TS | TS |  |  | 2026-06-06 | 2026-06-15 | 2026-06-16 | 2026-06-25 |  |  | 2026-07-01 | 2026-07-02 |  | 2026-07-04 | 2026-07-06 | [6 empty] | 2026-07-07 | 2026-07-10 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-18 | 65 | D1 | Rony | [5 empty] | NFL1 |  |  | Cut Ok | 1030 | 1030 | 0 | 0 | -4500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46189 | 0 | 29 | Jul'1 |  |  | 06.06.26
UTG-(Even & Odd) | 24240 15th | BAD0983V | 2000 | 356 | 2026-05-13 | 2026-05-16 | LDS OFF SHOULDER LS TS | TS |  |  | 2026-06-06 | 2026-06-13 | 2026-06-15 | 2026-06-27 |  |  | 2026-07-02 | 2026-07-03 |  | 2026-07-06 | 2026-07-07 | [6 empty] | 2026-07-08 | 2026-07-10 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-18 | 65 | D1 | Rony | [5 empty] | NFL1 |  |  | Cut Ok | 356 | 356 | 0 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 29 | Jul'1 |  |  | 06.06.26
UTG-(Even & Odd) | 16813 10th | BAD1319Q | 1000 | 330 | 2026-05-13 | 2026-05-16 | Long skirt w side slit | Skirt |  |  | 2026-06-06 | 2026-06-12 | 2026-06-13 | 2026-06-24 |  |  | 2026-06-30 | 2026-07-01 |  | 2026-07-03 | 2026-07-04 | [6 empty] | 2026-07-06 | 2026-07-08 |  |  | 2026-07-10 | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-18 | 65 | D2 | Rony | [5 empty] | NFL1 |  |  | Cut Ok | 330 | 317 | -13 | 0 | -1000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46186 | 0 | 29 | Jul'1 |  |  | 06.06.26
BS-ONL | 44608 2nd | 15364838 | 1236 | 215 | 2026-05-12 | 2026-05-13 | SS o nk TS | TS |  |  | 2026-06-05 | 2026-06-10 | 2026-06-16 | 2026-06-30 |  |  | 2026-07-09 | 2026-07-09 | 2026-07-15 | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-23 |  |  |  |  | 2026-07-27 | 2026-07-29 |  |  | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-10 | 2026-08-12 | 90 | O1 | Jannati | Chest |  | Lollipop-608 pcs frt 1 clr pig back no print ,,c.dan-628 pcs frt 2 clr pig back no print, |  |  | NFL2 |  |  | Cut Ok | 215 | 215 | 0 | 0 | -1236 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46189 | 0 | 33 | Jul'2 |  |  | 22.06.26
BS-ONL | 30011 20th | 15318144 | 14412 | 2188 | 2026-05-07 | 2026-05-09 | SS o nk TS | TS |  |  | 2026-05-20 | 2026-06-10 | 2026-06-12 | 2026-06-27 |  |  | 2026-06-30 | 2026-06-26 | 2026-07-04 | 2026-07-07 | 2026-07-11 | 2026-07-10 | 2026-07-17 |  |  | 2026-07-15 | 2026-07-22 | 2026-07-22 | 2026-07-31 |  |  | 2026-08-03 | 2026-08-06 | 2026-08-08 | 2026-08-10 | 2026-08-12 | 95 | L1 | Mainul | Chest | Chest | black animal-1536 pcs 1 clr pig 1 clr foil print no emb ,,black feather-1116 pcs photo print w 1 clr foil print no emb,,black leo brush-1116 pcs 7 clr rub 1 clr foil print no emb ,,black leo wild-1116 pcs 2 clr pig 1 clr foil print ,c.dan disco-600 pcs 1 clr pig print and 1 clr seq emb ,,c.dan love-816 pcs 1 clr pig 1 clr gltr and 1 clr seq emb ,,c.dan paris-816 pcs 2 clr pig 1 clr gltr and 1 clr seq emb ,,c.dan perfect-816 pcs 4 clr pig 1 clr gltr and 1 clr seq emb ,,c.dan scooter-816 pcs 2 clr pig 1 clr gltr and 1 clr seq emb ,,c.dan bycycle-816 pcs 2 clr pig 2 clr gltr print and 1 clr seq emb ,,c.dan feather-1116 pcs 6 clr pig 1 clr foil print and no emb ,,c.dan woman -936 pcs 6 clr pig 1 clr foil print and no emb ,,phantho attitute-864 pcs 2 clr rub 1 clr foil and no emb ,,pumic stone brush-816 pcs 6 clr pig 1 clr foil no emb ,,green brush-1116 pcs 6 clr pig 1 clr foil no emb |  |  | NFL2 |  |  | Cut Ok | 2188 | 2188 | 0 | 15088 | 676 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 33 | Jul'1 |  |  | 18.06.26
BS-ONL | 47760 | 15388847 | 516 | 115 | 2026-05-06 | 2026-05-11 | SS o nk TS | TS |  |  | 2026-06-08 | 2026-06-13 | 2026-06-20 | 2026-06-30 |  |  | 2026-07-06 | 2026-07-06 | 2026-07-11 | 2026-07-14 | 2026-07-14 | 2026-07-16 | 2026-07-18 |  |  |  |  | 2026-07-21 | 2026-07-22 |  |  | 2026-07-24 | 2026-07-27 | 2026-07-30 | 2026-08-17 | 2026-08-19 | 103 | N1 | Zahirul | Chest |  | black-516 pcs 3 clr rub 1 clr foil print |  |  | NFL2 |  |  | Cut Ok | 115 | 115 | 0 | 535 | 19 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46193 | 0 | 34 | Jul'2 |  |  | 30.06.26
BS-ONL | 47754 | 15388677 | 1326 | 885 | 2026-05-08 | 2026-05-13 | LS V wrap nk Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-06-10 | 2026-06-15 | 2026-06-22 | 2026-07-06 |  |  | 2026-07-10 | 2026-07-10 | 2026-07-16 | 2026-07-18 | 2026-07-20 | 2026-07-21 | 2026-07-23 |  |  |  |  | 2026-07-25 | 2026-07-28 |  |  | 2026-07-30 | 2026-08-03 | 2026-08-07 | 2026-08-17 | 2026-08-19 | 101 | R | Zahirul | Fr,Bk |  | coffe-1326 pcs frt back 1 clr rub print |  |  | NFL2 |  |  | Cut Ok | 885 | 885 | 0 | 0 | -1326 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46195 | 0 | 34 | Jul'2 |  |  | 17.07.26
BS-ONL | 47059 2nd | 15354114 | 1608 | 446 | 2026-05-08 | 2026-05-13 | SS o nk TS | TS |  |  | 2026-06-06 | 2026-06-10 | 2026-06-16 | 2026-06-30 |  |  | 2026-07-11 | 2026-07-11 |  | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-23 |  |  |  |  | 2026-07-25 | 2026-07-27 |  |  | 2026-07-29 | 2026-07-30 | 2026-07-30 | 2026-08-02 | 2026-08-04 | 86 | N1 | Zahirul | Chest |  | phanthom-732 pcs 2 clr rub ,,c.dan-876 pcs 1 clr high rub print |  |  | NFL2 |  |  | Cut Ok | 446 | 446 | 0 | 0 | -1608 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46189 | 0 | 32 | Jul'2 |  |  | 30.06.26
BS-ONL | 47755 | 15388679 | 1326 | 444 | 2026-05-08 | 2026-05-13 | SS o nk TS | TS |  |  | 2026-06-08 | 2026-06-15 | 2026-06-23 | 2026-07-10 |  |  | 2026-07-15 | 2026-07-15 | 2026-07-21 | 2026-07-23 | 2026-07-24 | [6 empty] | 2026-07-25 | 2026-07-27 |  |  | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-08-02 | 2026-08-04 | 86 | N1 | Zahirul | Fr,Bk |  | black-645 pcs frt 1 clr rub back no print ,,coffee-681 pcs frt back 1 clr rub |  |  | NFL2 |  |  | Cut Ok | 444 | 432 | -12 | 0 | -1326 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46196 | 0 | 32 | Jul'3 |  |  | 30.06.26
BS-ONL | 47757 | 15387146 | 580 | 320 | 2026-05-08 | 2026-05-14 | LS o nk TS w side slit waist drawstring | TS |  |  | 2026-06-10 | 2026-06-14 | 2026-06-20 | 2026-06-30 |  |  | 2026-07-11 | 2026-07-11 | 2026-07-20 | 2026-07-22 | 2026-07-22 | [6 empty] | 2026-07-24 | 2026-07-25 |  |  | 2026-07-28 | 2026-07-30 | 2026-08-07 | 2026-08-17 | 2026-08-19 | 101 | Q | Zahirul | [5 empty] | NFL2 |  |  | Cut Ok | 320 | 320 | 0 | 0 | -580 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46193 | 0 | 34 | Jul'3 |  |  | 17.07.26
BS-ONL | 46309 4th | 15188034 | 2000 | 520 | 2026-05-15 | 2026-05-16 | Legging w elatic waist belt | Legging |  |  | 2026-06-05 | 2026-06-09 | 2026-06-15 | 2026-06-26 |  |  | 2026-06-26 | 2026-06-26 |  | 2026-07-01 | 2026-07-02 | [6 empty] | 2026-07-04 | 2026-07-07 |  |  | 2026-07-09 | 2026-07-11 | 2026-07-15 | 2026-08-03 | 2026-08-05 | 80 | L2 | Zahirul | [5 empty] | NFL2 |  |  | Cut Ok | 520 | 520 | 0 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 32 | Jul'1 |  |  | 30.06.26
BS-ONL | 43102 5th | 15366301 | 2760 | 432 | 2026-05-09 | 2026-05-09 | SS o nk TS | TS |  |  | 2026-06-10 | 2026-06-16 | 2026-06-23 | 2026-07-08 |  |  | 2026-07-10 | 2026-07-10 |  | 2026-07-16 | 2026-07-17 | 2026-07-20 | 2026-07-22 |  |  |  |  | 2026-07-24 | 2026-07-28 |  |  | 2026-07-30 | 2026-07-31 | 2026-08-10 | 2026-09-07 | 2026-09-09 | 121 | K | Mainul | Chest |  | black-1380 pcs,,c.dan-1380 pcs both combo 1 clr gltr |  |  | NFL2 |  |  | Cut Ok | 432 | 432 | 0 | 2836 | 76 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46196 | 0 | 37 | Jul'2 |  |  | 18.06.26
BS-ONL | 47756 | 15387715 | 1302 | 277 | 2026-05-06 | 2026-05-11 | SS o nk TS | TS |  |  | 2026-06-08 | 2026-06-13 | 2026-06-17 | 2026-06-30 |  |  | 2026-07-11 | 2026-07-11 | 2026-07-18 | 2026-07-20 | 2026-07-20 | 2026-07-23 | 2026-07-27 |  |  |  |  | 2026-08-01 | 2026-08-03 |  |  | 2026-08-06 | 2026-08-08 | 2026-08-13 | 2026-08-30 | 2026-09-01 | 116 | N1 | Zahirul | Chest |  | blue-639 pcs,,N.sky-663 pcs both combo 1 clr puff print |  |  | NFL2 |  |  | Cut Ok | 277 | 277 | 0 | 0 | -1302 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46190 | 0 | 36 | Jul'2 |  |  | 18.07.26
BS-ONL | 47759 | 15388868 | 504 | 310 | 2026-05-08 | 2026-05-14 | LS Swt shirt w rib and slve contrast cut & sew | Swt Shirt |  |  | 2026-06-15 | 2026-06-19 | 2026-06-23 | 2026-07-08 |  |  | 2026-07-14 | 2026-07-14 | 2026-07-20 | 2026-07-22 | 2026-07-22 | 2026-07-25 | 2026-07-28 |  |  |  |  | 2026-08-01 | 2026-08-03 |  |  | 2026-08-06 | 2026-08-08 | 2026-08-12 | 2026-09-14 | 2026-09-16 | 129 | Q | Zahirul | Chest |  | LGM-501 pcs 2 clr rub print |  |  | NFL2 |  |  | Cut Ok | 310 | 310 | 0 | 537 | 33 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46196 | 0 | 38 | Jul'3 |  |  | 01.08.26
BS-ONL | 47758 | 15388436 | 1137 | 610 | 2026-05-06 | 2026-05-16 | LS boat nk Swt Shirt w rib | Swt Shirt |  |  | 2026-06-22 | 2026-06-26 | 2026-07-01 | 2026-07-12 |  |  | 2026-07-16 | 2026-07-27 | 2026-08-01 | 2026-08-06 | 2026-08-07 |  |  |  |  | 2026-08-07 | 2026-08-14 | 2026-08-17 | 2026-08-19 |  |  | 2026-08-21 | 2026-08-24 | 2026-08-26 | 2026-09-14 | 2026-09-16 | 131 | N2 | Zahirul |  | Front,Slv | n.sky-1137 pcs front one slve 1 clr Cording emb |  |  | NFL2 |  |  | Cut Ok | 610 | 610 | 0 | 1174 | 37 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 38 | Aug'1 |  |  | 20.08.26
OVS SPA | 47727 | 262POL025-6140 | 4428 | 889 | 2026-05-04 | 2026-05-09 | AOP LS Swt shirt collar placket cuff btm rib | Swt Shirt |  |  | 2026-07-01 | 2026-07-11 | 2026-07-13 | 2026-07-25 | 2026-07-27 | 2026-08-08 | 2026-08-20 | 2026-08-12 | 2026-08-19 | 2026-08-20 | 2026-08-22 |  |  |  |  | 2026-08-28 | 2026-08-31 | 2026-09-01 | 2026-09-07 |  |  | 2026-09-08 | 2026-09-10 | 2026-09-12 | 2026-09-14 | 2026-09-14 | 133 | A | Salam |  | Chest | Sugar swizzle-4428 pcs 1 clr terry emb | AOP |  | NFL1 |  |  | Cut Ok | 844 | 844 | 0 | 4518 | 90 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46216 | 0 | 38 | Aug'2 |  |  | 13.08.26
OVS SPA | 47728 | 262TSH026-6140 | 2275 | 233 | 2026-05-04 | 2026-05-09 | LS TS w bk nk key hole w snap btn and cuff gathering | TS |  |  | 2026-08-01 | 2026-08-10 | 2026-08-12 | 2026-08-25 |  |  | 2026-08-20 | 2026-08-08 | 2026-08-14 | 2026-08-15 | 2026-08-17 |  |  |  |  | 2026-08-24 | 2026-08-31 | 2026-09-01 | 2026-09-05 |  |  | 2026-09-07 | 2026-09-09 | 2026-09-11 | 2026-09-14 | 2026-09-14 | 133 | A | Salam |  | Chest | pink-2275 pcs 6 clr flat 1 clr chain stitch emb |  |  | NFL1 |  |  | Cut Ok | 233 | 233 | 0 | 2348 | 73 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46246 | 0 | 38 | Aug'2 |  |  | 13.08.26
BS-NMT | 43323 29th | 13180124 | 3120 | 373 | 2026-05-20 | 2026-05-22 | GIRLS SOLID LEGGINGS | Legging |  |  | 2026-06-05 | 2026-06-10 | 2026-06-12 | 2026-06-20 |  |  | 2026-06-18 | 2026-06-18 |  | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 |  |  |  |  | 2026-06-27 | 2026-06-29 |  |  | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-06 | 2026-07-08 | 133 | G1 | Jafar | WAIST |  | 3 combo label print |  |  | NFL1 |  |  | Cut Ok | 372 | 372 | 0 | 0 | -3120 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 28 | Jun'3 |  |  | 25.05.26
BS-NMT | 44842 9th | 13227981 | 1040 | 140 | 2026-05-20 | 2026-05-22 | GIRLS AOP LEGGING | LEGGING |  |  | 2026-06-05 | 2026-06-09 | 2026-06-15 | 2026-06-22 | 2026-06-25 | 2026-06-30 | 2026-06-27 | 2026-06-27 |  | 2026-07-02 | 2026-07-04 | 2026-07-06 | 2026-07-06 |  |  |  |  | 2026-07-08 | 2026-07-09 |  |  | 2026-07-11 | 2026-07-13 | 2026-07-15 | 2026-07-20 | 2026-07-22 | 133 | W1 | Jafar | WAIST |  | 1 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 140 | 140 | 0 | 0 | -1040 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 30 | Jul'1 |  |  | 25.05.26
BS-NMT | 43321 24th | 13205781 | 2040 | 248 | 2026-05-20 | 2026-05-22 | Legging | Legging |  |  | 2026-06-05 | 2026-06-09 | 2026-06-12 | 2026-06-20 |  |  | 2026-06-20 | 2026-06-20 |  | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 |  |  |  |  | 2026-06-29 | 2026-06-30 |  |  | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-06 | 2026-07-08 | 133 | W1 | Jafar | Waist |  | 1 combo label print |  |  | NFL3 |  |  | Cut Ok | 248 | 248 | 0 | 0 | -2040 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 28 | Jun'3 |  |  | 25.05.26
BS-ONL | 47784 | 15395035 | 2136 | 1032 | 2026-05-18 | 2026-05-19 | LS o nk TS w waist round yoke | TS |  |  | 2026-05-23 | 2026-06-08 | 2026-06-08 | 2026-06-18 |  |  | 2026-06-18 | 2026-06-18 | 2026-06-24 | 2026-06-26 | 2026-06-29 | [6 empty] | 2026-06-29 | 2026-07-03 |  |  | 2026-07-04 | 2026-07-04 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 49 | J | Zahirul | [5 empty] | NFL2 |  |  | Cut Ok | 1032 | 1032 | 0 | 0 | -2136 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 28 | Jun'3 |  |  | 05.06.26
BS-ONS | 46616 3rd | 22039183 | 6000 | 5632 | 2026-05-20 | 2026-05-23 | LS Swt Hoody | Hoody |  |  | 2026-06-05 | 2026-06-13 | 2026-06-13 | 2026-06-25 |  |  | 2026-06-20 | 2026-06-20 |  | 2026-06-25 | 2026-06-28 | 2026-06-27 | 2026-07-01 |  |  |  |  | 2026-07-01 | 2026-07-07 |  |  | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-13 | 2026-07-15 | 54 | C | Shakel | Fr,Bk |  | black-2008 pcs frt back 1 clr rub 1 clr puff print,,beluga-1008 pccs frt back 1 clr rub 1 clr puff print,,silver-3008 pcs frt back 1 clr rub 1 clr puff print |  |  | NFL1 |  |  | Cut Ok | 5631 | 5631 | 0 | 0 | -6000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46186 | 0 | 29 | Jun'3 |  |  | 18.06.26
BS-ONS | 26970 58th | 22002973 | 3920 | 863 | 2026-05-20 | 2026-05-23 | SS o nk TS | TS |  |  | 2026-06-06 | 2026-06-12 | 2026-06-17 | 2026-06-30 |  |  | 2026-07-02 | 2026-07-02 |  | 2026-07-07 | 2026-07-08 | [6 empty] | 2026-07-10 | 2026-07-13 |  |  | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-20 | 2026-07-22 | 61 | D1 | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 863 | 863 | 0 | 0 | -3920 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46190 | 0 | 30 | Jul'1 |  |  | 27.06.26
BS-ONS | 26827 53th | 22029225 | 1000 | 944 | 2026-05-21 | 2026-05-23 | LS Swt hoodie w kangaro pkt and drastring and cuff btm rib | HOODY |  |  | 2026-06-06 | 2026-06-10 | 2026-06-12 | 2026-06-22 |  |  | 2026-06-22 | 2026-06-22 |  | 2026-06-27 | 2026-06-29 | [6 empty] | 2026-07-01 | 2026-07-02 |  |  | 2026-07-03 | 2026-07-04 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 46 | R | Shakel | [5 empty] | NFL2 |  |  | Cut Ok | 945 | 945 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 28 | Jun'3 |  |  | 20.06.26
BS-ONS | 26827 54th | 22029225 | 10000 | 9233 | 2026-05-21 | 2026-05-23 | LS Swt hoodie w kangaro pkt and drastring and cuff btm rib | HOODY |  |  | 2026-06-08 | 2026-06-18 | 2026-06-15 | 2026-07-02 |  |  | 2026-07-01 | 2026-07-01 |  | 2026-07-06 | 2026-07-10 | [6 empty] | 2026-07-10 | 2026-07-17 |  |  | 2026-07-20 | 2026-07-21 | 2026-07-23 | 2026-07-27 | 2026-07-29 | 67 | R | Shakel | [5 empty] | NFL2 |  |  | Cut Ok | 9215 | 9215 | 0 | 0 | -10000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 31 | Jul'1 |  |  | 20.06.26
BS-ONS | 26828 69th | 22029226 | 3000 | 2076 | 2026-05-21 | 2026-05-23 | LS Swt shirt | Swt Shirt |  |  | 2026-06-06 | 2026-06-12 | 2026-06-15 | 2026-06-25 |  |  | 2026-06-22 | 2026-06-22 |  | 2026-06-27 | 2026-06-30 | [6 empty] | 2026-07-01 | 2026-07-03 |  |  | 2026-07-04 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 46 | E | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 2076 | 2076 | 0 | 0 | -3000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 28 | Jun'3 |  |  | 20.06.26
BS-ONS | 26828 70th | 22029226 | 9000 | 6049 | 2026-05-21 | 2026-05-23 | LS Swt shirt | Swt Shirt |  |  | 2026-06-06 | 2026-06-16 | 2026-06-15 | 2026-06-30 |  |  | 2026-06-24 | 2026-06-24 |  | 2026-06-29 | 2026-07-03 | [6 empty] | 2026-07-03 | 2026-07-08 |  |  | 2026-07-10 | 2026-07-13 | 2026-07-15 | 2026-07-20 | 2026-07-22 | 60 | E | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 6048 | 6048 | 0 | 0 | -9000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 30 | Jun'3 |  |  | 20.06.26
BS-ONS | 26828 71th | 22029226 | 10000 | 6701 | 2026-05-21 | 2026-05-23 | LS Swt shirt | Swt Shirt |  |  | 2026-06-08 | 2026-06-18 | 2026-06-15 | 2026-07-01 |  |  | 2026-06-26 | 2026-06-26 |  | 2026-07-02 | 2026-07-06 | [6 empty] | 2026-07-06 | 2026-07-11 |  |  | 2026-07-14 | 2026-07-15 | 2026-07-18 | 2026-07-27 | 2026-07-29 | 67 | E | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 6700 | 6700 | 0 | 0 | -10000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 31 | Jul'1 |  |  | 20.06.26
BS-ONS | 47819 | 22040527 | 2543 | 1313 | 2026-05-23 | 2026-05-25 | YD LS O nk TS | TS | 2026-06-05 | 2026-06-09 | 2026-06-10 | 2026-06-15 | 2026-06-13 | 2026-06-18 |  |  | 2026-06-15 | 2026-06-15 | 2026-06-19 | 2026-06-20 | 2026-06-22 | [6 empty] | 2026-06-23 | 2026-06-25 |  |  | 2026-06-26 | 2026-06-27 | 2026-06-29 | 2026-06-29 | 2026-07-01 | 37 | F | Shakel |  |  |  | YD |  | NFL1 |  |  | Cut Ok | 1313 | 1313 | 0 | 0 | -2543 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46186 | 0 | 27 | Jun'2 |  |  | 18.06.26
BS-ONS | 45964 10th | 22039968 | 2790 | 2024 | 2026-05-23 | 2026-05-25 | LS High nk Haalf Zipp Swt shirt | Swt Shirt |  |  | 2026-06-05 | 2026-06-10 | 2026-06-10 | 2026-06-19 |  |  | 2026-06-15 | 2026-06-15 |  | 2026-06-19 | 2026-06-20 | [6 empty] | 2026-06-22 | 2026-06-25 |  |  | 2026-06-26 | 2026-06-27 | 2026-06-29 | 2026-06-29 | 2026-07-01 | 37 | R | Shakel | [5 empty] | NFL2 |  |  | Cut Ok | 2022 | 2022 | 0 | 0 | -2790 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 27 | Jun'2 |  |  | 18.06.26
BS-ONS | 47818 | 22041282 | 7989 | 2700 | 2026-05-29 | 2026-06-05 | SS TS w nk and arm hole contrast piping | TS |  |  | 2026-06-08 | 2026-06-15 | 2026-06-13 | 2026-06-20 |  |  | 2026-06-15 | 2026-06-15 | 2026-06-18 | 2026-06-20 | 2026-06-22 | [6 empty] | 2026-06-22 | 2026-06-25 |  |  | 2026-06-26 | 2026-06-27 | 2026-06-29 | 2026-06-29 | 2026-07-01 | 31 | G1 | Shovon | [5 empty] | NFL1 |  |  | Cut Ok | 2699 | 2699 | 0 | 0 | -7989 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46186 | 0 | 27 | Jun'2 |  |  | 16.06.26
BS-ONL | 47763 1st | 15386479 | 5394 | 1516 | 2026-05-12 | 2026-05-18 | LS boat nk TS | TS |  |  | 2026-05-23 | 2026-06-11 | 2026-06-12 | 2026-06-25 |  |  | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-07-01 | 2026-07-03 | [6 empty] | 2026-07-02 | 2026-07-06 |  |  | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-06 | 53 | O2 | Jannati | [5 empty] | NFL2 |  |  | Cut Ok | 1516 | 1481 | -35 | 0 | -5394 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 28 | Jul'1 |  |  | 23.06.26
BS-ONL | 47773 | 15386687 | 535 | 185 | 2026-05-12 | 2026-05-18 | LS Swt shirt w woven slve | Swt Shirt |  |  | 2026-06-05 | 2026-06-09 | 2026-06-12 | 2026-06-22 |  |  | 2026-06-22 | 2026-06-22 | 2026-06-27 | 2026-06-29 | 2026-06-29 | [6 empty] | 2026-07-01 | 2026-07-02 |  |  | 2026-07-04 | 2026-07-08 | 2026-07-13 | 2026-07-13 | 2026-07-15 | 62 | Q | Jannati | [5 empty] | NFL2 |  |  | Cut Ok | 210 | 210 | 0 | 0 | -535 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 29 | Jun'3 |  |  | 26.06.26
BS-ONL | 47768 | 15386894 | 1724 | 442 | 2026-05-12 | 2026-05-25 | AOP LS Wrap cardigan w nk lace cuff btm letus and nk woven label bow | Cardigan |  |  | 2026-06-08 | 2026-06-15 | 2026-06-18 | 2026-06-24 | 2026-06-25 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 2026-07-07 | 2026-07-09 | 2026-07-10 | [6 empty] | 2026-07-13 | 2026-07-16 |  |  | 2026-07-18 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-22 | 69 | J | Jannati |  |  |  | AOP | Actual CCD 15/07 | NFL2 |  |  | Cut Ok | 431 | 431 | 0 | 0 | -1724 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46191 | 0 | 30 | Jul'1 |  |  | 20.06.26
BS-ONL | 47766 | 15386480 | 3966 | 1081 | 2026-05-12 | 2026-05-25 | LS v nk TS | TS |  |  | 2026-06-08 | 2026-06-15 | 2026-06-17 | 2026-06-29 |  |  | 2026-06-29 | 2026-06-29 | 2026-07-04 | 2026-07-07 | 2026-07-09 | [6 empty] | 2026-07-10 | 2026-07-14 |  |  | 2026-07-15 | 2026-07-16 | 2026-07-18 | 2026-07-20 | 2026-07-22 | 69 | O1 | Jannati |  |  |  |  | Actual CCD 15/07 | NFL2 |  |  | Cut Ok | 970 | 970 | 0 | 0 | -3966 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46190 | 0 | 30 | Jul'1 |  |  | 23.06.26
BS-ONL | 47765 | 15386477 | 6042 | 2091 | 2026-05-12 | 2026-05-25 | LS Inside Wrap nk TS | TS |  |  | 2026-06-06 | 2026-06-16 | 2026-06-15 | 2026-06-30 |  |  | 2026-06-27 | 2026-06-27 | 2026-07-04 | 2026-07-07 | 2026-07-10 | [6 empty] | 2026-07-10 | 2026-07-16 |  |  | 2026-07-17 | 2026-07-18 | 2026-07-18 | 2026-07-20 | 2026-07-22 | 69 | Q | Jannati |  |  |  |  | Actual CCD 15/07 | NFL2 |  |  | Cut Ok | 1511 | 1511 | 0 | 0 | -6042 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 30 | Jul'1 |  |  | 23.06.26
BS-ONL | 47770 | 15386714 | 3904 | 1852 | 2026-05-12 | 2026-05-21 | LS Contrast cu & sew Polo shirt w cuff rib collar placket btn | Polo |  |  | 2026-06-05 | 2026-06-12 | 2026-06-12 | 2026-06-24 |  |  | 2026-06-22 | 2026-06-22 | 2026-06-27 | 2026-06-29 | 2026-07-01 | [6 empty] | 2026-07-01 | 2026-07-07 |  |  | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-10 | 2026-07-12 | 59 | R+M | Jannati | [5 empty] | NFL2 |  |  | Cut Ok | 1852 | 1852 | 0 | 0 | -3904 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 29 | Jun'3 |  |  | 03.07.26
BS-ONL | 47786 | 15392970 | 1608 | 446 | 2026-05-11 | 2026-05-19 | LS boat nk TS | TS |  |  | 2026-06-05 | 2026-06-11 | 2026-06-12 | 2026-06-23 |  |  | 2026-06-24 | 2026-06-24 | 2026-06-29 | 2026-07-01 | 2026-07-02 | [6 empty] | 2026-07-04 | 2026-07-07 |  |  | 2026-07-09 | 2026-07-11 | 2026-07-13 | 2026-07-13 | 2026-07-15 | 63 | O2 | Mainul | [5 empty] | NFL2 |  |  | Cut Ok | 446 | 446 | 0 | 0 | -1608 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46185 | 0 | 29 | Jul'1 |  |  | 03.07.26
BS-ONL | 47787 | 15393027 | 1155 | 414 | 2026-05-11 | 2026-05-19 | LS o nk TS | TS |  |  | 2026-06-05 | 2026-06-12 | 2026-06-14 | 2026-06-24 |  |  | 2026-06-26 | 2026-06-26 | 2026-07-01 | 2026-07-02 | 2026-07-03 | [6 empty] | 2026-07-04 | 2026-07-06 |  |  | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-13 | 2026-07-15 | 63 | O1 | Mainul | [5 empty] | NFL2 |  |  | Cut Ok | 414 | 414 | 0 | 0 | -1155 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46187 | 0 | 29 | Jul'1 |  |  | 27.06.26
BS-ONL | 47785 | 15333192 | 1608 | 244 | 2026-05-11 | 2026-05-19 | SS o nk TS | TS |  |  | 2026-06-05 | 2026-06-08 | 2026-06-10 | 2026-06-20 |  |  | 2026-06-22 | 2026-06-22 | 2026-06-27 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-03 |  |  |  |  | 2026-07-06 | 2026-07-07 |  |  | 2026-07-08 | 2026-07-09 | 2026-07-11 | 2026-07-13 | 2026-07-15 | 63 | O1 | Mainul | Chest |  | c.dan beauty-804 pcs 8 clr pig 1 clr foil,,c.dan brush-804 pcs 9 clr pig 1 clr foil print |  |  | NFL2 |  |  | Cut Ok | 244 | 244 | 0 | 0 | -1608 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46183 | 0 | 29 | Jun'3 |  |  | 27.06.26
BS-ONL | 47488 | 15369134 | 1700 | 349 | 2026-05-22 | 2026-05-22 | LS v nk TS | TS |  |  | 2026-06-06 | 2026-06-10 | 2026-06-13 | 2026-06-24 |  |  | 2026-06-26 | 2026-06-26 | 2026-07-01 | 2026-07-03 | 2026-07-04 | [6 empty] | 2026-07-06 | 2026-07-08 |  |  | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 49 | O1 | Mainul | [5 empty] | NFL2 |  |  | Cut Ok | 349 | 349 | 0 | 0 | -1700 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46186 | 0 | 29 | Jul'1 |  |  | 18.06.26
BS-ONL | 21835 9th | 15254211 | 4500 | 522 | 2026-06-05 | 2026-06-05 | Strap Tank Top | Tank Top |  |  | 2026-06-10 | 2026-06-13 | 2026-06-22 | 2026-07-02 |  |  | 2026-07-01 | 2026-07-01 | 2026-07-06 | 2026-07-08 | 2026-07-09 | [6 empty] | 2026-07-11 | 2026-07-14 |  |  | 2026-07-16 | 2026-07-18 | 2026-07-22 | 2026-07-27 | 2026-07-29 | 52 | G1 | Mainul | [5 empty] | NFL1 |  |  | Cut Ok | 522 | 522 | 0 | 0 | -4500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46195 | 0 | 31 | Jul'1 |  |  | 08.07.26
BS-ONL | 30710 10th | 15209153 | 5040 | 743 | 2026-06-05 | 2026-06-05 | SS o nk TS | TS |  |  | 2026-06-10 | 2026-06-13 | 2026-06-20 | 2026-06-30 |  |  | 2026-06-27 | 2026-06-27 |  | 2026-07-02 | 2026-07-03 | [6 empty] | 2026-07-04 | 2026-07-07 |  |  | 2026-07-08 | 2026-07-09 | 2026-07-11 | 2026-07-13 | 2026-07-15 | 38 | G1 | Mainul | [5 empty] | NFL1 |  |  | Cut Ok | 743 | 743 | 0 | 0 | -5040 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46193 | 0 | 29 | Jul'1 |  |  | 11.06.26
BS-ONL | 30708 16th | 15201465 | 4680 | 773 | 2026-06-05 | 2026-06-05 | Long Tank Top | Tank top |  |  | 2026-06-11 | 2026-06-13 | 2026-06-20 | 2026-06-30 |  |  | 2026-06-27 | 2026-06-27 |  | 2026-07-03 | 2026-07-04 | [6 empty] | 2026-07-06 | 2026-07-08 |  |  | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-13 | 2026-07-15 | 38 | G1 | Mainul | [5 empty] | NFL1 |  |  | Cut Ok | 773 | 773 | 0 | 0 | -4680 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46193 | 0 | 29 | Jul'1 |  |  | 11.06.26
BS-ONL | 22034 53th | 15060061 | 13013 | 2127 | 2026-05-20 | 2026-05-22 | LDS TANK TOP | TANK TOP |  |  | 2026-07-03: 2026-06-22; 2026-07-04: 2026-06-18 |  | 2026-06-24 | 2026-06-27 | [6 empty] | 2026-07-01 | 2026-07-04 |  |  | 2026-07-06 | 2026-07-08 | 2026-07-10 | 2026-07-20 | 2026-07-22 | 61 | G1 | Imran |  |  |  |  | Stock fab from 43465 | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -13013 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 30 | Jun'3 |  |  | 06.06.26
BS-ONL | 22034 54th | 15060061 | 17006 | 2780 | 2026-05-20 | 2026-05-22 | LDS TANK TOP | TANK TOP |  |  | 2026-07-03: 2026-06-18; 2026-07-04: 2026-06-14 |  | 2026-06-18 | 2026-06-24 | [6 empty] | 2026-06-24 | 2026-06-30 |  |  | 2026-07-03 | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-15 | 54 | G1 | Imran |  |  |  |  | Stock fab from 43465/VMI | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -17006 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 29 | Jun'2 |  |  | 06.06.26
BS-ONL | 22040 26th | 152191323 | 6000 | 823 | 2026-05-17 | 2026-05-22 | LDS 2 PACK LEGGING | LEGGING |  |  | 2026-07-03: 2026-06-22; 2026-07-04: 2026-06-20 |  | 2026-06-25 | 2026-06-27 | [6 empty] | 2026-07-01 | 2026-07-04 |  |  | 2026-07-06 | 2026-07-08 | 2026-07-10 | 2026-07-27 | 2026-07-29 | 71 | L2 | Imran |  |  |  |  | Stock fab from 43465/4520 pcs need sewing | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -6000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 31 | Jun'3 |  |  | 06.06.26
BS-ONL | 22035 70th | 15095808 | 10074 | 1438 | 2026-05-19 | 2026-05-22 | LDS TANK TOP | TANK TOP |  |  | 2026-07-03: 2026-06-18; 2026-07-04: 2026-06-16 |  | 2026-06-22 | 2026-06-26 | [6 empty] | 2026-07-01 | 2026-07-04 |  |  | 2026-07-06 | 2026-07-07 | 2026-07-09 | 2026-07-13 | 2026-07-15 | 55 | ZA2 | Imran |  |  |  |  | Stock fab from 43465/VMI | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -10074 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 29 | Jun'3 |  |  | 06.06.26
BS-ONL | 47777 | 15395268 | 1410 | 321 | 2026-05-13 | 2026-05-21 | SS o nk TS | TS |  |  | 2026-06-08 | 2026-06-13 | 2026-06-16 | 2026-06-29 |  |  | 2026-06-29 | 2026-06-29 | 2026-07-04 | 2026-07-06 | 2026-07-06 |  |  | 2026-07-08 | 2026-07-16 |  |  | 2026-07-18 | 2026-07-21 |  |  | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-27 | 2026-07-29 | 75 | Q | Dalim | Stone |  | black-1410 pcs All body all over stone HP |  |  | NFL2 |  |  | Cut Ok | 321 | 321 | 0 | 0 | -1410 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46189 | 0 | 31 | Jul'1 |  |  | 29.06.26
GBX-New Look | 47403 3rd | 91533449 | 1520 | 196 | 2026-05-15 | 2026-05-19 | YD SL TS w full placket btn | TS | 2026-05-25 | 2026-06-09 | 2026-06-11 | 2026-06-16 | 2026-06-18 | 2026-06-23 |  |  | 2026-06-20 | 2026-06-20 |  | 2026-06-25 | 2026-06-26 | [6 empty] | 2026-06-27 | 2026-06-29 |  |  | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-04 | 2026-07-05 | 50 | N/3 | Shofi |  |  |  | YD |  | NCL |  |  | Ready Test Cut | 196 | 196 | 0 | 0 | -1520 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46191 | 0 | 28 | Jun'3
GBX-New Look | 47424 2nd | 91533583 | 5315 | 1740 | 2026-05-15 | 2026-05-19 | YD legging w drawstring | Legging | 2026-05-23 | 2026-06-09 | 2026-06-08 | 2026-06-19 | 2026-06-17 | 2026-06-22 |  |  | 2026-06-18 | 2026-06-18 |  | 2026-06-22 | 2026-06-25 | [6 empty] | 2026-06-25 | 2026-06-30 |  |  | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 50 | N/1 | Shofi |  |  |  | YD |  | NCL |  |  | Ready Test Cut | 1740 | 1740 | 0 | 0 | -5315 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46190 | 0 | 28 | Jun'3
GBX-Maurices | 47817 | 2195441/4255441 | 32136 | 16701 | 2026-05-23 | 2026-05-25 | LS Swt shirt w gmts dye acid wash | Swt Shirt |  |  | 2026-06-05 | 2026-06-12 | 2026-06-08 | 2026-06-22 | 2026-06-22 |  | 2026-06-11 | 2026-06-11 | 2026-06-17 | 2026-06-20 | 2026-06-27 |  |  | 2026-07-02 | 2026-07-13 |  |  | 2026-06-25 | 2026-06-08 | 2026-06-29 | 2026-07-10 | 2026-07-14 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 53 | N/1 | Mannan | Stone |  | black core-22785 pcs,,plus-9351 pcs all over stone at chest |  | stone at At Asia Linkage | NCL |  |  | Ready Test Cut | 17485 | 17485 | 0 | 0 | -32136 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46181 | 0 | 29 | Jun'2
GBX-TM Lewin | 47783 | 68684 | 420 | 320 | 2026-05-18 | 2026-05-19 | LS Cut & Sew Polo Shirt | Polo |  |  | 2026-06-09 | 2026-06-15 | 2026-06-18 | 2026-06-30 |  |  | 2026-07-02 | 2026-07-02 | 2026-07-08 | 2026-07-10 | 2026-07-11 | [6 empty] | 2026-07-14 | 2026-07-16 |  |  | 2026-07-17 | 2026-07-20 | 2026-07-22 | 2026-07-30 | 2026-07-30 | 73 | N/2 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 319 | 316 | -3 | 0 | -420 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46191 | 0 | 31 | Jul'1
GBX-TM Lewin | 47718 | 68681/68682 | 850 | 739 | 2026-05-20 | 2026-05-22 | LS polo Shirt w YD collar and placket button | Polo | 2026-06-18 | 2026-07-01 | 2026-06-25 | 2026-07-07 | 2026-07-01 | 2026-07-04 |  |  | 2026-07-06 | 2026-07-06 | 2026-07-13 | 2026-07-15 | 2026-07-15 | [6 empty] | 2026-07-17 | 2026-07-18 |  |  | 2026-07-20 | 2026-07-22 | 2026-07-23 | 2026-07-30 | 2026-07-30 | 71 | N/3 | Shofi |  |  |  | YD |  | NCL |  |  | Ready Test Cut | 738 | 738 | 0 | 0 | -850 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 31 | Jul'1
GBX-TM Lewin | 47782 | 68683 | 425 | 315 | 2026-05-22 | 2026-05-23 | LS cut & sew polo Shirt w YD collar and placket button | Polo | 2026-06-18 | 2026-06-24 | 2026-06-26 | 2026-06-30 | 2026-07-02 | 2026-07-06 |  |  | 2026-07-07 | 2026-07-07 | 2026-07-13 | 2026-07-15 | 2026-07-16 | [6 empty] | 2026-07-17 | 2026-07-18 |  |  | 2026-07-21 | 2026-07-23 | 2026-07-25 | 2026-07-30 | 2026-07-30 | 69 | N/3 | Shofi |  |  |  | YD |  | NCL |  |  | Ready Test Cut | 314 | 314 | 0 | 0 | -425 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46205 | 0 | 31 | Jul'2
UTG-(Even & Odd) | 44262 6th | BAD2927E | 2000 | 360 | 2026-05-23 | 2026-05-23 | LDS TS W LACE | TS |  |  | 2026-06-06 | 2026-06-15 | 2026-06-15 | 2026-06-27 |  |  | 2026-06-26 | 2026-06-30 |  | 2026-07-01 | 2026-07-02 | [6 empty] | 2026-07-03 | 2026-07-06 |  |  | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-11 | 2026-07-13 | 49 | N/2 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 360 | 360 | 0 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 29 | Jul'1
UTG-(Even & Odd) | 46305 2nd | BAD3139A | 701 | 98 | 2026-05-23 | 2026-05-23 | SS TS w back cutout lace and strap and side gathering | TS |  |  | 2026-06-06 | 2026-06-13 | 2026-06-15 | 2026-06-26 |  |  | 2026-06-26 | 2026-06-30 |  | 2026-07-01 | 2026-07-02 | [6 empty] | 2026-07-03 | 2026-07-06 |  |  | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-11 | 2026-07-13 | 49 | N/2 | Rony |  |  |  |  | Lace | NCL |  |  | Ready Test Cut | 98 | 98 | 0 | 0 | -701 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 29 | Jul'1
BS-ONS | 45964 8th | 22039968 | 2205 | 1569 | 2026-05-19 | 2026-05-22 | LS High nk Haalf Zipp Swt shirt | Swt Shirt |  |  | 2026-06-10 | 2026-06-17 | 2026-06-22 | 2026-07-06 |  |  | 2026-07-08 | 2026-07-08 |  | 2026-07-14 | 2026-07-15 | [6 empty] | 2026-07-17 | 2026-07-21 |  |  | 2026-07-23 | 2026-07-25 | 2026-07-29 | 2026-08-17 | 2026-08-19 | 90 | C | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 1569 | 1569 | 0 | 2251 | 46 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46195 | 0 | 34 | Jul'2 |  |  | 03.07.26
BS-ONS | 26827 51th | 22029225 | 4710 | 4290 | 2026-05-19 | 2026-05-22 | LS Swt hoodie w kangaro pkt and drastring and cuff btm rib | HOODY |  |  | 2026-06-06 | 2026-06-17 | 2026-06-15 | 2026-07-02 |  |  | 2026-07-02 | 2026-07-02 |  | 2026-07-08 | 2026-07-13 | [6 empty] | 2026-07-13 | 2026-07-18 |  |  | 2026-07-21 | 2026-07-22 | 2026-07-24 | 2026-08-15 | 2026-08-17 | 88 | R | Shakel | [5 empty] | NFL2 |  |  | Cut Ok | 4290 | 4290 | 0 | 0 | -4710 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 34 | Jul'1 |  |  | 03.07.26
BS-ONS | 26828 67th | 22029226 | 8820 | 5881 | 2026-05-19 | 2026-05-22 | LS Swt shirt | Swt Shirt |  |  | 2026-06-08 | 2026-06-20 | 2026-06-22 | 2026-07-10 |  |  | 2026-07-10 | 2026-07-10 |  | 2026-07-16 | 2026-07-20 | [6 empty] | 2026-07-22 | 2026-07-27 |  |  | 2026-07-29 | 2026-07-31 | 2026-08-03 | 2026-08-17 | 2026-08-19 | 90 | A | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 5880 | 5880 | 0 | 0 | -8820 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46195 | 0 | 34 | Jul'2 |  |  | 03.07.26
BS-ONL | 47772 | 15386506 | 2163 | 1175 | 2026-05-12 | 2026-05-18 | LS Swt hoodie w cuff rib btm S/J and drawstring | Hoody |  |  | 2026-06-06 | 2026-06-13 | 2026-06-18 | 2026-07-05 |  |  | 2026-07-06 | 2026-07-06 | 2026-07-12 | 2026-07-14 | 2026-07-15 | 2026-07-17 | 2026-07-20 |  |  |  |  | 2026-07-22 | 2026-07-25 |  |  | 2026-07-28 | 2026-07-30 | 2026-08-04 | 2026-08-10 | 2026-08-12 | 90 | R | Jannati | Fr,Bk |  | Navy-816 pcs frt 1 clr rub print back no print,,phanthom-531 pcs frt 1 clr rub print back no print ,,lollipop-816 pcs frt back 1 clr rub print |  |  | NFL2 |  |  | Cut Ok | 1175 | 1175 | 0 | 0 | -2163 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46191 | 0 | 33 | Jul'2 |  |  | 16.07.26
BS-ONL | 47771 | 15386782 | 3024 | 1338 | 2026-05-12 | 2026-05-19 | LS o nk Swt Shirt w cuff btm rib | Swt Shirt |  |  | 2026-06-06 | 2026-06-14 | 2026-06-15 | 2026-07-03 |  |  | 2026-07-06 | 2026-07-06 | 2026-07-11 | 2026-07-14 | 2026-07-17 | 2026-07-16 | 2026-07-18 | 2026-07-23 | 2026-07-30 |  |  | 2026-07-20 | 2026-07-24 |  |  | 2026-08-03 | 2026-08-04 | 2026-08-06 | 2026-08-10 | 2026-08-12 | 90 | N2 | Jannati | Chest,Stone |  | black-1527 pcs mark print 1 size pearl and stone attach,,LGM-1497 pcs mark print 1 size pearl attach |  |  | NFL2 |  |  | Cut Ok | 1351 | 1351 | 0 | 0 | -3024 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46188 | 0 | 33 | Jul'2 |  |  | 08.07.26
BS-ONL | 47789 | 15394278 | 1704 | 369 | 2026-05-11 | 2026-05-19 | LS v nk Dress w nk and slve mesh fabric | Dress |  |  | 2026-06-10 | 2026-06-15 | 2026-07-01 | 2026-07-10 |  |  | 2026-07-13 | 2026-07-13 | 2026-07-18 | 2026-07-21 | 2026-07-22 | [6 empty] | 2026-07-24 | 2026-07-28 |  |  | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-10 | 2026-08-12 | 91 | Q | Mainul |  |  |  |  | Imp Mesh | NFL2 |  |  | Cut Ok | 369 | 369 | 0 | 0 | -1704 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 33 | Jul'3 |  |  | 01.07.26
BS-ONL | 47788 | 15394276 | 1824 | 185 | 2026-05-11 | 2026-05-19 | LS v nk TS w nk and slve mesh fabric | TS |  |  | 2026-06-10 | 2026-06-15 | 2026-07-01 | 2026-07-12 |  |  | 2026-07-16 | 2026-07-16 | 2026-07-21 | 2026-07-23 | 2026-07-24 | [6 empty] | 2026-07-27 | 2026-07-30 |  |  | 2026-07-31 | 2026-08-03 | 2026-08-04 | 2026-08-10 | 2026-08-12 | 91 | K | Mainul |  |  |  |  | Imp Mesh | NFL2 |  |  | Cut Ok | 185 | 185 | 0 | 0 | -1824 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 33 | Jul'3 |  |  | 01.07.26
BS-ONL | 47790 | 15395038 | 6048 | 1943 | 2026-05-11 | 2026-05-19 | LS Swt Shirt w cuff btm rib | Swt Shirt |  |  | 2026-06-10 | 2026-06-20 | 2026-06-25 | 2026-07-11 |  |  | 2026-07-11 | 2026-07-14 | 2026-07-20 | 2026-07-22 | 2026-07-24 | [6 empty] | 2026-07-25 | 2026-07-30 |  |  | 2026-08-03 | 2026-08-04 | 2026-08-06 | 2026-08-10 | 2026-08-12 | 91 | N2 | Mainul | [5 empty] | NFL2 |  |  | Cut Ok | 1944 | 1944 | 0 | 0 | -6048 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46198 | 0 | 33 | Jul'3 |  |  | 18.07.26
OVS SPA | 47776 | 271PJA208-903 | 10680 | 9165 | 2026-05-15 | 2026-05-21 | AOP LS Blazer w collar full placket btn and Swt pant | Top & BTM |  |  | 2026-06-17 | 2026-06-30 | 2026-07-01 | 2026-07-14 | 2026-07-15 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-08-03 | 2026-08-04 | 2026-08-11 | [6 empty] | 2026-08-10 | 2026-08-24 |  |  | 2026-08-25 | 2026-08-26 | 2026-08-28 | 2026-08-31 | 2026-08-31 | 108 | A+E+N/3 | Salam |  |  |  | AOP |  | NFL1 |  |  | Cut Ok | 9389 | 9389 | 0 | 0 | -10680 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 36 | Aug'1 |  |  | 18.07.26
OVS SPA | 47801 | 271NDG1202-903 | 5662 | 2642 | 2026-05-20 | 2026-05-23 | LS Blazer w collar full placket btn and front pkt | Blazer |  |  | 2026-07-01 | 2026-07-11 | 2026-07-13 | 2026-07-25 |  |  | 2026-08-01 | 2026-07-24 | 2026-08-01 | 2026-08-03 | 2026-08-06 |  |  |  |  | 2026-08-06 | 2026-08-11 | 2026-08-11 | 2026-08-19 |  |  | 2026-08-20 | 2026-08-22 | 2026-08-24 | 2026-08-31 | 2026-08-31 | 103 | N/2 | Salam |  | Pkt | fig-2579 pcs,,rose-3083 pcs both combo flat emb at pkt confirmed by Merchant |  |  | NCL |  |  | Ready Test Cut | 2623 | 2623 | 0 | 0 | -5662 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46216 | 0 | 36 | Aug'1
OVS SPA | 47687 | 271VST004UTPC2-6110 | 8847 | 1032 | 2026-05-11 | 2026-05-19 | Tank Top w dtm Nk lace | Tank Top |  |  | 2026-07-01 | 2026-07-10 | 2026-07-11 | 2026-07-23 |  |  | 2026-07-20 | 2026-07-23 | 2026-07-27 | 2026-07-28 | 2026-07-31 | [6 empty] | 2026-08-01 | 2026-08-10 |  |  | 2026-08-11 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 2026-08-17 | 98 | C | Basir |  |  |  |  | Lace | NFL1 |  |  | Cut Ok | 1031 | 1031 | 0 | 0 | -8847 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46214 | 0 | 34 | Jul'3 |  |  | 25.07.26
OVS SPA | 47701 | 271NDG002SPT1N-6111 | 3834 | 1620 | 2026-05-11 | 2026-05-19 | AOP LS v nk Dress w front pkt | Dress |  |  | 2026-06-20 | 2026-06-30 | 2026-07-01 | 2026-07-13 | 2026-07-14 | 2026-07-25 | 2026-08-01 | 2026-08-03 | 2026-08-07 | 2026-08-08 | 2026-08-11 | [6 empty] | 2026-08-12 | 2026-08-18 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-24 | 2026-08-31 | 2026-08-31 | 112 | A | Basir |  |  |  | AOP |  | NFL1 |  |  | Cut Ok | 1668 | 1668 | 0 | 0 | -3834 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 36 | Aug'1 |  |  | 06.08.26
OVS SPA | 47702 | 271PJA006SPT1P-6111 | 9264 | 3055 | 2026-05-11 | 2026-05-19 | AOP LS v nk Dress w frt pkt nk contrast piping and Elasted pant | Top & BTM |  |  | 2026-06-18 | 2026-06-30 | 2026-07-01 | 2026-07-13 | 2026-07-14 | 2026-07-25 | 2026-08-01 | 2026-08-03 | 2026-08-07 | 2026-08-08 | 2026-08-11 | [6 empty] | 2026-08-12 | 2026-08-18 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-24 | 2026-08-31 | 2026-08-31 | 112 | N/2 | Basir |  |  |  | AOP |  | NCL |  |  | Ready Test Cut | 3162 | 3162 | 0 | 0 | -9264 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 36 | Aug'1
OVS SPA | 47703 | 271PJA007PRCM-6111 | 9250 | 3496 | 2026-05-11 | 2026-05-19 | AOP LS blazer w collar placket btn and Pant w drawstring | Top & BTM |  |  | 2026-06-18 | 2026-06-30 | 2026-07-01 | 2026-07-13 | 2026-07-14 | 2026-07-25 | 2026-08-01 | 2026-08-03 | 2026-08-07 | 2026-08-08 | 2026-08-11 | [6 empty] | 2026-08-12 | 2026-08-18 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-24 | 2026-08-30 | 2026-08-30 | 111 | A+E | Basir |  |  |  | AOP |  | NFL1 |  |  | Cut Ok | 3496 | 3496 | 0 | 0 | -9250 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 36 | Aug'1 |  |  | 06.08.26
UTG-(Even & Odd) | 42353 5th | BAD2529H | 1000 | 206 | 2026-05-23 | 2026-05-23 | LDS LEGGING W LACE | LEGGING |  |  | 2026-07-01 | 2026-07-08 | 2026-07-10 | 2026-07-20 |  |  | 2026-07-28 | 2026-07-29 |  | 2026-08-01 | 2026-08-01 | [6 empty] | 2026-08-03 | 2026-08-05 |  |  | 2026-08-06 | 2026-08-10 | 2026-08-12 | 2026-08-14 | 2026-08-14 | 83 | N/1 | Rony |  |  |  |  | Lace | NCL |  |  | Ready Test Cut | 206 | 206 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 33 | Aug'1
BS-ONS | 45964 9th | 22039968 | 3930 | 2834 | 2026-05-19 | 2026-05-22 | LS High nk Haalf Zipp Swt shirt | Swt Shirt |  |  | 2026-06-18 | 2026-06-30 | 2026-07-01 | 2026-07-20 |  |  | 2026-07-20 | 2026-07-20 |  | 2026-08-01 | 2026-08-04 | [6 empty] | 2026-08-06 | 2026-08-11 |  |  | 2026-08-13 | 2026-08-15 | 2026-08-20 | 2026-09-12 | 2026-09-14 | 116 | B | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 2834 | 2834 | 0 | 4028 | 98 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 38 | Aug'1 |  |  | 03.07.26
BS-ONS | 26827 52th | 22029225 | 5076 | 4610 | 2026-05-19 | 2026-05-22 | LS Swt hoodie w kangaro pkt and drastring and cuff btm rib | HOODY |  |  | 2026-06-15 | 2026-06-25 | 2026-07-01 | 2026-07-20 |  |  | 2026-07-18 | 2026-07-18 |  | 2026-07-24 | 2026-07-28 | [6 empty] | 2026-08-01 | 2026-08-07 |  |  | 2026-08-10 | 2026-08-12 | 2026-08-17 | 2026-09-12 | 2026-09-14 | 116 | R | Shakel | [5 empty] | NFL2 |  |  | Cut Ok | 4610 | 4610 | 0 | 5224 | 148 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 38 | Jul'3 |  |  | 18.07.26
BS-ONS | 26828 68th | 22029226 | 3245 | 2216 | 2026-05-19 | 2026-05-22 | LS Swt shirt | Swt Shirt |  |  | 2026-06-15 | 2026-06-22 | 2026-07-01 | 2026-07-17 |  |  | 2026-07-20 | 2026-07-20 |  | 2026-07-27 | 2026-07-29 | [6 empty] | 2026-08-01 | 2026-08-04 |  |  | 2026-08-06 | 2026-08-08 | 2026-08-12 | 2026-09-14 | 2026-09-16 | 118 | A | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 2236 | 2236 | 0 | 3368 | 123 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 38 | Jul'3 |  |  | 18.07.26
BS-ONL | 47763 2nd | 15386479 | 6909 | 1970 | 2026-05-12 | 2026-05-18 | LS boat nk TS | TS |  |  | 2026-06-14 | 2026-06-25 | 2026-06-28 | 2026-07-15 |  |  | 2026-07-15 | 2026-07-15 |  | 2026-07-22 | 2026-07-25 | [6 empty] | 2026-07-25 | 2026-07-30 |  |  | 2026-08-03 | 2026-08-06 | 2026-08-12 | 2026-09-07 | 2026-09-09 | 118 | O2 | Jannati | [5 empty] | NFL2 |  |  | Cut Ok | 1970 | 1959 | -11 | 7154 | 245 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46201 | 0 | 37 | Jul'3 |  |  | 23.06.26
OVS SPA | 47813 | 271VST0210SB-901 | 12280 | 1515 | 2026-05-20 | 2026-05-23 | Tank Top lace in nk | Tank Top |  |  | 2026-08-01 | 2026-08-10 | 2026-08-11 | 2026-08-24 |  |  | 2026-09-05 | 2026-09-03 | 2026-09-08 | 2026-09-09 | 2026-09-12 | 2026-09-12 | 2026-09-16 |  |  |  |  | 2026-09-15 | 2026-09-26 |  |  | 2026-09-28 | 2026-09-30 | 2026-10-02 | 2026-10-12 | 2026-10-12 | 145 | E | Salam | Heat Press/Heat Seal |  | 3 combo nk HP |  | Lace | NFL1 |  |  | Need Cut | 1514 | 1314 | -200 | 0 | -12280 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46245 | 0 | 42 | Sep'1 |  |  | 08.08.26
OVS SPA | 47814 | 271VST0211SB-901 | 11676 | 1148 | 2026-05-20 | 2026-05-23 | Strap V nk Tank Top w lac in Nk | Tank Top |  |  | 2026-08-01 | 2026-08-10 | 2026-08-11 | 2026-08-24 |  |  | 2026-09-05 | 2026-09-03 | 2026-09-08 | 2026-09-09 | 2026-09-12 | 2026-09-12 | 2026-09-16 |  |  |  |  | 2026-09-15 | 2026-09-26 |  |  | 2026-09-28 | 2026-09-30 | 2026-10-02 | 2026-10-12 | 2026-10-12 | 145 | E | Salam | Heat Press/Heat Seal |  | 3 combo nk HP |  | Lace | NFL1 |  |  | Need Cut | 1148 | 1093 | -55 | 0 | -11676 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46245 | 0 | 42 | Sep'1 |  |  | 08.08.26
BS-NMT | 43316 25th | 13234729 | 4440 | 794 | 2026-05-27 | 2026-06-08 | LS o nk TS | TS |  |  | 2026-06-15 | 2026-06-22 | 2026-06-22 | 2026-07-02 |  |  | 2026-07-01 | 2026-07-01 |  | 2026-07-04 | 2026-07-07 | 2026-07-07 | 2026-07-09 |  |  |  |  | 2026-07-10 | 2026-07-13 |  |  | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-20 | 2026-07-22 | 54 | ZA1 | Jafar | Nk |  | 4 combo label print |  |  | NFL3 |  |  | Cut Ok | 794 | 794 | 0 | 0 | -4440 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46195 | 0 | 30 | Jul'1 |  |  | 24.06.26
BS-NMT | 43330 10th | 13197665 | 1000 | 468 | 2026-05-27 | 2026-06-08 | LS Swt Zip hoodie | Hoody |  |  | 2026-06-15 | 2026-06-20 | 2026-06-24 | 2026-07-04 |  |  | 2026-07-04 | 2026-07-04 |  | 2026-07-10 | 2026-07-11 | [6 empty] | 2026-07-13 | 2026-07-15 |  |  | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-20 | 2026-07-22 | 54 | S | Jafar | [5 empty] | NFL3 |  |  | Cut Ok | 469 | 469 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46197 | 0 | 30 | Jul'1 |  |  | 25.06.26
BS-NMT | 43323 30th | 13180124 | 1040 | 106 | 2026-06-03 | 2026-06-08 | GIRLS SOLID LEGGINGS | Legging |  |  | 2026-06-16 | 2026-06-20 | 2026-06-25 | 2026-07-04 |  |  | 2026-07-04 | 2026-07-04 |  | 2026-07-09 | 2026-07-09 | 2026-07-11 | 2026-07-11 |  |  |  |  | 2026-07-14 | 2026-07-15 |  |  | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-22 | 47 | G1 | Jafar | WAIST |  | 1 combo label print |  |  | NFL1 |  |  | Cut Ok | 106 | 106 | 0 | 0 | -1040 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46198 | 0 | 30 | Jul'1 |  |  | 24.06.26
BS-NMT | 43327 14th | 13235093 | 1320 | 488 | 2026-05-27 | 2026-06-08 | Swt Pant w pkt waist belt drawstring | Pant |  |  | 2026-06-15 | 2026-06-20 | 2026-06-25 | 2026-07-06 |  |  | 2026-07-04 | 2026-07-04 |  | 2026-07-10 | 2026-07-11 | [6 empty] | 2026-07-13 | 2026-07-14 |  |  | 2026-07-15 | 2026-07-16 | 2026-07-18 | 2026-07-20 | 2026-07-22 | 54 | U | Jafar | [5 empty] | NFL3 |  |  | Cut Ok | 488 | 488 | 0 | 0 | -1320 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46198 | 0 | 30 | Jul'1 |  |  | 24.06.26
BS-NMT | 44019 16th | 13247093 | 1500 | 280 | 2026-05-27 | 2026-06-08 | Weist belt legging | Legging |  |  | 2026-06-15 | 2026-06-20 | 2026-06-25 | 2026-07-04 |  |  | 2026-07-04 | 2026-07-04 |  | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 |  |  |  |  | 2026-07-13 | 2026-07-15 |  |  | 2026-07-18 | 2026-07-18 | 2026-07-20 | 2026-07-20 | 2026-07-22 | 54 | Z | Jafar | WAIST |  | 1 combo label print |  |  | NFL3 |  |  | Cut Ok | 280 | 280 | 0 | 0 | -1500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46198 | 0 | 30 | Jul'1 |  |  | 24.06.26
BS-ONS | 47871 | 22041246 | 2133 | 1301 | 2026-06-04 | 2026-06-08 | LS Half zipper Swt Shirt w cuff btm rib | Swt Shirt |  |  | 2026-06-13 | 2026-06-20 | 2026-06-20 | 2026-07-02 |  |  | 2026-07-01 | 2026-07-01 | 2026-07-06 | 2026-07-08 | 2026-07-10 | [6 empty] | 2026-07-10 | 2026-07-14 |  |  | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-20 | 2026-07-22 | 46 | C | Shovon | [5 empty] | NFL1 |  |  | Cut Ok | 1300 | 1300 | 0 | 0 | -2133 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46193 | 0 | 30 | Jul'1 |  |  | 09.07.26
BS-ONS | 47873 | 22041181 | 1092 | 699 | 2026-06-04 | 2026-06-08 | LS Half zipper Swt Shirt w cuff btm rib w chest woven patch | Swt Shirt |  |  | 2026-06-13 | 2026-06-20 | 2026-06-21 | 2026-07-03 |  |  | 2026-07-02 | 2026-07-02 | 2026-07-08 | 2026-07-10 | 2026-07-11 | [6 empty] | 2026-07-13 | 2026-07-15 |  |  | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-22 | 46 | C | Shovon | [5 empty] | NFL1 |  |  | Cut Ok | 698 | 698 | 0 | 0 | -1092 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46194 | 0 | 30 | Jul'1 |  |  | 04.07.26
BS-ONS | 47872 | 22041180 | 1257 | 759 | 2026-06-04 | 2026-06-08 | LS Swt Shirt w cuff btm rib w chest rub patch | Swt Shirt |  |  | 2026-06-14 | 2026-06-22 | 2026-06-20 | 2026-07-04 |  |  | 2026-07-04 | 2026-07-04 | 2026-07-09 | 2026-07-11 | 2026-07-13 | [6 empty] | 2026-07-14 | 2026-07-15 |  |  | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-22 | 46 | E | Shovon | [5 empty] | NFL1 |  |  | Cut Ok | 760 | 760 | 0 | 0 | -1257 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46193 | 0 | 30 | Jul'2 |  |  | 04.07.26
BS-ONL | 44129 4th | 15229309 | 816 | 190 | 2026-06-04 | 2026-06-11 | LS BODY STOCKING w sholder slve gathering snap btn | BODY |  |  | 2026-08-01: 2026-07-07; 2026-08-03: 2026-07-07; 2026-08-08: 2026-07-13; 2026-08-11: 2026-07-14 | [6 empty] | 2026-07-16 | 2026-07-18 |  |  | 2026-07-20 | 2026-07-22 | 2026-07-24 | 2026-07-27 | 2026-07-29 | 53 | J | Jannati |  |  |  |  | Exp order/Stock fab from 43465 | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -816 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 31 | Jul'2 |  |  | 16.07.26
BS-ONL | 47893 | 15396053 | 2298 | 602 | 2026-06-06 | 2026-06-12 | LS ban collar Top w cross placket frog btn | TS |  |  | 2026-06-20 | 2026-06-25 | 2026-07-01 | 2026-07-11 |  |  | 2026-07-10 | 2026-07-10 | 2026-07-15 | 2026-07-17 | 2026-07-18 | [6 empty] | 2026-07-20 | 2026-07-23 |  |  | 2026-07-24 | 2026-07-25 | 2026-07-27 | 2026-07-27 | 2026-07-29 | 51 | J | Mainul | [5 empty] | NFL2 |  |  | Cut Ok | 602 | 602 | 0 | 0 | -2298 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 31 | Jul'2 |  |  | 09.07.26
BS-ONL | 47892 | 15396003 | 1680 | 304 | 2026-06-06 | 2026-06-12 | SS ban collar Top w cross placket frog btn | TS |  |  | 2026-06-18 | 2026-06-24 | 2026-07-01 | 2026-07-12 |  |  | 2026-07-10 | 2026-07-10 | 2026-07-15 | 2026-07-17 | 2026-07-18 | [6 empty] | 2026-07-20 | 2026-07-23 |  |  | 2026-07-24 | 2026-07-25 | 2026-07-27 | 2026-07-27 | 2026-07-29 | 51 | J | Mainul | [5 empty] | NFL2 |  |  | Cut Ok | 305 | 305 | 0 | 0 | -1680 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 31 | Jul'2 |  |  | 09.07.26
BS-ONL | 41875 14th | 15303956 | 1520 | 641 | 2026-06-04 | 2026-06-06 | LDS PANT W PKT | PANT |  |  | 2026-06-15 | 2026-06-20 | 2026-06-25 | 2026-07-06 |  |  | 2026-07-06 | 2026-07-06 |  | 2026-07-11 | 2026-07-13 |  |  |  |  | 2026-07-14 | 2026-07-15 | 2026-07-17 | 2026-07-20 |  |  | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-27 | 2026-07-29 | 53 | P | Khalid |  | LEG | BLACK 1520 PCS 1 CLR LETTERING EMB AT ONE LEG |  |  | NFL2 |  |  | Cut Ok | 641 | 641 | 0 | 0 | -1520 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46198 | 0 | 31 | Jul'2 |  |  | 20.06.26
BS-ONL | 45317 3rd | 15084518 | 1500 | 370 | 2026-06-09 | 2026-06-10 | LDS 3/4 FOLD LEGGING | Legging |  |  | 2026-08-01: 2026-06-21; 2026-08-03: 2026-06-21; 2026-08-07: 2026-06-24; 2026-08-08: 2026-06-26; 2026-08-11: 2026-06-27 | 2026-07-01 | 2026-07-02 |  |  |  |  | 2026-07-03 | 2026-07-04 |  |  | 2026-07-06 | 2026-07-08 | 2026-07-10 | 2026-07-13 | 2026-07-15 | 34 | L2 | Khalid | WAIST |  | 1 combo waist print |  | stock fab from 41880 20th | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 29 | Jun'3 |  |  | 20.06.26
BS-ONL | 45313 9th | 15311584 | 1615 | 304 | 2026-06-08 | 2026-06-10 | High waist shorts | Shorts |  |  | 2026-08-01: 2026-06-25; 2026-08-03: 2026-06-21; 2026-08-08: 2026-07-04; 2026-08-11: 2026-07-04 | 2026-07-07 | 2026-07-07 |  |  |  |  | 2026-07-09 | 2026-07-09 |  |  | 2026-07-11 | 2026-07-14 | 2026-07-15 | 2026-07-27 | 2026-07-29 | 49 | L2 | Khalid | WAIST |  | 1 combo label print |  | stock fab from 41880 20th | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1615 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 31 | Jul'1 |  |  | 20.06.26
GBX-New Look | 47870 | 9652101 | 3340 | 606 | 2026-06-08 | 2026-06-09 | LS TS w front full placket btn | TS |  |  | 2026-06-18 | 2026-06-22 | 2026-06-25 | 2026-07-06 |  |  | 2026-07-07 | 2026-07-07 | 2026-07-13 | 2026-07-15 | 2026-07-17 | [6 empty] | 2026-07-18 | 2026-07-22 |  |  | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-25 | 2026-07-26 | 47 | N/3 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 606 | 606 | 0 | 0 | -3340 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46198 | 0 | 31 | Jul'2
GBX-New Look | 47869 | 9652104 | 3040 | 745 | 2026-06-08 | 2026-06-09 | LS boat nk 2 in 1 TS w side gathering | TS |  |  | 2026-06-15 | 2026-06-20 | 2026-06-25 | 2026-07-05 |  |  | 2026-07-04 | 2026-07-04 | 2026-07-09 | 2026-07-11 | 2026-07-13 | [6 empty] | 2026-07-11 | 2026-07-18 |  |  | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-25 | 2026-07-26 | 47 | N/1 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 744 | 744 | 0 | 0 | -3040 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46198 | 0 | 31 | Jul'2
GBX-TM LEWIN | 44711 11th | 67936/67937/67939/68226 | 28685 | 6991 | 2026-06-08 | 2026-06-09 | MENS SS TS | TS |  |  | 2026-07-01 | 2026-07-04 | 2026-07-04 | 2026-07-13 |  |  | 2026-07-01 | 2026-07-01 |  | 2026-07-06 | 2026-07-15 | [6 empty] | 2026-07-09 | 2026-07-28 |  |  | 2026-07-29 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 52 | N/1 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 6992 | 6992 | 0 | 0 | -28685 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46207 | 0 | 31 | Jul'1
GBX-TM LEWIN | 44716 6th | 68234 | 1575 | 549 | 2026-06-08 | 2026-06-09 | YD SS TS | TS | 2026-06-23 | 2026-06-27 | 2026-06-30 | 2026-07-06 | 2026-07-07 | 2026-07-13 |  |  | 2026-07-13 | 2026-07-13 |  | 2026-07-17 | 2026-07-18 | [6 empty] | 2026-07-20 | 2026-07-22 |  |  | 2026-07-23 | 2026-07-24 | 2026-07-28 | 2026-07-30 | 2026-07-30 | 52 | N/1 | Shofi |  |  |  | YD |  | NCL |  |  | Ready Test Cut | 549 | 549 | 0 | 0 | -1575 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46210 | 0 | 31 | Jul'2
GBX-TM LEWIN | 44714 10th | 68245/68247 | 5381 | 1833 | 2026-06-08 | 2026-06-10 | MENS O NK TS W PLKT & BTN | TS |  |  | 2026-06-17 | 2026-06-24 | 2026-06-27 | 2026-07-11 |  |  | 2026-07-09 | 2026-07-09 |  | 2026-07-14 | 2026-07-17 | [6 empty] | 2026-07-17 | 2026-07-23 |  |  | 2026-07-25 | 2026-07-27 | 2026-07-28 | 2026-07-30 | 2026-07-30 | 52 | N/2 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 1835 | 1835 | 0 | 0 | -5381 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46200 | 0 | 31 | Jul'2
GBX-TM LEWIN | 44715 12th | 68166/68167/68168/68397 | 13377 | 4490 | 2026-06-10 | 2026-06-13 | MENS LS TS | TS |  |  | 2026-06-17 | 2026-06-27 | 2026-06-25 | 2026-07-10 |  |  | 2026-07-06 | 2026-07-06 |  | 2026-07-11 | 2026-07-15 | [6 empty] | 2026-07-14 | 2026-07-25 |  |  | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-30 | 50 | N/1 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 4490 | 4485 | -5 | 0 | -13377 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46198 | 0 | 31 | Jul'2
GBX-TM LEWIN | 46752 4th | 68502/68503/68496 | 1720 | 528 | 2026-06-10 | 2026-06-13 | YD SS o nk TS | TS | 2026-06-20 | 2026-06-27 | 2026-07-03 | 2026-07-10 | 2026-07-13 | 2026-07-17 |  |  | 2026-07-10 | 2026-07-10 |  | 2026-07-20 | 2026-07-21 | [6 empty] | 2026-07-23 | 2026-07-25 |  |  | 2026-07-27 | 2026-07-28 | 2026-07-28 | 2026-07-30 | 2026-07-30 | 50 | N/2 | Shofi |  |  |  | YD |  | NCL |  |  | Ready Test Cut | 528 | 528 | 0 | 0 | -1720 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46216 | 0 | 31 | Jul'2
GBX-TM LEWIN | 46696 3rd | 68490/68491/68492/68493 | 10505 | 2838 | 2026-06-10 | 2026-06-13 | SS o nk TS | TS |  |  | 2026-07-01 | 2026-07-06 | 2026-07-06 | 2026-07-15 |  |  | 2026-07-09 | 2026-07-09 |  | 2026-07-14 | 2026-07-17 | [6 empty] | 2026-07-17 | 2026-07-22 |  |  | 2026-07-24 | 2026-07-25 | 2026-07-27 | 2026-07-30 | 2026-07-30 | 50 | N/2 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 2891 | 2883 | -8 | 0 | -10505 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46209 | 0 | 31 | Jul'2
GBX-TM Lewin | 47740 2nd | 68670/68671/68672/68673/68674 | 2970 | 760 | 2026-06-10 | 2026-06-13 | SS crew nk TS | TS |  |  | 2026-07-02 | 2026-07-07 | 2026-07-07 | 2026-07-17 |  |  | 2026-07-09 | 2026-07-09 |  | 2026-07-17 | 2026-07-18 | [6 empty] | 2026-07-18 | 2026-07-22 |  |  | 2026-07-24 | 2026-07-25 | 2026-07-27 | 2026-07-30 | 2026-07-30 | 50 | N/1 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 760 | 760 | 0 | 0 | -2970 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46210 | 0 | 31 | Jul'2
GBX-TM LEWIN | 47934 | 68737/68738/68739/68740/68741/68742/68743 | 2450 | 907 | 2026-06-10 | 2026-06-13 | SS TS w placket btn | TS |  |  | 2026-06-20 | 2026-06-26 | 2026-06-29 | 2026-07-12 |  |  | 2026-07-10 | 2026-07-10 | 2026-07-15 | 2026-07-17 | 2026-07-18 | [6 empty] | 2026-07-20 | 2026-07-23 |  |  | 2026-07-25 | 2026-07-27 | 2026-07-28 | 2026-07-30 | 2026-07-30 | 50 | N/2 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 907 | 907 | 0 | 0 | -2450 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46202 | 0 | 31 | Jul'2
GBX-TM LEWIN | 47935 | 68724/68725/68726/68727/68728 | 2950 | 1040 | 2026-06-10 | 2026-06-13 | SS TS w nk Rib | TS |  |  | 2026-06-19 | 2026-06-25 | 2026-06-27 | 2026-07-10 |  |  | 2026-07-10 | 2026-07-10 | 2026-07-15 | 2026-07-17 | 2026-07-18 | [6 empty] | 2026-07-20 | 2026-07-23 |  |  | 2026-07-25 | 2026-07-27 | 2026-07-28 | 2026-07-30 | 2026-07-30 | 50 | N/1 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 1044 | 1044 | 0 | 0 | -2950 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46200 | 0 | 31 | Jul'2
UTG-AF | 42480 3rd | BAD1059mamaAL | 3000 | 604 | 2026-06-09 | 2026-06-10 | maternity legging | Legging |  |  | 2026-06-15 | 2026-06-25 | 2026-06-25 | 2026-07-04 |  |  | 2026-07-04 | 2026-07-06 |  | 2026-07-08 | 2026-07-09 | [6 empty] | 2026-07-10 | 2026-07-14 |  |  | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-20 | 39 | N/2 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 604 | 604 | 0 | 0 | -3000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46198 | 0 | 30 | Jul'1
UTG-(Even & Odd) | 45150 2nd | BAD2992A | 1600 | 280 | 2026-06-06 | 2026-06-15 | LS WRAP TOP | Dress | 2026-07-13: 2026-07-22; 2026-07-17: 2026-07-01 |  |  | 2026-07-01 | 2026-07-01 |  | 2026-07-02 | 2026-07-03 | [6 empty] | 2026-07-04 | 2026-07-06 |  |  | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-11 | 2026-07-13 | 35 | N/3 | Rony |  |  |  |  | STOCK & IMPORTED FABRIC | NCL |  |  | Ready Test Cut | 280 | 280 | 0 | 0 | -1600 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 29 | Jul'1
UTG-(Even & Odd) | 41318 16th | BAD1571AE | 600 | 158 | 2026-06-06 | 2026-06-15 | LDS CROPPED WRAP OVERLAP LS TS | TS |  |  | 2026-06-17 | 2026-06-20 | 2026-06-22 | 2026-07-01 |  |  | 2026-07-01 | 2026-07-01 |  | 2026-07-02 | 2026-07-03 | [6 empty] | 2026-07-04 | 2026-07-06 |  |  | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-11 | 2026-07-13 | 35 | N/1 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 158 | 158 | 0 | 0 | -600 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46195 | 0 | 29 | Jul'1
UTG-(Even & Odd) | 24230 20th | BAD0966AD | 1200 | 262 | 2026-06-06 | 2026-06-15 | LDS LS TS W LETTUCE | TS |  |  | 2026-06-17 | 2026-06-20 | 2026-06-22 | 2026-07-01 |  |  | 2026-07-01 | 2026-07-01 |  | 2026-07-02 | 2026-07-03 | [6 empty] | 2026-07-04 | 2026-07-06 |  |  | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-11 | 2026-07-13 | 35 | N/1 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 262 | 262 | 0 | 0 | -1200 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46195 | 0 | 29 | Jul'1
UTG-(Even & Odd) | 47875 | BAD3224 | 2000 | 396 | 2026-06-06 | 2026-06-15 | LS TS w back u nk | TS |  |  | 2026-06-17 | 2026-06-20 | 2026-06-22 | 2026-07-01 |  |  | 2026-07-01 | 2026-07-01 | 2026-07-03 | 2026-07-04 | 2026-07-04 | [6 empty] | 2026-07-06 | 2026-07-08 |  |  | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-13 | 35 | N/1 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 396 | 396 | 0 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46195 | 0 | 29 | Jul'1
UTG-(Even & Odd) | 47876 | BAD3217 | 1000 | 285 | 2026-06-06 | 2026-06-15 | YD LS round nk TS | TS | 2026-06-17 | 2026-06-23 | 2026-06-24 | 2026-06-29 | 2026-06-30 | 2026-07-03 |  |  | 2026-07-01 | 2026-07-01 |  | 2026-07-02 | 2026-07-03 | [6 empty] | 2026-07-04 | 2026-07-06 |  |  | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-11 | 2026-07-13 | 35 | N/1 | Rony |  |  |  | YD |  | NCL |  |  | Ready Test Cut | 285 | 285 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46203 | 0 | 29 | Jul'1
BS-NMT | 43325 14th | 13224921 | 1000 | 497 | 2026-06-03 | 2026-06-08 | LS Swt full Zip hoodie | Hoody |  |  | 2026-06-18 | 2026-06-24 | 2026-07-01 | 2026-07-13 |  |  | 2026-07-15 | 2026-07-15 |  | 2026-07-20 | 2026-07-21 | [6 empty] | 2026-07-23 | 2026-07-25 |  |  | 2026-07-28 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-05 | 61 | S | Jafar | [5 empty] | NFL3 |  |  | Cut Ok | 496 | 496 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 32 | Jul'2 |  |  | 25.06.26
BS-ONS | 45964 11th | 22039968 | 9000 | 6481 | 2026-05-26 | 2026-06-06 | LS High nk Haalf Zipp Swt shirt | Swt Shirt |  |  | 2026-06-25 | 2026-07-05 | 2026-07-02 | 2026-07-22 |  |  | 2026-07-20 | 2026-07-20 |  | 2026-07-28 | 2026-07-31 | [6 empty] | 2026-08-01 | 2026-08-11 |  |  | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-17 | 2026-08-19 | 83 | B | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 6480 | 6480 | 0 | 0 | -9000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46205 | 0 | 34 | Jul'3 |  |  | 03.07.26
BS-ONS | 41626 25th | 22031973 | 3030 | 2028 | 2026-06-11 | 2026-06-12 | MENS LONG SWT PANT W SIDE & BK PKT | PANT |  |  | 2026-06-18 | 2026-06-27 | 2026-07-01 | 2026-07-13 |  |  | 2026-07-13 | 2026-07-11 |  | 2026-07-17 | 2026-07-24 | [6 empty] | 2026-07-20 | 2026-07-24 |  |  | 2026-07-27 | 2026-07-28 | 2026-07-30 | 2026-08-10 | 2026-08-12 | 60 | B | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 2028 | 2026 | -2 | 0 | -3030 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 33 | Jul'2 |  |  | 18.07.26
BS-ONS | 26828 72th | 22029226 | 6350 | 4232 | 2026-06-12 | 2026-06-13 | LS Swt shirt | Swt Shirt |  |  | 2026-06-19 | 2026-06-26 | 2026-07-01 | 2026-07-15 |  |  | 2026-07-16 | 2026-07-16 |  | 2026-07-21 | 2026-07-23 | [6 empty] | 2026-07-24 | 2026-07-28 |  |  | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-05 | 52 | A | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 4232 | 4232 | 0 | 0 | -6350 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 32 | Jul'3 |  |  | 03.07.26
BS-ONS | 26970 59th | 22002973 | 2640 | 586 | 2026-06-12 | 2026-06-13 | SS o nk TS | TS |  |  | 2026-06-22 | 2026-06-27 | 2026-07-03 | 2026-07-15 |  |  | 2026-07-17 | 2026-07-17 |  | 2026-07-23 | 2026-07-24 | [6 empty] | 2026-07-24 | 2026-07-27 |  |  | 2026-07-25 | 2026-07-28 | 2026-07-30 | 2026-08-17 | 2026-08-19 | 66 | D1 | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 586 | 586 | 0 | 0 | -2640 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46206 | 0 | 34 | Jul'3 |  |  | 27.06.26
BS-ONS | 44076 17th | 22013782 | 3000 | 680 | 2026-06-12 | 2026-06-13 | SS T Shirt | TS |  |  | 2026-06-20 | 2026-06-25 | 2026-07-01 | 2026-07-11 |  |  | 2026-07-10 | 2026-07-10 |  | 2026-07-16 | 2026-07-17 | [6 empty] | 2026-07-20 | 2026-07-22 |  |  | 2026-07-24 | 2026-07-27 | 2026-07-30 | 2026-08-10 | 2026-08-12 | 59 | G2 | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 680 | 680 | 0 | 0 | -3000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 33 | Jul'2 |  |  | 03.07.26
BS-ONL | 47767 | 15387083 | 3379 | 1242 | 2026-05-12 | 2026-06-09 | LS TS w side waist tie knot w cross drawstring gathering | TS |  |  | 2026-06-17 | 2026-06-27 | 2026-07-01 | 2026-07-14 |  |  | 2026-07-15 | 2026-07-15 | 2026-07-20 | 2026-07-22 | 2026-07-24 | [6 empty] | 2026-07-25 | 2026-07-31 |  |  | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-10 | 2026-08-12 | 90 | J | Jannati | [5 empty] | NFL2 |  |  | Cut Ok | 1242 | 1242 | 0 | 0 | -3379 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 33 | Jul'3 |  |  | 13.07.26
BS-ONL | 41873 11th | 15303953 | 1520 | 697 | 2026-06-08 | 2026-06-10 | LDS HIGH NK SWT W FULL ZIPPER PKT, CUFF BOND PKT | Swt Shirt |  |  | 2026-06-18 | 2026-06-24 | 2026-07-01 | 2026-07-13 |  |  | 2026-07-10 | 2026-07-10 |  | 2026-07-16 | 2026-07-17 |  |  |  |  | 2026-07-18 | 2026-07-20 | 2026-07-22 | 2026-07-25 |  |  | 2026-07-27 | 2026-07-28 | 2026-07-30 | 2026-08-03 | 2026-08-05 | 56 | R | Khalid |  | CHEST | BLACK 1520 PCS 1 CLR FLAT EMB |  |  | NFL2 |  |  | Cut Ok | 697 | 697 | 0 | 0 | -1520 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 32 | Jul'2 |  |  | 22.06.26
BS-ONL | 27204 53th | 15323159 | 6080 | 1469 | 2026-06-03 | 2026-06-06 | LS o nk TS | TS |  |  | 2026-06-15 | 2026-06-23 | 2026-07-01 | 2026-07-10 |  |  | 2026-07-10 | 2026-07-10 |  | 2026-07-15 | 2026-07-16 | [6 empty] | 2026-07-20 | 2026-07-23 |  |  | 2026-07-25 | 2026-07-27 | 2026-07-30 | 2026-08-03 | 2026-08-05 | 61 | D2 | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 1469 | 1469 | 0 | 0 | -6080 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 32 | Jul'2 |  |  | 16.06.26
BS-ONL | 43969 37th | 15270390 | 3040 | 494 | 2026-06-03 | 2026-06-06 | SS o nk TS | TS |  |  | 2026-06-15 | 2026-06-18 | 2026-06-25 | 2026-07-03 |  |  | 2026-07-04 | 2026-07-04 |  | 2026-07-09 | 2026-07-10 | [6 empty] | 2026-07-13 | 2026-07-15 |  |  | 2026-07-17 | 2026-07-20 | 2026-07-23 | 2026-08-03 | 2026-08-05 | 61 | ZA1 | Dalim | [5 empty] | NFL3 |  |  | Cut Ok | 494 | 494 | 0 | 0 | -3040 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46198 | 0 | 32 | Jul'1 |  |  | 01.07.26
BS-ONL | 43969 38th | 15270390 | 3040 | 527 | 2026-06-12 | 2026-06-13 | SS o nk TS | TS |  |  | 2026-06-20 | 2026-06-25 | 2026-07-01 | 2026-07-10 |  |  | 2026-07-10 | 2026-07-10 |  | 2026-07-16 | 2026-07-17 | [6 empty] | 2026-07-20 | 2026-07-22 |  |  | 2026-07-24 | 2026-07-28 | 2026-07-30 | 2026-08-10 | 2026-08-12 | 59 | ZA1 | Dalim | [5 empty] | NFL3 |  |  | Cut Ok | 527 | 527 | 0 | 3078 | 38 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 33 | Jul'2 |  |  | 01.07.26
BS-ONL | 27204 54th | 15323159 | 15200 | 3648 | 2026-06-12 | 2026-06-13 | LS o nk TS | TS |  |  | 2026-06-21 | 2026-07-02 | 2026-07-01 | 2026-07-14 |  |  | 2026-07-13 | 2026-07-13 |  | 2026-07-18 | 2026-07-22 | [6 empty] | 2026-07-22 | 2026-07-28 |  |  | 2026-07-30 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-12 | 59 | D2 | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 3650 | 3647 | -3 | 0 | -15200 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 33 | Jul'2 |  |  | 16.06.26
BS-ONL | 47709 | 15299770 | 3220 | 436 | 2026-06-03 | 2026-06-13 | LS o nk TS | TS |  |  | 2026-06-22 | 2026-06-25 | 2026-07-01 | 2026-07-13 |  |  | 2026-07-15 | 2026-07-15 | 2026-07-20 | 2026-07-22 | 2026-07-23 | [6 empty] | 2026-07-24 | 2026-07-27 |  |  | 2026-07-29 | 2026-07-31 | 2026-08-06 | 2026-08-10 | 2026-08-12 | 68 | N1 | Abid | [5 empty] | NFL2 |  |  | Cut Ok | 437 | 437 | 0 | 0 | -3220 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 33 | Jul'3 |  |  | 24.07.26
OVS SPA | 47633 | 271PJA004AG2-6111 | 9652 | 2735 | 2026-05-23 | 2026-06-10 | AOP LS Swt shirt and Pant w twill tape string at waist | Top & BTM |  |  | 2026-06-20 | 2026-06-30 | 2026-07-01 | 2026-07-13 | 2026-07-14 | 2026-07-24 | 2026-07-25 | 2026-07-27 | 2026-08-01 | 2026-08-03 | 2026-08-05 | [6 empty] | 2026-08-06 | 2026-08-12 |  |  | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-17 | 2026-08-17 | 86 | Q+P | Basir |  |  |  | AOP |  | NFL2 |  |  | Cut Ok | 2734 | 2734 | 0 | 0 | -9652 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 34 | Aug'1 |  |  | 28.07.26
OVS SPA | 47631 | 271NDG001NGTC2-6111 | 4026 | 1215 | 2026-05-23 | 2026-06-10 | AOP LS Dress w front half placket btn | Dress |  |  | 2026-06-20 | 2026-06-30 | 2026-07-01 | 2026-07-13 | 2026-07-14 | 2026-07-21 | 2026-07-25 | 2026-07-27 | 2026-08-01 | 2026-08-03 | 2026-08-05 | [6 empty] | 2026-08-06 | 2026-08-12 |  |  | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-17 | 2026-08-17 | 86 | N/2 | Basir |  |  |  | AOP |  | NCL |  |  | Ready Test Cut | 1214 | 1214 | 0 | 0 | -4026 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 34 | Aug'1
OVS SPA | 47632 | 271PJA005PYJC2-6111 | 9652 | 2510 | 2026-05-23 | 2026-06-10 | AOP LS Swt shirt w front half Placket btn and pant set | Top & BTM |  |  | 2026-06-20 | 2026-06-30 | 2026-07-01 | 2026-07-13 | 2026-07-14 | 2026-07-21 | 2026-07-25 | 2026-07-27 | 2026-08-01 | 2026-08-03 | 2026-08-05 | [6 empty] | 2026-08-06 | 2026-08-12 |  |  | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-17 | 2026-08-17 | 86 | N/2 | Basir |  |  |  | AOP |  | NCL |  |  | Ready Test Cut | 2510 | 2510 | 0 | 0 | -9652 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 34 | Aug'1
BS-ONL | 47762 | 15387324 | 1656 | 476 | 2026-05-12 | 2026-06-09 | LS o nk Reglan cut & sew contrast TS | TS |  |  | 2026-06-24 | 2026-06-30 | 2026-07-05 | 2026-07-18 |  |  | 2026-07-21 | 2026-07-21 | 2026-07-27 | 2026-07-29 | 2026-07-30 | [6 empty] | 2026-08-06 | 2026-08-07 |  |  | 2026-08-10 | 2026-08-12 | 2026-08-15 | 2026-09-07 | 2026-09-09 | 118 | N1 | Jannati | [5 empty] | NFL2 |  |  | Cut Ok | 476 | 476 | 0 | 1712 | 56 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46208 | 0 | 37 | Jul'3 |  |  | 24.06.26
BS-ONL | 47774 | 15388023 | 513 | 315 | 2026-05-12 | 2026-06-09 | LS Swt shirt w slve cut & sew contrast | Swt Shirt |  |  | 2026-06-26 | 2026-06-30 | 2026-07-05 | 2026-07-20 |  |  | 2026-07-20 | 2026-07-20 | 2026-07-25 | 2026-07-28 | 2026-07-29 | 2026-08-01 | 2026-08-04 |  |  |  |  | 2026-08-06 | 2026-08-07 |  |  | 2026-08-08 | 2026-08-10 | 2026-08-13 | 2026-09-07 | 2026-09-09 | 118 | Q | Jannati | Fr,Bk |  | Tibetan Red-513 pcs frt back 1 clr rub |  |  | NFL2 |  |  | Cut Ok | 257 | 257 | 0 | 538 | 25 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46208 | 0 | 37 | Jul'3 |  |  | 08.07.26
BS-ONL | 46301 2nd | 15376003 | 1504 | 797 | 2026-06-04 | 2026-06-13 | LS Swt hoodie w cuff rib and drawstring | Hoody |  |  | 2026-07-01 | 2026-07-07 | 2026-07-13 | 2026-07-28 |  |  | 2026-08-06 | 2026-07-30 | 2026-08-10 | 2026-08-12 | 2026-08-13 | 2026-08-15 | 2026-08-17 |  |  |  |  | 2026-08-20 | 2026-08-22 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-31 | 2026-09-28 | 2026-09-30 | 116 | K | Khalid | Chest |  | stone-752 pcs,,green-752 pcs all combo 1 clr rub print |  |  | NFL2 |  |  | Cut Ok | 788 | 788 | 0 | 1553 | 49 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46216 | 0 | 40 | Aug'2 |  |  | 18.07.26
BS-ONL | 46304 2nd | 15382100 | 3630 | 1882 | 2026-06-04 | 2026-06-13 | LS full zip Swt hoodie w drawstring | Hoody |  |  | 2026-07-01 | 2026-07-10 | 2026-07-15 | 2026-07-30 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 2026-08-19 | 2026-08-21 |  |  |  |  | 2026-08-24 | 2026-08-29 |  |  | 2026-08-31 | 2026-09-03 | 2026-09-08 | 2026-09-28 | 2026-09-30 | 116 | R | Khalid | Chest |  | stone-1714 pcs,,green-1916 pcs all combo 1 clr rub print |  |  | NFL2 |  |  | Cut Ok | 1885 | 1885 | 0 | 3711 | 81 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46218 | 0 | 40 | Aug'2 |  |  | 18.07.26
BS-ONL | 46300 2nd | 15375918 | 1700 | 800 | 2026-06-04 | 2026-06-13 | Swt pant w side pkt drawstring | Pant |  |  | 2026-07-02 | 2026-07-08 | 2026-07-14 | 2026-07-30 |  |  | 2026-08-06 | 2026-08-06 |  | 2026-08-12 | 2026-08-13 | 2026-08-15 | 2026-08-17 |  |  |  |  | 2026-08-20 | 2026-08-22 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-31 | 2026-09-28 | 2026-09-30 | 116 | P | Khalid | Thigh |  | stone-898 pcs,,green-802 pcs all combo 1 clr rub print |  |  | NFL2 |  |  | Cut Ok | 800 | 800 | 0 | 1759 | 59 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46217 | 0 | 40 | Aug'2 |  |  | 18.07.26
BS-ONL | 44669 2nd | 15370923 | 1584 | 397 | 2026-06-04 | 2026-06-13 | High waist Legging | Legging |  |  | 2026-07-08 | 2026-07-12 | 2026-07-18 | 2026-07-30 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 2026-08-19 | 2026-08-20 |  |  |  |  | 2026-08-24 | 2026-08-26 |  |  | 2026-08-28 | 2026-08-31 | 2026-09-10 | 2026-09-21 | 2026-09-23 | 109 | L2 | Khalid | Leg |  | black-1584 pcs 1 clr rub at one leg |  |  | NFL2 |  |  | Cut Ok | 397 | 397 | 0 | 1622 | 38 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46221 | 0 | 39 | Aug'2 |  |  | 08.08.26
BS-ONL | 47889 | 15386645/15395981 | 4935 | 2587 | 2026-06-10 | 2026-06-15 | Swt pant w side pkt drawstring | Pant |  |  | 2026-07-01 | 2026-07-11 | 2026-07-13 | 2026-07-30 |  |  | 2026-08-06 | 2026-08-06 | 2026-08-11 | 2026-08-12 | 2026-08-15 | 2026-08-14 | 2026-08-18 |  |  |  |  | 2026-08-18 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-30 | 2026-09-06 | 2026-09-21 | 2026-09-23 | 103 | P | Khalid | Leg |  | stone-2366 pcs,,green-2569 pcs both combo 1 clr rub print |  |  | NFL2 |  |  | Cut Ok | 2594 | 2594 | 0 | 5062 | 127 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46216 | 0 | 39 | Aug'2 |  |  | 07.08.26
OVS SPA | 47745 | 271TSHFTT519-6172 | 9836 | 2110 | 2026-06-10 | 2026-06-12 | SS o nk TS w cotrast edge at slve and btm | TS |  |  | 2026-07-10 | 2026-07-22 | 2026-07-24 | 2026-08-11 |  |  | 2026-08-10 | 2026-08-12 | 2026-08-17 | 2026-08-18 | 2026-08-20 | [6 empty] | 2026-08-21 | 2026-08-27 |  |  | 2026-08-28 | 2026-08-29 | 2026-08-31 | 2026-09-07 | 2026-09-07 | 89 | G2 | Shaker | [5 empty] | NFL1 |  |  | Cut Ok | 2036 | 2036 | 0 | 9972 | 136 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46227 | 0 | 37 | Aug'2 |  |  | 07.08.26
OVS SPA | 47746 | 271TSHFTT519S-6172 | 5268 | 1226 | 2026-06-10 | 2026-06-13 | YD TS w contrast nk slve btm edge | TS | 2026-07-01 | 2026-07-11 | 2026-07-13 | 2026-07-24 | 2026-07-25 | 2026-08-05 |  |  | 2026-08-08 | 2026-08-10 | 2026-08-15 | 2026-08-17 | 2026-08-19 | [6 empty] | 2026-08-20 | 2026-08-25 |  |  | 2026-08-26 | 2026-08-28 | 2026-08-31 | 2026-09-07 | 2026-09-07 | 89 | G2 | Shaker |  |  |  | YD |  | NFL1 |  |  | Cut Ok | 1225 | 1203 | -22 | 5443 | 175 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46228 | 0 | 37 | Aug'2 |  |  | 07.08.26
OVS SPA | 47833 | 271TSH085-6140 | 2075 | 211 | 2026-05-20 | 2026-06-12 | LS TS w sangallo collar and bk nk wood btn | TS |  |  | 2026-08-01 | 2026-08-11 | 2026-08-12 | 2026-08-26 |  |  | 2026-09-04 | 2026-09-05 | 2026-09-09 | 2026-09-10 | 2026-09-11 |  |  |  |  | 2026-09-12 | 2026-09-16 | 2026-09-16 | 2026-09-19 |  |  | 2026-09-21 | 2026-09-23 | 2026-09-25 | 2026-09-28 | 2026-09-28 | 131 | A | Salam |  | Chest | pink -2075 pcs 4 clr flat emb |  |  | NFL1 |  |  | Size Set Run | 211 | 211 | 0 | 0 | -2075 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46246 | 0 | 40 | Sep'1 |  |  | 13.08.26
OVS SPA | 47867 | 271TSH073-227 | 6412 | 737 | 2026-06-05 | 2026-06-12 | LS TS w raw cut in collar slvee and bk nk placket snap btn | TS |  |  | 2026-08-01 | 2026-08-11 | 2026-08-12 | 2026-08-24 |  |  | 2026-08-28 | 2026-08-25 | 2026-08-31 | 2026-09-01 | 2026-09-03 |  |  |  |  | 2026-09-04 | 2026-09-08 | 2026-09-09 | 2026-09-15 |  |  | 2026-09-16 | 2026-09-18 | 2026-09-20 | 2026-09-28 | 2026-09-28 | 115 | A | Salam |  | Chest | stalactite-6412 pcs 3 clr cording emb |  |  | NFL1 |  |  | Need Cut | 737 | 737 | 0 | 0 | -6412 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46246 | 0 | 40 | Sep'1 |  |  | 25.08.26
OVS SPA | 47868 | 271POL074-227 | 7232 | 820 | 2026-06-05 | 2026-06-12 | LS TS w sangallo collar and front blacket w plastic btn | TS |  |  | 2026-08-01 | 2026-08-10 | 2026-08-11 | 2026-08-22 |  |  | 2026-09-01 | 2026-09-01 | 2026-09-05 | 2026-09-07 | 2026-09-09 | [6 empty] | 2026-09-10 | 2026-09-17 |  |  | 2026-09-18 | 2026-09-21 | 2026-09-23 | 2026-09-28 | 2026-09-28 | 115 | A | Salam | [5 empty] | NFL1 |  |  | Cut Ok | 820 | 820 | 0 | 7289 | 57 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46245 | 0 | 40 | Sep'1 |  |  | 25.08.26
OVS SPA | 47866 | 271SWT072-227 | 8099 | 1390 | 2026-06-05 | 2026-06-12 | LS Swt shirt w cuff nk rib and btm woven insert lace and bacl nk placket btn | Swt Shirt |  |  | 2026-08-01 | 2026-08-11 | 2026-08-12 | 2026-08-25 |  |  | 2026-09-02 | 2026-08-27 | 2026-09-02 | 2026-09-03 | 2026-09-05 |  |  |  |  | 2026-09-07 | 2026-09-11 | 2026-09-12 | 2026-09-18 |  |  | 2026-09-19 | 2026-09-21 | 2026-09-24 | 2026-09-28 | 2026-09-28 | 115 | C | Salam |  | Chest | Navy-8099 pcs 1 clr flat emb and chochet flower attach at sewing |  | Lace | NFL1 |  |  | Cut Ok | 1390 | 1390 | 0 | 8228 | 129 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46246 | 0 | 40 | Sep'1 |  |  | 20.08.26
OVS SPA | 47865 | 271SWT568-6142 | 3875 | 836 | 2026-06-05 | 2026-06-12 | LS swt cardigan w full placket snap btn bon pkt and YD flat knit collar btm cuff and contrast cut & sew slve | Cardigan | 2026-07-20 | 2026-07-31 | 2026-08-01 | 2026-08-11 | 2026-08-12 | 2026-08-25 |  |  | 2026-08-31 | 2026-08-22 | 2026-08-31 | 2026-09-01 | 2026-09-03 |  |  |  |  | 2026-09-03 | 2026-09-10 | 2026-09-10 | 2026-09-19 |  |  | 2026-09-21 | 2026-09-23 | 2026-09-25 | 2026-09-28 | 2026-09-28 | 115 | N/2 | Salam |  | Chest | dress blue-3875 pcs left part 3 clr flat emb right part patch attach emb |  |  | NCL |  |  | Ready Test Cut | 836 | 836 | 0 | 0 | -3875 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46246 | 0 | 40 | Sep'1
OVS SPA | 47791 | 271SWT110-282 | 5420 | 1195 | 2026-05-20 | 2026-06-13 | LS Full placket snap btn jacket w cuff btm flat knit and side bon pkt | Jacket | 2026-07-20 | 2026-07-31 | 2026-08-01 | 2026-08-10 | 2026-08-11 | 2026-08-24 |  |  | 2026-09-01 | 2026-08-25 | 2026-09-02 | 2026-09-03 | 2026-09-05 |  |  |  |  | 2026-09-07 | 2026-09-10 | 2026-09-11 | 2026-09-17 |  |  | 2026-09-18 | 2026-09-21 | 2026-09-23 | 2026-09-28 | 2026-09-28 | 131 | B | Khairul |  | Chest | b.cream -5420 pcs two part 2 clr flat emb | YD |  | NFL1 |  |  | Ready Test Cut | 1195 | 290 | -905 | 0 | -5420 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46245 | 0 | 40 | Sep'1 |  |  | 05.09.26
OVS SPA | 47792 | 271SWT122-282 | 2567 | 720 | 2026-05-20 | 2026-06-13 | LS Full zipper jacket w collar ,slve contrast cut & sew and side bon pkt | Jacket | 2026-07-20 | 2026-07-31 | 2026-08-01 | 2026-08-10 | 2026-08-11 | 2026-08-24 |  |  | 2026-09-06 | 2026-09-14 | 2026-09-21 | 2026-09-22 | 2026-09-25 | 2026-09-24 | 2026-09-26 |  |  | 2026-09-26 | 2026-09-29 | 2026-09-29 | 2026-10-05 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-10 | 2026-10-10 | 143 | B | Khairul | Chest | Chest | b.cream -2567 pcs 6 clr rub 3 clr flat emb | YD |  | NFL1 |  |  | File Due | 720 | 720 | 0 | 0 | -2567 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46245 | 0 | 41 | Sep'1
BS-ONS | 47794 | 22036580 | 4659 | 1503 | 2026-05-19 | 2026-06-06 | SS o nk TS w nk rib | TS |  |  | 2026-06-25 | 2026-07-05 | 2026-07-15 | 2026-07-30 |  |  | 2026-08-08 | 2026-08-08 | 2026-08-15 | 2026-08-18 | 2026-08-21 | 2026-08-24 | 2026-08-28 |  |  |  |  | 2026-09-01 | 2026-09-06 |  |  | 2026-09-08 | 2026-09-12 | 2026-09-16 | 2026-11-09 | 2026-11-11 | 174 | G1 | Shakel | Fr & Bk & Nk |  | black ISA-1389 pcs frt 1 clr rub back photo print ,,c.dan-2331 pcs frt 1 clr pig back photo print ,,black bubblegum-1011 pcs frt photo print back no print |  | License order | NFL1 |  |  | Cut Run | 1503 | 737 | -766 | 2141 | -2518 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46218 | 0 | 46 | Aug'2 |  |  | 08.08.26
BS-ONS | 47812 | 22040834 | 493 | 282 | 2026-05-19 | 2026-06-06 | Swt Pant w waist belt and drawstring | Pant |  |  | 2026-07-01 | 2026-07-05 | 2026-07-10 | 2026-07-23 |  |  | 2026-08-06 | 2026-08-01 | 2026-08-08 | 2026-08-10 | 2026-08-10 | 2026-08-13 | 2026-08-13 |  |  |  |  | 2026-08-17 | 2026-08-18 |  |  | 2026-08-20 | 2026-08-25 | 2026-08-27 | 2026-10-19 | 2026-10-21 | 153 | B | Shovon | Thigh |  | forest fog-493 pcs 1 clr rub print |  |  | NFL1 |  |  | Cut Ok | 282 | 282 | 0 | 513 | 20 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 43 | Aug'1 |  |  | 27.07.26
BS-ONS | 47811 | 22039022 | 2127 | 1703 | 2026-05-19 | 2026-06-06 | LS Swt hoody w rib and zipper at kangaroo pkt | Hoody |  |  | 2026-06-20 | 2026-06-30 | 2026-07-11 | 2026-07-28 |  |  | 2026-08-03 | 2026-08-03 | 2026-08-10 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 |  |  |  |  | 2026-08-24 | 2026-08-28 |  |  | 2026-08-31 | 2026-09-03 | 2026-09-08 | 2026-10-18 | 2026-10-20 | 152 | C | Shovon | Fr,Bk |  | forest fog-1213 pcs,,black-914 pcs both combo frt back 1 clr rub |  |  | NFL1 |  |  | Cut Run | 1714 | 1714 | 0 | 1969 | -158 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46214 | 0 | 43 | Aug'2 |  |  | 27.07.26
BS-ONL | 44671 2nd | 15370927 | 3267 | 486 | 2026-06-04 | 2026-06-13 | SS o nk TS | TS |  |  | 2026-07-01 | 2026-07-07 | 2026-07-14 | 2026-07-30 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-12 | 2026-08-14 | 2026-08-15 | 2026-08-17 | 2026-08-19 |  |  |  |  | 2026-08-21 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-28 | 2026-08-31 | 2026-10-17 | 2026-10-19 | 135 | O1 | Khalid | Chest |  | green-1244 pcs,red-854 pcs,,P stone-1169 pcs all combo 1 clr rub print |  |  | NFL2 |  |  | Cut Ok | 486 | 486 | 0 | 3365 | 98 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46217 | 0 | 43 | Aug'2 |  |  | 08.08.26
BS-ONL | 47891 | 15386639 | 2140 | 735 | 2026-06-04 | 2026-06-13 | High waist Legging | Legging |  |  | 2026-07-10 | 2026-07-15 | 2026-07-20 | 2026-07-30 |  |  | 2026-08-15 | 2026-08-15 | 2026-08-21 | 2026-08-24 | 2026-08-25 | [6 empty] | 2026-08-27 | 2026-08-29 |  |  | 2026-08-31 | 2026-09-03 | 2026-09-07 | 2026-10-17 | 2026-10-19 | 135 | P | Khalid | [5 empty] | NFL2 |  |  | Cut Ok | 735 | 735 | 0 | 2162 | 22 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46223 | 0 | 43 | Aug'3 |  |  | 08.08.26
BS-ONL | 44663 3rd | 15363833 | 2039 | 345 | 2026-06-04 | 2026-06-13 | SS o nk TS | TS |  |  | 2026-07-01 | 2026-07-06 | 2026-07-16 | 2026-07-30 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-12 | 2026-08-14 | 2026-08-15 | 2026-08-18 | 2026-08-21 |  |  |  |  | 2026-08-24 | 2026-08-26 |  |  | 2026-08-28 | 2026-08-31 | 2026-09-07 | 2026-10-19 | 2026-10-21 | 137 | O1 | Khalid | Chest |  | red-522 pcs,,green-1517 pcs all comb 4 clr rub 1 clr gold metalic foil |  |  | NFL2 |  |  | Cut Ok | 345 | 345 | 0 | 2113 | 74 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46219 | 0 | 43 | Aug'2 |  |  | 08.08.26
BS-ONL | 46303 2nd | 15376006 | 2700 | 632 | 2026-06-04 | 2026-06-13 | Short pant w side plt drawstring | Shorts |  |  | 2026-07-08 | 2026-07-15 | 2026-07-20 | 2026-08-06 |  |  | 2026-08-12 | 2026-08-12 | 2026-08-19 | 2026-08-22 | 2026-08-24 | 2026-08-26 | 2026-08-28 |  |  |  |  | 2026-09-01 | 2026-09-04 |  |  | 2026-09-06 | 2026-09-08 | 2026-09-12 | 2026-11-21 | 2026-11-23 | 170 | P | Khalid | Thigh |  | stone-1388 pcs,,green-1312 pcs all combo 1 clr rub print |  |  | NFL2 |  |  | Cut Ok | 633 | 633 | 0 | 2772 | 72 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46223 | 0 | 48 | Aug'3 |  |  | 08.08.26
BS-ONL | 44668 2nd | 15370922 | 1044 | 166 | 2026-06-04 | 2026-06-13 | High Waist Shorts | Shorts |  |  | 2026-07-08 | 2026-07-12 | 2026-07-18 | 2026-07-30 |  |  | 2026-08-08 | 2026-08-08 | 2026-08-15 | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-21 |  |  |  |  | 2026-08-24 | 2026-08-25 |  |  | 2026-08-27 | 2026-08-31 | 2026-09-07 | 2026-11-21 | 2026-11-23 | 170 | L2 | Khalid | Leg |  | black-1044 pcs 1 clr rub at one leg |  |  | NFL2 |  |  | Cut Ok | 166 | 166 | 0 | 1068 | 24 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46221 | 0 | 48 | Aug'2 |  |  | 08.08.26
OVS SPA | 47830 | 271JOG053-6140 | 4502 | 577 | 2026-05-21 | 2026-06-12 | AOP LS dress w bk nk placket snap btn and Solid elasted legging | Top & BTM |  |  | 2026-07-25 | 2026-08-07 | 2026-08-10 | 2026-08-22 | 2026-08-24 | 2026-09-05 | 2026-09-10 | 2026-09-11 | 2026-09-16 | 2026-09-17 | 2026-09-18 | [6 empty] | 2026-09-19 | 2026-09-25 |  |  | 2026-09-26 | 2026-09-28 | 2026-09-30 | 2026-10-05 | 2026-10-05 | 137 | N/2 | Salam |  |  |  | AOP |  | NCL |  |  | Ready Test Cut | 577 | 577 | 0 | 0 | -4502 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46244 | 0 | 41 | Sep'2
OVS SPA | 47831 | 271JOG090-6140 | 9228 | 1173 | 2026-05-20 | 2026-06-12 | AOP LS dress w bk nk placket snap btn and Solid elasted legging | Top & BTM |  |  | 2026-08-18 | 2026-08-31 | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-09-24 | 2026-09-26 | 2026-09-28 | 2026-10-03 | 2026-10-05 | 2026-10-09 | [6 empty] | 2026-10-08 | 2026-10-17 |  |  | 2026-10-19 | 2026-10-21 | 2026-10-23 | 2026-10-26 | 2026-10-26 | 159 | C+E | Salam |  |  |  | AOP |  | NFL1 |  |  | Need Test Cut | 1173 | 0 | -1173 | 0 | -9228 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46266 | 0 | 44 | Oct'1 |  |  | 07.09.26
OVS SPA | 47832 | 271TSH065-6140 | 4428 | 502 | 2026-05-20 | 2026-06-12 | LS TS w sangallo collar and bk nk wood btn | TS |  |  | 2026-08-20 | 2026-08-31 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-25 | 2026-09-19 | 2026-09-26 | 2026-09-28 | 2026-09-30 |  |  |  |  | 2026-10-01 | 2026-10-06 | 2026-10-06 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-19 | 152 | A | Salam |  | Chest | c.dan-4428 pcs 1 clr flat emb |  |  | NFL1 |  |  | Cut Run | 502 | 502 | 0 | 4314 | -114 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46266 | 0 | 43 | Sep'3 |  |  | 28.08.26
OVS SPA | 47834 | 271TSH087-6140 | 3110 | 420 | 2026-05-20 | 2026-06-12 | LS AOP TS w self fab collar lace and snap btn at bk placket | TS |  |  | 2026-08-20 | 2026-08-31 | 2026-09-01 | 2026-09-10 | 2026-09-11 | 2026-09-18 | 2026-09-30 | 2026-09-25 | 2026-10-02 | 2026-10-03 | 2026-10-05 |  |  |  |  | 2026-10-06 | 2026-10-09 | 2026-10-10 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-17 | 2026-10-20 | 2026-10-26 | 2026-10-26 | 159 | A | Salam |  | Chest | White AOP- 3110 pcs 2 clr flat emb at collar | AOP | Lace | NFL1 |  |  | Need Test Cut | 420 | 0 | -420 | 0 | -3110 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46266 | 0 | 44 | Oct'1 |  |  | 28.08.26
OVS SPA | 47836 | 271TSH561-6140 | 3750 | 413 | 2026-05-22 | 2026-06-12 | LS TS w snap btn in placket and nk rib | TS |  |  | 2026-08-20 | 2026-08-31 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-25 | 2026-09-19 | 2026-09-26 | 2026-09-28 | 2026-09-30 |  |  |  |  | 2026-10-01 | 2026-10-06 | 2026-10-06 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-19 | 150 | A | Salam |  | Chest | stalacite-3750 pcs 2 clr flat all over emb at chest |  |  | NFL1 |  |  | Need Test Cut | 413 | 0 | -413 | 0 | -3750 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46266 | 0 | 43 | Sep'3 |  |  | 08.08.26
OVS SPA | 47835 | 271SWT093-6140 | 3200 | 616 | 2026-05-20 | 2026-06-12 | LS Swt shirt w nk cuff btm rib and bk nk placket snap btn | Swt Shirt |  |  | 2026-09-01 | 2026-09-12 | 2026-09-15 | 2026-09-30 |  |  | 2026-10-10 | 2026-10-07 | 2026-10-13 | 2026-10-14 | 2026-10-16 |  |  |  |  | 2026-10-17 | 2026-10-21 | 2026-10-22 | 2026-10-27 |  |  | 2026-10-28 | 2026-10-30 | 2026-11-02 | 2026-11-09 | 2026-11-09 | 173 | A | Salam |  | Chest | first blush-3200 pcs 2 clr flat emb |  |  | NFL1 |  |  | Need Cut | 617 | 617 | 0 | 0 | -3200 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46280 | 0 | 46 | Oct'2 |  |  | 28.08.26
OVS SPA | 47802 | 271PJA211-903 | 5584 | 1680 | 2026-06-05 | 2026-06-12 | LS TS w nk lace front placket btn and Elasted pant w drawstring | Top & BTM |  |  | 2026-08-01 | 2026-08-10 | 2026-08-11 | 2026-08-24 |  |  | 2026-09-09 | 2026-09-10 | 2026-09-15 | 2026-09-16 | 2026-09-17 | [6 empty] | 2026-09-18 | 2026-09-23 |  |  | 2026-09-24 | 2026-09-26 | 2026-09-28 | 2026-10-12 | 2026-10-12 | 129 | N/3 | Salam |  |  |  |  | Lace | NCL |  |  | Ready Test Cut | 1680 | 1680 | 0 | 0 | -5584 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46245 | 0 | 42 | Sep'2
OVS SPA | 47803 | 271PJA212-903 | 3200 | 995 | 2026-06-05 | 2026-06-12 | AOP LS TS w nk lace front placket btn and Elasted pant w drawstring | Top & BTM |  |  | 2026-08-01 | 2026-08-10 | 2026-08-11 | 2026-08-22 | 2026-08-24 | 2026-09-04 | 2026-09-09 | 2026-09-10 | 2026-09-15 | 2026-09-16 | 2026-09-17 | [6 empty] | 2026-09-18 | 2026-09-23 |  |  | 2026-09-24 | 2026-09-26 | 2026-09-28 | 2026-10-12 | 2026-10-12 | 129 | N/3 | Salam |  |  |  | AOP | Lace | NCL |  |  | Ready Test Cut | 995 | 995 | 0 | 0 | -3200 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46245 | 0 | 42 | Sep'2
OVS SPA | 47945 | 271NDG213-903 | 3337 | 1368 | 2026-06-05 | 2026-06-12 | LS long dress w lace at nk and front flacket Mop btn | Dress |  |  | 2026-08-01 | 2026-08-12 | 2026-08-14 | 2026-08-28 |  |  | 2026-09-05 | 2026-09-07 | 2026-09-12 | 2026-09-14 | 2026-09-15 | [6 empty] | 2026-09-16 | 2026-09-22 |  |  | 2026-09-23 | 2026-09-25 | 2026-09-28 | 2026-10-12 | 2026-10-12 | 129 | B | Salam |  |  |  |  | Lace | NFL1 |  |  | Need Cut | 1368 | 1368 | 0 | 0 | -3337 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46248 | 0 | 42 | Sep'2 |  |  | 02.09.26
OVS SPA | 47805 | 271NDG214-903 | 1930 | 788 | 2026-06-05 | 2026-06-12 | AOPLS long dress w lace at nk and front flacket Mop btn | Dress |  |  | 2026-08-01 | 2026-08-10 | 2026-08-11 | 2026-08-22 | 2026-08-24 | 2026-09-02 | 2026-09-05 | 2026-09-07 | 2026-09-12 | 2026-09-14 | 2026-09-15 | [6 empty] | 2026-09-16 | 2026-09-22 |  |  | 2026-09-23 | 2026-09-25 | 2026-09-28 | 2026-10-12 | 2026-10-12 | 129 | B | Salam |  |  |  | AOP | Lace | NFL1 |  |  | Cut Ok | 788 | 788 | 0 | 1952 | 22 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46245 | 0 | 42 | Sep'2 |  |  | 08.08.26
OVS SPA | 47806 | 271TRO586-6142 | 5556 | 875 | 2026-06-05 | 2026-06-12 | AOP Elasted pant w flat drawstring | Pant |  |  | 2026-08-20 | 2026-08-31 | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-09-25 | 2026-10-03 | 2026-10-05 | 2026-10-09 | 2026-10-10 | 2026-10-12 | [6 empty] | 2026-10-13 | 2026-10-17 |  |  | 2026-10-19 | 2026-10-21 | 2026-10-23 | 2026-10-26 | 2026-10-26 | 143 | N/2 | Salam |  |  |  | AOP |  | NCL |  |  | Ready Test Cut | 875 | 875 | 0 | 0 | -5556 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46266 | 0 | 44 | Oct'1
OVS SPA | 47807 | 271TRO600-6142 | 5556 | 903 | 2026-06-05 | 2026-06-12 | AOP Elasted pant w front pkt & flat drawstring | Pant |  |  | 2026-08-20 | 2026-08-31 | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-09-25 | 2026-10-07 | 2026-10-08 | 2026-10-13 | 2026-10-14 | 2026-10-16 | [6 empty] | 2026-10-17 | 2026-10-27 |  |  | 2026-10-28 | 2026-10-30 | 2026-11-02 | 2026-11-09 | 2026-11-09 | 157 | N/2 | Salam |  |  |  | AOP |  | NCL |  |  | Ready Test Cut | 903 | 727 | -176 | 0 | -5556 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46266 | 0 | 46 | Oct'2
OVS SPA | 47742 | 271MMP009MDR2-6111 | 4018 | 1490 | 2026-05-23 | 2026-06-11 | Long Plazo Pant | Pant |  |  | 2026-09-01 | 2026-09-11 | 2026-09-12 | 2026-09-24 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-12 | 2026-10-13 | 2026-10-14 | [6 empty] | 2026-10-15 | 2026-10-21 |  |  | 2026-10-22 | 2026-10-24 | 2026-10-26 | 2026-11-02 | 2026-11-02 | 163 | H | Basir | [5 empty] | NFL1 |  |  | File Due | 1490 | 0 | -1490 | 0 | -4018 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46277 | 0 | 45 | Oct'2
OVS SPA | 47743 | 271NDG038ETM3R-6111 | 4018 | 1020 | 2026-05-23 | 2026-06-11 | SS night dress w lace at shlder & slve opening | Dress |  |  | 2026-09-01 | 2026-09-11 | 2026-09-12 | 2026-09-24 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-12 | 2026-10-13 | 2026-10-14 | [6 empty] | 2026-10-15 | 2026-10-21 |  |  | 2026-10-22 | 2026-10-24 | 2026-10-26 | 2026-11-02 | 2026-11-02 | 163 | A | Basir |  |  |  |  | Lace | NFL1 |  |  | File Due | 1020 | 0 | -1020 | 0 | -4018 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46277 | 0 | 45 | Oct'2
OVS SPA | 47744 | 271GOW003MDR4-6111 | 1516 | 724 | 2026-05-23 | 2026-06-11 | LS night Grown w waist knot and lace at slve opening | Dress |  |  | 2026-09-01 | 2026-09-11 | 2026-09-12 | 2026-09-24 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-12 | 2026-10-13 | 2026-10-14 | [6 empty] | 2026-10-15 | 2026-10-21 |  |  | 2026-10-22 | 2026-10-24 | 2026-10-26 | 2026-11-02 | 2026-11-02 | 163 | N/3 | Basir |  |  |  |  | Lace | NCL |  |  | File Due | 724 | 0 | -724 | 0 | -1516 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46277 | 0 | 45 | Oct'2
OVS SPA | 47815 | 271NDG020ETM1N-6111 | 4018 | 1574 | 2026-05-23 | 2026-06-11 | 3/4 Slve o nk TS Night dress w lace at slve opening | Dress |  |  | 2026-09-01 | 2026-09-11 | 2026-09-12 | 2026-09-24 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-12 | 2026-10-13 | 2026-10-14 | [6 empty] | 2026-10-15 | 2026-10-21 |  |  | 2026-10-22 | 2026-10-24 | 2026-10-26 | 2026-11-02 | 2026-11-02 | 163 | A | Basir |  |  |  |  | Lace | NFL1 |  |  | File Due | 1574 | 0 | -1574 | 0 | -4018 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46277 | 0 | 45 | Oct'2
BS-ONL | 22041 61th | 15204712 | 6080 | 1267 | 2026-06-13 | 2026-06-17 | LDS LS TS | TS |  |  | 2026-10-07: 2026-07-05; 2026-10-08: 2026-07-05; 2026-10-14: 2026-07-10; 2026-10-16: 2026-07-11 | [6 empty] | 2026-07-17 | 2026-07-20 |  |  | 2026-07-22 | 2026-07-24 | 2026-07-27 | 2026-08-03 | 2026-08-05 | 51 | G1 | Imran |  |  |  |  | Stock fab from 43465 | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -6080 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 32 | Jul'1 |  |  | 16.06.26
BS-ONL | 45314 4th | 15200077 | 1540 | 382 | 2026-06-15 | 2026-06-17 | LDS LEGGING W WAIST PRINT | Legging |  |  | 2026-10-07: 2026-07-01; 2026-10-08: 2026-06-25; 2026-10-14: 2026-07-01; 2026-10-16: 2026-07-02 | 2026-07-04 | 2026-07-06 |  |  |  |  | 2026-07-08 | 2026-07-10 |  |  | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-20 | 2026-07-22 | 35 | L2 | Khalid | WAIST |  | 1 combo label print |  | stock fab from 41880 20th | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1540 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 30 | Jul'1 |  |  | 20.06.26
BS-ONL | 41880 24th | 15185296 | 6000 | 2195 | 2026-06-15 | 2026-06-17 | HW legging Drawstring at leg opening | Legging |  |  | 2026-07-13 | 2026-07-18 | 2026-07-20 | 2026-07-31 |  |  | 2026-07-17 | 2026-07-17 |  | 2026-08-01 | 2026-08-06 | 2026-08-08 | 2026-08-11 |  |  |  |  | 2026-08-12 | 2026-08-15 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-24 | 2026-08-26 | 70 | H | Khalid | Waist |  | 1 combo waist lettering logo print |  |  | NFL1 |  |  | Cut Ok | 2195 | 2195 | 0 | 6087 | 87 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46223 | 0 | 35 | Aug'1 |  |  | 08.07.26
BS-NMT | 47946 | 13264455 | 1395 | 651 | 2026-06-12 | 2026-06-17 | Swt Pant w side pkt | Pant |  |  | 2026-06-20 | 2026-06-25 | 2026-06-27 | 2026-07-04 |  |  | 2026-07-03 | 2026-07-03 | 2026-07-08 | 2026-07-10 | 2026-07-11 | [6 empty] | 2026-07-13 | 2026-07-15 |  |  | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-20 | 2026-07-22 | 38 | X | Tomal | [5 empty] | NFL3 |  |  | Cut Ok | 651 | 651 | 0 | 0 | -1395 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46200 | 0 | 30 | Jul'2 |  |  | 08.07.26
BS-ONL | 44700 4th | 15315774 | 1452 | 899 | 2026-06-17 | 2026-06-20 | LS O NK SWT SHIRT | Swt Shirt |  |  | 2026-06-24 | 2026-06-30 | 2026-07-01 | 2026-07-09 |  |  | 2026-07-10 | 2026-07-05 |  | 2026-07-10 | 2026-07-11 |  |  |  |  | 2026-07-13 | 2026-07-18 | 2026-07-20 | 2026-07-22 |  |  | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-27 | 2026-07-29 | 40 | Q | Zahirul |  | Slv | black-1452 pcs BOTH SLV CUT OUT EMB |  |  | NFL2 |  |  | Cut Ok | 899 | 899 | 0 | 0 | -1452 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 31 | Jul'2 |  |  | 27.06.26
GBX-New Look | 47936 | 915-34480 | 18715 | 2043 | 2026-06-13 | 2026-06-16 | SS reglan contrast slve TS | TS |  |  | 2026-06-20 | 2026-06-27 | 2026-06-27 | 2026-07-08 |  |  | 2026-07-04 | 2026-07-04 | 2026-07-09 | 2026-07-11 | 2026-07-15 | [6 empty] | 2026-07-13 | 2026-07-23 |  |  | 2026-07-24 | 2026-07-24 | 2026-07-25 | 2026-07-25 | 2026-07-26 | 42 | N/2 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 2043 | 2043 | 0 | 0 | -18715 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46200 | 0 | 31 | Jul'2
UTG-(Even & Odd) | 44650 2nd | BAD2956A | 700 | 309 | 2026-06-11 | 2026-06-18 | LDS LS MINIDRESS | DRESS |  |  | 2026-06-23 | 2026-06-29 | 2026-06-30 | 2026-07-10 |  |  | 2026-07-11 | 2026-07-13 |  | 2026-07-17 | 2026-07-18 | [6 empty] | 2026-07-20 | 2026-07-21 |  |  | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-27 | 44 | N/3 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 309 | 309 | 0 | 0 | -700 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46203 | 0 | 31 | Jul'2
UTG-(Even & Odd) | 43622 5th | BAD2892D | 7500 | 510 | 2026-06-11 | 2026-06-18 | LDS TANK TOP W LACE | TANK TOP |  |  | 2026-06-23 | 2026-06-30 | 2026-06-30 | 2026-07-11 |  |  | 2026-07-07 | 2026-07-08 |  | 2026-07-13 | 2026-07-14 | [6 empty] | 2026-07-15 | 2026-07-20 |  |  | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-25 | 2026-07-27 | 44 | L | Rony | [5 empty] | NFL2 |  |  | Cut Ok | 510 | 510 | 0 | 0 | -7500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46203 | 0 | 31 | Jul'2 |  |  | 01.07.26
UTG-(Even & Odd) | 43618 5th | BAD2889D | 2400 | 400 | 2026-06-11 | 2026-06-18 | LDS SL SWAMSUIT | SUIT |  |  | 2026-06-23 | 2026-06-29 | 2026-06-30 | 2026-07-10 |  |  | 2026-07-10 | 2026-07-11 |  | 2026-07-15 | 2026-07-16 | [6 empty] | 2026-07-16 | 2026-07-20 |  |  | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-25 | 2026-07-27 | 44 | N/3 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 400 | 400 | 0 | 0 | -2400 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46203 | 0 | 31 | Jul'2
BS-NMT | 47947 | 13240796 | 805 | 112 | 2026-06-10 | 2026-06-22 | SS o nk TS | TS |  |  | 2026-07-06 | 2026-07-10 | 2026-07-20 | 2026-07-28 |  |  | 2026-08-01 | 2026-08-01 | 2026-08-10 | 2026-08-12 | 2026-08-12 |  |  | 2026-08-14 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-18 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-24 | 2026-08-26 | 75 | T1 | Tomal | Stone |  | white-805 pcs HP stone at chest |  |  | NFL3 |  |  | Cut Ok | 112 | 112 | 0 | 0 | -805 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46223 | 0 | 35 | Aug'2 |  |  | 06.08.26
BS-NMT | 47808 | 13267415 | 795 | 202 | 2026-05-15 | 2026-06-20 | YD LS Puff slve swt shirt w cuff btm rib | Swt Shirt | 2026-06-25 | 2026-06-30 | 2026-07-04 | 2026-07-10 | 2026-07-13 | 2026-07-18 |  |  | 2026-07-17 | 2026-07-17 | 2026-07-22 | 2026-07-24 | 2026-07-24 | [6 empty] | 2026-07-27 | 2026-07-28 |  |  | 2026-07-29 | 2026-07-31 | 2026-08-01 | 2026-08-03 | 2026-08-05 | 80 | T2 | Shamoly |  |  |  | YD |  | NFL3 |  |  | Cut Ok | 202 | 202 | 0 | 0 | -795 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46216 | 0 | 32 | Jul'3 |  |  | 13.07.26
BS-NMT | 47809 | 13267416 | 795 | 137 | 2026-05-15 | 2026-06-20 | YD Elasted Legging | Legging | 2026-06-25 | 2026-06-30 | 2026-07-04 | 2026-07-10 | 2026-07-13 | 2026-07-17 |  |  | 2026-07-18 | 2026-07-18 | 2026-07-23 | 2026-07-25 | 2026-07-25 | [6 empty] | 2026-07-28 | 2026-07-29 |  |  | 2026-07-30 | 2026-08-01 | 2026-08-01 | 2026-08-03 | 2026-08-05 | 80 | W2 | Shamoly |  |  |  | YD |  | NFL3 |  |  | Cut Ok | 137 | 137 | 0 | 0 | -795 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46216 | 0 | 32 | Jul'3 |  |  | 13.07.26
BS-NMT | 45154 2nd | 13238870 | 1005 | 161 | 2026-06-10 | 2026-06-20 | YD LS TS w Slve frill | TS | 2026-07-01 | 2026-07-05 | 2026-07-10 | 2026-07-15 | 2026-07-18 | 2026-07-24 |  |  | 2026-07-28 | 2026-07-28 | 2026-08-06 | 2026-08-08 | 2026-08-08 | 2026-08-11 | 2026-08-11 |  |  |  |  | 2026-08-13 | 2026-08-14 |  |  | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-24 | 2026-08-26 | 75 | T2 | Jafar | Nk |  | 1 combo label print | YD |  | NFL3 |  |  | Cut Ok | 161 | 161 | 0 | 1038 | 33 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46221 | 0 | 35 | Aug'1 |  |  | 14.07.26
BS-NMT | 45153 2nd | 13238875 | 1005 | 146 | 2026-06-10 | 2026-06-20 | YD legging w back pkt | LEGGING | 2026-07-01 | 2026-07-06 | 2026-07-10 | 2026-07-17 | 2026-07-20 | 2026-07-25 |  |  | 2026-07-29 | 2026-07-29 | 2026-08-07 | 2026-08-09 | 2026-08-10 | 2026-08-12 | 2026-08-13 |  |  |  |  | 2026-08-15 | 2026-08-17 |  |  | 2026-08-18 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 2026-08-26 | 75 | Y | Jafar | Waist |  | 1 combo label print | YD |  | NFL3 |  |  | Cut Ok | 146 | 146 | 0 | 0 | -1005 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46223 | 0 | 35 | Aug'1 |  |  | 14.07.26
BS-NMT | 43330 11th | 13197665 | 4320 | 1943 | 2026-06-17 | 2026-06-20 | LS Swt Zip hoodie w kangro pkt | Hoody |  |  | 2026-07-26 | 2026-07-10 | 2026-07-12 | 2026-07-27 |  |  | 2026-07-25 | 2026-07-25 |  | 2026-07-30 | 2026-08-06 | [6 empty] | 2026-08-06 | 2026-08-12 |  |  | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-17 | 2026-08-19 | 61 | S+T1 | Jafar | [5 empty] | NFL3 |  |  | Cut Ok | 1942 | 1942 | 0 | 4503 | 183 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46215 | 0 | 34 | Jul'3 |  |  | 18.07.26
BS-NMT | 43327 15th | 13235093 | 1020 | 377 | 2026-06-17 | 2026-06-20 | Swt Pant w pkt waist belt drawstring | Pant |  |  | 2026-07-06 | 2026-07-10 | 2026-07-15 | 2026-07-27 |  |  | 2026-08-01 | 2026-08-01 |  | 2026-08-07 | 2026-08-08 | [6 empty] | 2026-08-10 | 2026-08-11 |  |  | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-17 | 2026-08-19 | 61 | X | Jafar | [5 empty] | NFL3 |  |  | Cut Ok | 378 | 378 | 0 | 0 | -1020 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46218 | 0 | 34 | Aug'1 |  |  | 13.07.26
BS-NMT | 43321 25th | 13205781 | 2040 | 262 | 2026-06-17 | 2026-06-20 | Legging | Legging |  |  | 2026-06-26 | 2026-06-30 | 2026-07-05 | 2026-07-15 |  |  | 2026-07-15 | 2026-07-15 |  | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 |  |  |  |  | 2026-07-24 | 2026-07-25 |  |  | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-08-03 | 2026-08-05 | 47 | W2 | Jafar | Waist |  | 1 combo label print |  |  | NFL3 |  |  | Cut Ok | 262 | 262 | 0 | 2096 | 56 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46208 | 0 | 32 | Jul'2 |  |  | 13.07.26
BS-NMT | 43320 18th | 13216876 | 3055 | 277 | 2026-06-10 | 2026-06-20 | LS collar body w snap btn | Body |  |  | 2026-07-01 | 2026-07-05 | 2026-07-12 | 2026-07-22 |  |  | 2026-07-22 | 2026-07-22 |  | 2026-07-27 | 2026-07-28 | 2026-07-30 | 2026-07-31 |  |  |  |  | 2026-08-06 | 2026-08-10 |  |  | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-17 | 2026-08-19 | 68 | T2 | Jafar | Nk |  | 1 combo label print |  |  | NFL3 |  |  | Cut Ok | 278 | 278 | 0 | 0 | -3055 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46215 | 0 | 34 | Jul'3 |  |  | 25.07.26
BS-ONL | 44919 4th | 15322888 | 4380 | 1814 | 2026-06-13 | 2026-06-17 | LS crew nk Swt Shirt | Swt Shirt |  |  | 2026-06-20 | 2026-06-27 | 2026-07-01 | 2026-07-10 |  |  | 2026-07-10 | 2026-07-10 |  | 2026-07-15 | 2026-07-18 | 2026-07-18 | 2026-07-29 |  |  | 2026-07-29 | 2026-07-31 | 2026-08-01 | 2026-08-07 |  |  | 2026-08-08 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-12 | 58 | N2 | Mainul | Fr & Bk & Slv | Chest | c.dan blue-2145 pcss,,c.dan anis-2235 pcs both combo frt back both slve 1 clr pig stripe placement print and frt 1 clr lurex emb |  |  | NFL2 |  |  | Cut Ok | 1813 | 1813 | 0 | 0 | -4380 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 33 | Jul'2 |  |  | 07.07.26
BS-ONL | 43102 6th | 15366301 | 4800 | 752 | 2026-06-19 | 2026-06-20 | SS o nk TS | TS |  |  | 2026-06-25 | 2026-06-30 | 2026-07-01 | 2026-07-15 |  |  | 2026-07-15 | 2026-07-15 |  | 2026-07-20 | 2026-07-22 | 2026-07-22 | 2026-07-25 |  |  |  |  | 2026-07-27 | 2026-07-31 |  |  | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-10 | 2026-08-12 | 52 | K | Mainul | Chest |  | black-1200 pcs,,c.dan-1200 pcs,,green-1200 pcs,,brown-1200 pcs both combo 1 clr gltr |  |  | NFL2 |  |  | Cut Ok | 752 | 752 | 0 | 0 | -4800 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 33 | Jul'2 |  |  | 25.06.26
BS-ONL | 27204 55th | 15323159 | 12240 | 2932 | 2026-06-18 | 2026-06-20 | LS o nk TS | TS |  |  | 2026-06-25 | 2026-07-04 | 2026-07-02 | 2026-07-18 |  |  | 2026-07-17 | 2026-07-17 |  | 2026-07-21 | 2026-07-25 | [6 empty] | 2026-07-25 | 2026-07-30 |  |  | 2026-08-01 | 2026-08-06 | 2026-08-08 | 2026-08-10 | 2026-08-12 | 53 | F | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 2932 | 2932 | 0 | 0 | -12240 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46205 | 0 | 33 | Jul'3 |  |  | 07.07.26
BS-ONL | 43969 39th | 15270390 | 3840 | 621 | 2026-06-18 | 2026-06-20 | SS o nk TS | TS |  |  | 2026-06-26 | 2026-07-01 | 2026-07-05 | 2026-07-15 |  |  | 2026-07-15 | 2026-07-15 |  | 2026-07-20 | 2026-07-21 | [6 empty] | 2026-07-23 | 2026-07-25 |  |  | 2026-07-28 | 2026-07-29 | 2026-08-07 | 2026-08-17 | 2026-08-19 | 60 | ZA1 | Dalim | [5 empty] | NFL3 |  |  | Cut Ok | 621 | 621 | 0 | 3868 | 28 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46208 | 0 | 34 | Jul'2 |  |  | 01.07.26
GBX-New Look | 47937 | 915-34480 | 6080 | 696 | 2026-06-13 | 2026-06-16 | SS reglan AOP contrast slve TS | TS |  |  | 2026-06-23 | 2026-06-26 | 2026-06-27 | 2026-07-09 | 2026-07-11 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-21 | 2026-07-22 | 2026-07-24 | [6 empty] | 2026-07-24 | 2026-07-28 |  |  | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-01 | 49 | N/1 | Shofi |  |  |  | AOP |  | NCL |  |  | Ready Test Cut | 696 | 696 | 0 | 0 | -6080 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46200 | 0 | 31 | Jul'3
GBX-New Look | 47738 2nd | 9638422 | 5110 | 1771 | 2026-06-19 | 2026-06-20 | Dress w inner shorts | Dress |  |  | 2026-06-26 | 2026-07-05 | 2026-07-05 | 2026-07-20 |  |  | 2026-07-20 | 2026-07-20 |  | 2026-07-24 | 2026-07-27 | [6 empty] | 2026-07-27 | 2026-07-31 |  |  | 2026-08-01 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 50 | N/2 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 1771 | 1771 | 0 | 0 | -5110 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46208 | 0 | 33 | Jul'3
GBX-New Look | 48133 | OVS 0567 | 5050 | 1093 | 2026-06-19 | 2026-06-20 | LS o nk TS | TS |  |  | 2026-06-25 | 2026-07-01 | 2026-07-04 | 2026-07-13 |  |  | 2026-07-13 | 2026-07-13 | 2026-07-18 | 2026-07-20 | 2026-07-23 | 2026-07-22 | 2026-07-27 |  |  |  |  | 2026-07-27 | 2026-07-31 |  |  | 2026-08-01 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 50 | N/1 | Shofi | Chest,Nk |  | Burgundy-5050 pcs Photo print w 1 clr foil print |  |  | NCL |  |  | Ready Test Cut | 1093 | 1093 | 0 | 0 | -5050 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46207 | 0 | 33 | Jul'2
GBX-New Look | 48134 | Indo-201702 | 1620 | 363 | 2026-06-19 | 2026-06-20 | SS o nk TS | TS |  |  | 2026-07-01 | 2026-07-04 | 2026-07-07 | 2026-07-15 |  |  | 2026-07-15 | 2026-07-15 | 2026-07-20 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-27 |  |  |  |  | 2026-07-29 | 2026-07-30 |  |  | 2026-08-01 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 50 | N/1 | Shofi | Chest,Nk |  | D.grey-1620 pcs 5 clr rub 1 clr gltr print |  |  | NCL |  |  | Ready Test Cut | 364 | 364 | 0 | 0 | -1620 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46210 | 0 | 33 | Jul'3
GBX-New Look | 48135 | Indo-201700 | 820 | 193 | 2026-06-19 | 2026-06-20 | SS o nk TS | TS |  |  | 2026-07-01 | 2026-07-02 | 2026-07-06 | 2026-07-15 |  |  | 2026-07-16 | 2026-07-16 | 2026-07-22 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 2026-07-29 |  |  |  |  | 2026-08-01 | 2026-08-01 |  |  | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-08 | 2026-08-09 | 50 | N/1 | Shofi | Chest,Nk |  | D.grey-820 pcs photo print w 1 clr foil print |  |  | NCL |  |  | Ready Test Cut | 194 | 194 | 0 | 0 | -820 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46209 | 0 | 33 | Jul'3
GBX-New Look | 48137 | Indo-201694 | 515 | 128 | 2026-06-19 | 2026-06-20 | SS o nk TS | TS |  |  | 2026-06-27 | 2026-06-30 | 2026-07-06 | 2026-07-15 |  |  | 2026-07-16 | 2026-07-16 | 2026-07-21 | 2026-07-23 | 2026-07-23 | 2026-07-25 | 2026-07-28 |  |  |  |  | 2026-08-01 | 2026-08-01 |  |  | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-08 | 2026-08-09 | 50 | N/1 | Shofi | Chest,Nk |  | Red-515 pcs 5 clr pig print |  |  | NCL |  |  | Ready Test Cut | 129 | 129 | 0 | 0 | -515 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46209 | 0 | 33 | Jul'3
GBX-New Look | 48136 | Indo-201693 | 820 | 193 | 2026-06-19 | 2026-06-20 | SS o nk TS | TS |  |  | 2026-06-28 | 2026-06-30 | 2026-07-06 | 2026-07-15 |  |  | 2026-07-16 | 2026-07-16 | 2026-07-21 | 2026-07-23 | 2026-07-23 | 2026-07-25 | 2026-07-28 |  |  |  |  | 2026-07-30 | 2026-07-31 |  |  | 2026-08-01 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 50 | N/1 | Shofi | Chest,Nk |  | off white-820 pcs pig photo print |  |  | NCL |  |  | Ready Test Cut | 194 | 194 | 0 | 0 | -820 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46209 | 0 | 33 | Jul'3
GBX-New Look | 48141 | CONFJTSS37656 | 19042 | 2450 | 2026-06-22 | 2026-06-23 | YD SS o nk TS | TS | 2026-07-01 | 2026-07-11 | 2026-07-08 | 2026-07-20 | 2026-07-17 | 2026-07-25 |  |  | 2026-07-23 | 2026-07-23 | 2026-07-27 | 2026-07-29 | 2026-08-06 | [6 empty] | 2026-08-01 | 2026-08-12 |  |  | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-09-12 | 2026-09-12 | 82 | N/1 | Sifat |  |  |  | YD |  | NCL |  |  | Need Test Cut | 0 | 0 | 0 | 0 | -19042 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46220 | 0 | 37 | Jul'3
GBX-New Look | 48141 2nd | 9665076 | 18433 | 2399 | 2026-06-22 | 2026-06-23 | YD SS o nk TS | TS | 2026-07-01 | 2026-07-11 | 2026-07-08 | 2026-07-20 | 2026-07-17 | 2026-07-25 |  |  | 2026-07-23 | 2026-09-01 | 2026-07-27 | 2026-09-08 | 2026-09-12 | [6 empty] | 2026-09-10 | 2026-08-12 |  |  | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-09-26 | 2026-09-27 | 96 | N/1 | Sifat |  |  |  | YD |  | NCL |  |  | Need Test Cut | 2431 | 19 | -2412 | 0 | -18433 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46220 | 0 | 40 | Sep'1
UTG-AF | 42480 4th | BAD1059mamaAM | 2000 | 403 | 2026-06-13 | 2026-06-18 | maternity legging | Legging |  |  | 2026-06-22 | 2026-06-29 | 2026-06-30 | 2026-07-13 |  |  | 2026-07-20 | 2026-07-21 |  | 2026-07-23 | 2026-07-24 | [6 empty] | 2026-07-25 | 2026-07-28 |  |  | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-08 | 2026-08-10 | 56 | N/3 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 402 | 402 | 0 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46203 | 0 | 33 | Jul'3
UTG-AF | 30405 7th | BAD2498mamaI | 1200 | 512 | 2026-06-13 | 2026-06-18 | HW Long plazo | Plazo |  |  | 2026-06-22 | 2026-06-29 | 2026-06-30 | 2026-07-13 |  |  | 2026-07-20 | 2026-07-21 |  | 2026-07-23 | 2026-07-24 | [6 empty] | 2026-07-25 | 2026-07-27 |  |  | 2026-07-28 | 2026-07-30 | 2026-07-31 | 2026-08-08 | 2026-08-10 | 56 | N/3 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 512 | 512 | 0 | 0 | -1200 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46203 | 0 | 33 | Jul'3
UTG-AF | 46838 2nd | BAD3182MamaA | 3000 | 750 | 2026-06-13 | 2026-06-18 | LS boat nk TS | TS |  |  | 2026-07-01 | 2026-07-08 | 2026-07-10 | 2026-07-22 |  |  | 2026-07-25 | 2026-07-27 |  | 2026-07-30 | 2026-07-31 | [6 empty] | 2026-08-07 | 2026-08-11 |  |  | 2026-08-12 | 2026-08-14 | 2026-08-17 | 2026-08-22 | 2026-08-24 | 70 | G1 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 750 | 750 | 0 | 0 | -3000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 35 | Jul'3 |  |  | 22.07.26
UTG-AF | 47874 | BAD3221 | 600 | 100 | 2026-06-13 | 2026-06-18 | LS V nk TS w nk Lace | TS |  |  | 2026-07-01 | 2026-07-08 | 2026-07-10 | 2026-07-20 |  |  | 2026-07-25 | 2026-07-27 | 2026-07-31 | 2026-08-10 | 2026-08-11 | [6 empty] | 2026-08-13 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 70 | N/3 | Rana |  |  |  |  | Lace | NCL |  |  | Cut Ok | 100 | 100 | 0 | 0 | -600 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 35 | Aug'1
UTG-AF | 45092 8th | BAD2959mamaB | 2000 | 515 | 2026-06-13 | 2026-06-18 | AOP Long legging | Legging |  |  | 2026-07-25 | 2026-07-01 | 2026-07-02 | 2026-07-13 | 2026-07-14 | 2026-07-18 | 2026-07-17 | 2026-07-18 |  | 2026-07-22 | 2026-07-23 | [6 empty] | 2026-07-24 | 2026-07-27 |  |  | 2026-07-28 | 2026-07-29 | 2026-07-31 | 2026-08-08 | 2026-08-10 | 56 | D1 | Rana |  |  |  | AOP |  | NFL1 |  |  | Cut Ok | 515 | 515 | 0 | 0 | -2000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46205 | 0 | 33 | Jul'3 |  |  | 29.06.26
UTG-AF | 46152 6th | BAD0985AK/BAD3245 | 7400 | 1686 | 2026-06-13 | 2026-06-18 | LDS O NK LS TS | TS |  |  | 2026-07-01 | 2026-07-10 | 2026-07-11 | 2026-07-24 |  |  | 2026-07-24 | 2026-07-25 |  | 2026-07-29 | 2026-07-31 | [6 empty] | 2026-08-07 | 2026-08-13 |  |  | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 70 | G1 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 1686 | 1686 | 0 | 7766 | 366 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46214 | 0 | 35 | Jul'3 |  |  | 22.07.26
UTG-AF | 40675 10th | BAD1546mamaY | 5400 | 1325 | 2026-06-13 | 2026-06-18 | LDS BOAT NK LS TS | TS |  |  | 2026-07-01 | 2026-07-10 | 2026-07-11 | 2026-07-24 |  |  | 2026-07-25 | 2026-07-27 |  | 2026-07-29 | 2026-07-31 | [6 empty] | 2026-08-08 | 2026-08-13 |  |  | 2026-08-14 | 2026-08-17 | 2026-08-19 | 2026-08-22 | 2026-08-24 | 70 | G2 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 1326 | 1326 | 0 | 0 | -5400 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46214 | 0 | 35 | Jul'3 |  |  | 22.07.26
UTG-AF | 45294 2nd | BAD2540NursD | 2400 | 770 | 2026-06-13 | 2026-06-18 | LDS LS RIB WRAP TOP | TS |  |  | 2026-07-01 | 2026-07-13 | 2026-07-14 | 2026-07-25 |  |  | 2026-07-31 | 2026-08-01 |  | 2026-08-07 | 2026-08-08 | [6 empty] | 2026-08-10 | 2026-08-14 |  |  | 2026-08-15 | 2026-08-17 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 70 | E | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 770 | 770 | 0 | 2482 | 82 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46217 | 0 | 35 | Aug'1 |  |  | 24.07.26
UTG-AF | 43665 5th | BAD2229NursI | 2500 | 1155 | 2026-06-13 | 2026-06-18 | LDS LS NURSING TS | TS |  |  | 2026-07-01 | 2026-07-10 | 2026-07-11 | 2026-07-22 |  |  | 2026-08-01 | 2026-08-06 |  | 2026-08-08 | 2026-08-10 | [6 empty] | 2026-08-11 | 2026-08-14 |  |  | 2026-08-15 | 2026-08-18 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 70 | E | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 1155 | 1155 | 0 | 0 | -2500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46214 | 0 | 35 | Aug'1 |  |  | 28.07.26
UTG-AF | 44281 2nd | BAD2913mamaA | 400 | 115 | 2026-06-13 | 2026-06-18 | LS wrap TS w lace | TS |  |  | 2026-07-01 | 2026-07-06 | 2026-07-10 | 2026-07-22 |  |  | 2026-08-06 | 2026-08-08 |  | 2026-08-11 | 2026-08-12 | [6 empty] | 2026-08-13 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 70 | E | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 115 | 115 | 0 | 424 | 24 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 35 | Aug'2 |  |  | 28.07.26
UTG-AF | 44613 6th | BAD2908mamaF | 4400 | 1084 | 2026-06-13 | 2026-06-18 | LDS O NK TS TS | TS |  |  | 2026-07-01 | 2026-07-10 | 2026-07-11 | 2026-07-24 |  |  | 2026-07-30 | 2026-08-01 |  | 2026-08-06 | 2026-08-08 | [6 empty] | 2026-08-10 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 70 | D2 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 1084 | 1084 | 0 | 0 | -4400 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46214 | 0 | 35 | Aug'1 |  |  | 29.06.26
UTG-AF | 41712 14th | BAD2323mamaZ | 3600 | 924 | 2026-06-13 | 2026-06-18 | LDS LONG LEGGINGS | LEGGING |  |  | 2026-06-22 | 2026-06-30 | 2026-07-01 | 2026-07-14 |  |  | 2026-07-20 | 2026-07-21 |  | 2026-07-24 | 2026-07-25 | [6 empty] | 2026-07-27 | 2026-07-31 |  |  | 2026-08-01 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-10 | 56 | K1 | Rana | [5 empty] | NFL2 |  |  | Cut Ok | 924 | 924 | 0 | 0 | -3600 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 33 | Jul'3 |  |  | 29.06.26
UTG-AF | 42965 16th | BAD2530mamaAD/BAD3219mama | 9600 | 3999 | 2026-06-13 | 2026-06-18 | AOP & Sollid Long Plazoo | Plazo |  |  | 2026-06-22 | 2026-06-30 | 2026-07-01 | 2026-07-11 | 2026-07-13 | 2026-07-20 | 2026-07-20 | 2026-07-21 |  | 2026-07-24 | 2026-07-27 | [6 empty] | 2026-07-27 | 2026-08-01 |  |  | 2026-08-01 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-10 | 56 | K1 | Rana |  |  |  | AOP |  | NFL2 |  |  | Cut Ok | 4000 | 4000 | 0 | 0 | -9600 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 33 | Jul'3 |  |  | 29.06.26
UTG-AF | 42481 12th | BAD1279mAD/BAD2431mF | 7000 | 1361 | 2026-06-13 | 2026-06-18 | YD & Solid LDS NUIRSING TANK TOP | Tank Top | 2026-06-23 | 2026-06-30 | 2026-07-01 | 2026-07-11 | 2026-07-13 | 2026-07-24 |  |  | 2026-07-21 | 2026-08-01 |  | 2026-08-06 | 2026-08-08 | [6 empty] | 2026-08-10 | 2026-08-17 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 70 | K1 | Rana |  |  |  | YD |  | NFL2 |  |  | Cut Ok | 1361 | 1361 | 0 | 7288 | 288 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46216 | 0 | 35 | Aug'1 |  |  | 20.07.26
UTG-AF | 28918 5th | BAD1056mamaN | 3000 | 596 | 2026-06-13 | 2026-06-18 | LS o nk TS w side gathering | TS |  |  | 2026-07-01 | 2026-07-09 | 2026-07-10 | 2026-07-22 |  |  | 2026-08-07 | 2026-08-08 |  | 2026-08-11 | 2026-08-12 | [6 empty] | 2026-08-13 | 2026-08-17 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 70 | G2 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 596 | 596 | 0 | 0 | -3000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 35 | Aug'2 |  |  | 28.07.26
UTG-AF | 43664 2nd | BAD1298mamaZ | 7000 | 1847 | 2026-06-13 | 2026-06-18 | YD LDS BOAT NK LS TS | TS | 2026-06-25 | 2026-07-04 | 2026-07-06 | 2026-07-18 | 2026-07-20 | 2026-07-27 |  |  | 2026-07-30 | 2026-07-31 |  | 2026-08-07 | 2026-08-10 | [6 empty] | 2026-08-10 | 2026-08-17 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 70 | D1 | Rana |  |  |  | YD |  | NFL1 |  |  | Cut Ok | 1846 | 1846 | 0 | 7306 | 306 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46223 | 0 | 35 | Aug'1 |  |  | 22.07.26
UTG-AF | 40674 3rd | BAD2660mamaB | 900 | 184 | 2026-06-13 | 2026-06-18 | LS TS W POPLINE AT BOTTOM AN CUFFF | TS |  |  | 2026-07-01 | 2026-07-08 | 2026-07-10 | 2026-07-22 |  |  | 2026-07-31 | 2026-08-01 | 2026-08-08 | 2026-08-10 | 2026-08-11 | [6 empty] | 2026-08-12 | 2026-08-14 |  |  | 2026-08-15 | 2026-08-17 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 70 | N/3 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 184 | 184 | 0 | 0 | -900 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 35 | Aug'1
UTG-AF | 47928 | BAD3247 | 700 | 200 | 2026-06-13 | 2026-06-18 | LS Shirt w ful placket btn w waist elastic | Shirt |  |  | 2026-07-30 | 2026-07-30 | 2026-08-01 | 2026-08-08 |  |  | 2026-08-07 | 2026-08-08 | 2026-08-12 | 2026-08-13 | 2026-08-13 | [6 empty] | 2026-08-14 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 70 | N/3 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 200 | 200 | 0 | 0 | -700 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46235 | 0 | 35 | Aug'2
UTG-AF | 47929 | BAD3248 | 700 | 150 | 2026-06-13 | 2026-06-18 | LS o nk Wrap TS w slit & btn | TS |  |  | 2026-07-01 | 2026-07-07 | 2026-07-11 | 2026-07-23 |  |  | 2026-07-28 | 2026-07-29 | 2026-08-08 | 2026-08-10 | 2026-08-11 | [6 empty] | 2026-08-12 | 2026-08-14 |  |  | 2026-08-15 | 2026-08-17 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 70 | N/3 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 150 | 150 | 0 | 0 | -700 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46214 | 0 | 35 | Aug'1
UTG-AF | 47931 | BAD3243 | 600 | 115 | 2026-06-13 | 2026-06-18 | LS high nk TS w side gathering | TS |  |  | 2026-07-01 | 2026-07-10 | 2026-07-11 | 2026-07-23 |  |  | 2026-07-29 | 2026-07-30 | 2026-08-08 | 2026-08-10 | 2026-08-11 | [6 empty] | 2026-08-12 | 2026-08-14 |  |  | 2026-08-15 | 2026-08-17 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 70 | N/3 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 115 | 115 | 0 | 0 | -600 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46214 | 0 | 35 | Aug'1
UTG-AF | 44587 8th | BAD2548S | 3000 | 690 | 2026-06-12 | 2026-06-20 | LDS LS V NK TS | TS |  |  | 2026-07-01 | 2026-07-09 | 2026-07-10 | 2026-07-22 |  |  | 2026-08-08 | 2026-08-10 |  | 2026-08-11 | 2026-08-12 | [6 empty] | 2026-08-13 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 71 | G1 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 690 | 690 | 0 | 0 | -3000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 35 | Aug'2 |  |  | 22.07.26
UTG-AF | 43663 8th | BAD1634T | 3000 | 705 | 2026-06-12 | 2026-06-20 | LS o nk TS | TS |  |  | 2026-07-01 | 2026-07-09 | 2026-07-10 | 2026-07-22 |  |  | 2026-08-08 | 2026-08-10 |  | 2026-08-11 | 2026-08-12 | [6 empty] | 2026-08-13 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 71 | G1 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 705 | 705 | 0 | 3079 | 79 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 35 | Aug'2 |  |  | 29.06.26
UTG-AF | 40668 8th | BAD1630S | 1600 | 312 | 2026-06-12 | 2026-06-20 | LS o nk TS | TS |  |  | 2026-07-01 | 2026-07-08 | 2026-07-09 | 2026-07-20 |  |  | 2026-08-08 | 2026-08-10 |  | 2026-08-12 | 2026-08-13 | [6 empty] | 2026-08-14 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 71 | D2 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 312 | 312 | 0 | 1653 | 53 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46212 | 0 | 35 | Aug'2 |  |  | 29.06.26
UTG-AF | 42566 8th | BAD2784H | 1000 | 274 | 2026-06-12 | 2026-06-20 | SS POLO SHIRT W LACE | POLO |  |  | 2026-07-01 | 2026-07-10 | 2026-07-11 | 2026-07-23 |  |  | 2026-08-01 | 2026-08-10 |  | 2026-08-11 | 2026-08-12 | [6 empty] | 2026-08-13 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 71 | N/3 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 274 | 274 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46214 | 0 | 35 | Aug'2
UTG-AF | 45104 2nd | BAD2966A | 800 | 190 | 2026-06-12 | 2026-06-20 | LS polo w tipping collar placket | Polo |  |  | 2026-07-01 | 2026-07-18 | 2026-07-20 | 2026-07-28 |  |  | 2026-08-08 | 2026-08-10 |  | 2026-08-12 | 2026-08-13 | [6 empty] | 2026-08-14 | 2026-08-17 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 71 | N/3 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 190 | 190 | 0 | 0 | -800 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46223 | 0 | 35 | Aug'2
UTG-AF | 44586 3rd | BAD2940B | 1200 | 266 | 2026-06-12 | 2026-06-20 | LDS LS TS W SHLDR PLKT | TS |  |  | 2026-07-01 | 2026-07-11 | 2026-07-13 | 2026-07-25 |  |  | 2026-08-08 | 2026-08-10 |  | 2026-08-11 | 2026-08-12 | [6 empty] | 2026-08-13 | 2026-08-17 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 71 | N/3 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 266 | 266 | 0 | 0 | -1200 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46216 | 0 | 35 | Aug'2
UTG-AF | 40671 11th | BAD1298AJ | 2000 | 520 | 2026-06-12 | 2026-06-20 | YD LS boat nk TS | TS | 2026-06-25 | 2026-07-03 | 2026-07-04 | 2026-07-14 | 2026-07-15 | 2026-07-27 |  |  | 2026-08-08 | 2026-08-10 |  | 2026-08-12 | 2026-08-13 | [6 empty] | 2026-08-14 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 71 | D2 | Rana |  |  |  | YD |  | NFL1 |  |  | Cut Ok | 520 | 520 | 0 | 2095 | 95 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46218 | 0 | 35 | Aug'2 |  |  | 29.06.26
UTG-AF | 47932 | BAD3244 | 3000 | 690 | 2026-06-12 | 2026-06-20 | LS U nk TS | TS |  |  | 2026-07-01 | 2026-07-09 | 2026-07-10 | 2026-07-23 |  |  | 2026-07-25 | 2026-07-27 | 2026-08-10 | 2026-08-11 | 2026-08-12 | [6 empty] | 2026-08-13 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 71 | D2 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 690 | 690 | 0 | 3070 | 70 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 35 | Aug'2 |  |  | 25.07.26
UTG-AF | 47933 | BAD3246 | 1800 | 352 | 2026-06-12 | 2026-06-20 | LS grow nk TS | TS |  |  | 2026-07-01 | 2026-07-10 | 2026-07-11 | 2026-07-24 |  |  | 2026-07-31 | 2026-08-01 | 2026-08-10 | 2026-08-11 | 2026-08-12 | [6 empty] | 2026-08-13 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 71 | D1 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 352 | 352 | 0 | 1851 | 51 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46214 | 0 | 35 | Aug'2 |  |  | 25.07.26
UTG-(Even & Odd) | 46615 7th | BAD1318AA | 1000 | 300 | 2026-06-06 | 2026-06-19 | AOP SKIRT W SIDE SLIT | Skirt |  |  | 2026-06-23 | 2026-06-30 | 2026-07-01 | 2026-07-11 | 2026-07-13 | 2026-07-20 | 2026-07-23 | 2026-07-24 |  | 2026-07-27 | 2026-07-27 | [6 empty] | 2026-07-28 | 2026-07-30 |  |  | 2026-07-31 | 2026-08-01 | 2026-08-07 | 2026-08-14 | 2026-08-14 | 69 | G1 | Rony |  |  |  | AOP |  | NFL1 |  |  | Cut Ok | 300 | 300 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46204 | 0 | 33 | Jul'3 |  |  | 01.07.26
UTG-(Even & Odd) | 46872 2nd | BAD3191A | 1300 | 616 | 2026-06-06 | 2026-06-19 | LS TS mini dress | Dress |  |  | 2026-07-01 | 2026-07-09 | 2026-07-10 | 2026-07-22 |  |  | 2026-08-01 | 2026-08-08 |  | 2026-08-11 | 2026-08-12 | [6 empty] | 2026-08-13 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 77 | N/2 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 617 | 617 | 0 | 0 | -1300 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 35 | Aug'2
UTG-(Even & Odd) | 47877 | BAD3215 | 800 | 336 | 2026-06-06 | 2026-06-19 | LS dres wfront placket snap btn | Dress |  |  | 2026-07-01 | 2026-07-09 | 2026-07-10 | 2026-07-22 |  |  | 2026-07-24 | 2026-07-25 | 2026-08-10 | 2026-08-11 | 2026-08-12 | [6 empty] | 2026-08-13 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 77 | N/2 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 336 | 336 | 0 | 0 | -800 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 35 | Aug'2
UTG-(Even & Odd) | 47878 | BAD3216 | 1000 | 390 | 2026-06-06 | 2026-06-19 | LS dress w sleeve hole | Dress |  |  | 2026-07-01 | 2026-07-09 | 2026-07-10 | 2026-07-22 |  |  | 2026-07-24 | 2026-07-25 | 2026-08-10 | 2026-08-11 | 2026-08-12 | [6 empty] | 2026-08-13 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 77 | N/2 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 390 | 390 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 35 | Aug'2 |  |  | 18.07.26
UTG-(Even & Odd) | 23325 15th | BAD0960BC | 5100 | 1248 | 2026-06-10 | 2026-06-23 | LDS LS HIGH NK TS | TS |  |  | 2026-07-01 | 2026-07-08 | 2026-07-10 | 2026-07-22 |  |  | 2026-08-01 | 2026-08-08 |  | 2026-08-11 | 2026-08-12 | [6 empty] | 2026-08-13 | 2026-08-17 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 73 | ZA1 | Rony | [5 empty] | NFL3 |  |  | Cut Ok | 1248 | 1248 | 0 | 0 | -5100 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 35 | Aug'2 |  |  | 29.06.26
UTG-(Even & Odd) | 29928 9th | BAD2592I | 600 | 152 | 2026-06-10 | 2026-06-23 | LDS LS TS W spay WASH | TS |  |  | 2026-07-01 | 2026-07-10 | 2026-07-11 | 2026-07-23 |  |  | 2026-08-01 | 2026-08-01 |  | 2026-08-08 | 2026-08-08 | [6 empty] | 2026-08-10 | 2026-08-12 | 2026-08-13 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 73 | ZA1 | Rony |  |  |  |  | GMT WASH | NFL3 |  |  | Cut Ok | 152 | 152 | 0 | 0 | -600 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46214 | 0 | 35 | Aug'1 |  |  | 13.07.26
UTG-(Even & Odd) | 24230 21th | BAD0966AE | 2500 | 545 | 2026-06-10 | 2026-06-23 | LDS LS TS W LETTUCE | TS |  |  | 2026-07-01 | 2026-07-08 | 2026-07-10 | 2026-07-22 |  |  | 2026-08-01 | 2026-08-08 |  | 2026-08-12 | 2026-08-13 | [6 empty] | 2026-08-14 | 2026-08-17 |  |  | 2026-08-18 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 73 | N/1 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 545 | 545 | 0 | 0 | -2500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 35 | Aug'2
UTG-(Even & Odd) | 44047 11th | BAD0982AN | 6600 | 1610 | 2026-06-10 | 2026-06-23 | LDS LS BODYSUIT | SUIT |  |  | 2026-07-01 | 2026-07-08 | 2026-07-10 | 2026-07-18 |  |  | 2026-07-31 | 2026-08-01 |  | 2026-08-07 | 2026-08-08 | [6 empty] | 2026-08-10 | 2026-08-17 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 73 | V1 | Rony | [5 empty] | NFL3 |  |  | Cut Ok | 1610 | 1610 | 0 | 0 | -6600 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 35 | Aug'1 |  |  | 17.07.26
UTG-(Even & Odd) | 44596 4th | BAD2946C | 2800 | 720 | 2026-06-10 | 2026-06-23 | LDS LS BODYSUIT | SUIT |  |  | 2026-07-01 | 2026-07-08 | 2026-07-10 | 2026-07-22 |  |  | 2026-08-01 | 2026-08-08 |  | 2026-08-10 | 2026-08-11 | [6 empty] | 2026-08-12 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 73 | V1 | Rony | [5 empty] | NFL3 |  |  | Cut Ok | 720 | 720 | 0 | 0 | -2800 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 35 | Aug'1 |  |  | 15.07.26
UTG-(Even & Odd) | 27136 20th | BAD2497S | 1200 | 200 | 2026-06-10 | 2026-06-23 | LDS SS BODYSUIT | SUIT |  |  | 2026-07-01 | 2026-07-08 | 2026-07-10 | 2026-07-22 |  |  | 2026-08-01 | 2026-08-08 |  | 2026-08-11 | 2026-08-12 | [6 empty] | 2026-08-13 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 73 | V1 | Rony | [5 empty] | NFL3 |  |  | Cut Ok | 200 | 200 | 0 | 0 | -1200 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 35 | Aug'2 |  |  | 13.07.26
UTG-(Even & Odd) | 45963 10th | BAD0962BP | 1500 | 362 | 2026-06-10 | 2026-06-23 | LDS LS R NK TS | TS |  |  | 2026-07-01 | 2026-07-08 | 2026-07-10 | 2026-07-22 |  |  | 2026-08-01 | 2026-08-10 |  | 2026-08-11 | 2026-08-12 | [6 empty] | 2026-08-13 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 73 | Z | Rony | [5 empty] | NFL3 |  |  | Cut Ok | 362 | 362 | 0 | 0 | -1500 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 35 | Aug'2 |  |  | 14.07.26
UTG-(Even & Odd) | 46873 2nd | BAD3194A | 600 | 218 | 2026-06-10 | 2026-06-23 | LS boat nk TS | TS |  |  | 2026-07-01 | 2026-07-08 | 2026-07-10 | 2026-07-22 |  |  | 2026-08-01 | 2026-08-10 |  | 2026-08-11 | 2026-08-12 | [6 empty] | 2026-08-13 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 73 | N/1 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 218 | 218 | 0 | 0 | -600 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46213 | 0 | 35 | Aug'2
UTG-(Even & Odd) | 45150 3rd | BAD2992B | 1000 | 175 | 2026-06-10 | 2026-06-23 | LS WRAP TOP | Dress |  |  |  |  | 2026-07-21 | 2026-07-31 |  |  | 2026-08-01 | 2026-08-08 |  | 2026-08-12 | 2026-08-13 | [6 empty] | 2026-08-14 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 73 | N/3 | Rony |  |  |  |  | Imp Grey Fab stock | NCL |  |  | Ready Test Cut | 175 | 175 | 0 | 0 | -1000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46224 | 0 | 35 | Aug'2
UTG-(Even & Odd) | 41647 10th | BAD2678I | 800 | 180 | 2026-06-10 | 2026-06-23 | LS BALLARINA KNOT TOP | DRESS |  |  |  |  | 2026-07-21 | 2026-07-31 |  |  | 2026-08-01 | 2026-08-08 |  | 2026-08-12 | 2026-08-13 | [6 empty] | 2026-08-14 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 73 | N/3 | Rony |  |  |  |  | Imp Stock grey fab | NCL |  |  | Ready Test Cut | 180 | 180 | 0 | 0 | -800 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46224 | 0 | 35 | Aug'2
BS-NMT | 47906 | 13268190 | 1644 | 816 | 2026-06-10 | 2026-06-17 | LS Swt full Zipper Hoodie | Hoody |  |  | 2026-07-07 | 2026-07-12 | 2026-07-18 | 2026-08-06 |  |  | 2026-08-10 | 2026-08-10 | 2026-08-15 | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-21 |  |  |  |  | 2026-08-24 | 2026-08-26 |  |  | 2026-08-28 | 2026-08-31 | 2026-09-08 | 2026-09-21 | 2026-09-23 | 103 | S | Kamruzzaman | Chest |  | crockery-848 pcs 2 clr rub ,,spellbound-796 pcs 5 clr rub |  |  | NFL3 |  |  | Cut Ok | 816 | 816 | 0 | 1732 | 88 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46221 | 0 | 39 | Aug'2 |  |  | 06.08.26
BS-NMT | 47907 | 13238441 | 1240 | 297 | 2026-06-10 | 2026-06-17 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-07-05 | 2026-07-10 | 2026-07-13 | 2026-07-31 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-13 | 2026-08-15 | 2026-08-15 | 2026-08-17 | 2026-08-18 |  |  |  |  | 2026-08-20 | 2026-08-21 |  |  | 2026-08-24 | 2026-08-27 | 2026-09-08 | 2026-09-21 | 2026-09-23 | 103 | W1 | Kamruzzaman | Chest |  | evening blue-1210 pcs 4 clr rub 1 clr gltr |  |  | NFL3 |  |  | Cut Ok | 298 | 298 | 0 | 1255 | 15 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46216 | 0 | 39 | Aug'2 |  |  | 06.08.26
BS-NMT | 47908 | 13265105 | 1588 | 232 | 2026-06-10 | 2026-06-17 | AOP & Solid Elasted Legging | Legging |  |  | 2026-07-04 | 2026-07-10 | 2026-07-14 | 2026-07-28 | 2026-08-01 | 2026-08-07 | 2026-08-12 | 2026-08-12 | 2026-08-17 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 |  |  |  |  | 2026-08-24 | 2026-08-25 |  |  | 2026-08-27 | 2026-08-28 | 2026-08-31 | 2026-09-21 | 2026-09-23 | 103 | T1 | Kamruzzaman | leg |  | Ice AOP-794 pcs no print ,,violet-794 pcs both leg 3 clr rub | AOP |  | NFL3 |  |  | Cut Ok | 232 | 232 | 0 | 1656 | 68 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46217 | 0 | 39 | Aug'2 |  |  | 19.08.26
BS-NMT | 47909 | 13262473 | 1656 | 540 | 2026-06-10 | 2026-06-17 | Swt trouser w side pkt drawstring | Trouser |  |  | 2026-07-05 | 2026-07-12 | 2026-07-15 | 2026-07-31 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-13 | 2026-08-15 | 2026-08-17 | [6 empty] | 2026-08-24 | 2026-08-26 |  |  | 2026-08-28 | 2026-08-31 | 2026-09-08 | 2026-09-20 | 2026-09-22 | 102 | X | Kamruzzaman | [5 empty] | NFL3 |  |  | Cut Ok | 586 | 586 | 0 | 1722 | 66 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46218 | 0 | 39 | Aug'2 |  |  | 06.08.26
BS-NMT | 47910 | 13238423 | 1811 | 423 | 2026-06-10 | 2026-06-17 | Swt trouser w side pkt drawstring | Trouser |  |  | 2026-07-05 | 2026-07-10 | 2026-07-13 | 2026-07-31 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-13 | 2026-08-15 | 2026-08-17 |  |  |  |  | 2026-08-19 | 2026-08-20 | 2026-08-22 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-28 | 2026-09-07 | 2026-09-21 | 2026-09-23 | 103 | X | Kamruzzaman |  | Thigh | chocolate-813 pcs,,Violet-998 pcs both combo 3 clr flat emb at one leg |  |  | NFL3 |  |  | Cut Ok | 423 | 423 | 0 | 1911 | 100 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46216 | 0 | 39 | Aug'2 |  |  | 06.08.26
BS-NMT | 47911 | 13239189 | 6931 | 1548 | 2026-06-10 | 2026-06-17 | Swt trouser w side pkt drawstring | Trouser |  |  | 2026-07-01 | 2026-07-10 | 2026-07-12 | 2026-07-31 |  |  | 2026-08-06 | 2026-08-06 | 2026-08-12 | 2026-08-14 | 2026-08-17 |  |  |  |  | 2026-08-17 | 2026-08-19 | 2026-08-20 | 2026-08-26 |  |  | 2026-08-28 | 2026-08-31 | 2026-09-07 | 2026-09-21 | 2026-09-23 | 103 | X | Kamruzzaman |  | Thigh | crockery-1259 pcs 1 clr flat ,,mulled-2732 pcs 1 clr flat emb,,spell bound-2940 pcs 2 clr flat emb |  |  | NFL3 |  |  | Cut Ok | 1548 | 1548 | 0 | 7173 | 242 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46215 | 0 | 39 | Aug'2 |  |  | 06.08.26
BS-NMT | 47896 | 13224969/13229841 | 3104 | 629 | 2026-06-10 | 2026-06-17 | LS o nk TS | TS |  |  | 2026-07-01 | 2026-07-06 | 2026-07-13 | 2026-07-26 |  |  | 2026-08-01 | 2026-08-01 | 2026-08-08 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-15 |  |  |  |  | 2026-08-18 | 2026-08-21 |  |  | 2026-08-24 | 2026-08-27 | 2026-09-05 | 2026-09-20 | 2026-09-22 | 102 | ZA1 | Kamruzzaman | Chest,Nk |  | crockery-1552 pcs,spellbound-1552 pcs both combo 4 clr rub |  |  | NFL3 |  |  | Cut Ok | 628 | 628 | 0 | 3186 | 82 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46216 | 0 | 39 | Aug'1 |  |  | 30.07.26
BS-NMT | 47897 | 13224978/13229864 | 4380 | 595 | 2026-06-10 | 2026-06-17 | LS o nk TS | TS |  |  | 2026-07-01 | 2026-07-07 | 2026-07-14 | 2026-07-28 |  |  | 2026-08-01 | 2026-08-01 | 2026-08-08 | 2026-08-10 | 2026-08-13 | 2026-08-13 | 2026-08-17 |  |  |  |  | 2026-08-18 | 2026-08-21 |  |  | 2026-08-24 | 2026-08-26 | 2026-08-31 | 2026-09-20 | 2026-09-22 | 102 | ZA1 | Kamruzzaman | Chest,Nk |  | mostone-1855 pcs,,sepia-1070 pcs ,,spellbound-1455 pcs all comb 6 clr rub/Pig |  |  | NFL3 |  |  | Cut Ok | 594 | 594 | 0 | 4540 | 160 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46217 | 0 | 39 | Aug'1 |  |  | 30.07.26
BS-NMT | 47898 | 13224958/13229879 | 2604 | 328 | 2026-06-10 | 2026-06-17 | LS o nk TS | TS |  |  | 2026-07-03 | 2026-07-10 | 2026-07-14 | 2026-07-31 |  |  | 2026-08-06 | 2026-08-06 | 2026-08-12 | 2026-08-14 | 2026-08-15 | 2026-08-17 | 2026-08-19 |  |  |  |  | 2026-08-21 | 2026-08-22 |  |  | 2026-08-25 | 2026-08-28 | 2026-09-04 | 2026-09-21 | 2026-09-23 | 103 | ZA1 | Kamruzzaman | Chest,Nk |  | evening blue-1302 pcs 4 clr rub 1 clr gltr ,,Violet-1302 pcs 3 clr rub 1 clr gltr |  |  | NFL3 |  |  | Cut Ok | 328 | 328 | 0 | 2722 | 118 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46217 | 0 | 39 | Aug'2 |  |  | 30.07.26
BS-NMT | 47899 | 13259688/13261406 | 4132 | 885 | 2026-06-10 | 2026-06-17 | LS o nk TS | TS |  |  | 2026-07-05 | 2026-07-10 | 2026-07-15 | 2026-07-31 |  |  | 2026-08-06 | 2026-08-06 | 2026-08-10 | 2026-08-12 | 2026-08-14 | 2026-08-14 | 2026-08-17 |  |  |  |  | 2026-08-19 | 2026-08-22 |  |  | 2026-08-26 | 2026-08-29 | 2026-09-06 | 2026-09-21 | 2026-09-23 | 103 | ZA1 | Kamruzzaman | Chest,Nk |  | citadel-1991 pcs,,c.dan-2141 pcs both combo 4 clr rub |  |  | NFL3 |  |  | Cut Ok | 886 | 886 | 0 | 4252 | 120 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46218 | 0 | 39 | Aug'2 |  |  | 30.07.26
BS-NMT | 47900 | 13264522 | 2723 | 538 | 2026-06-10 | 2026-06-17 | AOP & Solid LS o nk TS | TS |  |  | 2026-07-01 | 2026-07-06 | 2026-07-12 | 2026-07-25 | 2026-07-27 | 2026-08-04 | 2026-08-06 | 2026-08-06 | 2026-08-11 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-18 |  |  |  |  | 2026-08-20 | 2026-08-22 |  |  | 2026-08-25 | 2026-08-28 | 2026-09-06 | 2026-09-21 | 2026-09-23 | 103 | ZA1 | Kamruzzaman | Chest,Nk |  | c.dan AOP -1324 pcs no print ,,Orchid-1399 pcs 2 clr rub | AOP |  | NFL3 |  |  | Cut Ok | 538 | 538 | 0 | 2809 | 86 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46215 | 0 | 39 | Aug'2 |  |  | 22.07.26
BS-NMT | 47901 | 13253226 | 6305 | 888 | 2026-06-10 | 2026-06-17 | LS o nk TS w front pkt | TS |  |  | 2026-07-01 | 2026-07-09 | 2026-07-15 | 2026-07-31 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-12 | 2026-08-14 | 2026-08-17 | 2026-08-17 | 2026-08-21 |  |  |  |  | 2026-08-24 | 2026-08-27 |  |  | 2026-08-29 | 2026-09-02 | 2026-09-04 | 2026-09-21 | 2026-09-23 | 103 | ZA1 | Kamruzzaman | Chest,Nk |  | crockery-1511 pcs ,,basil-2415 pcs,,Sepia-2379 pcs all combo 5 clr pig |  |  | NFL3 |  |  | Cut Ok | 888 | 887 | -1 | 6535 | 230 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46218 | 0 | 39 | Aug'2 |  |  | 30.07.26
BS-NMT | 47902 | 13238389/13242412 | 7050 | 911 | 2026-06-10 | 2026-06-17 | LS o nk TS | TS |  |  | 2026-07-04 | 2026-07-11 | 2026-07-15 | 2026-07-31 |  |  | 2026-08-06 | 2026-08-06 | 2026-08-12 | 2026-08-14 | 2026-08-18 | 2026-08-17 | 2026-08-21 |  |  |  |  | 2026-08-22 | 2026-08-26 |  |  | 2026-08-29 | 2026-08-31 | 2026-09-10 | 2026-09-21 | 2026-09-23 | 103 | ZA1 | Kamruzzaman | Chest,Nk |  | pink-1288 pcs 6 clr rub ,,blue-2727 pcs 3 clr rub 1 clr gltr ,,ice-3035 pcs 3 clr rub 1 clr gltr |  |  | NFL3 |  |  | Cut Ok | 910 | 910 | 0 | 7293 | 243 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46218 | 0 | 39 | Aug'2 |  |  | 30.07.26
BS-NMT | 47903 | 13264519 | 2016 | 381 | 2026-06-10 | 2026-06-17 | AOP LS dress | Dress |  |  | 2026-07-06 | 2026-07-10 | 2026-07-14 | 2026-07-28 | 2026-08-01 | 2026-08-10 | 2026-08-12 | 2026-08-12 | 2026-08-17 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 |  |  |  |  | 2026-08-25 | 2026-08-27 |  |  | 2026-08-29 | 2026-08-31 | 2026-09-10 | 2026-09-21 | 2026-09-23 | 103 | ZA1 | Kamruzzaman | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 395 | 395 | 0 | 2102 | 86 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46217 | 0 | 39 | Aug'2 |  |  | 30.07.26
BS-NMT | 47904 | 13264520 | 1746 | 419 | 2026-06-10 | 2026-06-17 | LS O nk Swt Shirt | Swt Shirt |  |  | 2026-07-06 | 2026-07-11 | 2026-07-14 | 2026-07-31 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-12 | 2026-08-14 | 2026-08-15 |  |  |  |  | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-22 |  |  | 2026-08-25 | 2026-08-27 | 2026-09-08 | 2026-09-21 | 2026-09-23 | 103 | W1 | Kamruzzaman |  | Chest | chocolate-793 pcs,,Violet-953 pcs both combo 3 clr flat emb |  |  | NFL3 |  |  | Cut Ok | 419 | 419 | 0 | 1825 | 79 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46217 | 0 | 39 | Aug'2 |  |  | 06.08.26
BS-NMT | 47905 | 13238188 | 7985 | 1830 | 2026-06-10 | 2026-06-17 | LS O nk Swt Shirt | Swt Shirt |  |  | 2026-07-01 | 2026-07-10 | 2026-07-13 | 2026-07-31 |  |  | 2026-08-06 | 2026-08-06 | 2026-08-11 | 2026-08-13 | 2026-08-16 |  |  |  |  | 2026-08-15 | 2026-08-19 | 2026-08-20 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-29 | 2026-09-10 | 2026-09-21 | 2026-09-23 | 103 | W1 | Kamruzzaman |  | Chest | crockery-1647 pcs 1 clr flat ,,mulled-3299 pcs 1 clr flat emb,,spell bound-3039 pcs 2 clr flat emb |  |  | NFL3 |  |  | Cut Ok | 1831 | 1831 | 0 | 8171 | 186 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46216 | 0 | 39 | Aug'2 |  |  | 06.08.26
BS-NMT | 47912 | 13264808 | 2724 | 504 | 2026-06-10 | 2026-06-17 | LS o nk TS w cuff btm letus | TS |  |  | 2026-07-05 | 2026-07-12 | 2026-07-15 | 2026-07-31 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 2026-08-19 | 2026-08-20 |  |  |  |  | 2026-08-22 | 2026-08-25 |  |  | 2026-08-27 | 2026-08-29 | 2026-09-06 | 2026-09-21 | 2026-09-23 | 103 | Z | Kamruzzaman | Nk |  | 3 combo label print |  |  | NFL3 |  |  | Cut Ok | 505 | 505 | 0 | 2802 | 78 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46218 | 0 | 39 | Aug'2 |  |  | 22.07.26
BS-NMT | 47913 | 13260940 | 3863 | 789 | 2026-06-10 | 2026-06-17 | Elsated Legging w letus at leg opening | Legging |  |  | 2026-07-04 | 2026-07-12 | 2026-07-15 | 2026-07-31 |  |  | 2026-08-06 | 2026-08-06 | 2026-08-12 | 2026-08-14 | 2026-08-17 | 2026-08-17 | 2026-08-18 |  |  |  |  | 2026-08-20 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-28 | 2026-09-07 | 2026-09-21 | 2026-09-23 | 103 | Z | Kamruzzaman | Waist |  | 3 combo label print |  |  | NFL3 |  |  | Cut Ok | 790 | 790 | 0 | 3984 | 121 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46218 | 0 | 39 | Aug'2 |  |  | 22.07.26
BS-NMT | 47949 | 13262408 | 600 | 170 | 2026-06-10 | 2026-06-22 | LS o nk TS | TS |  |  | 2026-08-15 | 2026-08-20 | 2026-08-01 | 2026-08-12 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-25 | 2026-08-27 | 2026-08-27 | [6 empty] | 2026-08-29 | 2026-08-31 |  |  | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-21 | 2026-09-23 | 103 | Z | Tomal | [5 empty] | NFL3 |  |  | Cut Ok | 171 | 171 | 0 | 624 | 24 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46235 | 0 | 39 | Aug'3 |  |  | 19.08.26
BS-NMT | 47950 | 13262864 | 2994 | 843 | 2026-06-10 | 2026-06-22 | YD LS o nk TS | TS | 2026-07-10 | 2026-07-18 | 2026-07-20 | 2026-08-03 | 2026-08-07 | 2026-08-17 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-25 | 2026-08-27 | 2026-08-31 | [6 empty] | 2026-09-01 | 2026-09-04 |  |  | 2026-09-07 | 2026-09-09 | 2026-09-12 | 2026-09-21 | 2026-09-23 | 103 | Z | Tomal |  |  |  | YD |  | NFL3 |  |  | Cut Ok | 844 | 839 | -5 | 3129 | 135 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46241 | 0 | 39 | Aug'3 |  |  | 06.08.26
BS-NMT | 48067 | 13262959 | 3168 | 922 | 2026-06-10 | 2026-06-23 | YD LS o nk TS | TS | 2026-07-15 | 2026-07-22 | 2026-07-25 | 2026-08-06 | 2026-08-08 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-22 | 2026-08-25 | 2026-08-27 | 2026-08-28 | 2026-09-02 |  |  |  |  | 2026-09-05 | 2026-09-09 |  |  | 2026-09-11 | 2026-09-14 | 2026-09-16 | 2026-09-21 | 2026-09-23 | 103 | Z | Shamoly | Chest,Nk |  | white cap-1008 pcs,,Nose-840 pcs,,Mole-1320 pcs all combo 1 clr gltr print | YD |  | NFL3 |  |  | Cut Run | 923 | 923 | 0 | 876 | -2292 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46242 | 0 | 39 | Aug'3 |  |  | 08.08.26
BS-NMT | 48071 | 13263485 | 1134 | 367 | 2026-06-10 | 2026-06-23 | LS Swt hoody | Hoody |  |  | 2026-07-18 | 2026-07-25 | 2026-08-03 | 2026-08-15 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-26 | 2026-08-28 | 2026-08-29 | 2026-09-01 | 2026-09-04 |  |  |  |  | 2026-09-07 | 2026-09-09 |  |  | 2026-09-12 | 2026-09-15 | 2026-09-16 | 2026-09-21 | 2026-09-23 | 103 | T2 | Shamoly | Chest |  | Peyote-1134 pcs 1 clr HD 1 clr gltr print |  |  | NFL3 |  |  | Cut Ok | 367 | 367 | 0 | 1161 | 27 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46237 | 0 | 39 | Aug'3 |  |  | 15.07.26
BS-NMT | 48072 | 13263490 | 996 | 266 | 2026-06-10 | 2026-06-23 | Elasted pant w side pkt | Pant |  |  | 2026-07-25 | 2026-07-31 | 2026-08-10 | 2026-08-20 |  |  | 2026-08-25 | 2026-08-25 | 2026-09-01 | 2026-09-03 | 2026-09-04 | [6 empty] | 2026-09-07 | 2026-09-08 |  |  | 2026-09-10 | 2026-09-14 | 2026-09-16 | 2026-09-21 | 2026-09-23 | 103 | X | Shamoly | [5 empty] | NFL3 |  |  | Cut Run | 266 | 266 | 0 | 982 | -14 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46244 | 0 | 39 | Sep'1 |  |  | 27.08.26
BS-NMT | 48073 | 13263395 | 5100 | 2101 | 2026-06-10 | 2026-06-23 | LS Swt hoody w cuff btm rib | Hoody |  |  | 2026-07-05 | 2026-07-15 | 2026-07-20 | 2026-08-08 |  |  | 2026-08-11 | 2026-08-11 | 2026-08-18 | 2026-08-20 | 2026-08-22 | 2026-08-22 | 2026-08-29 |  |  |  |  | 2026-09-01 | 2026-09-03 |  |  | 2026-09-07 | 2026-09-09 | 2026-09-12 | 2026-09-19 | 2026-09-21 | 101 | V | Shamoly | Fr,Bk |  | Navy-2352 pcs frt back 1 clr puff gltr print ,,white-2748 pcs frt back 2 clr puff gltr print |  |  | NFL3 |  |  | Cut Ok | 2102 | 2102 | 0 | 5232 | 132 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46223 | 0 | 39 | Aug'2 |  |  | 15.07.26
BS-NMT | 48069 | 13263273 | 5118 | 914 | 2026-06-10 | 2026-06-23 | SS o nk TS w frt woven label | TS |  |  | 2026-07-10 | 2026-07-15 | 2026-07-22 | 2026-08-07 |  |  | 2026-08-10 | 2026-08-10 | 2026-08-18 | 2026-08-20 | 2026-08-21 | 2026-08-24 | 2026-08-29 |  |  |  |  | 2026-09-01 | 2026-09-03 |  |  | 2026-09-07 | 2026-09-09 | 2026-09-14 | 2026-09-21 | 2026-09-23 | 103 | ZA1 | Shamoly | Fr & Bk & Nk |  | c.dan-2703 pcs frt 1 clr puff back 1 clr pig 1 clr puff,,grey-2415 pcs frt 1 clr puff back 2 clr rub 1 clr puff |  | Woven label | NFL3 |  |  | Cut Ok | 914 | 914 | 0 | 5290 | 172 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 39 | Aug'2 |  |  | 13.07.26
BS-NMT | 48068 | 13262960 | 818 | 2040 | 2026-06-10 | 2026-06-23 | YD Wide elasted pant w drawstring | Pant | 2026-07-15 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 2026-08-11 | 2026-08-18 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-28 | 2026-08-31 | 2026-09-01 | 2026-09-03 | 2026-09-04 |  |  |  |  | 2026-09-07 | 2026-09-09 |  |  | 2026-09-12 | 2026-09-14 | 2026-09-16 | 2026-09-21 | 2026-09-23 | 103 | X | Shamoly | Waist |  | 2 combo label print | YD |  | NFL3 |  |  | Cut Ok | 818 | 818 | 0 | 2125 | 1307 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46245 | 0 | 39 | Aug'3 |  |  | 08.08.26
BS-NMT | 48066 | 13262926 | 2880 | 490 | 2026-06-10 | 2026-06-23 | AOP elasted Legging | Legging |  |  | 2026-07-10 | 2026-07-16 | 2026-07-23 | 2026-08-07 | 2026-08-10 | 2026-08-18 | 2026-08-20 | 2026-08-20 | 2026-08-26 | 2026-08-28 | 2026-08-29 | 2026-09-01 | 2026-09-02 |  |  |  |  | 2026-09-04 | 2026-09-08 |  |  | 2026-09-10 | 2026-09-12 | 2026-09-16 | 2026-09-27 | 2026-09-29 | 109 | ZA2 | Shamoly | Waist |  | 3 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 396 | 396 | 0 | 3474 | 594 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46226 | 0 | 40 | Aug'3 |  |  | 13.07.26
BS-NMT | 48070 | 13263274 | 1650 | 974 | 2026-06-10 | 2026-06-23 | LS Swt Hoody w kangaroo pkt w woven label | Hoody |  |  | 2026-07-08 | 2026-07-16 | 2026-07-23 | 2026-08-10 |  |  | 2026-08-13 | 2026-08-13 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-25 | 2026-08-29 |  |  |  |  | 2026-09-03 | 2026-09-05 |  |  | 2026-09-08 | 2026-09-10 | 2026-09-12 | 2026-09-21 | 2026-09-23 | 103 | S | Shamoly | Fr,Bk |  | C.dan-795 pcs frt 1 clr puff back 1 clr rub 1 clr,,grey-855 pcs frt 1 clr puff back 1 clr rub 1 clr puff |  | Woven label | NFL3 |  |  | Cut Ok | 975 | 973 | -2 | 1732 | 82 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46226 | 0 | 39 | Aug'3 |  |  | 08.08.26
BS-NMT | 48065 | 13262924 | 2880 | 490 | 2026-06-10 | 2026-06-23 | AOP LS dress | Dress |  |  | 2026-07-12 | 2026-07-20 | 2026-07-27 | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-08-26 | 2026-08-26 | 2026-09-01 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-09 |  |  |  |  | 2026-09-11 | 2026-09-15 |  |  | 2026-09-17 | 2026-09-18 | 2026-09-23 | 2026-09-27 | 2026-09-29 | 109 | T2 | Shamoly | Nk |  | 3 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 490 | 490 | 0 | 2989 | 109 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46230 | 0 | 40 | Sep'1 |  |  | 13.07.26
BS-NMT | 47988 | 13263822 | 2431 | 295 | 2026-06-10 | 2026-06-20 | AOP waist fold Swt Pant | Pant |  |  | 2026-07-06 | 2026-07-15 | 2026-07-17 | 2026-07-29 | 2026-08-01 | 2026-08-08 | 2026-08-12 | 2026-08-12 | 2026-08-18 | 2026-08-20 | 2026-08-22 |  |  |  |  | 2026-08-24 | 2026-08-25 | 2026-08-27 | 2026-08-28 |  |  | 2026-08-31 | 2026-09-03 | 2026-09-07 | 2026-09-19 | 2026-09-21 | 101 | ZA2 | Mosaddik |  | Thigh | Basil-1222 pcs,,Spellbound-1209 pcs both combo 2 clr flat emb |  |  | NFL3 |  |  | Cut Ok | 296 | 296 | 0 | 2547 | 116 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46220 | 0 | 39 | Aug'2 |  |  | 17.08.26
BS-NMT | 47989 | 13263831 | 4466 | 353 | 2026-06-10 | 2026-06-20 | Rib Pant w fake fly and btn | Pant |  |  | 2026-07-10 | 2026-07-17 | 2026-07-21 | 2026-08-04 |  |  | 2026-08-06 | 2026-08-06 | 2026-08-12 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-22 |  |  | 2026-08-27 | 2026-08-25 | 2026-08-27 | 2026-08-31 |  |  | 2026-09-02 | 2026-09-04 | 2026-09-08 | 2026-09-21 | 2026-09-23 | 103 | U | Mosaddik | Waist | AOE | Basil-1988 pcs,,Spellbound-2478 pcs both combo two part 1 clr flat all over emb |  |  | NFL3 |  |  | Cut Ok | 353 | 353 | 0 | 4605 | 139 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46224 | 0 | 39 | Aug'2 |  |  | 29.07.26
BS-NMT | 47985 | 13263814 | 3684 | 537 | 2026-06-10 | 2026-06-20 | AOP & Solid LS Swt Shirt w cuff btm rib and slder snap btn | Swt Shirt |  |  | 2026-07-10 | 2026-07-17 | 2026-07-20 | 2026-08-03 | 2026-08-06 | 2026-08-13 | 2026-08-15 | 2026-08-15 | 2026-08-21 | 2026-08-24 | 2026-08-26 |  |  |  |  | 2026-08-26 | 2026-08-29 | 2026-08-27 | 2026-08-31 |  |  | 2026-09-03 | 2026-09-05 | 2026-09-08 | 2026-09-19 | 2026-09-21 | 101 | Y | Mosaddik |  | Chest | mellane AOP-2457 pcs no emb ,,orchid ice-1227 pcs 3 clr terry emb | AOP |  | NFL3 |  |  | Cut Ok | 537 | 531 | -6 | 3789 | 105 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46223 | 0 | 39 | Aug'3 |  |  | 29.07.26
BS-NMT | 47993 | 13263836 | 2828 | 345 | 2026-06-10 | 2026-06-20 | LS rib dress w shlder snap btn | Dress |  |  | 2026-07-10 | 2026-07-16 | 2026-07-23 | 2026-08-06 |  |  | 2026-08-10 | 2026-08-10 | 2026-08-15 | 2026-08-18 | 2026-08-19 | 2026-08-24 | 2026-08-26 |  |  | 2026-08-21 | 2026-08-28 | 2026-09-01 | 2026-09-03 |  |  | 2026-09-05 | 2026-09-07 | 2026-09-10 | 2026-09-21 | 2026-09-23 | 103 | Y | Mosaddik | Nk | AOE | pink-2030 pcs,,peyote-798 pcs both combo two part 1 clr flat all over emb |  |  | NFL3 |  |  | Cut Ok | 344 | 344 | 0 | 2904 | 76 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46226 | 0 | 39 | Aug'2 |  |  | 29.07.26
BS-NMT | 47982 | 13263810 | 1125 | 156 | 2026-06-10 | 2026-06-20 | LS Swt Shirt w cuff btm rib and slder snap btn | Swt Shirt |  |  | 2026-07-15 | 2026-07-20 | 2026-07-25 | 2026-08-08 |  |  | 2026-08-11 | 2026-08-11 | 2026-08-17 | 2026-08-19 | 2026-08-20 | 2026-08-22 | 2026-08-26 |  |  |  |  | 2026-08-28 | 2026-08-29 |  |  | 2026-09-03 | 2026-09-06 | 2026-09-10 | 2026-09-21 | 2026-09-23 | 103 | Y | Mosaddik | Chest |  | crockery-1125 pcs ambossed print |  |  | NFL3 |  |  | Cut Ok | 156 | 156 | 0 | 1193 | 68 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46228 | 0 | 39 | Aug'2 |  |  | 29.07.26
BS-NMT | 47984 | 13263813 | 1200 | 132 | 2026-06-10 | 2026-06-20 | AOP Swt pant w waist cuff rib and herringbone string | Pant |  |  | 2026-07-10 | 2026-07-15 | 2026-07-20 | 2026-08-02 | 2026-08-06 | 2026-08-15 | 2026-08-17 | 2026-08-17 | 2026-08-22 | 2026-08-25 | 2026-08-26 | [6 empty] | 2026-08-28 | 2026-08-29 |  |  | 2026-09-03 | 2026-09-08 | 2026-09-10 | 2026-09-19 | 2026-09-21 | 101 | U | Mosaddik |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 132 | 132 | 0 | 1230 | 30 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46223 | 0 | 39 | Aug'3 |  |  | 29.07.26
BS-NMT | 47979 | 13263751 | 2518 | 207 | 2026-06-10 | 2026-06-20 | LS O nk TS w shlder snap btn | TS |  |  | 2026-07-10 | 2026-07-15 | 2026-07-22 | 2026-08-04 |  |  | 2026-08-06 | 2026-08-06 | 2026-08-12 | 2026-08-14 | 2026-08-15 | 2026-08-18 | 2026-08-20 |  |  | 2026-08-22 | 2026-08-25 | 2026-08-27 | 2026-08-29 |  |  | 2026-09-03 | 2026-09-07 | 2026-09-10 | 2026-09-19 | 2026-09-21 | 101 | T1 | Mosaddik | Chest,Nk | Chest | Ice-1129 pcs,,pink-1389 pcs both combo 1 clr puff print and 2 clr flat 3 clr terry emb |  |  | NFL3 |  |  | Cut Ok | 207 | 207 | 0 | 2605 | 87 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 39 | Aug'2 |  |  | 29.07.26
BS-NMT | 47992 | 13263835 | 2330 | 76 | 2026-06-10 | 2026-06-20 | Scarf Bib | Bib |  |  | 2026-07-12 | 2026-07-15 | 2026-07-22 | 2026-08-04 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-13 | 2026-08-15 | 2026-08-17 |  |  |  |  | 2026-08-18 | 2026-08-22 | 2026-08-25 | 2026-08-26 |  |  | 2026-08-28 | 2026-08-31 | 2026-09-05 | 2026-09-21 | 2026-09-23 | 103 | T1 | Mosaddik |  | Chest | pink-1258 pcs,,peyote-1072 pcs all combo 1 clr flat all over emb |  |  | NFL3 |  |  | Cut Ok | 76 | 76 | 0 | 2503 | 173 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 39 | Aug'2 |  |  | 29.07.26
BS-NMT | 47990 | 13263833 | 1008 | 42 | 2026-06-10 | 2026-06-20 | Rib Hat | Hat |  |  | 2026-07-14 | 2026-07-19 | 2026-07-25 | 2026-08-08 |  |  | 2026-08-13 | 2026-08-13 | 2026-08-19 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 |  |  |  |  | 2026-08-27 | 2026-08-29 |  |  | 2026-08-31 | 2026-09-03 | 2026-09-06 | 2026-09-21 | 2026-09-23 | 103 | T1 | Mosaddik | Nk |  | 2 combo label print |  |  | NFL3 |  |  | Cut Ok | 42 | 42 | 0 | 1111 | 103 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46228 | 0 | 39 | Aug'3 |  |  | 21.08.26
BS-NMT | 47986 | 13263816 | 4207 | 293 | 2026-06-10 | 2026-06-20 | AOP & Solid Elasted Swt Legging | Legging |  |  | 2026-07-13 | 2026-07-18 | 2026-07-22 | 2026-08-02 | 2026-08-04 | 2026-08-12 | 2026-08-14 | 2026-08-14 | 2026-08-19 | 2026-08-21 | 2026-08-24 |  |  |  |  | 2026-08-21 | 2026-08-25 | 2026-08-25 | 2026-08-27 |  |  | 2026-08-29 | 2026-09-02 | 2026-09-06 | 2026-09-19 | 2026-09-21 | 101 | ZA2 | Mosaddik |  | Chest | mellane AOP-2491 pcs no emb ,,orchid ice-1716 pcs 3 clr terry emb | AOP |  | NFL3 |  |  | Cut Ok | 294 | 294 | 0 | 4324 | 117 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 39 | Aug'3 |  |  | 29.07.26
BS-NMT | 47995 | 13268151 | 810 | 94 | 2026-06-10 | 2026-06-20 | LS Swt Shirt w cuff btm rib and slder snap btn and Swt pant | Top & BTM |  |  | 2026-07-16 | 2026-07-20 | 2026-07-24 | 2026-08-04 | 2026-08-07 | 2026-08-14 | 2026-08-17 | 2026-08-17 | 2026-08-22 | 2026-08-25 | 2026-08-26 | [6 empty] | 2026-08-28 | 2026-08-29 |  |  | 2026-08-31 | 2026-09-04 | 2026-09-06 | 2026-09-21 | 2026-09-23 | 103 | Y+ZA2 | Mosaddik |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 94 | 92 | -2 | 852 | 42 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46227 | 0 | 39 | Aug'3 |  |  | 29.07.26
BS-NMT | 47978 | 13263748 | 1602 | 155 | 2026-06-10 | 2026-06-22 | LS O nk TS w shlder frill & snap btn | TS |  |  | 2026-07-10 | 2026-07-15 | 2026-08-01 | 2026-08-12 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-22 | 2026-08-25 | 2026-08-26 | 2026-08-26 | 2026-08-29 |  |  | 2026-08-31 | 2026-09-02 | 2026-09-04 | 2026-09-07 |  |  | 2026-09-09 | 2026-09-11 | 2026-09-14 | 2026-09-19 | 2026-09-21 | 101 | Y | Mosaddik | Chest,Nk | Chest | Ice-1602 pcs 3 clr rub print at patch and applique emb |  |  | NFL3 |  |  | Cut Ok | 155 | 155 | 0 | 1665 | 63 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46235 | 0 | 39 | Aug'3 |  |  | 07.08.26
BS-NMT | 47980 | 13263753 | 2294 | 198 | 2026-06-10 | 2026-06-22 | LS O nk TS w shlder snap btn | TS |  |  | 2026-07-10 | 2026-07-15 | 2026-07-25 | 2026-08-10 |  |  | 2026-08-14 | 2026-08-14 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-25 | 2026-08-28 |  |  |  |  | 2026-09-01 | 2026-09-03 |  |  | 2026-09-07 | 2026-09-09 | 2026-09-12 | 2026-09-19 | 2026-09-21 | 101 | T1 | Mosaddik | Chest,Nk |  | Basil-1372 pcs 3 clr rub 3 clr flock print ,,Peyote-922 pcs 3 clr rub 1 clr puff 1 clr flock print |  |  | NFL3 |  |  | Cut Ok | 198 | 198 | 0 | 2365 | 71 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46228 | 0 | 39 | Aug'3 |  |  | 29.07.26
BS-NMT | 47983 | 13263812 | 2019 | 282 | 2026-06-10 | 2026-06-22 | AOP LS Swt Shirt w cuff btm rib and shlder snap btn | Swt Shirt |  |  | 2026-07-05 | 2026-07-14 | 2026-07-20 | 2026-08-04 | 2026-08-08 | 2026-08-18 | 2026-08-22 | 2026-08-22 | 2026-08-28 | 2026-09-01 | 2026-09-02 | [6 empty] | 2026-09-04 | 2026-09-07 |  |  | 2026-09-09 | 2026-09-11 | 2026-09-13 | 2026-09-19 | 2026-09-21 | 101 | Y | Mosaddik |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 299 | 299 | 0 | 2106 | 87 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46223 | 0 | 39 | Sep'1 |  |  | 29.07.26
BS-NMT | 47994 | 13267228 | 1115 | 113 | 2026-06-10 | 2026-06-22 | LS Body w shlder btm snap btn | Body |  |  | 2026-07-10 | 2026-07-15 | 2026-08-01 | 2026-08-10 |  |  | 2026-08-15 | 2026-08-15 | 2026-08-20 | 2026-08-22 | 2026-08-22 | 2026-08-25 | 2026-08-25 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-29 | 2026-08-31 |  |  | 2026-09-03 | 2026-09-05 | 2026-09-09 | 2026-09-21 | 2026-09-23 | 103 | T2 | Mosaddik | Nk | Chest | Ice-1115 pcs 3 clr flat emb |  |  | NFL3 |  |  | Cut Ok | 113 | 113 | 0 | 1176 | 61 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46235 | 0 | 39 | Aug'3 |  |  | 17.08.26
BS-NMT | 47991 | 13263834 | 1882 | 66 | 2026-06-10 | 2026-06-22 | Scarf Bib | Bib |  |  | 2026-07-12 | 2026-07-18 | 2026-07-25 | 2026-08-10 |  |  | 2026-08-14 | 2026-08-14 | 2026-08-19 | 2026-08-21 | 2026-08-22 |  |  |  |  | 2026-08-25 | 2026-08-28 | 2026-09-01 | 2026-09-02 |  |  | 2026-09-04 | 2026-09-07 | 2026-09-10 | 2026-09-21 | 2026-09-23 | 103 | T1 | Mosaddik |  | Chest | Basil-848 pcs,,spellbound-1034 pcs both combo 1 clr flat all over emb |  |  | NFL3 |  |  | Cut Ok | 66 | 66 | 0 | 2040 | 158 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46228 | 0 | 39 | Aug'3 |  |  | 29.07.26
BS-NMT | 48002 | 13264347 | 6314 | 663 | 2026-06-10 | 2026-06-22 | AOP LS body w shlder btm snap btn nk picoting | Body |  |  | 2026-07-22 | 2026-08-04 | 2026-08-08 | 2026-08-22 | 2026-08-25 | 2026-09-04 | 2026-09-08 | 2026-09-08 | 2026-09-14 | 2026-09-17 | 2026-09-21 | 2026-09-21 | 2026-09-23 |  |  |  |  | 2026-09-25 | 2026-09-30 |  |  | 2026-10-03 | 2026-10-07 | 2026-10-12 | 2026-11-02 | 2026-11-04 | 145 | Y | Mosaddik | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | Cut Run | 663 | 347 | -316 | 3410 | -2904 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46242 | 0 | 45 | Sep'2 |  |  | 25.08.26
BS-NMT | 48003 | 13264348 | 4134 | 634 | 2026-06-10 | 2026-06-22 | AOP LS dress w shlder snap btn and nk picoting | Dress |  |  | 2026-07-25 | 2026-08-04 | 2026-08-10 | 2026-08-22 | 2026-08-26 | 2026-09-03 | 2026-09-08 | 2026-09-08 | 2026-09-14 | 2026-09-17 | 2026-09-21 | 2026-09-21 | 2026-09-23 |  |  |  |  | 2026-09-25 | 2026-09-30 |  |  | 2026-10-03 | 2026-10-06 | 2026-10-10 | 2026-11-01 | 2026-11-03 | 144 | T2 | Mosaddik | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | Cut Run | 634 | 333 | -301 | 2232 | -1902 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46244 | 0 | 45 | Sep'2 |  |  | 27.08.26
BS-NMT | 48004 | 13264349 | 5148 | 336 | 2026-06-10 | 2026-06-22 | AOP Legging w waist frill w letus and leg picoting | Legging |  |  | 2026-07-23 | 2026-07-31 | 2026-08-06 | 2026-08-18 | 2026-08-22 | 2026-08-31 | 2026-09-09 | 2026-09-09 | 2026-09-15 | 2026-09-18 | 2026-09-18 | 2026-09-21 | 2026-09-23 |  |  |  |  | 2026-09-25 | 2026-09-29 |  |  | 2026-10-03 | 2026-10-05 | 2026-10-10 | 2026-11-02 | 2026-11-04 | 145 | ZA2 | Mosaddik | Waist |  | 2 combo label print | AOP |  | NFL3 |  |  | Cut Run | 336 | 167 | -169 | 2616 | -2532 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46240 | 0 | 45 | Sep'2 |  |  | 25.08.26
BS-NMT | 47922 | 13263839 | 11660 | 1117 | 2026-06-10 | 2026-06-17 | LS Body w shlder and btm snap btn | Body |  |  | 2026-07-01 | 2026-07-11 | 2026-07-13 | 2026-07-30 |  |  | 2026-08-01 | 2026-08-01 | 2026-08-08 | 2026-08-10 | 2026-08-14 | 2026-08-15 | 2026-08-20 |  |  | 2026-08-12 | 2026-08-22 | 2026-08-22 | 2026-08-31 |  |  | 2026-09-03 | 2026-09-05 | 2026-09-08 | 2026-09-14 | 2026-09-16 | 96 | T1 | Jafar | Nk | AOE | basil-4833 pcs,,citadel-1354 pcs,,spellbound-5473 pcs all combo chest all over emb |  |  | NFL3 |  |  | Cut Ok | 1117 | 1117 | 0 | 12004 | 344 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46216 | 0 | 38 | Aug'1 |  |  | 06.08.26
BS-NMT | 47920 | 13263837 | 7221 | 211 | 2026-06-10 | 2026-06-17 | Elasted legging | Legging |  |  | 2026-07-13 | 2026-07-18 | 2026-07-22 | 2026-08-04 |  |  | 2026-08-06 | 2026-08-06 | 2026-08-12 | 2026-08-14 | 2026-08-17 | 2026-08-19 | 2026-08-22 |  |  | 2026-08-17 | 2026-08-24 | 2026-08-25 | 2026-08-29 |  |  | 2026-09-03 | 2026-09-05 | 2026-09-08 | 2026-09-14 | 2026-09-16 | 96 | ZA2 | Jafar | Waist | AOE | peyote-1632 pcs,,dawn pink-5589 pcs both combo one part all over 1 clr flat emb |  |  | NFL3 |  |  | Cut Ok | 211 | 211 | 0 | 7379 | 158 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 38 | Aug'2 |  |  | 06.08.26
BS-NMT | 47921 | 13263838 | 12823 | 1218 | 2026-06-10 | 2026-06-17 | LS Body w shlder and btm snap btn | Body |  |  | 2026-07-10 | 2026-07-18 | 2026-07-20 | 2026-08-04 |  |  | 2026-08-06 | 2026-08-06 | 2026-08-12 | 2026-08-14 | 2026-08-29 | 2026-08-19 | 2026-08-23 |  |  | 2026-08-17 | 2026-08-27 | 2026-08-27 | 2026-09-08 |  |  | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-14 | 2026-09-16 | 96 | T2 | Jafar | Nk | AOE | peyote-4556 pcs,,dawn pink-6821 pcs,Lilas-1446 pcs both combo chest all over 1 clr flat emb |  |  | NFL3 |  |  | Cut Ok | 1218 | 1218 | 0 | 13270 | 447 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46223 | 0 | 38 | Aug'2 |  |  | 06.08.26
BS-NMT | 47919 | 13263396 | 12351 | 1832 | 2026-06-10 | 2026-06-17 | SS o nk TS | TS |  |  | 2026-07-03 | 2026-07-10 | 2026-07-15 | 2026-07-30 |  |  | 2026-08-01 | 2026-08-01 | 2026-08-10 | 2026-08-12 | 2026-08-15 | 2026-08-14 | 2026-08-20 |  |  |  |  | 2026-08-22 | 2026-08-29 |  |  | 2026-08-31 | 2026-09-03 | 2026-09-08 | 2026-09-14 | 2026-09-16 | 96 | W1 | Jafar | Fr & Bk & Nk |  | Navy-5684 pcs frt back 1 clr puff 1 clr gltr ,,white-6667 pcs frt back 2 clr puff 1 clr gltr |  |  | NFL3 |  |  | Cut Ok | 1833 | 1833 | 0 | 12607 | 256 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46218 | 0 | 38 | Aug'2 |  |  | 06.08.26
BS-NMT | 43326 13th | 13242465 | 2278 | 672 | 2026-06-10 | 2026-06-17 | Swt Long pant w pkt | Pant |  |  | 2026-07-10 | 2026-07-15 | 2026-07-20 | 2026-08-06 |  |  | 2026-08-10 | 2026-08-10 |  | 2026-08-17 | 2026-08-18 | [6 empty] | 2026-08-20 | 2026-08-22 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-31 | 2026-09-14 | 2026-09-16 | 96 | U | Jafar | [5 empty] | NFL3 |  |  | Cut Ok | 672 | 672 | 0 | 2367 | 89 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46223 | 0 | 38 | Aug'2 |  |  | 18.07.26
BS-NMT | 43316 26th | 13234729 | 14012 | 2313 | 2026-06-10 | 2026-06-17 | LS o nk TS | TS |  |  | 2026-07-01 | 2026-07-13 | 2026-07-15 | 2026-07-30 |  |  | 2026-08-01 | 2026-08-01 |  | 2026-08-07 | 2026-08-11 | 2026-08-10 | 2026-08-13 |  |  |  |  | 2026-08-13 | 2026-08-18 |  |  | 2026-08-21 | 2026-08-25 | 2026-08-31 | 2026-09-14 | 2026-09-16 | 96 | ZA1 | Jafar | Nk |  | 4 combo label print |  |  | NFL3 |  |  | Cut Ok | 2312 | 2312 | 0 | 14288 | 276 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46218 | 0 | 38 | Aug'1 |  |  | 18.07.26
BS-NMT | 46499 2nd | 13259554 | 6122 | 1133 | 2026-06-10 | 2026-06-17 | LS AOP Dress | Dress |  |  | 2026-07-02 | 2026-07-11 | 2026-07-14 | 2026-07-27 | 2026-08-01 | 2026-08-10 | 2026-08-12 | 2026-08-12 |  | 2026-08-17 | 2026-08-20 | 2026-08-19 | 2026-08-21 |  |  |  |  | 2026-08-22 | 2026-08-27 |  |  | 2026-08-31 | 2026-09-03 | 2026-09-05 | 2026-09-14 | 2026-09-16 | 96 | Y | Jafar | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 1133 | 1133 | 0 | 6265 | 143 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46217 | 0 | 38 | Aug'2 |  |  | 30.07.26
BS-NMT | 44023 12th | 13246492 | 8434 | 478 | 2026-06-10 | 2026-06-17 | AOP Legging | Legging |  |  | 2026-07-10 | 2026-07-15 | 2026-07-17 | 2026-07-30 | 2026-08-01 | 2026-08-10 | 2026-08-10 | 2026-08-10 |  | 2026-08-16 | 2026-08-19 | 2026-08-18 | 2026-08-21 |  |  |  |  | 2026-08-22 | 2026-08-26 |  |  | 2026-08-28 | 2026-08-31 | 2026-09-09 | 2026-09-14 | 2026-09-16 | 96 | ZA2 | Jafar | waist |  | 3 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 477 | 477 | 0 | 8625 | 191 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46220 | 0 | 38 | Aug'2 |  |  | 20.07.26
BS-NMT | 44020 12th | 13246480 | 4424 | 435 | 2026-06-10 | 2026-06-17 | AOP LS body Suit w snap btn | Body |  |  | 2026-07-07 | 2026-07-12 | 2026-07-16 | 2026-07-28 | 2026-08-01 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-15 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 |  |  |  |  | 2026-08-22 | 2026-08-26 |  |  | 2026-08-28 | 2026-09-05 | 2026-09-07 | 2026-09-14 | 2026-09-16 | 96 | T2 | Jafar | Nk |  | 1 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 435 | 435 | 0 | 4498 | 74 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46219 | 0 | 38 | Aug'2 |  |  | 08.08.26
BS-NMT | 43317 18th | 13238720 | 4064 | 891 | 2026-06-10 | 2026-06-17 | AOP TROUSER W SIDE PKT | TROUSER |  |  | 2026-07-06 | 2026-07-11 | 2026-07-15 | 2026-07-29 | 2026-08-01 | 2026-08-10 | 2026-08-12 | 2026-08-12 |  | 2026-08-17 | 2026-08-19 | [6 empty] | 2026-08-21 | 2026-08-25 |  |  | 2026-08-27 | 2026-08-29 | 2026-09-06 | 2026-09-14 | 2026-09-16 | 96 | U | Jafar |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 891 | 827 | -64 | 4148 | 84 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46218 | 0 | 38 | Aug'2
BS-NMT | 46491 4th | 13225095 | 13334 | 1883 | 2026-06-10 | 2026-06-18 | YD LS o nk TS | TS | 2026-07-25 | 2026-07-08 | 2026-07-10 | 2026-07-25 | 2026-07-24 | 2026-08-03 |  |  | 2026-08-01 | 2026-08-01 |  | 2026-08-13 | 2026-08-18 | 2026-08-17 | 2026-08-21 |  |  |  |  | 2026-08-20 | 2026-08-31 |  |  | 2026-09-03 | 2026-09-05 | 2026-09-07 | 2026-09-14 | 2026-09-16 | 96 | L1 | Jafar | Chest,Nk |  | indigo-2672 pcs,,green-2000 pcs,,Sepia-8662 pcs all combo 1 clr puff print | YD |  | NFL2 |  |  | Cut Ok | 1884 | 1842 | -42 | 13669 | 335 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46227 | 0 | 38 | Aug'2 |  |  | 18.07.26
BS-NMT | 43323 31th | 13180124 | 8703 | 1069 | 2026-06-10 | 2026-06-18 | GIRLS SOLID LEGGINGS | Legging |  |  | 2026-07-02 | 2026-07-08 | 2026-07-15 | 2026-07-30 |  |  | 2026-08-06 | 2026-08-06 |  | 2026-08-11 | 2026-08-14 | 2026-08-14 | 2026-08-17 |  |  |  |  | 2026-08-19 | 2026-08-22 |  |  | 2026-08-25 | 2026-08-27 | 2026-09-03 | 2026-09-14 | 2026-09-16 | 96 | D2 | Jafar | WAIST |  | 5 combo label print |  |  | NFL1 |  |  | Cut Ok | 1069 | 1069 | 0 | 9000 | 297 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46218 | 0 | 38 | Aug'2 |  |  | 18.07.26
BS-NMT | 44019 17th | 13247093 | 2925 | 541 | 2026-06-10 | 2026-06-18 | Weist belt legging | Legging |  |  | 2026-07-12 | 2026-07-18 | 2026-07-25 | 2026-08-10 |  |  | 2026-08-14 | 2026-08-14 |  | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-23 |  |  |  |  | 2026-08-24 | 2026-08-27 |  |  | 2026-08-29 | 2026-09-03 | 2026-09-07 | 2026-09-14 | 2026-09-16 | 96 | T1 | Jafar | WAIST |  | 2 combo label print |  |  | NFL3 |  |  | Cut Ok | 541 | 541 | 0 | 3018 | 93 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46228 | 0 | 38 | Aug'2 |  |  | 25.07.26
BS-NMT | 43319 21th | 13238718 | 8564 | 1629 | 2026-06-10 | 2026-06-18 | AOP LS Swt shirt | Swt Shirt |  |  | 2026-07-02 | 2026-07-11 | 2026-07-14 | 2026-07-31 | 2026-08-02 | 2026-08-12 | 2026-08-14 | 2026-08-14 |  | 2026-08-19 | 2026-08-21 | [6 empty] | 2026-08-22 | 2026-08-27 |  |  | 2026-08-29 | 2026-09-03 | 2026-09-07 | 2026-09-12 | 2026-09-14 | 94 | W1 | Jafar |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 1630 | 1630 | 0 | 12899 | 4335 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46217 | 0 | 38 | Aug'2 |  |  | 18.07.26
BS-NMT | 46494 3rd | 13242490 | 8208 | 1599 | 2026-06-10 | 2026-06-20 | LS YD o nk TS | TS | 2026-07-01 | 2026-07-10 | 2026-07-12 | 2026-07-24 | 2026-07-22 | 2026-08-01 |  |  | 2026-08-01 | 2026-08-01 |  | 2026-08-10 | 2026-08-14 | 2026-08-12 | 2026-08-17 |  |  |  |  | 2026-08-17 | 2026-08-22 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-31 | 2026-09-13 | 2026-09-15 | 95 | Z | Jafar | Chest,Nk |  | Tender-2784 pcs,,Navy-2784 pcs ,,d.sapp-1320 pcs,,white-1320pcs all combo 1 clr gltr print | YD |  | NFL3 |  |  | Cut Ok | 1601 | 1601 | 0 | 8494 | 286 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 38 | Aug'1 |  |  | 25.07.26
BS-NMT | 46493 3rd | 13242426 | 9940 | 1384 | 2026-06-10 | 2026-06-20 | LS YD TS w slder frill | TS | 2026-07-01 | 2026-07-10 | 2026-07-13 | 2026-07-25 | 2026-07-29 | 2026-08-07 |  |  | 2026-08-10 | 2026-08-10 |  | 2026-08-15 | 2026-08-20 | 2026-08-19 | 2026-08-24 |  |  |  |  | 2026-08-24 | 2026-08-31 |  |  | 2026-09-03 | 2026-09-05 | 2026-09-08 | 2026-09-14 | 2026-09-16 | 96 | A | Jafar | Chest,Nk |  | d.sapp-2072 pcs,,white-2072 pcs,,tendor YD-2898,,Tendor solid-2898 pcs all combo 1 clr gltr print | YD |  | NFL1 |  |  | Cut Ok | 1386 | 1386 | 0 | 10310 | 370 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46232 | 0 | 38 | Aug'2 |  |  | 25.07.26
BS-NMT | 47924 | 13264822 | 4170 | 410 | 2026-06-10 | 2026-06-20 | LS Body w shlder and btm snap btn | Body |  |  | 2026-07-10 | 2026-07-16 | 2026-07-24 | 2026-08-07 |  |  | 2026-08-10 | 2026-08-10 | 2026-08-15 | 2026-08-17 | 2026-08-20 | 2026-08-20 | 2026-08-22 |  |  | 2026-08-20 | 2026-08-25 | 2026-08-27 | 2026-08-31 |  |  | 2026-09-03 | 2026-09-05 | 2026-09-08 | 2026-09-13 | 2026-09-15 | 95 | T2 | Jafar | Nk | Chest | Lilas-2085 pcss 1 clr flat all over emb at chest,,wild-2085 pcs no emb |  |  | NFL3 |  |  | Cut Ok | 410 | 410 | 0 | 4411 | 241 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46227 | 0 | 38 | Aug'2 |  |  | 06.08.26
BS-NMT | 47925 | 13264824 | 3678 | 377 | 2026-06-10 | 2026-06-20 | LS Body w shlder and btm snap btn | Body |  |  | 2026-07-10 | 2026-07-15 | 2026-07-22 | 2026-08-04 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-13 | 2026-08-15 | 2026-08-18 | 2026-08-20 | 2026-08-22 |  |  | 2026-08-19 | 2026-08-25 | 2026-08-27 | 2026-08-31 |  |  | 2026-09-03 | 2026-09-05 | 2026-09-10 | 2026-09-13 | 2026-09-15 | 95 | T2 | Jafar | Nk | Chest | Citadel-1839 pcs 1 clr flat all over emb at chest,,spellbound-1839 pcs no emb |  |  | NFL3 |  |  | Cut Ok | 376 | 376 | 0 | 3805 | 127 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 38 | Aug'2 |  |  | 06.08.26
BS-NMT | 47923 | 13264623 | 6432 | 929 | 2026-06-10 | 2026-06-20 | YD LS o nk TS | TS | 2026-07-12 | 2026-07-18 | 2026-07-20 | 2026-08-04 | 2026-08-07 | 2026-08-13 |  |  | 2026-08-15 | 2026-08-15 | 2026-08-21 | 2026-08-24 | 2026-08-27 | 2026-08-27 | 2026-08-29 |  |  |  |  | 2026-09-01 | 2026-09-05 |  |  | 2026-09-08 | 2026-09-09 | 2026-09-11 | 2026-09-14 | 2026-09-16 | 96 | Z | Jafar | Nk |  | 2 combo label print | YD |  | NFL3 |  |  | Cut Ok | 1471 | 1471 | 0 | 6645 | 213 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46241 | 0 | 38 | Aug'3 |  |  | 11.08.26
BS-NMT | 47956 | 13263826 | 2909 | 1534 | 2026-06-10 | 2026-06-22 | Swt pant w side bk pkt and drawstring | Pant |  |  | 2026-07-05 | 2026-07-15 | 2026-07-22 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-10 | 2026-08-18 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 2026-08-28 |  |  |  |  | 2026-09-01 | 2026-09-05 |  |  | 2026-09-08 | 2026-09-10 | 2026-09-15 | 2026-09-21 | 2026-09-23 | 103 | X+Y | Tomal | Thigh |  | crockery-804 pcs,,basil-1310 pcs,,grey-795 pcs all combo 1 clr HD 1 clr rub print |  | woven label | NFL3 |  |  | Cut Ok | 1535 | 1535 | 0 | 3065 | 156 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 39 | Aug'2 |  |  | 11.08.26
BS-NMT | 47948 | 13252737 | 2230 | 816 | 2026-06-10 | 2026-06-22 | LS cut & sew reglan Swt hoody w hood and bk horn | Hoody |  |  | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-08-10 |  |  | 2026-08-13 | 2026-08-13 | 2026-08-18 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 2026-08-28 |  |  |  |  | 2026-09-01 | 2026-09-04 |  |  | 2026-09-07 | 2026-09-09 | 2026-09-14 | 2026-09-21 | 2026-09-23 | 103 | S | Tomal | Chest |  | crockery-1325 pcs,,basil-905 pcs both combo 1 clr puff print |  |  | NFL3 |  |  | Cut Ok | 817 | 817 | 0 | 2281 | 51 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 39 | Aug'2 |  |  | 06.08.26
BS-NMT | 47953 | 13263760 | 1627 | 801 | 2026-06-10 | 2026-06-22 | LS Swt hoody w kangaro pkt | Hoody |  |  | 2026-07-10 | 2026-07-15 | 2026-07-22 | 2026-08-10 |  |  | 2026-08-12 | 2026-08-12 | 2026-08-18 | 2026-08-20 | 2026-08-21 | 2026-08-24 | 2026-08-28 |  |  |  |  | 2026-09-01 | 2026-09-03 |  |  | 2026-09-07 | 2026-09-08 | 2026-09-12 | 2026-09-21 | 2026-09-23 | 103 | S | Tomal | Fr,Bk |  | basil-806 pcs,,grey-821 pcs both combo frt back 1 clr rub |  | woven label | NFL3 |  |  | Cut Ok | 802 | 802 | 0 | 1695 | 68 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 39 | Aug'2 |  |  | 11.08.26
BS-NMT | 47962 | 13264503 | 1002 | 488 | 2026-06-10 | 2026-06-22 | LS Swt hoody w cuff btm rib | Hoody |  |  | 2026-07-10 | 2026-07-15 | 2026-07-23 | 2026-08-10 |  |  | 2026-08-12 | 2026-08-12 | 2026-08-18 | 2026-08-20 | 2026-08-21 | 2026-08-24 | 2026-08-28 |  |  |  |  | 2026-09-02 | 2026-09-04 |  |  | 2026-09-07 | 2026-09-09 | 2026-09-12 | 2026-09-21 | 2026-09-23 | 103 | S | Tomal | Fr,Bk |  | black-1002 pcs frt 5 clr puff back 7 clr rub print |  |  | NFL3 |  |  | Cut Ok | 487 | 487 | 0 | 1037 | 35 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46226 | 0 | 39 | Aug'2 |  |  | 06.08.26
BS-NMT | 47958 | 13264045 | 3438 | 1034 | 2026-06-10 | 2026-06-22 | LS Swt Shirt nk and btm contrast double layer | Swt Shirt |  |  | 2026-07-05 | 2026-07-15 | 2026-07-20 | 2026-08-10 |  |  | 2026-08-13 | 2026-08-13 | 2026-08-19 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 2026-08-28 |  |  |  |  | 2026-09-03 | 2026-09-07 |  |  | 2026-09-09 | 2026-09-12 | 2026-09-15 | 2026-09-21 | 2026-09-23 | 103 | S | Tomal | Chest |  | Basil-1275 pcs,,mosstone-1362 pcs,,blue-801 pcs all combo chest embossed print |  | Flag label | NFL3 |  |  | Cut Ok | 1035 | 1035 | 0 | 3563 | 125 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46223 | 0 | 39 | Aug'3 |  |  | 19.08.26
BS-NMT | 47955 | 13263825 | 2240 | 938 | 2026-06-10 | 2026-06-22 | LS Swt Shirt nk and btm contrast double layer | Swt Shirt |  |  | 2026-07-05 | 2026-07-15 | 2026-07-20 | 2026-08-09 |  |  | 2026-08-11 | 2026-08-11 | 2026-08-17 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-28 |  |  |  |  | 2026-09-02 | 2026-09-05 |  |  | 2026-09-08 | 2026-09-10 | 2026-09-12 | 2026-09-21 | 2026-09-23 | 103 | S | Tomal | Chest |  | Basil-1456 pcs,,mosstone-784 pcs,,blue-801 pcs all combo 1 clr rub chest embossed print |  |  | NFL3 |  |  | Cut Ok | 982 | 969 | -13 | 2311 | 71 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46223 | 0 | 39 | Aug'2 |  |  | 04.09.26
BS-NMT | 47952 | 13263756 | 1660 | 624 | 2026-06-10 | 2026-06-22 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-07-12 | 2026-07-17 | 2026-07-25 | 2026-08-10 |  |  | 2026-08-12 | 2026-08-12 | 2026-08-18 | 2026-08-20 | 2026-08-21 | 2026-08-24 | 2026-08-27 |  |  |  |  | 2026-09-01 | 2026-09-02 |  |  | 2026-09-04 | 2026-09-07 | 2026-09-10 | 2026-09-21 | 2026-09-23 | 103 | Y | Tomal | Chest |  | Spellbound-1660 pcs photo print |  | woven label | NFL3 |  |  | Cut Ok | 624 | 624 | 0 | 1720 | 60 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46228 | 0 | 39 | Aug'2 |  |  | 26.08.26
BS-NMT | 47957 | 13264043 | 2252 | 422 | 2026-06-10 | 2026-06-22 | SS o nk TS | TS |  |  | 2026-07-10 | 2026-07-15 | 2026-07-25 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-10 | 2026-08-15 | 2026-08-18 | 2026-08-19 | 2026-08-21 | 2026-08-25 |  |  |  |  | 2026-08-27 | 2026-08-28 |  |  | 2026-08-31 | 2026-09-03 | 2026-09-06 | 2026-09-21 | 2026-09-23 | 103 | W2 | Tomal | Chest,Nk |  | Basil-996 pcs,,spellbound-1256 pcs both combo 3 clr rub 1 clr HD print |  | woven label | NFL3 |  |  | Cut Ok | 423 | 423 | 0 | 2328 | 76 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46228 | 0 | 39 | Aug'2 |  |  | 06.08.26
BS-NMT | 47954 | 13263761 | 4712 | 938 | 2026-06-10 | 2026-06-22 | SS o nk TS w blind stitch | TS |  |  | 2026-07-07 | 2026-07-14 | 2026-07-22 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-10 | 2026-08-15 | 2026-08-17 | 2026-08-19 | 2026-08-20 | 2026-08-25 |  |  |  |  | 2026-08-27 | 2026-08-31 |  |  | 2026-09-02 | 2026-09-04 | 2026-09-08 | 2026-09-21 | 2026-09-23 | 103 | W2 | Tomal | Fr & Bk & Nk |  | basil-2636 pcs,,c.dancer-2076 pcs both combo frt 1 clr rub back photo print |  | Flag label | NFL3 |  |  | Cut Ok | 938 | 938 | 0 | 4924 | 212 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 39 | Aug'2 |  |  | 06.08.26
BS-NMT | 47951 | 13263679 | 2268 | 397 | 2026-06-10 | 2026-06-22 | SS o nk TS | TS |  |  | 2026-07-10 | 2026-07-15 | 2026-07-24 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-10 | 2026-08-15 | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-25 |  |  |  |  | 2026-08-27 | 2026-08-29 |  |  | 2026-09-02 | 2026-09-04 | 2026-09-07 | 2026-09-21 | 2026-09-23 | 103 | ZA1 | Tomal | Chest,Nk |  | Basil-1296 pcs 3 clr rub 2 clr puff print ,,spelbound-1626 pcs 4 clr rub 2 clr puf print |  | Flag label | NFL3 |  |  | Cut Ok | 397 | 397 | 0 | 3030 | 762 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46227 | 0 | 39 | Aug'2 |  |  | 06.08.26
BS-NMT | 47963 | 13264504 | 6084 | 1079 | 2026-06-10 | 2026-06-22 | SS o nk TS | TS |  |  | 2026-07-07 | 2026-07-12 | 2026-07-21 | 2026-08-04 |  |  | 2026-08-08 | 2026-08-08 | 2026-08-14 | 2026-08-17 | 2026-08-19 | 2026-08-19 | 2026-08-25 |  |  |  |  | 2026-08-27 | 2026-08-31 |  |  | 2026-09-03 | 2026-09-05 | 2026-09-09 | 2026-09-21 | 2026-09-23 | 103 | W2 | Tomal | Fr & Bk & Nk |  | c.dan-2895 pcs front 1 clr puff back 1 clr rub ,,black-3189 pcs front 5 clr puff back 6 clr rub |  |  | NFL3 |  |  | Cut Ok | 1079 | 1079 | 0 | 6241 | 157 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46224 | 0 | 39 | Aug'2 |  |  | 06.08.26
BS-NMT | 47961 | 13264459 | 1008 | 175 | 2026-06-10 | 2026-06-22 | SS o nk TS w blind stitch | TS |  |  | 2026-07-12 | 2026-07-15 | 2026-08-01 | 2026-08-12 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-22 | 2026-08-25 | 2026-08-25 | 2026-08-27 | 2026-08-29 |  |  |  |  | 2026-09-01 | 2026-09-02 |  |  | 2026-09-04 | 2026-09-07 | 2026-09-10 | 2026-09-21 | 2026-09-23 | 103 | Z | Tomal | Chest,Nk |  | black-1008 pcss photo print |  |  | NFL3 |  |  | Cut Ok | 175 | 175 | 0 | 1054 | 46 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46235 | 0 | 39 | Aug'3 |  |  | 06.08.26
BS-NMT | 47959 | 13264047 | 3008 | 915 | 2026-06-10 | 2026-06-23 | Cut & sew Swt pant w side back pkt | Pant |  |  | 2026-07-06 | 2026-07-16 | 2026-07-21 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-10 | 2026-08-18 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 2026-08-29 |  |  |  |  | 2026-09-03 | 2026-09-09 |  |  | 2026-09-11 | 2026-09-14 | 2026-09-16 | 2026-09-21 | 2026-09-23 | 103 | X | Tomal | Pkt |  | crocory-840 pcs,,Basil-1406 pcs,,mosstone-762 pcs all combo amboosed print at pkt |  | Woven label | NFL3 |  |  | Cut Ok | 916 | 916 | 0 | 3125 | 117 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46224 | 0 | 39 | Aug'2 |  |  | 15.08.26
BS-NMT | 47960 | 13264052 | 6021 | 1064 | 2026-06-10 | 2026-06-23 | YD LS o nk TS | TS | 2026-07-10 | 2026-07-18 | 2026-07-22 | 2026-08-07 | 2026-08-12 | 2026-08-20 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-28 | 2026-09-01 | 2026-09-04 | [6 empty] | 2026-09-04 | 2026-09-10 |  |  | 2026-09-12 | 2026-09-14 | 2026-09-16 | 2026-09-21 | 2026-09-23 | 103 | Z | Tomal |  |  |  | YD |  | NFL3 |  |  | Cut Run | 1063 | 1055 | -8 | 3709 | -2312 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46246 | 0 | 39 | Sep'1 |  |  | 06.08.26
BS-NMT | 48038 | 13264383 | 4768 | 885 | 2026-06-10 | 2026-06-19 | SS o nk TS w btm lace gmts dye acid wash | TS |  |  | 2026-07-10 | 2026-07-17 | 2026-07-23 | 2026-07-31 |  |  | 2026-08-08 | 2026-08-08 | 2026-08-18 | 2026-08-21 | 2026-08-24 | 2026-09-07 | 2026-09-12 |  |  |  |  | 2026-08-25 | 2026-08-29 | 2026-08-31 | 2026-09-07 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-21 | 2026-09-23 | 103 | Z | Haider | Chest,Nk |  | black-2565 pcs,,Gray-2203 pcs both combo 2 clr rub print |  | Gmts dye acid wash | NFL3 |  |  | Cut Ok | 894 | 894 | 0 | 5433 | 665 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46226 | 0 | 39 | Aug'3 |  |  | 28.07.26
BS-NMT | 48039 | 13264387 | 2160 | 303 | 2026-06-10 | 2026-06-20 | SS o nk TS | TS |  |  | 2026-07-10 | 2026-07-15 | 2026-07-22 | 2026-08-06 |  |  | 2026-08-10 | 2026-08-10 | 2026-08-17 | 2026-08-20 | 2026-08-21 | 2026-08-24 | 2026-08-25 |  |  | 2026-08-24 | 2026-08-28 | 2026-09-01 | 2026-09-02 |  |  | 2026-09-04 | 2026-09-07 | 2026-09-10 | 2026-09-21 | 2026-09-23 | 103 | Z | Haider | Nk | Chest | Ice-1080 pcs,,c.dan-1080 pcs both combo 2 clr seq emb |  |  | NFL3 |  |  | Cut Ok | 304 | 304 | 0 | 2216 | 56 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 39 | Aug'2 |  |  | 28.07.26
BS-NMT | 48040 | 13264362 | 2634 | 461 | 2026-06-10 | 2026-06-20 | SS o nk TS | TS |  |  | 2026-07-12 | 2026-07-17 | 2026-07-22 | 2026-08-04 |  |  | 2026-08-08 | 2026-08-08 | 2026-08-14 | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-21 | 2026-08-24 | 2026-08-26 |  |  | 2026-08-28 | 2026-08-29 |  |  | 2026-09-02 | 2026-09-04 | 2026-09-07 | 2026-09-21 | 2026-09-23 | 103 | ZA1 | Haider | Chest,Nk & stone |  | cashmere-1212 pcs,,lce-1422 pcs both combo 1 clr flock print and 1 size HP stone at chest |  |  | NFL3 |  |  | Cut Ok | 460 | 460 | 0 | 2730 | 96 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 39 | Aug'2 |  |  | 06.08.26
BS-NMT | 48041 | 13259417 | 4881 | 616 | 2026-06-10 | 2026-06-20 | SS boat nk wrap shlder TS w side wrinkle effect | TS |  |  | 2026-07-10 | 2026-07-18 | 2026-07-22 | 2026-08-06 |  |  | 2026-08-08 | 2026-08-08 | 2026-08-15 | 2026-08-17 | 2026-08-19 | 2026-08-19 | 2026-08-21 |  |  |  |  | 2026-08-24 | 2026-08-27 |  |  | 2026-08-29 | 2026-08-31 | 2026-09-06 | 2026-09-19 | 2026-09-21 | 101 | Z | Haider | Nk |  | 4 combo nk label print |  |  | NFL3 |  |  | Cut Ok | 616 | 616 | 0 | 5008 | 127 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 39 | Aug'2 |  |  | 28.07.26
BS-NMT | 48045 | 13263716 | 5633 | 2548 | 2026-06-10 | 2026-06-20 | Elasted swt pant w barrel shape and side pkt | Pant |  |  | 2026-07-10 | 2026-07-18 | 2026-07-22 | 2026-08-10 |  |  | 2026-08-12 | 2026-08-12 | 2026-08-19 | 2026-08-21 | 2026-08-24 | [6 empty] | 2026-08-24 | 2026-08-31 |  |  | 2026-09-03 | 2026-09-07 | 2026-09-10 | 2026-09-19 | 2026-09-21 | 101 | X | Haider | [5 empty] | NFL3 |  |  | Cut Ok | 2549 | 2549 | 0 | 5835 | 202 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 39 | Aug'3 |  |  | 28.07.26
BS-NMT | 48046 | 13263715 | 5531 | 3925 | 2026-06-10 | 2026-06-20 | LS Double layer elasted ballon hem Hoody w kangaroo pkt | Hoody |  |  | 2026-07-05 | 2026-07-15 | 2026-07-20 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-10 | 2026-08-18 | 2026-08-20 | 2026-08-24 | [6 empty] | 2026-08-24 | 2026-08-31 |  |  | 2026-09-03 | 2026-09-05 | 2026-09-08 | 2026-09-19 | 2026-09-21 | 101 | S+T1 | Haider | [5 empty] | NFL3 |  |  | Cut Ok | 3925 | 3925 | 0 | 5714 | 183 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46223 | 0 | 39 | Aug'2 |  |  | 07.08.26
BS-NMT | 48047 | 13264215 | 3956 | 1089 | 2026-06-10 | 2026-06-20 | LS Swt Shirt dress w nk cuff btm rib btm S/J mesh attach | Dress |  |  | 2026-07-07 | 2026-07-15 | 2026-07-22 | 2026-08-10 |  |  | 2026-08-13 | 2026-08-13 | 2026-08-19 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 2026-08-29 |  |  |  |  | 2026-09-01 | 2026-09-05 |  |  | 2026-09-07 | 2026-09-09 | 2026-09-12 | 2026-09-21 | 2026-09-23 | 103 | S | Haider | Chest |  | blue-910 pcs,,violet-3046 pcs both combo 1 clr gltr gel print |  |  | NFL3 |  |  | Cut Ok | 1089 | 1083 | -6 | 4039 | 83 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 39 | Aug'3 |  |  | 28.07.26
BS-NMT | 48048 | 13267097 | 900 | 88 | 2026-06-10 | 2026-06-20 | Elasted legging w letus | Legging |  |  | 2026-07-17 | 2026-07-20 | 2026-07-25 | 2026-08-08 |  |  | 2026-08-12 | 2026-08-12 | 2026-08-18 | 2026-08-20 | 2026-08-20 | 2026-08-24 | 2026-08-24 |  |  | 2026-08-24 | 2026-08-27 | 2026-09-01 | 2026-09-02 |  |  | 2026-09-04 | 2026-09-07 | 2026-09-10 | 2026-09-21 | 2026-09-23 | 103 | Z | Haider | Waist | AOE | pink-900 pcs 4 part 3 clr flat all over emb |  |  | NFL3 |  |  | Cut Ok | 88 | 88 | 0 | 960 | 60 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46228 | 0 | 39 | Aug'2 |  |  | 28.07.26
BS-NMT | 48049 | 13267096 | 1110 | 132 | 2026-06-10 | 2026-06-20 | LS o nk TS w letus stich | TS |  |  | 2026-07-15 | 2026-07-18 | 2026-07-25 | 2026-08-08 |  |  | 2026-08-12 | 2026-08-12 | 2026-08-18 | 2026-08-20 | 2026-08-20 | 2026-08-24 | 2026-08-25 |  |  | 2026-08-24 | 2026-08-28 | 2026-09-01 | 2026-09-02 |  |  | 2026-09-04 | 2026-09-07 | 2026-09-09 | 2026-09-21 | 2026-09-23 | 103 | Z | Haider | Nk | AOE | pink-1110 pcs 3 clr flat all over emb at chest |  |  | NFL3 |  |  | Cut Ok | 132 | 132 | 0 | 1160 | 50 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46228 | 0 | 39 | Aug'2 |  |  | 06.08.26
BS-NMT | 48043 | 13263727 | 1005 | 416 | 2026-06-10 | 2026-06-22 | LS reglan Swt Shirt w rib | Swt Shirt |  |  | 2026-07-10 | 2026-07-16 | 2026-07-25 | 2026-08-10 |  |  | 2026-08-15 | 2026-08-15 | 2026-08-22 | 2026-08-25 | 2026-08-25 |  |  | 2026-09-02 | 2026-09-10 |  |  | 2026-08-27 | 2026-08-28 |  |  | 2026-09-12 | 2026-09-14 | 2026-09-15 | 2026-09-21 | 2026-09-23 | 103 | Z | Haider | Stone |  | black -1005 pcs slve and nk seam line HP stone |  |  | NFL3 |  |  | Cut Ok | 413 | 413 | 0 | 1074 | 69 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46228 | 0 | 39 | Aug'3 |  |  | 28.07.26
BS-NMT | 48042 | 13263722 | 1389 | 524 | 2026-06-10 | 2026-06-22 | YS LS boat nk Long dress w side slit | Dress | 2026-07-10 | 2026-07-16 | 2026-07-20 | 2026-07-30 | 2026-08-03 | 2026-08-08 |  |  | 2026-08-13 | 2026-08-13 | 2026-08-19 | 2026-08-21 | 2026-08-22 |  |  | 2026-08-25 | 2026-08-28 |  |  | 2026-09-01 | 2026-09-03 |  |  | 2026-09-05 | 2026-09-08 | 2026-09-10 | 2026-09-21 | 2026-09-23 | 103 | T2 | Haider | Stone |  | C.dan-1389 pcs stone HP at chest | YD |  | NFL3 |  |  | Cut Ok | 524 | 524 | 0 | 1462 | 73 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46237 | 0 | 39 | Aug'3 |  |  | 07.08.26
BS-NMT | 48050 | 13267591 | 1005 | 193 | 2026-06-10 | 2026-06-22 | LS o nk Dress w btm mesh | Dress |  |  | 2026-07-18 | 2026-07-25 | 2026-08-01 | 2026-08-15 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-26 | 2026-08-28 | 2026-08-29 | 2026-09-02 | 2026-09-02 |  |  | 2026-09-02 | 2026-09-04 | 2026-09-07 | 2026-09-09 |  |  | 2026-09-10 | 2026-09-12 | 2026-09-15 | 2026-09-21 | 2026-09-23 | 103 | S | Haider | Nk | Chest | Ice-1005 pcs 1 clr flat emb |  | Mesh | NFL3 |  |  | Cut Ok | 193 | 193 | 0 | 1044 | 39 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46235 | 0 | 39 | Aug'3 |  |  | 08.08.26
BS-NMT | 48054 | 13264032 | 1929 | 645 | 2026-06-10 | 2026-06-22 | LS cut & sew full zipper Swt Hoodie | Hoody |  |  | 2026-07-08 | 2026-07-14 | 2026-07-22 | 2026-08-03 |  |  | 2026-08-06 | 2026-08-06 | 2026-08-12 | 2026-08-14 | 2026-08-15 |  |  |  |  | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-29 | 2026-09-06 | 2026-09-21 | 2026-09-23 | 103 | S | Haider |  | Slv | Violet-1929 pcs one slve 3 clr flat emb |  |  | NFL3 |  |  | Cut Run | 645 | 645 | 0 | 1653 | -276 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 39 | Aug'2 |  |  | 25.07.26
BS-NMT | 48055 | 13264034 | 1372 | 341 | 2026-06-10 | 2026-06-22 | Swt Pant w side pkt | Swt Shirt |  |  | 2026-07-10 | 2026-07-15 | 2026-07-23 | 2026-09-07 |  |  | 2026-08-11 | 2026-08-11 | 2026-08-17 | 2026-08-19 | 2026-08-20 | [6 empty] | 2026-08-22 | 2026-08-25 |  |  | 2026-08-27 | 2026-08-29 | 2026-09-03 | 2026-09-21 | 2026-09-23 | 103 | X | Haider | [5 empty] | NFL3 |  |  | Cut Ok | 341 | 341 | 0 | 1483 | 111 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46226 | 0 | 39 | Aug'2 |  |  | 25.07.26
BS-NMT | 48053 | 13264821 | 1150 | 232 | 2026-06-10 | 2026-06-22 | YD LS dress w btm mesh | Dress | 2026-07-12 | 2026-07-18 | 2026-07-22 | 2026-08-03 | 2026-08-07 | 2026-08-15 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-25 | 2026-08-28 | 2026-08-29 | 2026-09-01 | 2026-09-02 |  |  |  |  | 2026-09-07 | 2026-09-09 |  |  | 2026-09-12 | 2026-09-15 | 2026-09-18 | 2026-09-21 | 2026-09-23 | 103 | S | Haider | Nk |  | 1 combo label print | YD |  | NFL3 |  |  | Cut Ok | 233 | 233 | 0 | 1199 | 49 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46241 | 0 | 39 | Aug'3 |  |  | 28.07.26
BS-NMT | 48052 | 13267576 | 2170 | 316 | 2026-06-10 | 2026-06-23 | YD LS O Nk TS | TS | 2026-07-15 | 2026-07-20 | 2026-07-25 | 2026-08-04 | 2026-08-07 | 2026-08-15 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-26 | 2026-08-28 | 2026-08-29 | 2026-09-01 | 2026-09-02 |  |  |  |  | 2026-09-04 | 2026-09-07 |  |  | 2026-09-09 | 2026-09-12 | 2026-09-15 | 2026-09-21 | 2026-09-23 | 103 | Z | Haider | Nk |  | 1 combo label print | YD |  | NFL3 |  |  | Cut Ok | 316 | 316 | 0 | 2244 | 74 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46241 | 0 | 39 | Aug'3 |  |  | 28.07.26
BS-NMT | 48051 | 13267577 | 2155 | 264 | 2026-06-10 | 2026-06-23 | YD Elasted Legging | Legging | 2026-07-18 | 2026-07-24 | 2026-07-27 | 2026-08-06 | 2026-08-08 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-22 | 2026-08-25 | 2026-08-26 | 2026-08-28 | 2026-08-29 |  |  |  |  | 2026-09-01 | 2026-09-03 |  |  | 2026-09-05 | 2026-09-08 | 2026-09-10 | 2026-09-21 | 2026-09-23 | 103 | ZA2 | Haider | Waist |  | 1 combo label print | YD |  | NFL3 |  |  | Cut Ok | 264 | 264 | 0 | 2210 | 55 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46242 | 0 | 39 | Aug'3 |  |  | 06.08.26
BS-NMT | 48044 | 13267470 | 5080 | 1080 | 2026-06-10 | 2026-06-23 | YD SS o nk TS | TS | 2026-07-12 | 2026-07-20 | 2026-07-22 | 2026-08-06 | 2026-08-10 | 2026-08-17 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-26 | 2026-08-28 | 2026-09-01 | 2026-09-01 | 2026-09-03 |  |  |  |  | 2026-09-04 | 2026-09-09 |  |  | 2026-09-11 | 2026-09-14 | 2026-09-16 | 2026-09-19 | 2026-09-21 | 101 | Z | Haider | Nk |  | 3 combo label print | YD |  | NFL3 |  |  | Cut Ok | 1257 | 1245 | -12 | 5288 | 208 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46244 | 0 | 39 | Aug'3 |  |  | 06.08.26
BS-NMT | 48058 | 13264030 | 810 | 126 | 2026-06-10 | 2026-06-23 | LS puff Slve Cut&sew TS | TS |  |  | 2026-07-27 | 2026-08-30 | 2026-08-10 | 2026-08-22 |  |  | 2026-08-25 | 2026-08-25 | 2026-09-01 | 2026-09-03 | 2026-09-03 | 2026-09-05 | 2026-09-10 |  |  |  |  | 2026-09-12 | 2026-09-14 |  |  | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-21 | 101 | T2 | Haider | Chest,Nk |  | Ice-810 pcs 2 clr rub 3 clr gltr gel print |  |  | NFL3 |  |  | Cut Ok | 125 | 125 | 0 | 825 | 15 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46244 | 0 | 39 | Sep'1 |  |  | 25.07.26
BS-NMT | 48059 | 13264005 | 2607 | 493 | 2026-06-10 | 2026-06-23 | YD elasted Flared Pant | Pant | 2026-07-17 | 2026-07-25 | 2026-08-01 | 2026-08-10 | 2026-08-18 | 2026-08-24 |  |  | 2026-08-27 | 2026-08-27 | 2026-09-03 | 2026-09-05 | 2026-09-07 | 2026-09-09 | 2026-09-10 |  |  |  |  | 2026-09-12 | 2026-09-12 |  |  | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-21 | 2026-09-23 | 103 | T1 | Haider | Waist |  | 3 combo label print | YD |  | NFL3 |  |  | Cut Run | 493 | 493 | 0 | 1046 | -1561 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46252 | 0 | 39 | Sep'1 |  |  | 25.07.26
BS-NMT | 48056 | 13263670 | 1840 | 620 | 2026-06-10 | 2026-06-23 | LS Swt dress w cut & sew | Dress |  |  | 2026-07-15 | 2026-07-20 | 2026-08-01 | 2026-08-17 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-26 | 2026-08-28 | 2026-08-29 | 2026-09-01 | 2026-09-04 |  |  |  |  | 2026-09-07 | 2026-09-09 |  |  | 2026-09-11 | 2026-09-14 | 2026-09-17 | 2026-09-21 | 2026-09-23 | 103 | T2 | Haider | Chest |  | blue-935 pcs,,violet-905 pcs both combo 4 clr rub 1 clr gltr print |  |  | NFL3 |  |  | Cut Ok | 620 | 620 | 0 | 1895 | 55 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46235 | 0 | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48060 | 13264002 | 4387 | 1245 | 2026-06-10 | 2026-06-23 | LS Swt Shirt w cuff btm rib | Swt Shirt |  |  | 2026-07-15 | 2026-07-24 | 2026-08-01 | 2026-08-18 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-26 | 2026-08-28 | 2026-08-30 | 2026-09-01 | 2026-09-04 |  |  |  |  | 2026-09-07 | 2026-09-10 |  |  | 2026-09-11 | 2026-09-14 | 2026-09-16 | 2026-09-21 | 2026-09-23 | 103 | Y | Haider | Chest |  | blue-871 pcss,,vanila-957 pcs,,pepper-792 pcs,,violet-1767 pcs all combo 1 clr puff gltr print |  |  | NFL3 |  |  | Cut Ok | 1245 | 927 | -318 | 4569 | 182 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46235 | 0 | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48057 | 13263652 | 5608 | 1483 | 2026-06-10 | 2026-06-23 | LS Swt Shirt w cuff btm rib | Swt Shirt |  |  | 2026-07-01 | 2026-07-10 | 2026-07-16 | 2026-08-04 |  |  | 2026-08-08 | 2026-08-08 | 2026-08-15 | 2026-08-17 | 2026-08-20 | 2026-08-20 | 2026-08-31 |  |  |  |  | 2026-09-01 | 2026-09-04 |  |  | 2026-09-07 | 2026-09-09 | 2026-09-14 | 2026-09-21 | 2026-09-23 | 103 | W2 | Haider | Fr & Bk & Slv |  | chocolate-3482 pcs,,violet-2126 pcs both combo frt back both slve 2 clr rub 1 clr puff gltr print |  |  | NFL3 |  |  | Cut Ok | 1484 | 1484 | 0 | 5793 | 185 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46219 | 0 | 39 | Aug'2 |  |  | 25.07.26
BS-ONL | 47890 | 15386646/15395980 | 2181 | 1127 | 2026-06-09 | 2026-06-17 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-07-06 | 2026-07-12 | 2026-07-15 | 2026-07-31 |  |  | 2026-08-08 | 2026-08-08 | 2026-08-15 | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-21 |  |  |  |  | 2026-08-24 | 2026-08-26 |  |  | 2026-08-28 | 2026-08-31 | 2026-09-07 | 2026-09-21 | 2026-09-23 | 104 | N2 | Khalid | Chest |  | stone-684 pcs,,green-1497 pcs both combo 1 clr rub print |  |  | NFL2 |  |  | Cut Run | 1126 | 1111 | -15 | 2002 | -179 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46218 | 0 | 39 | Aug'2 |  |  | 07.08.26
BS-ONL | 47976 | 15396688 | 2430 | 168 | 2026-06-16 | 2026-06-19 | Adustable strap v nk Tank top w nk Lace | Tank Top |  |  | 2026-07-12 | 2026-07-18 | 2026-07-23 | 2026-08-06 |  |  | 2026-08-11 | 2026-08-11 | 2026-08-17 | 2026-08-20 | 2026-08-21 | [6 empty] | 2026-08-24 | 2026-08-27 |  |  | 2026-08-29 | 2026-09-02 | 2026-09-05 | 2026-09-14 | 2026-09-16 | 90 | Q | Dalim |  |  |  |  | Lace | NFL2 |  |  | Cut Ok | 168 | 168 | 0 | 2478 | 48 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46226 | 0 | 38 | Aug'2 |  |  | 22.07.26
BS-ONL | 47975 | 15396687 | 4470 | 1326 | 2026-06-16 | 2026-06-19 | Long plazoo w waist elastic lace and bow attach | Plazo |  |  | 2026-07-01 | 2026-07-15 | 2026-07-23 | 2026-08-08 |  |  | 2026-08-14 | 2026-08-14 | 2026-08-20 | 2026-08-22 | 2026-08-25 | [6 empty] | 2026-08-26 | 2026-08-31 |  |  | 2026-09-03 | 2026-09-05 | 2026-09-08 | 2026-09-14 | 2026-09-16 | 90 | P | Dalim |  |  |  |  | Lace | NFL2 |  |  | Cut Ok | 1274 | 1274 | 0 | 4509 | 39 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46226 | 0 | 38 | Aug'3 |  |  | 22.07.26
BS-ONL | 47977 | 15396689 | 2670 | 467 | 2026-06-16 | 2026-06-20 | LS TS w nk lace and bow attach btm letus stitch | TS |  |  | 2026-07-13 | 2026-07-20 | 2026-07-25 | 2026-08-07 |  |  | 2026-08-10 | 2026-08-10 | 2026-08-15 | 2026-08-20 | 2026-08-21 | [6 empty] | 2026-08-24 | 2026-08-27 |  |  | 2026-08-29 | 2026-08-31 | 2026-09-06 | 2026-09-14 | 2026-09-16 | 90 | K | Dalim |  |  |  |  | Lace | NFL2 |  |  | Cut Ok | 469 | 469 | 0 | 2718 | 48 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46228 | 0 | 38 | Aug'2 |  |  | 10.08.26
OVS SPA | 47863 | 271TSH111-6156 | 3031 | 635 | 2026-06-10 | 2026-06-20 | LS o nk TS w shlder insert mesh and front jaquard label | TS |  |  | 2026-07-20 | 2026-07-31 | 2026-08-01 | 2026-08-13 |  |  | 2026-08-15 | 2026-08-08 | 2026-08-15 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-22 |  |  |  |  | 2026-08-25 | 2026-08-28 |  |  | 2026-08-29 | 2026-09-01 | 2026-09-03 | 2026-09-07 | 2026-09-07 | 89 | E | Khairul | BK,NK |  | coconut milk-3031 pcs 2 clr HD print and nk 1 clr foil print |  |  | NFL1 |  |  | Cut Ok | 550 | 550 | 0 | 3122 | 91 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46235 | 0 | 37 | Aug'2 |  |  | 27.08.26
UTG-(Even & Odd) | 45093 3rd | BAD2961B | 1000 | 252 | 2026-06-06 | 2026-06-19 | LS R NK TS | TS |  |  | 2026-08-01 | 2026-08-08 | 2026-08-10 | 2026-08-22 |  |  | 2026-09-03 | 2026-09-04 |  | 2026-09-07 | 2026-09-09 | [6 empty] | 2026-09-09 | 2026-09-11 |  |  | 2026-09-12 | 2026-09-14 | 2026-09-16 | 2026-09-19 | 2026-09-21 | 105 | G1 | Rony | [5 empty] | NFL1 |  |  | Cut Ok | 252 | 252 | 0 | 1052 | 52 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46244 | 0 | 39 | Sep'1 |  |  | 29.07.26
UTG-(Even & Odd) | 24301 9th | BAD0958P | 1000 | 406 | 2026-06-06 | 2026-06-19 | SL long Dress w side slit | Dress |  |  | 2026-08-01 | 2026-08-10 | 2026-08-11 | 2026-08-24 |  |  | 2026-09-02 | 2026-09-03 |  | 2026-09-08 | 2026-09-09 | [6 empty] | 2026-09-10 | 2026-09-12 |  |  | 2026-09-14 | 2026-09-15 | 2026-09-17 | 2026-09-19 | 2026-09-21 | 105 | N/3 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 406 | 385 | -21 | 0 | -1000 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46245 | 0 | 39 | Sep'1
BS-NMT | 47914 | 13265511 | 5124 | 662 | 2026-06-10 | 2026-06-17 | Elsated Legging w letus at leg opening | Legging |  |  | 2026-07-10 | 2026-07-17 | 2026-07-20 | 2026-08-07 |  |  | 2026-08-14 | 2026-08-14 | 2026-08-20 | 2026-08-24 | 2026-08-24 | 2026-08-26 | 2026-08-29 |  |  |  |  | 2026-09-01 | 2026-09-04 |  |  | 2026-09-07 | 2026-09-10 | 2026-09-15 | 2026-10-26 | 2026-10-28 | 138 | Z | Kamruzzaman | Waist |  | 3 combo label print |  |  | NFL3 |  |  | Cut Ok | 661 | 661 | 0 | 5322 | 198 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46223 | 0 | 44 | Aug'3 |  |  | 30.07.26
BS-NMT | 47915 | 13238448 | 2713 | 538 | 2026-06-10 | 2026-06-17 | LS Dress w letus stitch | Dress |  |  | 2026-07-20 | 2026-07-30 | 2026-08-10 | 2026-08-22 |  |  | 2026-08-28 | 2026-08-28 | 2026-09-04 | 2026-09-07 | 2026-09-08 | 2026-09-10 | 2026-09-14 |  |  |  |  | 2026-09-17 | 2026-09-19 |  |  | 2026-09-23 | 2026-09-25 | 2026-09-30 | 2026-10-26 | 2026-10-28 | 138 | Y | Kamruzzaman | Chest,Nk |  | chocolate-794 pcs,,pink-1120 pcs,,blue-799 pcs all combo 1 clr gltr print |  |  | NFL3 |  |  | Cut Ok | 497 | 497 | 0 | 2810 | 97 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46244 | 0 | 44 | Sep'1 |  |  | 30.07.26
BS-NMT | 47916 | 13266539 | 2670 | 323 | 2026-06-10 | 2026-06-17 | LS O nk TS w letus | TS |  |  | 2026-07-10 | 2026-07-17 | 2026-07-22 | 2026-08-10 |  |  | 2026-08-15 | 2026-08-15 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 2026-08-26 | 2026-08-29 |  |  |  |  | 2026-09-01 | 2026-09-03 |  |  | 2026-09-05 | 2026-09-09 | 2026-09-15 | 2026-10-26 | 2026-10-28 | 138 | Z | Kamruzzaman | Chest,Nk |  | chocolate-813 pcs,,pink-1023 pcs,,blue-834 pcs all combo 1 clr gltr print |  |  | NFL3 |  |  | Cut Ok | 323 | 323 | 0 | 2774 | 104 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 44 | Aug'3 |  |  | 30.07.26
BS-NMT | 47917 | 13264518 | 1608 | 208 | 2026-06-10 | 2026-06-17 | LS o nk TS | TS |  |  | 2026-07-10 | 2026-07-15 | 2026-07-23 | 2026-08-10 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-22 | 2026-08-24 | 2026-08-25 | 2026-08-27 | 2026-08-29 |  |  |  |  | 2026-09-02 | 2026-09-03 |  |  | 2026-09-05 | 2026-09-08 | 2026-09-10 | 2026-10-26 | 2026-10-28 | 138 | ZA1 | Kamruzzaman | Chest,Nk |  | c.dan-804 pcs 2 clr rub 1 clr gltr ,,pink-804 pcs 5 clr rub |  |  | NFL3 |  |  | Cut Ok | 208 | 208 | 0 | 1674 | 66 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46226 | 0 | 44 | Aug'3 |  |  | 22.07.26
BS-NMT | 47918 | 13224957/13229878 | 4029 | 487 | 2026-06-10 | 2026-06-17 | LS o nk TS | TS |  |  | 2026-07-10 | 2026-07-15 | 2026-07-22 | 2026-08-10 |  |  | 2026-08-14 | 2026-08-14 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-25 | 2026-08-29 |  |  |  |  | 2026-09-01 | 2026-09-03 |  |  | 2026-09-05 | 2026-09-08 | 2026-09-16 | 2026-10-25 | 2026-10-27 | 137 | ZA1 | Kamruzzaman | Chest,Nk |  | Pink-2052 pcs,,ice-1977 pcs both combo 5 clr rub 1 clr gltr |  |  | NFL3 |  |  | Cut Ok | 487 | 487 | 0 | 4200 | 171 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46225 | 0 | 44 | Aug'3 |  |  | 30.07.26
BS-NMT | 47967 | 13264279 | 1170 | 162 | 2026-06-10 | 2026-06-23 | SS o nk TS | TS |  |  | 2026-08-01 | 2026-08-06 | 2026-08-12 | 2026-08-25 |  |  | 2026-08-28 | 2026-08-28 | 2026-09-04 | 2026-09-07 | 2026-09-08 | 2026-09-10 | 2026-09-12 | 2026-09-15 | 2026-09-17 |  |  | 2026-09-19 | 2026-09-21 |  |  | 2026-09-23 | 2026-09-25 | 2026-09-30 | 2026-10-26 | 2026-10-28 | 138 | Z | Tomal | Chest,Stone |  | n sky-1170 pcs back 1 clr gltr print and 1 size rine stone HP |  |  | NFL3 |  |  | Cut Ok | 162 | 162 | 0 | 1209 | 39 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46246 | 0 | 44 | Sep'1 |  |  | 19.08.26
BS-NMT | 47966 | 13262133 | 645 | 141 | 2026-06-10 | 2026-06-23 | Long ballon Slve TS | TS |  |  | 2026-08-03 | 2026-08-08 | 2026-08-18 | 2026-08-31 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-14 | 2026-09-16 | 2026-09-16 | [6 empty] | 2026-09-21 | 2026-09-22 |  |  | 2026-09-24 | 2026-09-26 | 2026-09-30 | 2026-10-26 | 2026-10-28 | 138 | Y | Tomal | [5 empty] | NFL3 |  |  | File Due | 141 | 141 | 0 | 0 | -645 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46252 | 0 | 44 | Sep'2
BS-NMT | 47964 | 13245644 | 795 | 321 | 2026-06-10 | 2026-06-23 | Wide Swt pant w waist belt | Pant |  |  | 2026-08-01 | 2026-08-06 | 2026-08-14 | 2026-08-30 |  |  | 2026-09-05 | 2026-09-05 | 2026-09-11 | 2026-09-14 | 2026-09-15 | [6 empty] | 2026-09-17 | 2026-09-18 |  |  | 2026-09-21 | 2026-09-23 | 2026-09-26 | 2026-10-26 | 2026-10-28 | 138 | T2 | Tomal | [5 empty] | NFL3 |  |  | Cut Ok | 321 | 316 | -5 | 826 | 31 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46248 | 0 | 44 | Sep'2 |  |  | 19.08.26
BS-NMT | 47965 | 13259270 | 1458 | 838 | 2026-06-10 | 2026-06-23 | LS Swt Hoody w cuff btm rib | Hoody |  |  | 2026-08-01 | 2026-08-07 | 2026-08-14 | 2026-08-31 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-15 | 2026-09-17 | 2026-09-18 | [6 empty] | 2026-09-21 | 2026-09-23 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-30 | 2026-10-26 | 2026-10-28 | 138 | V | Tomal | [5 empty] | NFL3 |  |  | Cut Run | 838 | 816 | -22 | 1227 | -231 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46248 | 0 | 44 | Sep'2 |  |  | 19.08.26
UTG-AF | 42230 3rd | BAD2719mamaB | 2400 | 521 | 2026-06-13 | 2026-06-18 | AOP & solid Skirt | Skirt |  |  | 2026-08-25 | 2026-08-31 | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-09-21 | 2026-10-02 | 2026-10-03 |  | 2026-10-06 | 2026-10-07 | [6 empty] | 2026-10-08 | 2026-10-10 |  |  | 2026-10-12 | 2026-10-14 | 2026-10-16 | 2026-10-24 | 2026-10-26 | 133 | G1 | Rana |  |  |  | AOP |  | NFL1 |  |  | CAD | 521 | 521 | 0 | 0 | -2400 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46266 | 0 | 44 | Oct'1 |  |  | 15.09.26
BS-NMT | 48077 | 13251213 | 9909 | 1445 | 2026-06-10 | 2026-06-23 | SS o nk TS | TS |  |  | 2026-07-13 | 2026-07-20 | 2026-08-01 | 2026-08-18 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-27 | 2026-08-29 | 2026-09-02 | 2026-09-02 | 2026-09-08 |  |  |  |  | 2026-09-09 | 2026-09-14 |  |  | 2026-09-17 | 2026-09-19 | 2026-09-25 | 2026-11-02 | 2026-11-04 | 145 | ZA1 | Shamoly | Fr & Bk & Nk |  | C.dan-3748 pcs frt 4 clr pig back no print ,,nosegay-3748 pcs frt 3 clr pig back no print ,,Mole-2413 pcs frt 3 clr pig back 5 clr pig |  |  | NFL3 |  |  | Cut Ok | 1446 | 1389 | -57 | 9930 | 21 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46235 | 0 | 45 | Aug'3 |  |  | 16.07.26
BS-NMT | 48079 | 13262914 | 3244 | 1473 | 2026-06-10 | 2026-06-23 | LS swt hoodie w cuff btm rib | Hoody |  |  | 2026-07-15 | 2026-07-25 | 2026-08-08 | 2026-08-24 |  |  | 2026-08-28 | 2026-08-28 | 2026-09-04 | 2026-09-07 | 2026-09-08 | 2026-09-10 | 2026-09-15 |  |  |  |  | 2026-09-18 | 2026-09-22 |  |  | 2026-09-25 | 2026-09-28 | 2026-10-05 | 2026-11-02 | 2026-11-04 | 145 | V | Shamoly | Fr,Bk |  | Green-863 pcs frt 3 clr rub back no print ,,black-1231 pcs frt 2 clr rub back no print ,,winter-1150 pcs frt back 2 clr rub |  |  | NFL3 |  |  | Cut Ok | 1473 | 1473 | 0 | 3359 | 115 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46242 | 0 | 45 | Sep'1 |  |  | 16.07.26
BS-NMT | 48075 | 13250961/13267089 | 10068 | 1552 | 2026-06-10 | 2026-06-23 | SS o nk TS | TS |  |  | 2026-07-15 | 2026-07-23 | 2026-08-06 | 2026-08-24 |  |  | 2026-08-27 | 2026-08-27 | 2026-09-02 | 2026-09-05 | 2026-09-09 | 2026-09-09 | 2026-09-15 |  |  |  |  | 2026-09-17 | 2026-09-23 |  |  | 2026-09-26 | 2026-09-29 | 2026-10-05 | 2026-11-01 | 2026-11-03 | 144 | ZA1 | Shamoly | Fr & Bk & Nk |  | Green-2645 pcs frt back 2 clr rub ,,black-1902 pcs front 3 clr rub back 6 clr rub ,,white-2588 pcs front 3 clr pig back 6 clr pig,,winter-2933 pcs frt 1 clr rub back no print |  |  | NFL3 |  |  | Cut Ok | 1553 | 1524 | -29 | 10330 | 262 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46240 | 0 | 45 | Sep'1 |  |  | 16.07.26
BS-NMT | 48080 | 13262919 | 1560 | 647 | 2026-06-10 | 2026-06-23 | Swt Pant w side pkt drawstring | Pant |  |  | 2026-07-15 | 2026-07-22 | 2026-08-06 | 2026-08-21 |  |  | 2026-08-27 | 2026-08-27 | 2026-09-04 | 2026-09-07 | 2026-09-08 | 2026-09-10 | 2026-09-12 |  |  |  |  | 2026-09-15 | 2026-09-18 |  |  | 2026-09-21 | 2026-09-23 | 2026-09-28 | 2026-11-02 | 2026-11-04 | 145 | X | Shamoly | Thigh |  | black-780 pcs,,winter-780 pcs both combo 2 clr rub print |  |  | NFL3 |  |  | Cut Ok | 648 | 648 | 0 | 1647 | 87 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46240 | 0 | 45 | Sep'1 |  |  | 16.07.26
BS-NMT | 48076 | 13250999/13267095 | 10946 | 980 | 2026-06-10 | 2026-06-23 | SS o nk TS | TS |  |  | 2026-07-15 | 2026-07-24 | 2026-08-01 | 2026-08-18 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-29 | 2026-09-01 | 2026-09-04 | 2026-09-04 | 2026-09-11 |  |  |  |  | 2026-09-14 | 2026-09-18 |  |  | 2026-09-22 | 2026-09-24 | 2026-09-30 | 2026-11-01 | 2026-11-03 | 144 | ZA1 | Shamoly | Fr & Bk & Nk |  | verdant green-2688 pcs frt 3 clr rub back no print ,,cameo green-2752 pcs frt 4 clr rub back no print ,, white-2340 pcs frt 2 clr pig back 4 clr pig ,,winter-3166 pcs frt 4 clr rub back no print |  |  | NFL3 |  |  | Cut Ok | 980 | 927 | -53 | 11178 | 232 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46235 | 0 | 45 | Sep'1 |  |  | 16.07.26
BS-NMT | 48078 | 13251485/13255895 | 19809 | 1655 | 2026-06-10 | 2026-06-23 | SS o nk TS | TS |  |  | 2026-07-15 | 2026-07-25 | 2026-08-01 | 2026-08-18 |  |  | 2026-08-25 | 2026-08-25 | 2026-09-01 | 2026-09-04 | 2026-09-08 | 2026-09-07 | 2026-09-14 |  |  |  |  | 2026-09-16 | 2026-09-22 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-30 | 2026-11-01 | 2026-11-03 | 144 | ZA1 | Shamoly | Fr & Bk & Nk |  | white cap-3028 pcs frt 3 clr pig back 4 clr pig ,,barberry-5940 pcs frt 1 clr pig 1 clr gltr back no print ,,Nose gay-6015 pcs frt 3 clr pig 1 clr gltr back no print ,,lichen-4826 pcs frt 2 clr pig 1 clr gltr back no print |  |  | NFL3 |  |  | Cut Run | 1655 | 1609 | -46 | 19720 | -89 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46235 | 0 | 45 | Sep'1 |  |  | 16.07.26
BS-NMT | 48082 | 13251015 | 9407 | 1309 | 2026-06-10 | 2026-06-23 | Swt Shorts w side pkt drawstring | Shorts |  |  | 2026-07-25 | 2026-08-06 | 2026-08-10 | 2026-08-27 |  |  | 2026-08-31 | 2026-08-28 | 2026-09-05 | 2026-09-08 | 2026-09-12 |  |  |  |  | 2026-09-11 | 2026-09-16 | 2026-09-18 | 2026-09-25 |  |  | 2026-09-28 | 2026-09-30 | 2026-10-06 | 2026-12-19 | 2026-12-21 | 192 | U | Shamoly |  | Thigh | Navy-3867 pcs,,Tapestry-2704 pcs,,carafe-2836 pcs all combo 3 clr flat emb |  |  | NFL3 |  |  | Need Cut | 1309 | 1309 | 0 | 0 | -9407 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46244 | 0 | 52 | Sep'1 |  |  | 01.08.26
BS-NMT | 48090 | 13262945 | 8809 | 790 | 2026-06-10 | 2026-06-23 | SS o nk TS | TS |  |  | 2026-08-01 | 2026-08-07 | 2026-08-14 | 2026-08-31 |  |  | 2026-09-05 | 2026-09-05 | 2026-09-10 | 2026-09-12 | 2026-09-15 | 2026-09-16 | 2026-09-21 |  |  |  |  | 2026-09-23 | 2026-09-26 |  |  | 2026-09-29 | 2026-10-04 | 2026-10-08 | 2026-12-19 | 2026-12-21 | 192 | ZA1 | Shamoly | Chest,Nk |  | Tapestry-3166 pcs 2 clr rub 1 clr HD print ,,winter-2619 pcs 2 clr pig 1 clr HD print ,,white-3024 pcs 2 clr rub 1 clr foil print |  |  | NFL3 |  |  | Need Cut | 790 | 784 | -6 | 0 | -8809 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46248 | 0 | 52 | Sep'2 |  |  | 01.08.26
BS-NMT | 48089 | 13262944/13267100 | 19104 | 1775 | 2026-06-10 | 2026-06-23 | AOP SS o nk TS | TS |  |  | 2026-07-08 | 2026-07-18 | 2026-07-24 | 2026-08-10 | 2026-08-13 | 2026-08-26 | 2026-08-28 | 2026-08-28 | 2026-09-05 | 2026-09-09 | 2026-09-13 | 2026-09-12 | 2026-09-18 |  |  |  |  | 2026-09-21 | 2026-09-26 |  |  | 2026-09-29 | 2026-10-04 | 2026-10-10 | 2026-12-19 | 2026-12-21 | 192 | W2 | Shamoly | Chest,Nk |  | Tapestry-4850 pcs 6 clr rub ,,winter-5100 pcs 2 clr rub ,,white-9154 pcs 3 clr pig | AOP |  | NFL3 |  |  | Need Cut | 1776 | 1721 | -55 | 0 | -19104 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46227 | 0 | 52 | Sep'1 |  |  | 01.08.26
BS-NMT | 48088 | 13262931 | 2616 | 491 | 2026-06-10 | 2026-06-23 | AOP SS o nk TS | TS |  |  | 2026-07-25 | 2026-07-30 | 2026-08-10 | 2026-08-24 | 2026-08-27 | 2026-09-04 | 2026-09-07 | 2026-09-07 | 2026-09-12 | 2026-09-15 | 2026-09-16 | 2026-09-18 | 2026-09-22 |  |  |  |  | 2026-09-24 | 2026-09-26 |  |  | 2026-09-29 | 2026-10-03 | 2026-10-06 | 2026-12-21 | 2026-12-23 | 194 | W2 | Shamoly | Chest,Nk |  | tapestry-1308 pcs,,b white-1308 pcs both combo 1 clr rub | AOP |  | NFL3 |  |  | Need Cut | 490 | 490 | 0 | 0 | -2616 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46244 | 0 | 52 | Sep'2 |  |  | 01.08.26
BS-NMT | 48084 | 13251502 | 1808 | 316 | 2026-06-10 | 2026-06-23 | AOP Swt Pant w side pkt with letus frill and tape string | Pant |  |  | 2026-07-25 | 2026-07-30 | 2026-08-07 | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-05 | 2026-09-05 | 2026-09-11 | 2026-09-14 | 2026-09-15 | 2026-09-17 | 2026-09-18 |  |  |  |  | 2026-09-21 | 2026-09-24 |  |  | 2026-09-26 | 2026-09-29 | 2026-10-06 | 2026-12-19 | 2026-12-21 | 192 | X | Shamoly | Waist |  | 2 combo label print | AOP |  | NFL3 |  |  | Need Cut | 316 | 249 | -67 | 0 | -1808 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46241 | 0 | 52 | Sep'2 |  |  | 01.08.26
BS-NMT | 48083 | 13251499 | 9389 | 1487 | 2026-06-10 | 2026-06-23 | AOP SS puff slve dress | Dress |  |  | 2026-07-20 | 2026-07-30 | 2026-08-06 | 2026-08-20 | 2026-08-22 | 2026-08-31 | 2026-09-02 | 2026-09-02 | 2026-09-07 | 2026-09-10 | 2026-09-14 | 2026-09-14 | 2026-09-18 |  |  |  |  | 2026-09-21 | 2026-09-26 |  |  | 2026-09-29 | 2026-10-04 | 2026-10-10 | 2026-12-19 | 2026-12-21 | 192 | V | Shamoly | Nk |  | 3 combo label print | AOP |  | NFL3 |  |  | Need Cut | 1487 | 1077 | -410 | 0 | -9389 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46240 | 0 | 52 | Sep'1 |  |  | 01.08.26
BS-NMT | 48086 | 13262929 | 3480 | 659 | 2026-06-10 | 2026-06-23 | SS o nk TS | TS |  |  | 2026-08-01 | 2026-08-07 | 2026-08-13 | 2026-08-28 |  |  | 2026-09-03 | 2026-09-03 | 2026-09-10 | 2026-09-12 | 2026-09-14 | 2026-09-16 | 2026-09-17 |  |  | 2026-09-16 | 2026-09-19 | 2026-09-22 | 2026-09-25 |  |  | 2026-09-28 | 2026-09-30 | 2026-10-10 | 2026-12-19 | 2026-12-21 | 192 | W2 | Shamoly | Nk | Chest | navy-1240 pcs,,Tapestry-1084 pcs,,carafe-1156 pcs all combo 1 clr flat emb |  |  | NFL3 |  |  | Cut Ok | 660 | 660 | 0 | 3600 | 120 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46247 | 0 | 52 | Sep'2 |  |  | 01.08.26
BS-NMT | 48081 | 13251009/13256010 | 9712 | 114 | 2026-06-10 | 2026-06-23 | SS o nk TS | TS |  |  | 2026-07-25 | 2026-08-04 | 2026-08-08 | 2026-08-25 |  |  | 2026-08-28 | 2026-08-28 | 2026-09-05 | 2026-09-08 | 2026-09-12 | 2026-09-12 | 2026-09-15 |  |  | 2026-09-11 | 2026-09-15 | 2026-09-18 | 2026-09-23 |  |  | 2026-09-26 | 2026-09-29 | 2026-10-05 | 2026-12-19 | 2026-12-21 | 192 | W2 | Shamoly | Nk | Chest | navy-3740 pcs,,Tapestry-3356 pcs,,carafe-2616 pcs all combo 4 clr flat emb |  |  | NFL3 |  |  | Need Cut | 1115 | 1110 | -5 | 0 | -9712 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46242 | 0 | 52 | Sep'1 |  |  | 01.08.26
BS-NMT | 47968 | 13264546 | 1875 | 516 | 2026-06-10 | 2026-06-23 | LS full zipper Swt Shirt | Swt Shirt |  |  | 2026-07-27 | 2026-08-04 | 2026-08-11 | 2026-08-25 |  |  | 2026-08-28 | 2026-08-28 | 2026-09-05 | 2026-09-08 | 2026-09-09 | 2026-09-11 | 2026-09-18 |  |  |  |  | 2026-09-21 | 2026-09-24 |  |  | 2026-09-26 | 2026-09-29 | 2026-10-06 | 2026-11-02 | 2026-11-04 | 145 | S | Tomal | Fr & Bk & Slv |  | Spellbound-1875 pcs frt two part back both slve 6 clr rub print |  |  | NFL3 |  |  | Cut Ok | 515 | 515 | 0 | 1925 | 50 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46245 | 0 | 45 | Sep'1 |  |  | 19.08.26
BS-NMT | 47974 | 13264562 | 810 | 192 | 2026-06-10 | 2026-06-23 | Swt Pant w side pkt drawstring and side contrast pannel | Pant |  |  | 2026-08-01 | 2026-08-06 | 2026-08-15 | 2026-08-31 |  |  | 2026-09-05 | 2026-09-05 | 2026-09-11 | 2026-09-14 | 2026-09-15 | [6 empty] | 2026-09-17 | 2026-09-18 |  |  | 2026-09-22 | 2026-09-24 | 2026-09-30 | 2026-11-02 | 2026-11-04 | 145 | X | Tomal | [5 empty] | NFL3 |  |  | Need Cut | 193 | 177 | -16 | 0 | -810 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46249 | 0 | 45 | Sep'2 |  |  | 19.08.26
BS-NMT | 47969 | 13264547 | 801 | 194 | 2026-06-10 | 2026-06-23 | Swt Pant w side pkt drawstring | Pant |  |  | 2026-08-01 | 2026-08-06 | 2026-08-14 | 2026-08-27 |  |  | 2026-09-01 | 2026-09-01 | 2026-09-07 | 2026-09-09 | 2026-09-10 | 2026-09-12 | 2026-09-19 |  |  |  |  | 2026-09-22 | 2026-09-24 |  |  | 2026-09-26 | 2026-09-29 | 2026-10-05 | 2026-11-02 | 2026-11-04 | 145 | X | Tomal | leg |  | Spellbound-801 pcs 4 part 6 clr rub print |  |  | NFL3 |  |  | Need Cut | 194 | 194 | 0 | 0 | -801 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46248 | 0 | 45 | Sep'1 |  |  | 19.08.26
BS-NMT | 47973 | 13264561 | 1053 | 254 | 2026-06-10 | 2026-06-23 | LS high nk half zipper cut&sew Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-08-01 | 2026-08-06 | 2026-08-13 | 2026-08-30 |  |  | 2026-09-03 | 2026-09-03 | 2026-09-09 | 2026-09-11 | 2026-09-12 | 2026-09-15 | 2026-09-21 |  |  |  |  | 2026-09-24 | 2026-09-28 |  |  | 2026-09-30 | 2026-10-03 | 2026-10-08 | 2026-11-02 | 2026-11-04 | 145 | S | Tomal | Chest | Chest | Spellbound-1053 pcs two part 1 clr rub print and 1 clr flat 1 clr terry emb |  |  | NFL3 |  |  | Need Cut | 254 | 198 | -56 | 0 | -1053 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46247 | 0 | 45 | Sep'2 |  |  | 19.08.26
BS-NMT | 47972 | 13264558 | 2640 | 378 | 2026-06-10 | 2026-06-23 | LS o nk TS w nk cuff rib | TS |  |  | 2026-08-01 | 2026-08-07 | 2026-08-15 | 2026-08-30 |  |  | 2026-09-03 | 2026-09-03 | 2026-09-09 | 2026-09-11 | 2026-09-12 | 2026-09-14 | 2026-09-18 |  |  |  |  | 2026-09-21 | 2026-09-23 |  |  | 2026-09-26 | 2026-09-29 | 2026-10-06 | 2026-11-02 | 2026-11-04 | 145 | Z | Tomal | Chest,Nk |  | Basil-1320 pcs 7 clr rub 1 clr gel print ,,spellbound-1320 pcs 6 clr rub 1 clr gel print |  | Flag Label | NFL3 |  |  | Need Cut | 378 | 378 | 0 | 0 | -2640 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46249 | 0 | 45 | Sep'2 |  |  | 19.08.26
BS-NMT | 47971 | 13264550 | 1905 | 479 | 2026-06-10 | 2026-06-23 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-08-01 | 2026-08-06 | 2026-08-10 | 2026-08-25 |  |  | 2026-08-27 | 2026-08-27 | 2026-09-04 | 2026-09-07 | 2026-09-08 |  |  |  |  | 2026-09-10 | 2026-09-18 | 2026-09-21 | 2026-09-22 |  |  | 2026-09-24 | 2026-09-28 | 2026-11-06 | 2026-11-02 | 2026-11-04 | 145 | Z | Tomal |  | Chest | citadel-840 pcs 2 clr flat 4 clr terry emb ,,spellbound-1065 pcs 1 clr flat 2 clr terry emb |  |  | NFL3 |  |  | Cut Ok | 479 | 405 | -74 | 1975 | 70 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46244 | 0 | 45 | Sep'1 |  |  | 19.08.26
BS-NMT | 47970 | 13264549 | 4977 | 668 | 2026-06-10 | 2026-06-23 | LS o nk TS | TS |  |  | 2026-07-25 | 2026-07-30 | 2026-08-10 | 2026-08-24 |  |  | 2026-08-28 | 2026-08-28 | 2026-09-03 | 2026-09-05 | 2026-09-07 | 2026-09-09 | 2026-09-14 |  |  |  |  | 2026-09-16 | 2026-09-19 |  |  | 2026-09-22 | 2026-09-24 | 2026-09-30 | 2026-11-02 | 2026-11-04 | 145 | W2 | Tomal | Chest,Nk |  | citadel-2296 pcs 2 clr rub 4 clr puff ,,spellbound-2681 pcs 2 clr rub 3 clr puff print |  | flag label | NFL3 |  |  | Cut Ok | 667 | 667 | 0 | 5160 | 183 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | -46244 | 0 | 45 | Sep'1 |  |  | 19.08.26
BS-ONS | 48145 | 22042261 | 2748 | 1056 | 2026-06-22 | 2026-06-25 | YD LS o nk TS w nk contrast rib | TS | 2026-07-01 | 2026-07-05 | 2026-07-06 | 2026-07-11 | 2026-07-10 | 2026-07-14 |  |  | 2026-07-10 | 2026-07-10 | 2026-07-15 | 2026-07-17 | 2026-07-18 | [6 empty] | 2026-07-20 | 2026-07-23 |  |  | 2026-07-24 | 2026-07-25 | 2026-07-27 | 2026-07-27 | 2026-07-29 | 35 | G1 | Shovon |  |  |  | YD |  | NFL1 |  |  | Cut Ok | 1030 | 1030 | 0 | 0 | -2748 | [11 empty] | 31 | Jul'2 |  |  | 13.07.26
BS-ONS | 47818 2nd | 22041282 | 15018 | 5137 | 2026-06-24 | 2026-06-25 | SS TS w nk and arm hole contrast piping | TS |  |  | 2026-06-22 | 2026-06-29 | 2026-06-29 | 2026-07-03 |  |  | 2026-07-02 | 2026-06-30 |  | 2026-07-03 | 2026-07-07 | [6 empty] | 2026-07-06 | 2026-07-10 |  |  | 2026-07-11 | 2026-07-11 | 2026-07-13 | 2026-07-13 | 2026-07-15 | 19 | F | Shovon | [5 empty] | NFL1 |  |  | Cut Ok | 5138 | 5138 | 0 | 0 | -15018 | [11 empty] | 29 | Jul'1 |  |  | 30.06.26
BS-ONL | 30710 11th | 15209153 | 6840 | 1073 | 2026-06-24 | 2026-06-25 | SS o nk TS | TS |  |  | 2026-06-27 | 2026-06-30 | 2026-07-01 | 2026-07-10 |  |  | 2026-07-10 | 2026-07-10 |  | 2026-07-15 | 2026-07-17 | [6 empty] | 2026-07-20 | 2026-07-23 |  |  | 2026-07-24 | 2026-07-25 | 2026-07-25 | 2026-07-27 | 2026-07-29 | 33 | G2 | Mainul |  |  |  |  | 5 clr fab stock from job 24540 40th | NFL1 |  |  | Cut Ok | 1071 | 1071 | 0 | 0 | -6840 | [11 empty] | 31 | Jul'2 |  |  | 07.07.26
BS-ONL | 30711 7th | 15209156 | 5490 | 1076 | 2026-06-24 | 2026-06-25 | LS o nk TS | TS |  |  | 2026-06-29 | 2026-07-02 | 2026-07-01 | 2026-07-11 |  |  | 2026-07-10 | 2026-07-10 |  | 2026-07-15 | 2026-07-17 | [6 empty] | 2026-07-20 | 2026-07-22 |  |  | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-27 | 2026-07-29 | 33 | ZA2 | Mainul | [5 empty] | NFL3 |  |  | Cut Ok | 1076 | 1076 | 0 | 0 | -5490 | [11 empty] | 31 | Jul'2 |  |  | 07.07.26
BS-ONL | 48139 | 15397312 | 3000 | 772 | 2026-06-19 | 2026-06-25 | LS v nk TS | TS |  |  | 2026-06-25 | 2026-06-30 | 2026-07-01 | 2026-07-11 |  |  | 2026-07-10 | 2026-07-10 | 2026-07-15 | 2026-07-17 | 2026-07-18 | [6 empty] | 2026-07-20 | 2026-07-22 |  |  | 2026-07-23 | 2026-07-25 | 2026-07-25 | 2026-07-25 | 2026-07-27 | 36 | M | Mainul | [5 empty] | NFL2 |  |  | Cut Ok | 772 | 772 | 0 | 0 | -3000 | [11 empty] | 31 | Jul'2 |  |  | 07.07.26
BS-NMT | 48247 | 13264758 | 810 | 247 | 2026-06-26 | 2026-06-27 | YD LS o nk TS | TS | 2026-07-10 | 2026-07-16 | 2026-07-20 | 2026-07-28 | 2026-08-30 | 2026-08-04 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-13 | 2026-08-15 | 2026-08-17 | [6 empty] | 2026-08-19 | 2026-08-20 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-22 | 2026-08-24 | 2026-08-26 | 59 | Y | Tomal |  |  |  | YD |  | NFL3 |  |  | Cut Ok | 247 | 247 | 0 | 0 | -810 | [11 empty] | 35 | Aug'2 |  |  | 06.08.26
BS-NMT | 47950 2nd | 13262864 | 3330 | 982 | 2026-06-26 | 2026-06-27 | YD LS o nk TS | TS | 2026-07-10 | 2026-07-17 | 2026-07-18 | 2026-07-30 | 2026-07-30 | 2026-08-06 |  |  | 2026-08-06 | 2026-08-06 | 2026-08-11 | 2026-08-13 | 2026-08-17 | [6 empty] | 2026-08-17 | 2026-08-20 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-24 | 2026-08-24 | 2026-08-26 | 59 | Y | Tomal |  |  |  | YD |  | NFL3 |  |  | Cut Ok | 984 | 984 | 0 | 3507 | 177 | [11 empty] | 35 | Aug'2 |  |  | 06.08.26
BS-ONS | 30588 19th | 22031724 | 3000 | 1283 | 2026-06-25 | 2026-06-26 | SS o nk TS | TS |  |  | 2026-07-01 | 2026-07-10 | 2026-07-13 | 2026-07-20 |  |  | 2026-07-20 | 2026-07-20 |  | 2026-07-24 | 2026-07-25 | [6 empty] | 2026-07-27 | 2026-07-29 |  |  | 2026-07-31 | 2026-08-01 | 2026-08-06 | 2026-08-10 | 2026-08-12 | 46 | G2 | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 1283 | 1283 | 0 | 3097 | 97 | [11 empty] | 33 | Jul'3 |  |  | 07.07.26
BS-ONL | 27204 56th | 15323159 | 2328 | 559 | 2026-06-24 | 2026-06-25 | LS o nk TS | TS |  |  | 2026-07-01 | 2026-07-04 | 2026-07-08 | 2026-07-18 |  |  | 2026-07-17 | 2026-07-17 |  | 2026-07-22 | 2026-07-23 | [6 empty] | 2026-07-27 | 2026-07-28 |  |  | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-08 | 2026-08-10 | 45 | G2 | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 558 | 558 | 0 | 0 | -2328 | [11 empty] | 33 | Jul'3 |  |  | 07.07.26
GBX-Maurices | 48245 1st | 2524991/4704991 | 33550 | 12052 | 2026-06-27 | 2026-06-27 | LS self nk binding TS W banded hem | TS |  |  | 2026-07-12 | 2026-07-23 | 2026-07-18 | 2026-08-08 |  |  | 2026-07-28 | 2026-07-23 | 2026-07-28 | 2026-08-01 | 2026-08-10 | 2026-08-09 | 2026-08-22 |  |  |  |  | 2026-08-07 | 2026-08-21 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 59 | N/1 | Mannan | Heat Press/Heat Seal |  | 2 combo nk HP |  |  | NCL |  |  | Ready Test Cut | 11151 | 11151 | 0 | 0 | -33550 | [11 empty] | 35 | Aug'1
UTG-AF | 46152 7th | BAD0985AKL | 2000 | 450 | 2026-06-27 | 2026-06-27 | LDS O NK LS TS | TS |  |  | 2026-07-03 | 2026-07-10 | 2026-07-11 | 2026-07-22 |  |  | 2026-07-28 | 2026-07-29 |  | 2026-07-30 | 2026-07-31 | [6 empty] | 2026-08-06 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-11 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 49 | G2 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 450 | 450 | 0 | 2156 | 156 | [11 empty] | 34 | Jul'3 |  |  | 22.07.26
UTG-AF | 44587 9th | BAD2548T | 1800 | 435 | 2026-06-27 | 2026-06-27 | LDS LS V NK TS | TS |  |  | 2026-07-03 | 2026-07-10 | 2026-07-11 | 2026-07-22 |  |  | 2026-07-28 | 2026-07-29 |  | 2026-07-30 | 2026-07-31 | [6 empty] | 2026-08-06 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-11 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 49 | G2 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 435 | 435 | 0 | 0 | -1800 | [11 empty] | 34 | Jul'3 |  |  | 22.07.26
UTG-AF | 40672 6th | BAD0934AD | 800 | 19 | 2026-06-27 | 2026-06-27 | LDS O NK LS TS | TS |  |  | 2026-07-03 | 2026-07-10 | 2026-07-11 | 2026-07-22 |  |  | 2026-07-28 | 2026-07-29 |  | 2026-07-30 | 2026-07-31 | [6 empty] | 2026-08-06 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-11 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 49 | G2 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 195 | 195 | 0 | 850 | 50 | [11 empty] | 34 | Jul'3 |  |  | 23.07.26
UTG-(Even & Odd) | 47881 | BAD3240 | 1200 | 316 | 2026-06-12 | 2026-06-25 | LS o nk TS w front half placket btn w gmts dye acid wash | TS |  |  | 2026-07-01 | 2026-07-09 | 2026-07-10 | 2026-07-22 |  |  | 2026-07-23 | 2026-07-24 | 2026-08-08 | 2026-08-10 | 2026-08-11 | [6 empty] | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 71 | N/3 | Rony |  |  |  |  | Gmts dye acid wash | NCL |  |  | Ready Test Cut | 316 | 316 | 0 | 0 | -1200 | [11 empty] | 35 | Aug'1 |  |  | 18.07.06
UTG-(Even & Odd) | 47882 | BAD3239 | 1800 | 300 | 2026-06-12 | 2026-06-25 | SL High Nk TS | TS |  |  | 2026-07-01 | 2026-07-09 | 2026-07-10 | 2026-07-22 |  |  | 2026-07-28 | 2026-07-29 | 2026-08-11 | 2026-08-12 | 2026-08-13 | [6 empty] | 2026-08-14 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 71 | L | Rony | [5 empty] | NFL2 |  |  | Cut Ok | 300 | 300 | 0 | 0 | -1800 | [11 empty] | 35 | Aug'2 |  |  | 18.07.26
UTG-(Even & Odd) | 47883 | BAD3241 | 1600 | 268 | 2026-06-12 | 2026-06-25 | LS o nk TS | TS |  |  | 2026-07-01 | 2026-07-13 | 2026-07-14 | 2026-07-30 |  |  | 2026-07-28 | 2026-07-29 | 2026-08-11 | 2026-08-12 | 2026-08-13 | [6 empty] | 2026-08-14 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 71 | L | Rony | [5 empty] | NFL2 |  |  | Cut Ok | 268 | 268 | 0 | 0 | -1600 | [11 empty] | 35 | Aug'2 |  |  | 18.07.26
UTG-(Even & Odd) | 47884 | BAD3225 | 1000 | 155 | 2026-06-12 | 2026-06-25 | LS TS w 4 part snap btn | TS |  |  | 2026-07-01 | 2026-07-08 | 2026-07-10 | 2026-07-22 |  |  | 2026-07-28 | 2026-07-29 | 2026-08-11 | 2026-08-12 | 2026-08-13 | [6 empty] | 2026-08-14 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 71 | N/2 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 155 | 155 | 0 | 0 | -1000 | [11 empty] | 35 | Aug'2 |  |  | 18.07.26
UTG-(Even & Odd) | 47885 | BAD3227 | 500 | 110 | 2026-06-12 | 2026-06-25 | LS boat nk TS w studs | TS |  |  | 2026-07-01 | 2026-07-09 | 2026-07-10 | 2026-07-23 |  |  | 2026-07-20 | 2026-07-22 | 2026-08-07 | 2026-08-08 | 2026-08-10 |  |  | 2026-08-10 | 2026-08-13 |  |  | 2026-08-14 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 71 | N/1 | Rony | Stone |  | black-500 pcs cheat all over HP studs |  | Elegant developed | NCL |  |  | Ready Test Cut | 110 | 110 | 0 | 0 | -500 | [11 empty] | 35 | Aug'1
UTG-(Even & Odd) | 47886 | BAD3226 | 1000 | 230 | 2026-06-12 | 2026-06-25 | LS body suit w snap btn | Body |  |  | 2026-07-01 | 2026-07-08 | 2026-07-10 | 2026-07-22 |  |  | 2026-07-28 | 2026-07-29 | 2026-08-11 | 2026-08-12 | 2026-08-13 | [6 empty] | 2026-08-14 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 71 | N/2 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 230 | 230 | 0 | 0 | -1000 | [11 empty] | 35 | Aug'2 |  |  | 18.07.26
UTG-(Even & Odd) | 47887 | BAD3242 | 600 | 175 | 2026-06-12 | 2026-06-25 | YD LS high nk TS | TS | 2026-07-01 | 2026-07-09 | 2026-07-10 | 2026-07-20 | 2026-07-21 | 2026-07-28 |  |  | 2026-07-28 | 2026-07-29 | 2026-08-11 | 2026-08-12 | 2026-08-13 | [6 empty] | 2026-08-14 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 71 | L | Rony |  |  |  | YD |  | NFL2 |  |  | Cut Ok | 175 | 175 | 0 | 640 | 40 | [11 empty] | 35 | Aug'2 |  |  | 14.07.26
UTG-(Even & Odd) | 47888 | BAD3228 | 600 | 145 | 2026-06-12 | 2026-06-25 | LS ballarina knot Body suit w cap snap btn | Body | 2026-07-21: 2026-07-10; 2026-07-28: 2026-07-22 |  |  | 2026-07-28 | 2026-07-29 | 2026-08-11 | 2026-08-12 | 2026-08-13 | [6 empty] | 2026-08-14 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 71 | N/3 | Rony |  |  |  |  | Imp Stock grey fab | NCL |  |  | Ready Test Cut | 145 | 145 | 0 | 0 | -600 | [11 empty] | 35 | Aug'2
BS-NMT | 47981 | 13263755 | 1721 | 150 | 2026-06-10 | 2026-06-24 | LS o nk TS shlder snap btn | TS |  |  | 2026-07-13 | 2026-07-18 | 2026-07-22 | 2026-08-06 |  |  | 2026-08-09 | 2026-08-09 | 2026-08-15 | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-22 |  |  | 2026-08-25 | 2026-08-29 | 2026-09-03 | 2026-09-05 |  |  | 2026-09-08 | 2026-09-10 | 2026-09-12 | 2026-09-19 | 2026-09-21 | 101 | Y | Mosaddik | Nk | Chest | forget-899 pcs 3 clr flat w applique emb,,peyote-822 pcs 4 clr flat w applique emb |  |  | NFL3 |  |  | Cut Ok | 151 | 151 | 0 | 1776 | 55 | [11 empty] | 39 | Aug'2 |  |  | 29.07.26
BS-NMT | 47996 | 13263954 | 2370 | 341 | 2026-06-10 | 2026-06-27 | LS swt card w front full placket ring snap btn | Cardigan |  |  | 2026-07-18 | 2026-07-21 | 2026-08-01 | 2026-08-13 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-28 | 2026-09-01 | 2026-09-03 | [6 empty] | 2026-09-04 | 2026-09-09 |  |  | 2026-09-11 | 2026-09-13 | 2026-09-15 | 2026-09-21 | 2026-09-23 | 103 | S | Mosaddik |  |  |  |  | Imp fab on 07/08 | NFL3 |  |  | Need Cut | 13 | 13 | 0 | 0 | -2370 | [11 empty] | 39 | Sep'1 |  |  | 21.08.26
BS-NMT | 47997 | 13263955 | 2370 | 260 | 2026-06-10 | 2026-06-27 | Swt Pant w frill at waist | Pant | [8 empty] | 2026-08-17 | 2026-08-17 | 2026-08-25 | 2026-08-27 | 2026-08-29 | [6 empty] | 2026-09-01 | 2026-09-03 |  |  | 2026-09-05 | 2026-09-08 | 2026-09-10 | 2026-09-19 | 2026-09-21 | 101 | U | Mosaddik |  |  |  |  | Imp fab on 07/08 | NFL3 |  |  | Need Cut | 0 | 0 | 0 | 0 | -2370 | [11 empty] | 39 | Aug'3 |  |  | 28.08.26
BS-NMT | 47987 | 13263821 | 3218 | 571 | 2026-06-10 | 2026-06-27 | AOP contrast slve LS Swt Shirt w cuff btm rib and shlder snap btn | Swt Shirt |  |  | 2026-07-10 | 2026-07-16 | 2026-07-20 | 2026-08-04 | 2026-08-07 | 2026-08-15 | 2026-08-18 | 2026-08-18 | 2026-08-24 | 2026-08-26 | 2026-08-29 |  |  |  |  | 2026-09-01 | 2026-09-03 | 2026-09-07 | 2026-09-10 |  |  | 2026-09-12 | 2026-09-14 | 2026-09-16 | 2026-09-19 | 2026-09-21 | 101 | Y | Mosaddik |  | Chest | Basil-1393 pcs,,spellbound-1825 pcs both combo 2 clr flat emb | AOP |  | NFL3 |  |  | Cut Ok | 571 | 571 | 0 | 3371 | 153 | [11 empty] | 39 | Aug'3 |  |  | 29.07.26
BS-ONL | 44675 2nd | 15365756 | 11044 | 2356 | 2026-06-23 | 2026-06-25 | LS V nk TS w dtm lace in nk & front ruching | TS |  |  | 2026-07-05 | 2026-07-15 | 2026-07-20 | 2026-08-06 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-11 | 2026-08-12 | 2026-08-17 | 2026-08-14 | 2026-08-20 |  |  |  |  | 2026-08-19 | 2026-08-28 |  |  | 2026-09-02 | 2026-09-03 | 2026-09-05 | 2026-09-14 | 2026-09-16 | 83 | O1 | Jannati | Nk |  | 6 combo nk 1 clr rub print |  |  | NFL2 |  |  | Cut Ok | 2097 | 2084 | -13 | 11313 | 269 | [11 empty] | 38 | Aug'2 |  |  | 23.07.26
BS-ONL | 44677 2nd | 15366520 | 7968 | 1256 | 2026-06-23 | 2026-06-25 | SS o nk TS | TS |  |  | 2026-07-05 | 2026-07-15 | 2026-07-21 | 2026-08-06 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-13 | 2026-08-15 | 2026-08-18 | 2026-08-18 | 2026-08-24 |  |  |  |  | 2026-08-24 | 2026-08-31 |  |  | 2026-09-02 | 2026-09-04 | 2026-09-07 | 2026-09-14 | 2026-09-16 | 83 | N1 | Jannati | Chest |  | C.dan-2704 pcs 3 clr pig,,white-2632 pcs 4 clr pig ,,black leo-2632 pcs 4 clr urb |  |  | NFL2 |  |  | Cut Ok | 1210 | 1210 | 0 | 8176 | 208 | [11 empty] | 38 | Aug'2 |  |  | 14.07.26
BS-ONL | 44672 4th | 15367075 | 23772 | 4683 | 2026-06-23 | 2026-06-25 | SS o nk TS | TS |  |  | 2026-07-01 | 2026-07-13 | 2026-07-15 | 2026-07-04 |  |  | 2026-08-15 | 2026-08-01 | 2026-08-08 | 2026-08-11 | 2026-08-17 | 2026-08-14 | 2026-08-27 |  |  | 2026-08-22 | 2026-08-29 | 2026-09-01 | 2026-09-14 |  |  | 2026-09-16 | 2026-09-10 | 2026-09-12 | 2026-09-14 | 2026-09-16 | 83 | O2 | Jannati | Fr,Bk | Chest | Sunlight-792 pcs chest 10 clr pig photo print and no emb ,,purple-4442 pcs frt 3 clr rub w photo print w 4 clr puff and 1 clr flat emb back back 5 clr rub one slve 2 clr rub ,,corsage-5006 pcs frt 3 clr rub 4 clr puff and 3 clr flat emb back 3 clr rub print ,,magenta-2353 pcs frt back 1 clr rub and no emb ,,pink-2884 pcs chest 1 clr pig and no emb ,,c.dan simple-2976 pcs ,,c.dan lemon-5319 pcs chest 3 clr rub photo print w 3 clr puff and 1 clr flat emb |  | 1 clr print artwork due | NFL2 |  |  | Cut Ok | 4707 | 4707 | 0 | 24345 | 573 | [11 empty] | 38 | Aug'2 |  |  | 25.07.26
BS-ONL | 48177 | 15388314 | 1704 | 293 | 2026-06-24 | 2026-06-27 | SS TS w DTM lace at nk and slve | TS |  |  | 2026-07-20 | 2026-07-25 | 2026-08-01 | 2026-08-12 |  |  | 2026-08-14 | 2026-08-14 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 2026-08-25 | 2026-08-26 |  |  |  |  | 2026-08-28 | 2026-08-31 |  |  | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-14 | 2026-09-16 | 82 | O1 | Jannati | Nk |  | 2 combo nk label print |  |  | NFL2 |  |  | Cut Ok | 294 | 294 | 0 | 1752 | 48 | [11 empty] | 38 | Aug'3 |  |  | 29.07.26
BS-ONL | 48180 | 15388877 | 1534 | 768 | 2026-06-24 | 2026-06-27 | LS Swt shirt w cuff btm rib and contrast stitch | Swt Shirt |  |  | 2026-07-15 | 2026-07-22 | 2026-07-25 | 2026-08-13 |  |  | 2026-08-12 | 2026-08-12 | 2026-08-17 | 2026-08-19 | 2026-08-20 | [6 empty] | 2026-08-22 | 2026-08-25 |  |  | 2026-08-27 | 2026-08-29 | 2026-09-03 | 2026-09-13 | 2026-09-15 | 81 | Q | Jannati | [5 empty] | NFL2 |  |  | Cut Ok | 768 | 768 | 0 | 1585 | 51 | [11 empty] | 38 | Aug'2 |  |  | 07.08.26
BS-ONL | 48175 | 15387015 | 1416 | 413 | 2026-06-24 | 2026-06-27 | LS Square wrap nk TS | TS |  |  | 2026-07-20 | 2026-07-25 | 2026-08-01 | 2026-08-12 |  |  | 2026-08-14 | 2026-08-14 | 2026-08-20 | 2026-08-22 | 2026-08-24 | [6 empty] | 2026-08-26 | 2026-08-28 |  |  | 2026-08-31 | 2026-09-02 | 2026-09-04 | 2026-09-14 | 2026-09-16 | 82 | M | Jannati | [5 empty] | NFL2 |  |  | Cut Ok | 413 | 413 | 0 | 1458 | 42 | [11 empty] | 38 | Aug'3 |  |  | 09.07.26
BS-ONL | 48171 | 15388040 | 10578 | 2000 | 2026-06-24 | 2026-06-27 | LS o nk TS w lace at nk & slve also btm letus stitch | TS |  |  | 2026-07-13 | 2026-07-23 | 2026-07-23 | 2026-08-08 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-13 | 2026-08-15 | 2026-08-19 | 2026-08-18 | 2026-08-22 |  |  |  |  | 2026-08-21 | 2026-08-29 |  |  | 2026-09-02 | 2026-09-04 | 2026-09-07 | 2026-09-14 | 2026-09-16 | 82 | M | Jannati | Nk |  | 7 combo 1 clr rub print at nk |  | Lace | NFL2 |  |  | Cut Ok | 2000 | 2000 | 0 | 10864 | 286 | [11 empty] | 38 | Aug'2 |  |  | 14.07.26
BS-ONL | 48181 | 15388549 | 525 | 232 | 2026-06-24 | 2026-06-27 | LS AOP double layer Swt shirt w nk cuff rib | Swt Shirt |  |  | 2026-07-12 | 2026-07-18 | 2026-07-21 | 2026-08-03 | 2026-08-06 | 2026-08-12 | 2026-08-14 | 2026-08-14 | 2026-08-20 | 2026-08-22 | 2026-08-22 |  |  |  |  | 2026-08-25 | 2026-08-26 | 2026-08-28 | 2026-08-29 |  |  | 2026-09-02 | 2026-09-05 | 2026-09-08 | 2026-09-13 | 2026-09-15 | 81 | R | Jannati |  | Chest | LGm-525 pcs 1 clr flat emb |  |  | NFL2 |  |  | Cut Ok | 312 | 311 | -1 | 546 | 21 | [11 empty] | 38 | Aug'3 |  |  | 12.08.26
BS-ONL | 48176 | 15388593 | 4032 | 580 | 2026-06-24 | 2026-06-27 | SS o nk TS | TS | 2026-07-21: 2026-07-15; 2026-07-28: 2026-07-28 |  |  | 2026-08-06 | 2026-08-06 | 2026-08-10 | 2026-08-12 | 2026-08-14 | 2026-08-14 | 2026-08-18 | 2026-08-18 | 2026-08-21 |  |  | 2026-08-22 | 2026-08-26 |  |  | 2026-08-28 | 2026-08-31 | 2026-09-03 | 2026-09-14 | 2026-09-16 | 82 | M | Jannati | Chest,Stone |  | c.dan viva-2064 pcs,,c.dan chic-1968 pcs both combo photo print and HP stone at chest |  | Stone at NFL | NFL2 |  |  | Cut Ok | 580 | 580 | 0 | 4129 | 97 | [11 empty] | 38 | Aug'2 |  |  | 29.07.26
BS-ONL | 48159 | 15395529 | 2010 | 322 | 2026-06-24 | 2026-06-27 | YD SS o nk TS | TS | 2026-07-14 | 2026-07-20 | 2026-07-24 | 2026-07-30 | 2026-08-03 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-10 | 2026-08-15 | 2026-08-17 | 2026-08-19 |  |  |  |  | 2026-08-20 | 2026-08-26 | 2026-08-28 | 2026-08-31 |  |  | 2026-09-03 | 2026-09-05 | 2026-09-10 | 2026-09-14 | 2026-09-16 | 82 | N1 | Mainul |  | Chest | white-1005 pcs,,corsage-1005 pcs both 1 clr flat emb and 1 clr seq all over emb at chest | YD |  | NFL2 |  |  | Cut Ok | 322 | 322 | 0 | 2127 | 117 | [11 empty] | 38 | Aug'2 |  |  | 26.08.26
BS-ONL | 44840 8th | 15318962 | 6575 | 3885 | 2026-06-25 | 2026-06-27 | LS HOOD SWT W DRAWSTING | HOODY | [8 empty] | 2026-07-25 | 2026-07-04 |  | 2026-07-08 | 2026-07-13 | 2026-07-13 | 2026-07-31 |  |  | 2026-08-01 | 2026-08-08 | 2026-08-10 | 2026-08-15 |  |  | 2026-08-18 | 2026-08-20 | 2026-08-25 | 2026-09-14 | 2026-09-16 | 81 | R | Imran | slv,Chest | Chest | c.dan mermaid-1700 pcs,,c.dan navy-4875 pcs both combo 1 CLR PALCEMENT PRINT at chest and both slve and chest 1 CLR LURTEX EMB |  | stock fab from 44870 7th+29402 35th | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 6761 | 186 | [11 empty] | 38 | Jul'1 |  |  | 07.08.26
BS-ONL | 29402 43th | 15312874 | 15012 | 8500 | 2026-06-23 | 2026-06-27 | LS Swt hoodie w drawstring | Hoody |  |  | 2026-07-10 | 2026-07-25 | 2026-07-20 | 2026-08-11 |  |  | 2026-08-06 | 2026-08-06 |  | 2026-08-12 | 2026-08-17 |  |  |  |  | 2026-08-15 | 2026-08-20 | 2026-08-20 | 2026-08-28 |  |  | 2026-08-31 | 2026-09-02 | 2026-09-05 | 2026-09-14 | 2026-09-16 | 83 | H | Imran |  | Chest,Pkt | air blue-2412 pcs,,anise-5460 pcs,,n.sky-840 pcs,,pink-5460 pcs,,granita-840 pcs all combo chest and btm side 1 CLR FLAT EMB |  |  | NFL1 |  |  | Cut Ok | 8502 | 8411 | -91 | 15342 | 330 | [11 empty] | 38 | Aug'2 |  |  | 07.08.26
BS-ONL | 47047 2nd | 15384146 | 3345 | 809 | 2026-06-23 | 2026-06-27 | LS o nk TS w btm lace | TS |  |  | 2026-07-15 | 2026-07-20 | 2026-08-01 | 2026-08-12 |  |  | 2026-08-10 | 2026-08-10 |  | 2026-08-15 | 2026-08-17 | [6 empty] | 2026-08-19 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-28 | 2026-08-31 | 2026-09-14 | 2026-09-16 | 83 | N1 | Imran |  |  |  |  | Lace | NFL2 |  |  | Cut Ok | 809 | 809 | 0 | 3444 | 99 | [11 empty] | 38 | Aug'2 |  |  | 25.07.26
BS-ONL | 26766 20th | 15316135 | 3408 | 1650 | 2026-06-23 | 2026-06-27 | LDS PANT W PKT drawstring | PANT |  |  | 2026-07-15 | 2026-07-22 | 2026-07-22 | 2026-08-10 |  |  | 2026-08-07 | 2026-08-07 |  | 2026-08-12 | 2026-08-15 |  |  |  |  | 2026-08-14 | 2026-08-18 | 2026-08-20 | 2026-08-25 |  |  | 2026-08-02 | 2026-08-29 | 2026-08-31 | 2026-09-14 | 2026-09-16 | 83 | P | Imran |  | Thigh | anise flower-1704 pcs,,pink-1704 pcs both combo 1 clr flat emb |  |  | NFL2 |  |  | Cut Ok | 1650 | 1650 | 0 | 3523 | 115 | [11 empty] | 38 | Aug'2 |  |  | 07.08.26
BS-ONL | 48258 | 15385031 | 26278 | 4790 | 2026-06-23 | 2026-06-27 | SS o nk TS w btm lace attach | TS |  |  | 2026-07-15 | 2026-07-25 | 2026-07-27 | 2026-08-15 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-24 | 2026-08-27 | 2026-09-02 | [6 empty] | 2026-09-01 | 2026-09-15 |  |  | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-19 | 2026-09-21 | 88 | K | Imran |  |  |  |  | Lace | NFL2 |  |  | Cut Ok | 4790 | 4790 | 0 | 26539 | 261 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-ONL | 48185 | 15382071 | 504 | 190 | 2026-06-24 | 2026-06-27 | LS o nk TS | TS |  |  | 2026-07-20 | 2026-07-24 | 2026-08-03 | 2026-08-13 |  |  | 2026-08-15 | 2026-08-15 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 2026-08-26 | 2026-08-26 |  |  |  |  | 2026-08-28 | 2026-08-29 |  |  | 2026-09-02 | 2026-09-05 | 2026-09-07 | 2026-09-14 | 2026-09-16 | 82 | N1 | Zahirul | Nk |  | 1 combo nk 1 clr rub label print |  |  | NFL2 |  |  | Cut Ok | 190 | 190 | 0 | 521 | 17 | [11 empty] | 38 | Aug'3 |  |  | 22.07.26
BS-ONL | 48188 | 15299502 | 7842 | 1540 | 2026-06-24 | 2026-06-27 | SS O nk TS | TS |  |  | 2026-07-15 | 2026-07-22 | 2026-07-23 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-10 | 2026-08-15 | 2026-08-17 | 2026-08-20 | 2026-08-20 | 2026-08-24 |  |  |  |  | 2026-08-25 | 2026-08-31 |  |  | 2026-09-02 | 2026-09-04 | 2026-09-08 | 2026-09-14 | 2026-09-16 | 82 | N2 | Zahirul | Chest |  | black-762 pcs,,ether-1290 pcs,,c.dan-642 pcs,,pink-2532 pcs,,anise-2616 pcs all combo chest 1 clr gltr print |  |  | NFL2 |  |  | Cut Ok | 1540 | 1540 | 0 | 8049 | 207 | [11 empty] | 38 | Aug'2 |  |  | 09.07.26
BS-ONL | 48128 | 15389798 | 720 | 178 | 2026-06-17 | 2026-06-25 | LS v nk TS w nk lace and front gathering | TS |  |  | 2026-07-15 | 2026-07-20 | 2026-08-01 | 2026-08-12 |  |  | 2026-08-14 | 2026-08-14 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 2026-08-24 | 2026-08-26 |  |  |  |  | 2026-08-26 | 2026-08-28 |  |  | 2026-08-31 | 2026-09-02 | 2026-09-04 | 2026-09-14 | 2026-09-16 | 89 | O1 | Zahirul | Nk |  | 3 combo nk 1 clr rub print |  | Lace | NFL2 |  |  | Cut Ok | 178 | 178 | 0 | 769 | 49 | [11 empty] | 38 | Aug'3 |  |  | 19.08.26
BS-ONL | 48127 | 15394337 | 1356 | 390 | 2026-06-17 | 2026-06-25 | LS cardigan w front binding knpt | Cardigan |  |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-10 | 2026-08-15 | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-21 |  |  |  |  | 2026-08-24 | 2026-08-26 |  |  | 2026-08-28 | 2026-08-31 | 2026-09-05 | 2026-09-14 | 2026-09-16 | 89 | K | Zahirul | Nk |  | 3 combo nk 1 clr rub print |  |  | NFL2 |  |  | Cut Ok | 415 | 415 | 0 | 1434 | 78 | [11 empty] | 38 | Aug'2 |  |  | 19.08.26
OVS SPA | 47778 | 271LEG002-6153 | 5382 | 2269 | 2026-06-19 | 2026-06-27 | Waist fold legging w contrast side piping | Legging |  |  | 2026-07-15 | 2026-07-28 | 2026-07-30 | 2026-08-12 |  |  | 2026-08-14 | 2026-08-10 | 2026-08-15 | 2026-08-17 | 2026-08-19 | 2026-08-20 | 2026-08-22 |  |  |  |  | 2026-08-24 | 2026-08-31 |  |  | 2026-09-01 | 2026-09-03 | 2026-09-05 | 2026-09-07 | 2026-09-07 | 80 | G1 | Sirajul | Waist |  | black-5382 pcs 1 clr foil waist size label print |  |  | NFL1 |  |  | Cut Ok | 2269 | 2269 | 0 | 5436 | 54 | [11 empty] | 37 | Aug'2 |  |  | 18.08.26
OVS SPA | 47779 | 271TRO017-6153 | 2994 | 1465 | 2026-06-19 | 2026-06-27 | Long cut& sew trouser w side pkt drawstring | Trouser |  |  | 2026-07-10 | 2026-07-20 | 2026-07-21 | 2026-08-05 |  |  | 2026-08-14 | 2026-08-08 | 2026-08-15 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-21 |  |  |  |  | 2026-08-24 | 2026-08-29 |  |  | 2026-08-31 | 2026-09-02 | 2026-09-04 | 2026-09-07 | 2026-09-07 | 80 | H | Sirajul | Waist |  | light grey-2994 pcs 1 clr foil size label print |  |  | NFL1 |  |  | Cut Ok | 1465 | 1465 | 0 | 3120 | 126 | [11 empty] | 37 | Aug'2 |  |  | 12.08.26
OVS SPA | 47780 | 271TSH006-6153 | 5382 | 942 | 2026-06-19 | 2026-06-27 | SS TS w back and slve yoke w front jaquared label | TS |  |  | 2026-07-01 | 2026-07-13 | 2026-07-14 | 2026-07-25 |  |  | 2026-08-12 | 2026-08-04 | 2026-08-12 | 2026-08-13 | 2026-08-15 | 2026-08-15 | 2026-08-22 |  |  |  |  | 2026-08-22 | 2026-08-27 |  |  | 2026-08-28 | 2026-08-31 | 2026-09-02 | 2026-09-07 | 2026-09-07 | 80 | E | Sirajul | Chest, Nk & Slv |  | white-5382 pcs front both slve 2 clr rub print and nk 1 clr foil print |  |  | NFL1 |  |  | Cut Ok | 941 | 941 | 0 | 5520 | 138 | [11 empty] | 37 | Aug'2 |  |  | 13.08.26
OVS SPA | 47781 | 271SWT008-6153 | 2994 | 1035 | 2026-06-19 | 2026-06-27 | LS Swt shirt w front back vertical cut & sew and frt jaqurd label | Swt Shirt |  |  | 2026-07-13 | 2026-07-24 | 2026-07-25 | 2026-08-10 |  |  | 2026-08-14 | 2026-08-10 | 2026-08-15 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-22 |  |  |  |  | 2026-08-24 | 2026-08-29 |  |  | 2026-08-31 | 2026-09-02 | 2026-09-04 | 2026-09-07 | 2026-09-07 | 80 | N/3 | Sirajul | Nk |  | light grey-2994 pcs 1 clr foil size label print |  |  | NCL |  |  | Ready Test Cut | 1035 | 1035 | 0 | 0 | -2994 | [11 empty] | 37 | Aug'2
OVS SPA | 48150 | 271TSH009-6153 | 5094 | 1169 | 2026-06-19 | 2026-06-27 | SS drop shlder TS w shlder yoke | TS |  |  | 2026-08-01 | 2026-08-11 | 2026-08-12 | 2026-08-25 |  |  | 2026-09-07 | 2026-09-05 | 2026-09-10 | 2026-09-11 | 2026-09-14 | [6 empty] | 2026-09-15 | 2026-09-19 |  |  | 2026-09-21 | 2026-09-23 | 2026-09-25 | 2026-09-26 | 2026-09-26 | 99 | D2 | Sirajul | [5 empty] | NFL1 |  |  | Cut Ok | 1209 | 1209 | 0 | 5148 | 54 | [11 empty] | 39 | Sep'2 |  |  | 20.08.26
OVS SPA | 48151 | 271TSH010-6153 | 5118 | 1113 | 2026-06-19 | 2026-06-27 | YD SS double Layer TS w insert solid | TS | 2026-07-20 | 2026-07-31 | 2026-08-01 | 2026-08-11 | 2026-08-12 | 2026-08-25 |  |  | 2026-09-05 | 2026-08-28 | 2026-09-03 | 2026-09-04 | 2026-09-07 |  |  |  |  | 2026-09-08 | 2026-09-14 | 2026-09-14 | 2026-09-19 |  |  | 2026-09-21 | 2026-09-23 | 2026-09-25 | 2026-09-26 | 2026-09-26 | 99 | J | Sirajul |  | Chest | white-5118 pcs 1 clr flat emb | YD |  | NFL2 |  |  | Size Set Run | 1113 | 1113 | 0 | 0 | -5118 | [11 empty] | 39 | Sep'1 |  |  | 24.08.26
OVS SPA | 47729 | 271MMP006CMS12-6111 | 7539 | 2111 | 2026-06-12 | 2026-06-27 | AOP LS reglan O nk TS | TS |  |  | 2026-07-18 | 2026-07-30 | 2026-08-01 | 2026-08-12 | 2026-08-13 | 2026-08-22 | 2026-08-31 | 2026-09-01 | 2026-09-05 | 2026-09-07 | 2026-09-09 | [6 empty] | 2026-09-10 | 2026-09-17 |  |  | 2026-09-18 | 2026-09-21 | 2026-09-23 | 2026-09-26 | 2026-09-26 | 106 | G2 | Basir |  |  |  | AOP |  | NFL1 |  |  | Cut Run | 2112 | 2112 | 0 | 6573 | -966 | [11 empty] | 39 | Sep'1 |  |  | 02.09.26
OVS SPA | 47730 | 271MMP007CMS13-6111 | 7539 | 2186 | 2026-06-12 | 2026-06-27 | AOP long pant w drawstring | Pant |  |  | 2026-07-18 | 2026-07-31 | 2026-08-01 | 2026-08-14 | 2026-08-15 | 2026-08-25 | 2026-08-27 | 2026-08-28 | 2026-09-04 | 2026-09-05 | 2026-09-08 | [6 empty] | 2026-09-09 | 2026-09-18 |  |  | 2026-09-19 | 2026-09-21 | 2026-09-23 | 2026-09-26 | 2026-09-26 | 106 | H | Basir |  |  |  | AOP |  | NFL1 |  |  | Cut Run | 2187 | 2118 | -69 | 4242 | -3297 | [11 empty] | 39 | Sep'1 |  |  | 29.08.26
OVS SPA | 47731 | 271NDG003DRSL-6111 | 5226 | 2021 | 2026-06-12 | 2026-06-27 | AOP LS o nk Long dress | Dress |  |  | 2026-07-18 | 2026-07-31 | 2026-08-01 | 2026-08-13 | 2026-08-14 | 2026-08-24 | 2026-08-31 | 2026-09-01 | 2026-09-05 | 2026-09-07 | 2026-09-09 | [6 empty] | 2026-09-10 | 2026-09-17 |  |  | 2026-09-18 | 2026-09-21 | 2026-09-23 | 2026-09-26 | 2026-09-26 | 106 | A | Basir |  |  |  | AOP |  | NFL1 |  |  | Cut Run | 2020 | 2020 | 0 | 3087 | -2139 | [11 empty] | 39 | Sep'1 |  |  | 02.09.26
OVS SPA | 47732 | 271NDG004LDY8-6111 | 5051 | 2075 | 2026-06-12 | 2026-06-27 | LS cut& sew dress w front placket btn | Dress |  |  | 2026-07-15 | 2026-07-27 | 2026-08-01 | 2026-08-13 | 2026-08-14 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-09-03 | 2026-09-04 | 2026-09-07 | [6 empty] | 2026-09-08 | 2026-09-16 |  |  | 2026-09-17 | 2026-09-19 | 2026-09-21 | 2026-09-26 | 2026-09-26 | 106 | N/2 | Basir |  |  |  | AOP |  | NCL |  |  | Ready Test Cut | 2074 | 2074 | 0 | 0 | -5051 | [11 empty] | 39 | Sep'1
OVS SPA | 47734 | 271PJA018AG1-6111 | 10852 | 2894 | 2026-06-12 | 2026-06-27 | LS v nk TS w placket btn nk lace and long pant | Top & BTM |  |  | 2026-08-01 | 2026-08-13 | 2026-08-14 | 2026-08-17 |  |  | 2026-08-31 | 2026-09-01 | 2026-09-05 | 2026-09-07 | 2026-09-11 | [6 empty] | 2026-09-11 | 2026-09-17 |  |  | 2026-09-18 | 2026-09-21 | 2026-09-23 | 2026-09-26 | 2026-09-26 | 106 | N/2 | Basir |  |  |  |  | Lace | NCL |  |  | Ready Test Cut | 2894 | 2894 | 0 | 0 | -10852 | [11 empty] | 39 | Sep'1
OVS SPA | 47735 | 271PJA019AG2-6111 | 16690 | 4680 | 2026-06-12 | 2026-06-27 | AOP LS Swt shirt w cuff btm rib and pant w twill tape hem rib | Top & BTM |  |  | 2026-07-15 | 2026-07-28 | 2026-08-01 | 2026-08-12 | 2026-08-13 | 2026-08-24 | 2026-08-26 | 2026-08-27 | 2026-09-02 | 2026-09-03 | 2026-09-08 | [6 empty] | 2026-09-07 | 2026-09-17 |  |  | 2026-09-18 | 2026-09-21 | 2026-09-23 | 2026-09-26 | 2026-09-26 | 106 | C+E | Basir |  |  |  | AOP |  | NFL1 |  |  | Cut Ok | 4681 | 4460 | -221 | 16708 | 18 | [11 empty] | 39 | Sep'1 |  |  | 27.08.26
OVS SPA | 47736 | 271PJA021PD4-6111 | 16278 | 4219 | 2026-06-12 | 2026-06-27 | AOP LS TS w frt placket btn and elasted long pant | Top & BTM |  |  | 2026-07-15 | 2026-07-28 | 2026-08-01 | 2026-08-12 | 2026-08-13 | 2026-08-24 | 2026-08-26 | 2026-08-27 | 2026-09-02 | 2026-09-03 | 2026-09-08 | [6 empty] | 2026-09-07 | 2026-09-17 |  |  | 2026-09-18 | 2026-09-21 | 2026-09-23 | 2026-09-26 | 2026-09-26 | 106 | C+E | Basir |  |  |  | AOP |  | NFL1 |  |  | Cut Run | 4218 | 4076 | -142 | 10396 | -5882 | [11 empty] | 39 | Sep'1 |  |  | 28.08.26
OVS SPA | 47737 | 271PJA022PD7-6111 | 14678 | 3975 | 2026-06-12 | 2026-06-27 | AOP LS TS w full placket btn and elasted pant | Top & BTM |  |  | 2026-07-15 | 2026-07-28 | 2026-08-01 | 2026-08-14 | 2026-08-14 | 2026-08-25 | 2026-08-31 | 2026-08-26 | 2026-09-02 | 2026-09-03 | 2026-09-10 | [6 empty] | 2026-09-09 | 2026-09-18 |  |  | 2026-09-19 | 2026-09-21 | 2026-09-23 | 2026-09-26 | 2026-09-26 | 106 | N/3 | Basir |  |  |  | AOP |  | NCL |  |  | Ready Test Cut | 3976 | 3151 | -825 | 0 | -14678 | [11 empty] | 39 | Sep'1
OVS SPA | 47793 | 271PJA017PTV1-6111 | 19688 | 5980 | 2026-06-12 | 2026-06-27 | AOP LS TS w frt placket btn and elasted long pant w string | Top & BTM |  |  | 2026-07-10 | 2026-07-25 | 2026-07-25 | 2026-08-10 | 2026-08-11 | 2026-08-22 | 2026-09-01 | 2026-08-20 | 2026-08-26 | 2026-08-27 | 2026-09-03 |  |  |  |  | 2026-09-02 | 2026-09-09 | 2026-09-08 | 2026-09-18 |  |  | 2026-09-19 | 2026-09-21 | 2026-09-23 | 2026-09-26 | 2026-09-26 | 106 | N/2 | Basir |  | Chest | blue top-3211 pcs,,violet top-3011 pcs,,grey top-1811 pcs,,white top-1811 pcs all combo 1 clr flat emb,,,btm all AOP -9844 pcs no emb | AOP |  | NCL |  |  | Ready Test Cut | 5980 | 4989 | -991 | 0 | -19688 | [11 empty] | 39 | Aug'3
OVS SPA | 48241 | 271TSHT184W-6084 | 10965 | 1663 | 2026-06-12 | 2026-06-27 | SS O nk TS | TS |  |  | 2026-07-18 | 2026-07-31 | 2026-08-01 | 2026-08-13 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-26 | 2026-08-27 | 2026-08-31 | [6 empty] | 2026-09-01 | 2026-09-07 |  |  | 2026-09-08 | 2026-09-10 | 2026-09-12 | 2026-09-15 | 2026-09-15 | 95 | D2 | Basir | [5 empty] | NFL1 |  |  | Cut Ok | 1663 | 1663 | 0 | 11142 | 177 | [11 empty] | 38 | Aug'3 |  |  | 18.08.26
OVS SPA | 47733 | 271NDG005PD8-6111 | 2626 | 888 | 2026-06-12 | 2026-06-27 | AOP long dress w full placket btn | Dress |  |  | 2026-07-20 | 2026-07-31 | 2026-08-01 | 2026-08-12 | 2026-08-13 | 2026-08-24 | 2026-08-27 | 2026-08-28 | 2026-09-04 | 2026-09-05 | 2026-09-07 | [6 empty] | 2026-09-08 | 2026-09-14 |  |  | 2026-09-15 | 2026-09-17 | 2026-09-19 | 2026-09-26 | 2026-09-26 | 106 | N/2 | Basir |  |  |  | AOP |  | NCL |  |  | Ready Test Cut | 888 | 888 | 0 | 0 | -2626 | [11 empty] | 39 | Sep'1
BS-ONL | 48179 | 15388277 | 4179 | 2046 | 2026-06-24 | 2026-06-27 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-07-15 | 2026-07-25 | 2026-07-27 | 2026-08-15 |  |  | 2026-08-14 | 2026-08-14 | 2026-08-21 | 2026-08-24 | 2026-08-27 |  |  |  |  | 2026-08-27 | 2026-09-07 | 2026-09-10 | 2026-09-15 |  |  | 2026-09-17 | 2026-09-19 | 2026-09-23 | 2026-10-12 | 2026-10-14 | 110 | Q | Jannati |  | Front,Slv | pink-1240 pcs,,soft-1984 pcs,,LGM-955 pcs all combo frt both slve 1 clr terry emb |  |  | NFL2 |  |  | Cut Ok | 2046 | 1821 | -225 | 4266 | 87 | [11 empty] | 42 | Aug'3 |  |  | 30.07.26
BS-ONL | 30011 21th | 15318144 | 12597 | 1912 | 2026-06-24 | 2026-06-25 | SS o nk TS | TS |  |  | 2026-07-05 | 2026-07-15 | 2026-07-22 | 2026-08-08 |  |  | 2026-08-15 | 2026-08-07 |  | 2026-08-12 | 2026-08-17 | 2026-08-15 | 2026-08-22 | 2026-08-20 | 2026-08-25 | 2026-08-25 | 2026-08-31 | 2026-09-01 | 2026-09-08 |  |  | 2026-09-12 | 2026-09-15 | 2026-09-18 | 2026-10-12 | 2026-10-14 | 110 | L1 | Mainul | Chest,Stone | Chest | c.dan lady denim-936 pcs photo print w foil print no emb ,,c.dan lady jacket-936 pcs photo print w 2 clr gltr and no emb ,,c.dan lady pant-936 pcs photo print w 1 clr foil print and no emb,,C.dan lemon au-816 pcs 8 clr pig photo print w 1 clr foil and no emb ,,C.dan lemon delce-816 pcs 9 clr pig photo print w 1 clr gltr and stone HP and no emb ,,c.dan lemon portofino-816 pcs 9 clr pig photo print w 1 clr gltr and stone HP and no emb ,,c.dan lemon positano-936 pcs 9 clr pig photo print w 1 clr gltr and stone HP and no emb,,c.dan scratced-1500 pcs 1 clr pig 1 clr foil print and no emb ,,black animal-1500 pcs 1 clr rub 1 clr foil and no emb ,,balsam dream-1605 pcs 2 clr pig 1 clr foil print and 1 clr seq emb ,,phanthom attitude-900 pcs 2 clr rub 1 clr foil print and no emb ,,walnut etenal-900 pcs 1 clr rub 1 clr foil and no emb |  | 1 combo seq and 3 combo stone HP | NFL2 |  |  | Cut Ok | 1912 | 1912 | 0 | 13022 | 425 | [11 empty] | 42 | Aug'2 |  |  | 25.07.26
BS-ONL | 48161 | 15369012 | 4032 | 619 | 2026-06-24 | 2026-06-27 | SS o nk TS w slve fold tuck | TS |  |  | 2026-07-18 | 2026-07-23 | 2026-07-27 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-10 | 2026-08-15 | 2026-08-17 | 2026-08-20 | 2026-08-20 | 2026-08-26 |  |  | 2026-08-26 | 2026-08-29 | 2026-09-01 | 2026-09-03 |  |  | 2026-09-07 | 2026-09-09 | 2026-09-12 | 2026-10-12 | 2026-10-14 | 110 | N1 | Mainul | Chest | Chest | c.dan sky-2016 pcs,,c.dan pink-2016 pcs both combo 1 clr pig stripe place ment print and 1 clr lurex emb |  |  | NFL2 |  |  | Cut Ok | 619 | 619 | 0 | 4158 | 126 | [11 empty] | 42 | Aug'2 |  |  | 07.08.26
BS-ONL | 48162 | 15390521 | 2016 | 339 | 2026-06-24 | 2026-06-27 | SS V nk TS w slve fold tuck | TS |  |  | 2026-07-17 | 2026-07-23 | 2026-07-25 | 2026-08-10 |  |  | 2026-08-13 | 2026-08-13 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-25 | 2026-08-28 |  |  |  |  | 2026-09-01 | 2026-09-02 |  |  | 2026-09-04 | 2026-09-07 | 2026-09-12 | 2026-10-12 | 2026-10-14 | 110 | K | Mainul | Chest |  | c.dan-672 pcs,,blue-672 pcs,,pink-672 pcs all combo 4 clr rub 1 clr gltr print |  |  | NFL2 |  |  | Cut Ok | 339 | 339 | 0 | 2088 | 72 | [11 empty] | 42 | Aug'3 |  |  | 07.08.26
BS-ONL | 44115 14th | 15315687 | 3705 | 1694 | 2026-06-23 | 2026-06-27 | Ls Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-07-15 | 2026-07-20 | 2026-07-20 | 2026-08-06 |  |  | 2026-08-10 | 2026-08-01 |  | 2026-08-06 | 2026-08-09 |  |  |  |  | 2026-08-08 | 2026-09-03 | 2026-09-05 | 2026-09-09 |  |  | 2026-09-12 | 2026-09-15 | 2026-09-19 | 2026-10-12 | 2026-10-14 | 111 | A | Imran |  | Slv | lolipop-1431 pcs,,black-1449 pcs,,soft chambray-825 pcs all combo both slve CUTOUT EMB |  |  | NFL1 |  |  | Cut Ok | 1695 | 1695 | 0 | 3821 | 116 | [11 empty] | 42 | Aug'2 |  |  | 07.08.26
OVS SPA | 48130 | 271TSH090-227 | 5832 | 705 | 2026-06-22 | 2026-06-26 | YD LS o nk TS w Letus stitch | TS | 2026-08-10 | 2026-08-20 | 2026-08-21 | 2026-08-31 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-21 | 2026-09-12 | 2026-09-19 | 2026-09-21 | 2026-09-23 |  |  |  |  | 2026-09-24 | 2026-09-30 | 2026-10-01 | 2026-10-05 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-09 | 2026-10-12 | 2026-10-12 | 112 | G1 | Salam |  | Chest | White-5832 pcs 1 clr Terry patch emb | YD | Need Artwork confirmation by merchant | NFL1 |  |  | Need Test Cut | 705 | 0 | -705 | 0 | -5832 | [11 empty] | 42 | Sep'3 |  |  | 02.09.26
OVS SPA | 48131 | 271TSH091-227 | 4588 | 478 | 2026-06-22 | 2026-06-26 | LS TS w back nk placket btn | TS |  |  | 2026-08-01 | 2026-08-10 | 2026-08-11 | 2026-08-21 |  |  | 2026-09-12 | 2026-09-01 | 2026-09-07 | 2026-09-08 | 2026-09-10 | 2026-09-11 | 2026-09-16 |  |  | 2026-09-16 | 2026-09-23 | 2026-09-23 | 2026-09-30 |  |  | 2026-10-01 | 2026-10-03 | 2026-10-05 | 2026-10-12 | 2026-10-12 | 112 | D1 | Salam | Chest | Chest | lucent white-4588 pcs chest 1 clr pig and applique lazer cut fabric attach emb and 4 clr terry emb |  | Need Artwork confirmation by merchant | NFL1 |  |  | Size Set Run Emb | 478 | 478 | 0 | 0 | -4588 | [11 empty] | 42 | Sep'1 |  |  | 07.09.26
BS-NMT | 48008 | 13264361 | 5961 | 563 | 2026-06-10 | 2026-06-24 | AOP waist fold swt pant w rib | Pant |  |  | 2026-08-02 | 2026-08-10 | 2026-08-14 | 2026-08-28 | 2026-09-01 | 2026-09-10 | 2026-09-16 | 2026-09-16 | 2026-09-22 | 2026-09-25 | 2026-09-28 | [6 empty] | 2026-10-01 | 2026-10-06 |  |  | 2026-10-08 | 2026-10-12 | 2026-10-15 | 2026-11-01 | 2026-11-03 | 144 | ZA2 | Mosaddik |  |  |  | AOP |  | NFL3 |  |  | Cut Run | 691 | 596 | -95 | 1824 | -4137 | [11 empty] | 45 | Sep'3 |  |  | 28.08.26
BS-NMT | 48006 | 13264355 | 2141 | 260 | 2026-06-10 | 2026-06-24 | Waist fold swt pant w rib | Pant |  |  | 2026-08-06 | 2026-08-10 | 2026-08-16 | 2026-08-31 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-14 | 2026-09-16 | 2026-09-17 |  |  |  |  | 2026-09-19 | 2026-09-26 | 2026-10-01 | 2026-10-03 |  |  | 2026-10-06 | 2026-10-08 | 2026-10-13 | 2026-10-30 | 2026-11-02 | 142 | Z | Mosaddik |  | Leg | pink-2141 pcs leg two part 3 clr flat all over emb |  |  | NFL3 |  |  | Need Cut | 261 | 261 | 0 | 0 | -2141 | [11 empty] | 45 | Sep'2 |  |  | 27.08.26
BS-NMT | 48001 | 13264343 | 1865 | 221 | 2026-06-10 | 2026-06-24 | Waist fold swt pant w rib | Pant |  |  | 2026-08-06 | 2026-08-12 | 2026-08-17 | 2026-08-31 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-14 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-21 |  |  | 2026-09-21 | 2026-09-26 | 2026-10-01 | 2026-10-03 |  |  | 2026-10-06 | 2026-10-08 | 2026-10-13 | 2026-11-01 | 2026-11-03 | 144 | Z | Mosaddik | Thigh | Thigh | peyote-1865 pcs 1 clr rub and 1 clr flat 1 clr terry emb |  |  | NFL3 |  |  | Need Cut | 220 | 220 | 0 | 0 | -1865 | [11 empty] | 45 | Sep'2 |  |  | 02.09.26
BS-NMT | 48005 | 13264353 | 2421 | 349 | 2026-06-10 | 2026-06-24 | LS swt shirt w w rib & shlder snap btn | Swt Shirt |  |  | 2026-08-04 | 2026-08-10 | 2026-08-14 | 31/9 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-17 | 2026-09-19 | 2026-09-21 |  |  |  |  | 2026-09-23 | 2026-09-30 | 2026-10-04 | 2026-10-08 |  |  | 2026-10-12 | 2026-10-15 | 2026-10-19 | 2026-10-30 | 2026-11-02 | 142 | T2 | Mosaddik |  | Front,Slv | pink-2421 pcs chest both slve 3 clr flat all over emb |  |  | NFL3 |  |  | Cut Ok | 350 | 350 | 0 | 2560 | 139 | [11 empty] | 45 | Sep'2 |  |  | 27.08.26
BS-NMT | 48007 | 13264360 | 6752 | 724 | 2026-06-10 | 2026-06-24 | AOP LS swt shirt w w rib & shlder snap btn | Swt Shirt |  |  | 2026-07-25 | 2026-08-02 | 2026-08-06 | 2026-08-20 | 2026-08-24 | 2026-09-03 | 2026-09-05 | 2026-09-05 | 2026-09-12 | 2026-09-16 | 2026-09-19 |  |  |  |  | 2026-09-19 | 2026-09-28 | 2026-10-01 | 2026-10-07 |  |  | 2026-10-10 | 2026-10-12 | 2026-10-14 | 2026-11-01 | 2026-11-03 | 144 | T2 | Mosaddik |  | Chest | pink-3141 pcs,,peyote-3611 pcs both combo 3 clr flat 2 clr terry emb | AOP |  | NFL3 |  |  | Need Cut | 948 | 797 | -151 | 0 | -6752 | [11 empty] | 45 | Sep'2 |  |  | 25.08.26
BS-NMT | 48000 | 13264342 | 2566 | 364 | 2026-06-10 | 2026-06-24 | LS swt shirt w w rib & shlder snap btn | Swt Shirt |  |  | 2026-08-02 | 2026-08-08 | 2026-08-16 | 2026-08-31 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-14 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-21 |  |  | 2026-09-19 | 2026-09-26 | 2026-10-01 | 2026-10-04 |  |  | 2026-10-07 | 2026-10-10 | 2026-10-13 | 2026-11-01 | 2026-11-03 | 144 | T2 | Mosaddik | Chest | Chest | peyote-2566 pcs 1 clr rub and 1 clr flat 1 clr terry emb |  |  | NFL3 |  |  | Need Cut | 364 | 364 | 0 | 0 | -2566 | [11 empty] | 45 | Sep'2 |  |  | 25.08.26
BS-NMT | 48012 | 13264421 | 1020 | 196 | 2026-06-10 | 2026-06-27 | LS reglan contrast Slve full zipper Swt body w YD cuff nk rib | Body |  |  | 2026-08-01 | 2026-08-06 | 2026-08-13 | 2026-08-27 |  |  | 2026-09-04 | 2026-09-04 | 2026-09-10 | 2026-09-14 | 2026-09-15 |  |  |  |  | 2026-09-17 | 2026-09-22 | 2026-09-25 | 2026-09-29 |  |  | 2026-10-03 | 2026-10-06 | 2026-10-10 | 2026-11-02 | 2026-11-04 | 145 | S | Mosaddik |  | Chest | basil-1020 pcs 1 clr terry emb |  |  | NFL3 |  |  | File Due | 197 | 54 | -143 | 0 | -1020 | [11 empty] | 45 | Sep'2
BS-NMT | 48013 | 13267227 | 2979 | 334 | 2026-06-10 | 2026-06-27 | LS Body w shlder btm snap btn | Body |  |  | 2026-07-25 | 2026-07-31 | 2026-08-10 | 2026-08-25 |  |  | 2026-09-02 | 2026-09-02 | 2026-09-09 | 2026-09-12 | 2026-09-15 | 2026-09-16 | 2026-09-17 |  |  | 2026-09-16 | 2026-09-21 | 2026-09-24 | 2026-09-28 |  |  | 2026-09-30 | 2026-10-03 | 2026-10-08 | 2026-11-02 | 2026-11-04 | 145 | Y | Mosaddik | Nk | Chest | Basil-1932 pcs,,spellbound-1047 pcs both combo applique fab attach emb |  |  | NFL3 |  |  | Need Cut | 335 | 335 | 0 | 0 | -2979 | [11 empty] | 45 | Sep'2 |  |  | 27.08.26
BS-NMT | 48011 | 13264416 | 1534 | 155 | 2026-06-10 | 2026-06-27 | LS O nk TS w shlder snap btn | TS |  |  | 2026-07-20 | 2026-07-25 | 2026-08-10 | 2026-08-24 |  |  | 2026-08-28 | 2026-08-28 | 2026-09-05 | 2026-09-09 | 2026-09-10 | 2026-09-14 | 2026-09-16 |  |  | 2026-09-14 | 2026-09-18 | 2026-09-21 | 2026-09-23 |  |  | 2026-09-25 | 2026-09-28 | 2026-10-05 | 2026-11-02 | 2026-11-04 | 145 | T2 | Mosaddik | Nk | Chest | Basil-767 pcs,,spellbound-767 pcs both combo applique fab attach emb |  |  | NFL3 |  |  | Cut Ok | 154 | 154 | 0 | 1622 | 88 | [11 empty] | 45 | Sep'1 |  |  | 25.08.26
BS-NMT | 47999 | 13225450 | 1200 | 114 | 2026-06-10 | 2026-06-27 | YD waist fold legging | Legging | 2026-08-01 | 2026-08-06 | 2026-08-10 | 2026-08-15 | 2026-08-20 | 2026-08-25 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-11 | 2026-09-14 | 2026-09-15 | 2026-09-17 | 2026-09-18 |  |  |  |  | 2026-09-21 | 2026-09-22 |  |  | 2026-09-24 | 2026-09-28 | 2026-09-30 | 2026-11-01 | 2026-11-03 | 144 | ZA2 | Mosaddik | Waist |  | 1 combo label print | YD |  | NFL3 |  |  | Need Cut FB | 120 | 0 | -120 | 0 | -1200 | [11 empty] | 45 | Sep'2 |  |  | 27.08.26
BS-NMT | 48009 | 13264403 | 3452 | 475 | 2026-06-10 | 2026-06-27 | LS Swt body w reglan contrast slve frt pkt and frt placket btn btm snap btn | Body |  |  | 2026-07-15 | 2026-07-31 | 2026-08-08 | 2026-08-26 |  |  | 2026-09-01 | 2026-09-01 | 2026-09-07 | 2026-09-09 | 2026-09-12 | 2026-09-14 | 2026-09-15 |  |  |  |  | 2026-09-17 | 2026-09-22 |  |  | 2026-09-24 | 2026-09-26 | 2026-09-30 | 2026-10-30 | 2026-11-02 | 142 | S | Mosaddik | Nk |  | 2 combo label print |  |  | NFL3 |  |  | Need Cut | 476 | 311 | -165 | 0 | -3452 | [11 empty] | 45 | Sep'1 |  |  | 02.09.26
BS-NMT | 47998 | 13225449 | 1200 | 114 | 2026-06-10 | 2026-06-27 | YD LS body w shlder btm snap btn | Body | 2026-08-01 | 2026-08-07 | 2026-08-12 | 2026-08-18 | 2026-08-22 | 2026-08-28 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-16 | 2026-09-18 | 2026-09-19 | 2026-09-22 | 2026-09-23 |  |  |  |  | 2026-09-26 | 2026-09-28 |  |  | 2026-09-30 | 2026-10-05 | 2026-10-08 | 2026-11-01 | 2026-11-03 | 144 | Y | Mosaddik | Nk |  | 1 combo label print | YD |  | NFL3 |  |  | Need Test Cut | 172 | 0 | -172 | 0 | -1200 | [11 empty] | 45 | Sep'2 |  |  | 27.08.26
BS-NMT | 48010 | 13264405 | 4995 | 524 | 2026-06-10 | 2026-06-27 | Swt panr w side by pkt and tape drawstring | Pant |  |  | 2026-07-20 | 2026-08-04 | 2026-08-12 | 2026-08-28 |  |  | 2026-08-31 | 2026-08-31 | 2026-09-05 | 2026-09-09 | 2026-09-12 | [6 empty] | 2026-09-15 | 2026-09-19 |  |  | 2026-09-22 | 2026-09-24 | 2026-09-28 | 2026-11-02 | 2026-11-04 | 145 | U | Mosaddik | [5 empty] | NFL3 |  |  | Cut Ok | 524 | 524 | 0 | 5096 | 101 | [11 empty] | 45 | Sep'1 |  |  | 27.08.26
BS-NMT | 48061 | 13264486 | 4371 | 521 | 2026-06-10 | 2026-06-24 | AOP Elasted Legging | Legging |  |  | 2026-07-22 | 2026-08-06 | 2026-08-12 | 2026-08-25 | 2026-09-01 | 2026-09-07 | 2026-09-10 | 2026-09-10 | 2026-09-16 | 2026-09-18 | 2026-09-21 | 2026-09-22 | 2026-09-24 |  |  |  |  | 2026-09-25 | 2026-09-28 |  |  | 2026-09-30 | 2026-10-04 | 2026-10-10 | 2026-11-02 | 2026-11-04 | 145 | ZA2 | Haider | Waist |  | 2 combo label print | AOP |  | NFL3 |  |  | Need Cut | 521 | 219 | -302 | 0 | -4371 | [11 empty] | 45 | Sep'2 |  |  | 25.07.26
BS-NMT | 48062 | 13264488 | 3679 | 880 | 2026-06-10 | 2026-06-24 | AOP LS Dress w shlder frill | Dress |  |  | 2026-07-25 | 2026-08-06 | 2026-08-12 | 2026-08-26 | 2026-09-01 | 2026-09-08 | 2026-09-12 | 2026-09-12 | 2026-09-19 | 2026-09-22 | 2026-09-23 | 2026-09-25 | 2026-09-28 |  |  |  |  | 2026-10-01 | 2026-10-07 |  |  | 2026-10-10 | 2026-10-12 | 2026-10-15 | 2026-11-02 | 2026-11-04 | 145 | S | Haider | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | Need Cut | 880 | 399 | -481 | 0 | -3679 | [11 empty] | 45 | Sep'3 |  |  | 25.07.26
BS-NMT | 48063 | 13264487 | 4708 | 655 | 2026-06-10 | 2026-06-24 | AOP LS o nk TS | TS |  |  | 2026-07-25 | 2026-08-08 | 2026-08-10 | 2026-08-23 | 2026-08-25 | 2026-09-05 | 2026-09-10 | 2026-09-10 | 2026-09-16 | 2026-09-18 | 2026-09-22 | 2026-09-22 | 2026-09-24 |  |  |  |  | 2026-09-26 | 2026-09-29 |  |  | 2026-10-03 | 2026-10-06 | 2026-10-10 | 2026-11-02 | 2026-11-04 | 145 | ZA1 | Haider | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | Need Cut | 655 | 608 | -47 | 0 | -4708 | [11 empty] | 45 | Sep'2 |  |  | 25.07.26
BS-NMT | 48064 | 13264809 | 1002 | 119 | 2026-06-10 | 2026-06-24 | LS o nk back nk Hole w btn and front nk lace attach | TS |  |  | 2026-08-01 | 2026-08-10 | 2026-08-16 | 2026-08-31 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-14 | 2026-09-16 | 2026-09-17 | 2026-09-19 | 2026-09-21 |  |  |  |  | 2026-09-23 | 2026-09-25 |  |  | 2026-09-28 | 2026-09-30 | 2026-10-07 | 2026-11-02 | 2026-11-04 | 145 | Y | Haider | Nk |  | 1 combo label print |  | Lace | NFL3 |  |  | Need Cut | 119 | 119 | 0 | 0 | -1002 | [11 empty] | 45 | Sep'2 |  |  | 25.07.26
BS-ONS | 44077 8th | 22012786 | 49920 | 10478 | 2026-06-18 | 2026-06-27 | MENS R NK SS TS W SELF FABRIC NK BINDING | TS |  |  | 2026-07-10 | 2026-07-28 | 2026-07-25 | 2026-08-17 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-24 | 2026-08-26 | 2026-09-04 | [6 empty] | 2026-09-01 | 2026-09-17 |  |  | 2026-09-19 | 2026-09-22 | 2026-09-28 | 2026-11-09 | 2026-11-11 | 144 | G1 | Shovon | [5 empty] | NFL1 |  |  | Cut Ok | 10477 | 10400 | -77 | 50770 | 850 | [11 empty] | 46 | Aug'3 |  |  | 15.08.26
BS-ONS | 45691 2nd | 22028147 | 7734 | 1405 | 2026-06-18 | 2026-06-27 | SS o nk TS w nk rib | TS |  |  | 2026-07-15 | 2026-09-10 | 2026-08-01 | 2026-09-17 |  |  | 2026-08-15 | 2026-08-15 | 2026-08-20 | 2026-08-22 | 2026-09-19 | 2026-08-25 | 2026-08-31 |  |  |  |  | 2026-09-23 | 2026-09-28 |  |  | 2026-09-30 | 2026-10-03 | 2026-10-04 | 2026-11-09 | 2026-11-11 | 144 | D1 | Shovon | Heat Press/Heat Seal |  | flint-1314 pcs,,gray-1314 pcs,,desert-1314 ps,,black-1896 pcs,,white-1896 pcs all combo logo print heat press |  |  | NFL1 |  |  | Cut Run | 1722 | 1363 | -359 | 5817 | -1917 | [11 empty] | 46 | Aug'3 |  |  | 17.08.26
BS-ONL | 48178 | 15388315 | 3072 | 768 | 2026-06-24 | 2026-06-27 | LS o nk TS w lace at nk and Slve opening | TS |  |  | 2026-07-22 | 2026-08-04 | 2026-08-10 | 2026-08-25 |  |  | 2026-08-28 | 2026-08-28 | 2026-09-04 | 2026-09-07 | 2026-09-09 | 2026-09-11 | 2026-09-12 |  |  |  |  | 2026-09-14 | 2026-09-17 |  |  | 2026-09-18 | 2026-09-22 | 2026-09-25 | 2026-11-09 | 2026-11-11 | 138 | L | Jannati | Nk |  | 5 combo nk label 1 clr rub print |  | Lace | NFL2 |  |  | Need Cut | 768 | 768 | 0 | 0 | -3072 | [11 empty] | 46 | Sep'1 |  |  | 06.08.26
BS-ONL | 48167 | 15297685 | 6780 | 1762 | 2026-06-24 | 2026-06-27 | solid & YD SS bat slve blind stitch long dress w waist self drawstring | Dress | 2026-07-15 | 2026-07-25 | 2026-07-27 | 2026-08-10 | 2026-08-10 | 2026-08-25 |  |  | 2026-08-27 | 2026-08-27 | 2026-09-02 | 2026-09-05 | 2026-09-09 | [6 empty] | 2026-09-10 | 2026-09-17 |  |  | 2026-09-19 | 2026-09-22 | 2026-09-25 | 2026-12-14 | 2026-12-16 | 173 | K | Mainul |  |  |  | YD |  | NFL2 |  |  | Size Set Run | 1762 | 1758 | -4 | 0 | -6780 | [11 empty] | 51 | Sep'1 |  |  | 04.09.26
OVS SPA | 48132 | 271POL120-227 | 5200 | 594 | 2026-06-22 | 2026-06-26 | AOP SS Polo w solid collar placket btn w side slit | Polo |  |  | 2026-09-01 | 2026-09-10 | 2026-09-11 | 2026-09-19 | 2026-09-21 | 2026-09-30 | 2026-10-10 | 2026-10-01 | 2026-10-07 | 2026-10-08 | 2026-10-10 |  |  |  |  | 2026-10-14 | 2026-10-20 | 2026-10-20 | 2026-10-28 |  |  | 2026-10-30 | 2026-11-02 | 2026-11-06 | 2026-11-16 | 2026-11-16 | 147 | N/2 | Salam |  | Chest | Suar swizzle-5200 pcs 6 clr flat all over emb | AOP |  | NCL |  |  | File Due | 594 | 0 | -594 | 0 | -5200 | [11 empty] | 47 | Oct'1
OVS SPA | 47816 | 271PJA041MZ3B-6111 | 12450 | 3387 | 2026-06-17 | 2026-06-27 | LS frt key hole placket btn and AOP elasted pant w waist tassel drawstring | Top & BTM |  |  | 2026-08-15 | 2026-08-28 | 2026-09-01 | 2026-09-14 | 2026-09-14 | 2026-09-23 | 2026-10-05 | 2026-09-28 | 2026-10-05 | 2026-10-06 | 2026-10-10 |  |  |  |  | 2026-10-09 | 2026-10-15 | 2026-10-15 | 2026-10-24 |  |  | 2026-10-26 | 2026-10-28 | 2026-10-30 | 2026-11-02 | 2026-11-02 | 138 | N/3 | Basir |  | Chest | cream top-2075 pcs,,grey top-2075 pcs,,pink top-2075 pcs all combo 1 clr flat emb,,,all btm AOP-6225 pcs no emb | AOP |  | NCL |  |  | File Due | 3387 | 1236 | -2151 | 0 | -12450 | [11 empty] | 45 | Oct'1
OVS SPA | 47825 | 271NDG019PTR1-6111 | 2113 | 787 | 2026-06-12 | 2026-06-27 | LS v nk night dress w frt placket btn | Dress |  |  | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-09-28 |  |  | 2026-10-10 | 2026-10-12 | 2026-10-17 | 2026-10-19 | 2026-10-20 | [6 empty] | 2026-10-21 | 2026-10-24 |  |  | 2026-10-26 | 2026-10-28 | 2026-10-30 | 2026-11-02 | 2026-11-02 | 143 | N/2 | Basir | [5 empty] | NCL |  |  | File Due | 787 | 0 | -787 | 0 | -2113 | [11 empty] | 45 | Oct'2
OVS SPA | 47826 | 271PJA040PTR2-6111 | 5066 | 1397 | 2026-06-12 | 2026-06-27 | LS v nk TS w frt placket btn and long pant | Top & BTM |  |  | 2026-09-01 | 2026-09-14 | 2026-09-15 | 2026-09-30 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-13 | 2026-10-14 | 2026-10-16 | [6 empty] | 2026-10-17 | 2026-10-24 |  |  | 2026-10-26 | 2026-10-28 | 2026-10-30 | 2026-11-02 | 2026-11-02 | 143 | C+E | Basir | [5 empty] | NFL1 |  |  | File Due | 1397 | 0 | -1397 | 0 | -5066 | [11 empty] | 45 | Oct'2
OVS SPA | 47827 | 271GOW004PTR3-6111 | 1511 | 667 | 2026-06-12 | 2026-06-27 | LS wrap night grown dress w waist self string | Dress |  |  | 2026-09-01 | 2026-10-14 | 2026-10-15 | 2026-10-30 |  |  | 2026-10-10 | 2026-10-12 | 2026-10-16 | 2026-10-17 | 2026-10-19 | [6 empty] | 2026-10-20 | 2026-10-23 |  |  | 2026-10-24 | 2026-10-26 | 2026-10-28 | 2026-11-02 | 2026-11-02 | 143 | N/3 | Basir | [5 empty] | NCL |  |  | File Due | 667 | 0 | -667 | 0 | -1511 | [11 empty] | 45 | Oct'2
OVS SPA | 47894 | 271MMP008ETM1R-6111 | 4030 | 1149 | 2026-06-12 | 2026-06-27 | 3/4 slve o nk TS w lace at slve opening | TS |  |  | 2026-09-01 | 2026-09-12 | 2026-09-15 | 2026-09-30 |  |  | 2026-10-09 | 2026-10-10 | 2026-10-14 | 2026-10-15 | 2026-10-16 | [6 empty] | 2026-10-17 | 2026-10-21 |  |  | 2026-10-22 | 2026-10-24 | 2026-10-26 | 2026-11-02 | 2026-11-02 | 143 | D1 | Basir |  |  |  |  | Lace | NFL1 |  |  | File Due | 1148 | 0 | -1148 | 0 | -4030 | [11 empty] | 45 | Oct'2
OVS SPA | 48035 | 271MMP010VF3B-6111 | 4436 | 1536 | 2026-06-12 | 2026-06-27 | LS blazer w collar full placket btn and woven piping at placket slve | Blazer |  |  | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-09-28 |  |  | 2026-10-09 | 2026-10-10 | 2026-10-15 | 2026-10-16 | 2026-10-17 | [6 empty] | 2026-10-21 | 2026-10-27 |  |  | 2026-10-28 | 2026-10-29 | 2026-10-31 | 2026-11-02 | 2026-11-02 | 143 | N/3 | Basir | [5 empty] | NCL |  |  | File Due | 1536 | 0 | -1536 | 0 | -4436 | [11 empty] | 45 | Oct'2
OVS SPA | 48036 | 271MMP011VF4B-6111 | 4436 | 1442 | 2026-06-15 | 2026-06-27 | Long pant w woven piping | Pant |  |  | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-09-26 |  |  | 2026-10-06 | 2026-10-05 | 2026-10-10 | 2026-10-12 | 2026-10-14 | [6 empty] | 2026-10-15 | 2026-10-22 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-28 | 2026-11-02 | 2026-11-02 | 140 | H | Basir | [5 empty] | NFL1 |  |  | File Due | 1441 | 914 | -527 | 0 | -4436 | [11 empty] | 45 | Oct'2
OVS SPA | 48037 | 271PJA022PKFBW-6111 | 9044 | 2657 | 2026-06-15 | 2026-06-27 | AOP Blazer w collar placket btn front pkt and trouser w drawstring | Top & BTM |  |  | 2026-08-17 | 2026-08-28 | 2026-09-01 | 2026-09-14 | 2026-09-15 | 2026-09-25 | 2026-10-02 | 2026-10-03 | 2026-10-07 | 2026-10-08 | 2026-10-10 | [6 empty] | 2026-10-12 | 2026-10-19 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-24 | 2026-11-02 | 2026-11-02 | 140 | N/3 | Basir |  |  |  | AOP |  | NCL |  |  | File Due | 2656 | 0 | -2656 | 0 | -9044 | [11 empty] | 45 | Oct'1
BS-ONL | 48264 | 15369310 | 504 | 350 | 2026-06-26 | 2026-06-30 | LS o nk Swt shirt long dress w nk cuff rib | Dress |  |  | 2026-07-10 | 2026-07-15 | 2026-07-20 | 2026-07-28 |  |  | 2026-07-28 | 2026-08-01 | 2026-08-07 | 2026-08-08 | 2026-08-08 | 2026-08-11 | 2026-08-14 |  |  |  |  | 2026-08-17 | 2026-08-18 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 2026-08-26 | 59 | J | Zahirul | Sleeve |  | black-504 pcs both slve all over 3 clr puff print |  |  | NFL2 |  |  | Cut Ok | 350 | 350 | 0 | 524 | 20 | [11 empty] | 35 | Aug'1 |  |  | 02.07.26
BS-ONS | 48199 | 22042193 | 19284 | 4998 | 2026-07-01 | 2026-07-02 | SS o nk TS w nk rib | TS |  |  | 2026-07-03 | 2026-07-09 | 2026-07-09 | 2026-07-18 |  |  | 2026-07-13 | 2026-07-11 | 2026-07-15 | 2026-07-16 | 2026-07-21 | [6 empty] | 2026-07-18 | 2026-07-24 |  |  | 2026-07-25 | 2026-07-25 | 2026-07-27 | 2026-07-27 | 2026-07-29 | 26 | ZA2 | Shovon | [5 empty] | NFL3 |  |  | Cut Ok | 4997 | 4997 | 0 | 0 | -19284 | [11 empty] | 31 | Jul'2 |  |  | 13.07.26
BS-ONL | 22036 36th | 15131538 | 1000 | 187 | 2026-07-02 | 2026-07-04 | LDS LEGGING | LEGGING |  |  | 2026-10-02: 2026-07-07; 2026-10-03: 2026-07-06; 2026-10-08: 2026-07-06; 2026-10-10: 2026-07-07 | [6 empty] | 2026-07-08 | 2026-07-09 |  |  | 2026-07-10 | 2026-07-11 | 2026-07-13 | 2026-07-13 | 2026-07-15 | 11 | NFL3 | Imran |  |  |  |  | Stock fab from 43465 /1000 pcs need sewing | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1000 | [11 empty] | 29 | Jul'1 |  |  | 06.07.26
BS-NMT | 43323 32th | 13180124 | 4560 | 562 | 2026-07-02 | 2026-07-04 | GIRLS SOLID LEGGINGS | Legging |  |  | 2026-07-07 | 2026-07-07 | 2026-07-10 | 2026-07-18 |  |  | 2026-07-18 | 2026-07-14 |  | 2026-07-19 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  |  |  |  | 2026-07-24 | 2026-07-26 |  |  | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-08-03 | 2026-08-05 | 32 | ZA2 | Jafar | WAIST |  | 3 combo label print |  |  | NFL3 |  |  | Cut Ok | 562 | 562 | 0 | 0 | -4560 | [11 empty] | 32 | Jul'2 |  |  | 13.07.26
BS-NMT | 43323 33th | 13180124 | 7120 | 871 | 2026-07-02 | 2026-07-04 | GIRLS SOLID LEGGINGS | Legging |  |  | 2026-07-07 | 2026-07-10 | 2026-07-14 | 2026-07-24 |  |  | 2026-07-21 | 2026-07-21 |  | 2026-07-24 | 2026-07-27 | 2026-07-28 | 2026-07-31 |  |  |  |  | 2026-08-01 | 2026-08-07 |  |  | 2026-08-10 | 2026-08-12 | 2026-08-13 | 2026-08-17 | 2026-08-19 | 46 | W1 | Jafar | WAIST |  | 4 combo label print |  |  | NFL3 |  |  | Cut Ok | 871 | 871 | 0 | 0 | -7120 | [11 empty] | 34 | Jul'3 |  |  | 13.07.26
BS-NMT | 44019 18th | 13247093 | 2040 | 347 | 2026-07-02 | 2026-07-04 | Weist belt legging | Legging |  |  | 2026-07-08 | 2026-07-14 | 2026-07-17 | 2026-07-27 |  |  | 2026-07-25 | 2026-07-25 |  | 2026-08-01 | 2026-08-06 | 2026-08-07 | 2026-08-08 |  |  |  |  | 2026-08-10 | 2026-08-12 |  |  | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-17 | 2026-08-19 | 46 | Z | Jafar | WAIST |  | 1 combo label print |  |  | NFL3 |  |  | Cut Ok | 347 | 347 | 0 | 0 | -2040 | [11 empty] | 34 | Aug'1 |  |  | 13.07.26
BS-NMT | 43316 27th | 13234729 | 5520 | 944 | 2026-07-02 | 2026-07-04 | LS o nk TS | TS |  |  | 2026-07-07 | 2026-07-13 | 2026-07-13 | 2026-07-25 |  |  | 2026-07-25 | 2026-07-21 |  | 2026-07-25 | 2026-07-28 | 2026-07-28 | 2026-07-31 |  |  |  |  | 2026-08-01 | 2026-08-08 |  |  | 2026-08-11 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 2026-08-19 | 46 | ZA1 | Jafar | Nk |  | 4 combo label print |  |  | NFL3 |  |  | Cut Ok | 944 | 944 | 0 | 5678 | 158 | [11 empty] | 34 | Jul'3 |  |  | 13.07.26
BS-ONS | 48283 | 22042341 | 5370 | 3637 | 2026-07-01 | 2026-07-06 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-07-13 | 2026-07-24 | 2026-07-25 | 2026-08-10 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-13 | 2026-08-13 | 2026-08-17 |  |  |  |  | 2026-08-17 | 2026-08-20 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-24 | 2026-08-24 | 2026-08-26 | 54 | E | Shakel | Fr,Bk |  | Mulch-2678 pcs,,milk-2708 pcs both combo frt back 2 clr pig 1 clr puff |  |  | NFL1 |  |  | Cut Ok | 3638 | 3638 | 0 | 0 | -5370 | [11 empty] | 35 | Aug'2 |  |  | 08.08.26
BS-ONL | 22041 62th | 15204712 | 3040 | 634 | 2026-06-25 | 2026-06-30 | LS o nk TS | TS |  |  | 2026-10-02: 2026-07-25; 2026-10-03: 2026-07-21; 2026-10-08: 2026-07-27; 2026-10-10: 2026-07-28 | [6 empty] | 2026-08-06 | 2026-08-07 |  |  | 2026-08-08 | 2026-08-10 | 2026-08-12 | 2026-08-17 | 2026-08-19 | 53 | G1 | Imran |  |  |  |  | Stock fab from 43465 | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 3073 | 33 | [11 empty] | 34 | Jul'3 |  |  | 17.07.26
BS-ONL | 46748 11th | 15244714 | 1512 | 253 | 2026-06-25 | 2026-06-30 | SS o nk TS | TS |  |  | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-22 |  |  | 2026-07-20 | 2026-07-20 |  | 2026-07-25 | 2026-07-25 | 2026-07-28 | 2026-07-29 |  |  |  |  | 2026-08-01 | 2026-08-06 |  |  | 2026-08-07 | 2026-08-08 | 2026-08-08 | 2026-08-10 | 2026-08-12 | 46 | F | Imran | Chest |  | n.sky-1512 pcs 1 clr gltr print |  |  | NFL1 |  |  | Cut Ok | 254 | 254 | 0 | 0 | -1512 | [11 empty] | 33 | Jul'3 |  |  | 17.07.26
BS-ONL | 45317 4th | 15084518 | 1500 | 389 | 2026-06-30 | 2026-07-02 | 3/4 waist FOLD LEGGING | Legging |  |  | 2026-10-02: 2026-07-30; 2026-10-03: 2026-07-18; 2026-10-08: 2026-07-24; 2026-10-10: 2026-07-25 | 2026-08-01 | 2026-08-01 |  |  |  |  | 2026-08-07 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-12 | 2026-08-15 | 2026-08-17 | 2026-08-19 | 48 | L2 | Khalid | WAIST |  | 1 combo waist print |  | stock fab from 41880 23th | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1500 | [11 empty] | 34 | Jul'3 |  |  | 08.07.26
BS-ONL | 45314 5th | 15200077 | 1540 | 385 | 2026-06-30 | 2026-07-02 | LEGGING W WAIST PRINT | Legging |  |  | 2026-10-02: 2026-07-30; 2026-10-03: 2026-07-20; 2026-10-08: 2026-07-25; 2026-10-10: 2026-07-26 | 2026-08-02 | 2026-08-07 |  |  |  |  | 2026-08-12 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-20 | 2026-08-24 | 2026-08-26 | 55 | L2 | Khalid | WAIST |  | 1 combo label print |  | stock fab from 41880 23th | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1540 | [11 empty] | 35 | Jul'3 |  |  | 08.07.26
BS-ONL | 41873 12th | 15303953 | 1520 | 700 | 2026-06-30 | 2026-07-02 | HIGH NK SWT W FULL ZIPPER PKT, CUFF BOND PKT | Swt Shirt |  |  | 2026-10-02: 2026-07-25; 2026-10-03: 2026-07-17; 2026-10-08: 2026-07-22; 2026-10-10: 2026-07-24 |  |  |  |  | 2026-07-28 | 2026-07-29 | 2026-08-08 | 2026-08-12 |  |  | 2026-08-14 | 2026-08-15 | 2026-08-18 | 2026-08-24 | 2026-08-26 | 55 | R | Khalid |  | CHEST | BLACK 1520 PCS 1 CLR FLAT EMB |  | stock fab from 41873 7th | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 1562 | 42 | [11 empty] | 35 | Jul'3 |  |  | 08.07.26
BS-ONL | 45320 6th | 15303954 | 1520 | 709 | 2026-06-30 | 2026-07-02 | Swt pant w side pkt drawstring | PANT |  |  | 2026-10-02: 2026-07-25; 2026-10-03: 2026-07-15; 2026-10-08: 2026-07-21; 2026-10-10: 2026-07-22 |  |  |  |  | 2026-08-02 | 2026-08-06 | 2026-08-07 | 2026-08-10 |  |  | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-24 | 2026-08-26 | 55 | P | Khalid |  | Thigh | black-1520 pcs 1 clr flat emb |  | stock fab from 41873 7th | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -1520 | [11 empty] | 35 | Jul'3 |  |  | 08.07.26
BS-ONL | 41880 25th | 15062199/15185296 | 2300 | 978 | 2026-06-30 | 2026-07-04 | HW legging Drawstring at leg opening | Legging |  |  | 2026-10-02: 2026-07-17; 2026-10-03: 2026-07-11; 2026-10-08: 2026-07-10; 2026-10-10: 2026-07-11 | 2026-07-16 | 2026-07-18 |  |  |  |  | 2026-07-20 | 2026-07-24 |  |  | 2026-07-27 | 2026-07-28 | 2026-08-30 | 2026-08-03 | 2026-08-05 | 34 | E | Khalid | Waist |  | 1 combo waist lettering logo print |  | stock fab from 41880 23th | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 2358 | 58 | [11 empty] | 32 | Jul'1 |  |  | 08.07.26
BS-ONL | 48188 2nd | 15299502 | 1040 | 205 | 2026-07-03 | 2026-07-04 | SS O nk TS | TS |  |  | 2026-07-09 | 2026-07-13 | 2026-07-15 | 2026-07-23 |  |  | 2026-07-22 | 2026-07-22 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-31 | 2026-08-01 |  |  |  |  | 2026-08-06 | 2026-08-07 |  |  | 2026-08-08 | 2026-08-08 | 2026-08-10 | 2026-08-10 | 2026-08-12 | 38 | O1 | Zahirul | Chest |  | black-1040 pcs chest 1 clr gltr print |  |  | NFL2 |  |  | Cut Ok | 205 | 205 | 0 | 1063 | 23 | [11 empty] | 33 | Jul'3 |  |  | 09.07.26
BS-ONL | 48281 | 15391443 | 1776 | 425 | 2026-06-30 | 2026-07-01 | LS High nk TS | TS |  |  | 2026-07-04 | 2026-07-08 | 2026-07-11 | 2026-07-18 |  |  | 2026-07-17 | 2026-07-17 | 2026-07-22 | 2026-07-23 | 2026-07-24 | [6 empty] | 2026-07-27 | 2026-07-28 |  |  | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-05 | 34 | G2 | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 426 | 426 | 0 | 0 | -1776 | [11 empty] | 32 | Jul'3 |  |  | 07.07.26
BS-ONL | 27204 57th | 15323159 | 18320 | 4378 | 2026-06-24 | 2026-07-06 | LS o nk TS | TS |  |  | 2026-07-10 | 2026-07-20 | 2026-07-20 | 2026-08-08 |  |  | 2026-08-08 | 2026-08-07 |  | 2026-08-12 | 2026-08-15 | [6 empty] | 2026-08-15 | 2026-08-21 |  |  | 2026-08-22 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-26 | 61 | G2 | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 4379 | 4379 | 0 | 18480 | 160 | [11 empty] | 35 | Aug'2 |  |  | 07.07.26
GBX-New Look | 47405 3rd | 93328977 | 1213 | 328 | 2026-06-29 | 2026-06-30 | LS O nk TS | TS |  |  | 2026-07-03 | 2026-07-07 | 2026-07-11 | 2026-07-18 |  |  | 2026-07-18 | 2026-07-18 |  | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 |  |  |  |  | 2026-07-28 | 2026-07-29 |  |  | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-01 | 2026-08-01 | 33 | N/1 | Morad | Nk |  | 1 combo nk size label print |  |  | NCL |  |  | Ready Test Cut | 328 | 328 | 0 | 0 | -1213 | [11 empty] | 31 | Jul'3
GBX-New Look | 47936 2nd | 9657695 | 2021 | 228 | 2026-06-29 | 2026-07-01 | SS reglan contrast slve TS | TS |  |  | 2026-07-06 | 2026-07-10 | 2026-07-12 | 2026-07-24 |  |  | 2026-07-24 | 2026-07-24 |  | 2026-07-28 | 2026-07-29 | [6 empty] | 2026-08-01 | 2026-08-06 |  |  | 2026-08-07 | 2026-08-08 | 2026-08-08 | 2026-08-08 | 2026-08-09 | 40 | N/2 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 228 | 228 | 0 | 0 | -2021 | [11 empty] | 33 | Jul'3
GBX-New Look | 47936 3rd | 9657695 | 1220 | 141 | 2026-07-01 | 2026-07-04 | SS reglan contrast slve TS | TS |  |  | 2026-07-10 | 2026-07-14 | 2026-07-17 | 2026-07-28 |  |  | 2026-07-25 | 2026-07-25 |  | 2026-08-01 | 2026-08-01 | [6 empty] | 2026-08-06 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-15 | 2026-08-16 | 45 | N/2 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 141 | 141 | 0 | 0 | -1220 | [11 empty] | 34 | Aug'1
GBX-Anthony's | 47356 2nd | 67941/68173 | 630 | 171 | 2026-07-01 | 2026-07-06 | SS o nk TS | TS |  |  | 2026-07-16 | 2026-07-20 | 2026-07-27 | 2026-08-08 |  |  | 2026-08-08 | 2026-08-08 |  | 2026-08-14 | 2026-08-14 | [6 empty] | 2026-08-17 | 2026-08-18 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-22 | 2026-08-25 | 2026-08-25 | 55 | N/1 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 170 | 170 | 0 | 0 | -630 | [11 empty] | 35 | Aug'2
GBX-Anthony's | 47354 2nd | 68151/68176/68214 | 945 | 301 | 2026-07-04 | 2026-07-06 | YD SS o nk TS | TS | 2026-07-18 | 2026-07-24 | 2026-07-28 | 2026-08-03 | 2026-08-07 | 2026-08-12 |  |  | 2026-08-08 | 2026-08-08 |  | 2026-08-14 | 2026-08-15 | [6 empty] | 2026-08-18 | 2026-08-19 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-25 | 2026-08-25 | 52 | N/1 | Shofi |  |  |  | YD |  | NCL |  |  | Ready Test Cut | 303 | 303 | 0 | 0 | -945 | [11 empty] | 35 | Aug'2
GBX-Anthony's | 47355 2nd | 68236/68237 | 630 | 190 | 2026-07-01 | 2026-07-06 | SS o nk TS w YD nk slve rib | TS | 2026-07-13 | 2026-07-18 | 2026-07-20 | 2026-07-25 | 2026-08-01 | 2026-08-10 |  |  | 2026-08-10 | 2026-08-10 |  | 2026-08-15 | 2026-08-15 | [6 empty] | 2026-08-18 | 2026-08-19 |  |  | 2026-08-20 | 2026-08-22 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 55 | N/1 | Shofi |  |  |  | YD |  | NCL |  |  | Ready Test Cut | 188 | 188 | 0 | 0 | -630 | [11 empty] | 35 | Aug'2
GBX-Maurices | 48245 2nd | 2524991/4704991 | 54498 | 22165 | 2026-07-02 | 2026-07-04 | YD LS self nk binding TS W banded hem | TS | 2026-07-06 | 2026-07-25 | 2026-07-18 | 2026-08-03 | 2026-08-25 | 2026-08-12 |  |  | 2026-07-28 | 2026-07-25 | 2026-08-01 | 2026-08-07 | 2026-08-15 | 2026-08-12 | 2026-08-24 |  |  |  |  | 2026-08-10 | 2026-08-22 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 54 | N/2+N/3 | Mannan | Heat Press/Heat Seal |  | 3 combo nk HP | YD |  | NCL |  |  | Cut Run | 20409 | 20409 | 0 | 12374 | -42124 | [11 empty] | 35 | Aug'1
GBX-TM Lewin | 48280 | 68772/68773/68774/68775 | 1660 | 1355 | 2026-07-01 | 2026-07-04 | LS high nk half zipper Swt shirt | Swt Shirt |  |  | 2026-07-08 | 2026-07-18 | 2026-07-20 | 2026-08-03 |  |  | 2026-08-01 | 2026-08-01 | 2026-08-10 | 2026-08-12 | 2026-08-13 | [6 empty] | 2026-08-15 | 2026-08-18 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 52 | N/2 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 1352 | 1328 | -24 | 0 | -1660 | [11 empty] | 35 | Aug'2
GBX-TM Lewin | 48279 | 68767/68768/68769/68770/68771 | 1600 | 1255 | 2026-07-01 | 2026-07-04 | LS Polo w collar placket btn | Polo |  |  | 2026-07-08 | 2026-07-18 | 2026-07-20 | 2026-08-04 |  |  | 2026-08-01 | 2026-08-01 | 2026-08-10 | 2026-08-12 | 2026-08-14 | [6 empty] | 2026-08-15 | 2026-08-19 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-22 | 2026-08-23 | 52 | N/3 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 1250 | 1246 | -4 | 0 | -1600 | [11 empty] | 35 | Aug'2
GBX-TM LEWIN | 44711 12th | 67936/67937/67939/68175/68226/68229 | 9800 | 2420 | 2026-07-04 | 2026-07-06 | MENS SS TS | TS |  |  | 2026-07-15 | 2026-07-24 | 2026-07-25 | 2026-08-08 |  |  | 2026-08-07 | 2026-08-07 |  | 2026-08-12 | 2026-08-15 | [6 empty] | 2026-08-15 | 2026-08-22 |  |  | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-29 | 2026-08-30 | 56 | N/1 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 2421 | 2417 | -4 | 0 | -9800 | [11 empty] | 36 | Aug'2
GBX-TM LEWIN | 47935 2nd | 68724/68725/68726/68727/68728 | 2730 | 993 | 2026-07-04 | 2026-07-06 | SS TS w nk Rib | TS |  |  | 2026-07-15 | 2026-07-22 | 2026-07-25 | 2026-08-10 |  |  | 2026-08-08 | 2026-08-08 |  | 2026-08-14 | 2026-08-15 | [6 empty] | 2026-08-18 | 2026-08-21 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-28 | 2026-08-28 | 55 | N/1 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 993 | 993 | 0 | 0 | -2730 | [11 empty] | 35 | Aug'2
GBX-TM LEWIN | 47934 2nd | 68737/68738/68739/68740/68741/68742/68743 | 2415 | 870 | 2026-07-04 | 2026-07-06 | SS TS w placket btn | TS |  |  | 2026-07-12 | 2026-07-20 | 2026-07-24 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-10 |  | 2026-08-14 | 2026-08-15 | [6 empty] | 2026-08-17 | 2026-08-20 |  |  | 2026-08-22 | 2026-08-24 | 2026-08-25 | 2026-08-28 | 2026-08-28 | 55 | N/2 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 871 | 871 | 0 | 0 | -2415 | [11 empty] | 35 | Aug'2
GBX-TM LEWIN | 46696 4th | 68490/68491/68492/68493 | 5670 | 1575 | 2026-07-04 | 2026-07-06 | SS o nk TS | TS |  |  | 2026-07-14 | 2026-07-20 | 2026-07-25 | 2026-08-10 |  |  | 2026-08-08 | 2026-08-08 |  | 2026-08-14 | 2026-08-17 | [6 empty] | 2026-08-17 | 2026-08-21 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-28 | 2026-08-28 | 55 | N/2 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 1574 | 1574 | 0 | 0 | -5670 | [11 empty] | 35 | Aug'2
GBX-TM Lewin | 47740 3rd | 68670/68671/68672/68673/68674 | 2940 | 765 | 2026-07-04 | 2026-07-06 | SS crew nk TS | TS |  |  | 2026-07-15 | 2026-07-20 | 2026-07-25 | 2026-08-10 |  |  | 2026-08-10 | 2026-08-10 |  | 2026-08-14 | 2026-08-15 | [6 empty] | 2026-08-18 | 2026-08-21 |  |  | 2026-08-22 | 2026-08-24 | 2026-08-25 | 2026-08-28 | 2026-08-28 | 55 | N/1 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 766 | 766 | 0 | 0 | -2940 | [11 empty] | 35 | Aug'2
GBX-TM LEWIN | 44716 7th | 68234 | 525 | 202 | 2026-07-04 | 2026-07-06 | YD SS TS | TS | 2026-07-20 | 2026-07-25 | 2026-08-01 | 2026-08-06 | 2026-08-10 | 2026-08-15 |  |  | 2026-08-15 | 2026-08-15 |  | 2026-08-20 | 2026-08-20 | [6 empty] | 2026-08-22 | 2026-08-24 |  |  | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-28 | 55 | N/1 | Shofi |  |  |  | YD |  | NCL |  |  | Ready Test Cut | 202 | 202 | 0 | 0 | -525 | [11 empty] | 35 | Aug'2
GBX-TM LEWIN | 44714 11th | 68245/68246/68247/68248/68249/68250 | 7245 | 2451 | 2026-07-04 | 2026-07-06 | MENS O NK TS W PLKT & BTN | TS |  |  | 2026-07-13 | 2026-07-20 | 2026-07-24 | 2026-08-08 |  |  | 2026-08-07 | 2026-08-07 |  | 2026-08-12 | 2026-08-15 | [6 empty] | 2026-08-15 | 2026-08-22 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-28 | 2026-08-28 | 55 | N/2 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 2451 | 2451 | 0 | 0 | -7245 | [11 empty] | 35 | Aug'2
GBX-TM LEWIN | 44715 13th | 68166/68167/68168/68231/68397/68399 | 7980 | 2880 | 2026-07-04 | 2026-07-06 | MENS LS TS | TS |  |  | 2026-07-15 | 2026-07-24 | 2026-07-27 | 2026-08-10 |  |  | 2026-08-08 | 2026-08-08 |  | 2026-08-13 | 2026-08-15 | [6 empty] | 2026-08-17 | 2026-08-22 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-28 | 2026-08-28 | 55 | N/1 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 2710 | 2700 | -10 | 0 | -7980 | [11 empty] | 35 | Aug'2
UTG-(Even & Odd) | 44262 7th | BAD2927F | 1400 | 266 | 2026-06-29 | 2026-06-30 | LS TS W LACE | TS |  |  | 2026-07-03 | 2026-07-08 | 2026-07-09 | 2026-07-22 |  |  | 2026-07-31 | 2026-08-01 |  | 2026-08-06 | 2026-08-07 | [6 empty] | 2026-08-07 | 2026-08-10 |  |  | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 47 | K1 | Rony |  |  |  |  | Lace | NFL2 |  |  | Cut Ok | 266 | 266 | 0 | 0 | -1400 | [11 empty] | 34 | Aug'1 |  |  | 15.07.26
UTG-(Even & Odd) | 41645 9th | BAD2681H | 1400 | 330 | 2026-06-27 | 2026-06-30 | Cropped LS TS w placket | TS |  |  | 2026-07-03 | 2026-07-08 | 2026-07-09 | 2026-07-22 |  |  | 2026-07-31 | 2026-08-01 |  | 2026-08-06 | 2026-08-07 | [6 empty] | 2026-08-07 | 2026-08-10 |  |  | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 49 | K1 | Rony | [5 empty] | NFL2 |  |  | Cut Ok | 330 | 330 | 0 | 1470 | 70 | [11 empty] | 34 | Aug'1 |  |  | 15.07.26
UTG-(Even & Odd) | 44596 5th | BAD2946D | 2000 | 520 | 2026-06-27 | 2026-06-30 | LS BODYSUIT | SUIT |  |  | 2026-07-03 | 2026-07-08 | 2026-07-09 | 2026-07-22 |  |  | 2026-07-31 | 2026-08-01 |  | 2026-08-06 | 2026-08-07 | [6 empty] | 2026-08-07 | 2026-08-11 |  |  | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 49 | V1 | Rony | [5 empty] | NFL3 |  |  | Cut Ok | 520 | 520 | 0 | 0 | -2000 | [11 empty] | 34 | Aug'1 |  |  | 15.07.26
UTG-(Even & Odd) | 30702 5th | BAD2643D | 1600 | 420 | 2026-06-27 | 2026-06-30 | LS Squre nk body suit | Body |  |  | 2026-07-03 | 2026-07-08 | 2026-07-09 | 2026-07-22 |  |  | 2026-07-31 | 2026-08-01 |  | 2026-08-06 | 2026-08-07 | [6 empty] | 2026-08-07 | 2026-08-10 |  |  | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 49 | V1 | Rony | [5 empty] | NFL3 |  |  | Cut Ok | 420 | 420 | 0 | 0 | -1600 | [11 empty] | 34 | Aug'1 |  |  | 15.07.26
UTG-(Even & Odd) | 24230 22th | BAD0966AH | 1800 | 398 | 2026-06-27 | 2026-06-30 | LS TS w letus stitch | TS |  |  | 2026-07-03 | 2026-07-08 | 2026-07-09 | 2026-07-22 |  |  | 2026-07-31 | 2026-08-01 |  | 2026-08-06 | 2026-08-07 | [6 empty] | 2026-08-08 | 2026-08-10 |  |  | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 49 | Z | Rony | [5 empty] | NFL3 |  |  | Cut Ok | 398 | 398 | 0 | 0 | -1800 | [11 empty] | 34 | Aug'1 |  |  | 17.07.26
UTG-(Even & Odd) | 23325 16th | BAD0960BF | 800 | 205 | 2026-06-27 | 2026-06-30 | LS HIGH NK TS | TS |  |  | 2026-07-03 | 2026-07-08 | 2026-07-09 | 2026-07-22 |  |  | 2026-07-31 | 2026-08-01 |  | 2026-08-06 | 2026-08-06 | [6 empty] | 2026-08-07 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-11 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 49 | Z | Rony | [5 empty] | NFL3 |  |  | Cut Ok | 205 | 205 | 0 | 0 | -800 | [11 empty] | 34 | Aug'1 |  |  | 13.07.26
UTG-(Even & Odd) | 41637 8th | BAD1502O | 4400 | 1070 | 2026-06-27 | 2026-06-30 | LS ROLL NK TS | TS |  |  | 2026-07-03 | 2026-07-08 | 2026-07-09 | 2026-07-22 |  |  | 2026-07-31 | 2026-08-01 |  | 2026-08-06 | 2026-08-08 | [6 empty] | 2026-08-08 | 2026-08-11 |  |  | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 49 | Z | Rony | [5 empty] | NFL3 |  |  | Cut Ok | 1070 | 1070 | 0 | 0 | -4400 | [11 empty] | 34 | Aug'1 |  |  | 18.07.26
UTG-(Even & Odd) | 30703 11th | BAD2640M/BAD2640K | 1700 | 374 | 2026-06-27 | 2026-06-30 | BODYSUIT W ZIPPER | SUIT |  |  | 2026-07-03 | 2026-07-09 | 2026-07-10 | 2026-07-23 |  |  | 2026-07-31 | 2026-08-01 |  | 2026-08-06 | 2026-08-06 | [6 empty] | 2026-08-08 | 2026-08-11 |  |  | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 49 | V1 | Rony | [5 empty] | NFL3 |  |  | Cut Ok | 374 | 374 | 0 | 0 | -1700 | [11 empty] | 34 | Aug'1 |  |  | 15.07.26
UTG-(Even & Odd) | 41647 11th | BAD2678J | 2000 | 420 | 2026-06-27 | 2026-06-30 | LS BALLARINA KNOT TOP | DRESS | 2026-08-10: 2026-07-13; 2026-08-15: 2026-07-22 |  |  | 2026-07-31 | 2026-08-01 |  | 2026-08-11 | 2026-08-12 | [6 empty] | 2026-08-12 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 56 | N/3 | Rony |  |  |  |  | Imp Stock grey fab | NCL |  |  | Ready Test Cut | 420 | 420 | 0 | 0 | -2000 | [11 empty] | 35 | Aug'2
UTG-(Even & Odd) | 41318 18th | BAD1571AG/BAD1571AH | 700 | 184 | 2026-07-01 | 2026-07-03 | CROPPED WRAP OVERLAP LS TS | TS |  |  | 2026-07-06 | 2026-07-10 | 2026-07-11 | 2026-07-23 |  |  | 2026-07-30 | 2026-08-01 |  | 2026-08-06 | 2026-08-06 | [6 empty] | 2026-08-07 | 2026-08-10 |  |  | 2026-08-11 | 2026-08-12 | 2026-08-14 | 2026-08-15 | 2026-08-17 | 45 | N/2 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 184 | 184 | 0 | 0 | -700 | [11 empty] | 34 | Aug'1
UTG-(Even & Odd) | 45150 4th | BAD2992C/BAD2992D | 800 | 142 | 2026-07-01 | 2026-07-03 | LS WRAP TOP | Dress | 2026-08-10: 2026-07-10; 2026-08-15: 2026-07-22 |  |  | 2026-07-30 | 2026-08-01 |  | 2026-08-06 | 2026-08-06 | [6 empty] | 2026-08-07 | 2026-08-10 |  |  | 2026-08-11 | 2026-08-12 | 2026-08-14 | 2026-08-15 | 2026-08-17 | 45 | Q | Rony |  |  |  |  | Imp Grey Fab stock | NFL2 |  |  | Cut Ok | 142 | 142 | 0 | 0 | -800 | [11 empty] | 34 | Aug'1 |  |  | 14.07.26
UTG-(Even & Odd) | 46706 2nd | BAD3157A | 3200 | 480 | 2026-07-01 | 2026-07-03 | SS o nk TS | TS |  |  | 2026-07-07 | 2026-07-10 | 2026-07-11 | 2026-07-22 |  |  | 2026-07-31 | 2026-08-01 |  | 2026-08-06 | 2026-08-07 | [6 empty] | 2026-08-08 | 2026-08-10 |  |  | 2026-08-10 | 2026-08-11 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 45 | ZA2 | Rony | [5 empty] | NFL3 |  |  | Cut Ok | 480 | 480 | 0 | 0 | -3200 | [11 empty] | 34 | Aug'1 |  |  | 14.07.26
UTG-(Even & Odd) | 47875 2nd | BAD3224A/BAD3224B | 1000 | 198 | 2026-07-01 | 2026-07-03 | LS TS w back u nk | TS |  |  | 2026-07-06 | 2026-07-10 | 2026-07-11 | 2026-07-23 |  |  | 2026-07-30 | 2026-08-01 |  | 2026-08-06 | 2026-08-07 | [6 empty] | 2026-08-08 | 2026-08-10 |  |  | 2026-08-11 | 2026-08-12 | 2026-08-14 | 2026-08-15 | 2026-08-17 | 45 | ZA2 | Rony | [5 empty] | NFL3 |  |  | Cut Ok | 198 | 198 | 0 | 1050 | 50 | [11 empty] | 34 | Aug'1 |  |  | 17.07.26
UTG-(Even & Odd) | 43618 6th | BAD2889E | 4000 | 662 | 2026-07-01 | 2026-07-03 | SL SWAMSUIT | SUIT |  |  | 2026-07-06 | 2026-07-10 | 2026-07-11 | 2026-07-23 |  |  | 2026-07-28 | 2026-08-01 |  | 2026-08-06 | 2026-08-08 | [6 empty] | 2026-08-07 | 2026-08-11 |  |  | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 45 | K1 | Rony | [5 empty] | NFL2 |  |  | Cut Ok | 662 | 662 | 0 | 0 | -4000 | [11 empty] | 34 | Aug'1 |  |  | 14.07.26
UTG-(Even & Odd) | 46703 2nd | BAD3165A/BAD3165B | 1000 | 255 | 2026-07-01 | 2026-07-03 | LS Collar less Shirt w full placket snap btn | Shirt |  |  | 2026-07-06 | 2026-07-10 | 2026-07-11 | 2026-07-23 |  |  | 2026-07-30 | 2026-08-01 |  | 2026-08-06 | 2026-08-07 | [6 empty] | 2026-08-07 | 2026-08-10 |  |  | 2026-08-12 | 2026-08-12 | 2026-08-14 | 2026-08-15 | 2026-08-17 | 45 | J | Rony |  |  |  |  | Snap btn | NFL2 |  |  | Cut Ok | 255 | 255 | 0 | 1045 | 45 | [11 empty] | 34 | Aug'1 |  |  | 18.07.26
UTG-(Even & Odd) | 43624 4th | BAD2888C/BAD2888D | 3000 | 590 | 2026-07-01 | 2026-07-03 | SL body siut | SUIT |  |  | 2026-07-06 | 2026-07-10 | 2026-07-11 | 2026-07-23 |  |  | 2026-07-29 | 2026-08-01 |  | 2026-08-06 | 2026-08-07 | [6 empty] | 2026-08-07 | 2026-08-11 |  |  | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 45 | J | Rony | [5 empty] | NFL2 |  |  | Cut Ok | 590 | 590 | 0 | 0 | -3000 | [11 empty] | 34 | Aug'1 |  |  | 14.07.26
UTG-(Even & Odd) | 44596 6th | BAD2946E/BAD2946F | 2000 | 520 | 2026-07-01 | 2026-07-03 | LS BODYSUIT | SUIT |  |  | 2026-07-06 | 2026-07-10 | 2026-07-11 | 2026-07-23 |  |  | 2026-07-29 | 2026-08-01 |  | 2026-08-06 | 2026-08-07 | [6 empty] | 2026-08-07 | 2026-08-10 |  |  | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 45 | J | Rony | [5 empty] | NFL2 |  |  | Cut Ok | 520 | 520 | 0 | 0 | -2000 | [11 empty] | 34 | Aug'1 |  |  | 15.07.26
UTG-(Even & Odd) | 41645 11th | BAD2681I | 1600 | 380 | 2026-07-01 | 2026-07-03 | Cropped LS TS w placket | TS |  |  | 2026-07-07 | 2026-07-10 | 2026-07-11 | 2026-07-23 |  |  | 2026-07-30 | 2026-08-01 |  | 2026-08-06 | 2026-08-07 | [6 empty] | 2026-08-07 | 2026-08-10 |  |  | 2026-08-11 | 2026-08-12 | 2026-08-14 | 2026-08-15 | 2026-08-17 | 45 | Q | Rony | [5 empty] | NFL2 |  |  | Cut Ok | 380 | 380 | 0 | 1683 | 83 | [11 empty] | 34 | Aug'1 |  |  | 15.07.26
BS-NMT | 48014 | 13249094 | 1606 | 183 | 2026-06-10 | 2026-06-29 | LS wrap body w full snap btn | Body |  |  | 2026-07-20 | 2026-07-25 | 2026-08-02 | 2026-08-15 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-26 | 2026-08-28 | 2026-08-29 | 2026-09-01 | 2026-09-02 |  |  |  |  | 2026-09-05 | 2026-09-07 |  |  | 2026-09-09 | 2026-09-12 | 2026-09-16 | 2026-09-21 | 2026-09-23 | 103 | T2 | Sabikun | Nk |  | 2 combo label print |  |  | NFL3 |  |  | Cut Ok | 183 | 183 | 0 | 1655 | 49 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48015 | 13249095 | 1010 | 115 | 2026-06-10 | 2026-06-29 | LS wrap body w full snap btn | Body |  |  | 2026-07-20 | 2026-07-24 | 2026-08-03 | 2026-08-14 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-22 | 2026-08-25 | 2026-08-26 | 2026-08-28 | 2026-08-29 |  |  |  |  | 2026-09-03 | 2026-09-04 |  |  | 2026-09-07 | 2026-09-09 | 2026-09-12 | 2026-09-21 | 2026-09-23 | 103 | T2 | Sabikun | Nk |  | 1 combo label print |  |  | NFL3 |  |  | Cut Ok | 115 | 115 | 0 | 1042 | 32 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48016 | 13266985 | 1020 | 82 | 2026-06-10 | 2026-06-29 | Swt pant w waist rib aand tape string | Pant |  |  | 2026-07-20 | 2026-07-24 | 2026-07-27 | 2026-08-13 |  |  | 2026-08-15 | 2026-08-15 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | 2026-08-29 |  |  |  |  | 2026-09-02 | 2026-09-03 |  |  | 2026-09-07 | 2026-09-09 | 2026-09-14 | 2026-09-21 | 2026-09-23 | 103 | U | Sabikun | Thigh |  | basil-510 pcs 3 clr rub 1 clr puff,,citadel-510 pcs 1 clr rub 1 clr puff |  |  | NFL3 |  |  | Cut Ok | 84 | 84 | 0 | 1088 | 68 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48017 | 13226052 | 1590 | 234 | 2026-06-10 | 2026-06-29 | LS Swt cardigan w full zipper and cuff btm rib | Cardigan |  |  | 2026-07-20 | 2026-07-26 | 2026-08-01 | 2026-08-15 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-24 | 2026-08-26 | 2026-08-28 | 2026-08-29 | 2026-09-02 |  |  |  |  | 2026-09-04 | 2026-09-07 |  |  | 2026-09-09 | 2026-09-11 | 2026-09-14 | 2026-09-21 | 2026-09-23 | 103 | X | Sabikun | Chest |  | pink-795 pcs 3 clr pig 1 clr gltr ,,peyote-795 pcs 4 clr pig 1 clr gltr |  |  | NFL3 |  |  | Cut Ok | 234 | 234 | 0 | 1858 | 268 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48018 | 13253735 | 810 | 75 | 2026-06-10 | 2026-06-29 | AOP LS Body w snap btn and Swt pant w tape string | Top & BTM |  |  | 2026-07-15 | 2026-07-20 | 2026-07-25 | 2026-08-07 | 2026-08-10 | 2026-08-17 | 2026-08-20 | 2026-08-20 | 2026-08-26 | 2026-08-28 | 2026-08-29 | 2026-09-02 | 2026-09-04 |  |  |  |  | 2026-09-07 | 2026-09-08 |  |  | 2026-09-10 | 2026-09-14 | 2026-09-16 | 2026-09-21 | 2026-09-23 | 103 | U+T2 | Sabikun | Nk,Thigh & waist |  | peyote top-405 pcs no print ,,citadel btm-405 pcs 1 clr rub puff | AOP |  | NFL3 |  |  | Cut Ok | 75 | 75 | 0 | 852 | 42 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48019 | 13251961 | 1993 | 173 | 2026-06-10 | 2026-06-29 | LS o nk TS w shlder snap btn | TS |  |  | 2026-07-20 | 2026-07-25 | 2026-08-01 | 2026-08-15 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-24 | 2026-08-27 | 2026-08-28 | 2026-09-01 | 2026-09-04 |  |  |  |  | 2026-09-07 | 2026-09-09 |  |  | 2026-09-11 | 2026-09-13 | 2026-09-15 | 2026-09-21 | 2026-09-23 | 103 | T1 | Sabikun | Chest,Nk |  | peyote-931 pcs 4 clr pig 1 clr puff,,c.dan-531 pcs 2 clr pig 1 clr puff ,,spellbound-531 pcs 2 clr pig 1 clr puff |  |  | NFL3 |  |  | Cut Ok | 172 | 172 | 0 | 2128 | 135 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48020 | 13251951 | 1348 | 201 | 2026-06-10 | 2026-06-29 | AOP LS swt shirt w shlder snap btn | TS |  |  | 2026-07-12 | 2026-07-17 | 2026-07-21 | 2026-08-04 | 2026-08-07 | 2026-08-15 | 2026-08-18 | 2026-08-18 | 2026-08-25 | 2026-08-27 | 2026-08-28 | [6 empty] | 2026-09-01 | 2026-09-02 |  |  | 2026-09-05 | 2026-09-08 | 2026-09-10 | 2026-09-21 | 2026-09-23 | 103 | Y | Sabikun |  |  |  | AOP |  | NFL3 |  |  | Cut Run | 201 | 190 | -11 | 1301 | -47 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48021 | 13251906 | 2595 | 308 | 2026-06-10 | 2026-06-29 | AOP & SolidWaist fold pant w rib at waist | Pant |  |  | 2026-07-15 | 2026-07-20 | 2026-07-22 | 2026-08-06 | 2026-08-08 | 2026-08-15 | 2026-08-17 | 2026-08-17 | 2026-08-22 | 2026-08-25 | 2026-08-26 | 2026-08-28 | 2026-08-31 |  |  |  |  | 2026-09-03 | 2026-09-05 |  |  | 2026-09-07 | 2026-09-09 | 2026-09-12 | 2026-09-21 | 2026-09-23 | 103 | ZA2 | Sabikun | Thigh |  | Ice AOP -1012 pcs no print ,,pink-877 pcs 4 clr rub,,peyote AOP-706 pcs no print | AOP |  | NFL3 |  |  | Cut Ok | 308 | 300 | -8 | 2640 | 45 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48022 | 13251953 | 2480 | 299 | 2026-06-10 | 2026-06-29 | AOP & SolidWaist fold pant w rib at waist | Pant |  |  | 2026-07-12 | 2026-07-18 | 2026-07-23 | 2026-08-07 | 2026-08-10 | 2026-08-17 | 2026-08-19 | 2026-08-19 | 2026-08-24 | 2026-08-26 | 2026-08-27 | 2026-08-29 | 2026-08-31 |  |  |  |  | 2026-09-03 | 2026-09-05 |  |  | 2026-09-08 | 2026-09-10 | 2026-09-14 | 2026-09-21 | 2026-09-23 | 103 | ZA2 | Sabikun | Thigh |  | Spellbound AOP-800 pcs no print ,,citadel-815 pcs 4 clr rub 1 clr puff print ,,AOP peyote-865 pcs no print | AOP |  | NFL3 |  |  | Cut Ok | 299 | 294 | -5 | 2587 | 107 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48023 | 13226071 | 3015 | 286 | 2026-06-10 | 2026-06-29 | AOP & solid LS body w shlder btm snap btn | Body |  |  | 2026-07-15 | 2026-07-20 | 2026-07-22 | 2026-08-06 | 2026-08-08 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 2026-08-24 | 2026-08-26 | 2026-08-27 | 2026-08-29 | 2026-09-02 |  |  |  |  | 2026-09-05 | 2026-09-08 |  |  | 2026-09-10 | 2026-09-12 | 2026-09-14 | 2026-09-21 | 2026-09-23 | 103 | T2 | Sabikun | Chest,Nk |  | Spellbound AOP-927 pcs no print ,,citadel-1044 pcs 4 clr rub print ,,AOP peyote-1044 pcs no print | AOP |  | NFL3 |  |  | Cut Ok | 286 | 286 | 0 | 3129 | 114 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48024 | 13255270 | 2670 | 355 | 2026-06-10 | 2026-06-29 | AOP & Solid LS swt shirt w shlder snap btn and swt pant | Top & BTM |  |  | 2026-07-15 | 2026-07-21 | 2026-07-23 | 2026-08-08 | 2026-08-10 | 2026-08-17 | 2026-08-19 | 2026-08-19 | 2026-08-24 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-31 |  |  |  |  | 2026-09-03 | 2026-09-07 |  |  | 2026-09-09 | 2026-09-12 | 2026-09-16 | 2026-09-21 | 2026-09-23 | 103 | U+Y | Sabikun | Chest & Leg |  | pink top -405 pcs 4 clr rub at chest,,pink btm-405 pcs 4 clr rub at one leg,,peyote top AOP-930 pcs no print ,,peyote btm AOP -930 pcs no print | AOP |  | NFL3 |  |  | Cut Ok | 404 | 404 | 0 | 2796 | 126 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48025 | 13251958 | 2968 | 314 | 2026-06-10 | 2026-06-29 | Swt pant w waist rib aand tape string | Pant |  |  | 2026-07-15 | 2026-07-22 | 2026-07-27 | 2026-08-12 |  |  | 2026-08-14 | 2026-08-14 | 2026-08-19 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-28 |  |  |  |  | 2026-09-01 | 2026-09-04 |  |  | 2026-09-07 | 2026-09-09 | 2026-09-15 | 2026-09-21 | 2026-09-23 | 103 | U | Sabikun | Waist & Thigh |  | Basil-1010 pcs 3 clr rub 1 clr puff ,,sepia-844 pcs 2 clr rub 1 clr puff,,citadel-1114 pcs 1 clr rub 1 clr puff |  |  | NFL3 |  |  | Cut Ok | 313 | 313 | 0 | 3133 | 165 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48026 | 13252211 | 1836 | 101 | 2026-06-10 | 2026-06-29 | AOP & Solid Elasted legging | Legging |  |  | 2026-07-15 | 2026-07-18 | 2026-07-22 | 2026-08-04 | 2026-08-08 | 2026-08-14 | 2026-08-15 | 2026-08-15 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | 2026-08-29 |  |  |  |  | 2026-09-01 | 2026-09-02 |  |  | 2026-09-04 | 2026-09-07 | 2026-09-09 | 2026-09-21 | 2026-09-23 | 103 | ZA2 | Sabikun | Chest,Nk,Waist |  | pink -918 pcs 4 clr rub 1 clr gltr ,,peyote AOP-918 pcs no print | AOP |  | NFL3 |  |  | Cut Ok | 101 | 101 | 0 | 1908 | 72 | [11 empty] | 39 | Aug'3 |  |  | 19.08.26
BS-NMT | 48027 | 13226053 | 1416 | 124 | 2026-06-10 | 2026-06-29 | LS o nk TS w shlder snap btn | TS |  |  | 2026-07-18 | 2026-07-22 | 2026-08-02 | 2026-08-15 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-26 | 2026-08-28 | 2026-08-29 | 2026-09-01 | 2026-09-03 |  |  |  |  | 2026-09-07 | 2026-09-09 |  |  | 2026-09-11 | 2026-09-13 | 2026-09-15 | 2026-09-21 | 2026-09-23 | 103 | T1 | Sabikun | Chest,Nk |  | pink-708 pcs 3 clr pig 1 clr gltr,,ice-708 pcs 4 clr pig 1 clr gltr |  |  | NFL3 |  |  | Cut Ok | 124 | 124 | 0 | 1500 | 84 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48028 | 13226054 | 2637 | 256 | 2026-06-10 | 2026-06-29 | AOP & solid LS body w shlder btm snap btn | Body |  |  | 2026-07-15 | 2026-07-20 | 2026-07-23 | 2026-08-04 | 2026-08-08 | 2026-08-15 | 2026-08-17 | 2026-08-17 | 2026-08-22 | 2026-08-24 | 2026-08-25 | 2026-08-27 | 2026-08-29 |  |  |  |  | 2026-09-01 | 2026-09-03 |  |  | 2026-09-05 | 2026-09-08 | 2026-09-10 | 2026-09-21 | 2026-09-23 | 103 | T2 | Sabikun | Chest,Nk |  | Ice AOP -918 pcs no print ,,pink-918 pcs 4 clr pig 1 clr gltr ,,peyote AOP-801 pcs no print | AOP |  | NFL3 |  |  | Cut Ok | 257 | 257 | 0 | 2738 | 101 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48029 | 13226065 | 1608 | 235 | 2026-06-10 | 2026-06-29 | LS Swt cardigan w full zipper and cuff btm rib | Cardigan |  |  | 2026-07-20 | 2026-07-25 | 2026-08-04 | 2026-08-17 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-26 | 2026-08-28 | 2026-08-29 | 2026-09-01 | 2026-09-03 |  |  |  |  | 2026-09-07 | 2026-09-09 |  |  | 2026-09-11 | 2026-09-14 | 2026-09-16 | 2026-09-21 | 2026-09-23 | 103 | X | Sabikun | Chest |  | Basil-804 pcs 3 clr rub 1 clr pufff,,Citadel-804 pcs 1 clr rub 1 clr puff |  |  | NFL3 |  |  | Cut Ok | 234 | 234 | 0 | 1706 | 98 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48030 | 13268149 | 810 | 77 | 2026-06-10 | 2026-06-29 | LS O nk TS w shlder snap btn and swt pant w tape string | Top & BTM |  |  | 2026-07-20 | 2026-07-25 | 2026-08-04 | 2026-08-18 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-26 | 2026-08-28 | 2026-08-29 | 2026-09-01 | 2026-09-03 |  |  |  |  | 2026-09-07 | 2026-09-08 |  |  | 2026-09-10 | 2026-09-12 | 2026-09-15 | 2026-09-21 | 2026-09-23 | 103 | U+Y | Sabikun | Chest,Nk & Thigh |  | peyote top-405 pcs 4 clr rub 1 clr puff,,basil btm-405 pcs 3 clr rub 1 clr puff |  |  | NFL3 |  |  | Cut Ok | 77 | 77 | 0 | 874 | 64 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48031 | 13255268 | 1860 | 256 | 2026-06-10 | 2026-06-29 | AOP swt shirt w shlder snap btn and Waist fold pant | Top & BTM |  |  | 2026-07-15 | 2026-07-21 | 2026-07-25 | 2026-08-08 | 2026-08-12 | 2026-08-20 | 2026-08-22 | 2026-08-22 | 2026-08-29 | 2026-09-01 | 2026-09-02 | [6 empty] | 2026-09-04 | 2026-09-07 |  |  | 2026-09-09 | 2026-09-12 | 2026-09-15 | 2026-09-21 | 2026-09-23 | 103 | U+Y | Sabikun |  |  |  | AOP |  | NFL3 |  |  | Cut Ok | 257 | 257 | 0 | 1928 | 68 | [11 empty] | 39 | Sep'1 |  |  | 25.07.26
BS-NMT | 48032 | 13253726 | 810 | 80 | 2026-06-10 | 2026-06-29 | LS O nk TS w shlder snap btn | TS |  |  | 2026-07-20 | 2026-07-25 | 2026-08-02 | 2026-08-15 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-26 | 2026-08-28 | 2026-08-29 | 2026-09-01 | 2026-09-03 |  |  |  |  | 2026-09-05 | 2026-09-07 |  |  | 2026-09-09 | 2026-09-11 | 2026-09-15 | 2026-09-21 | 2026-09-23 | 103 | T1 | Sabikun | Chest,Nk |  | c.dan-405 pcs 2 clr p[ig 1 clr puff,,spellbound-405 pcs 2 clr rub 1 clr puff |  |  | NFL3 |  |  | Cut Ok | 80 | 80 | 0 | 881 | 71 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48033 | 13230043 | 810 | 74 | 2026-06-10 | 2026-06-29 | LS O nk TS w shlder snap btn | TS |  |  | 2026-07-20 | 2026-07-24 | 2026-08-01 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-25 | 2026-08-28 | 2026-08-29 | 2026-09-01 | 2026-09-03 |  |  |  |  | 2026-09-07 | 2026-09-08 |  |  | 2026-09-10 | 2026-09-12 | 2026-09-15 | 2026-09-21 | 2026-09-23 | 103 | T1 | Sabikun | Chest,Nk |  | Ice-405 pcs 4 clr pig 1 clr gltr,,pink-405 pcs 4 clr pig 1 clr gltr |  |  | NFL3 |  |  | Cut Ok | 74 | 72 | -2 | 880 | 70 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-NMT | 48034 | 13251904 | 1320 | 193 | 2026-06-10 | 2026-06-29 | AOP & Solid LS swt shirt w shlder snap btn | Swt Shirt |  |  | 2026-07-10 | 2026-07-15 | 2026-07-20 | 2026-08-04 | 2026-08-04 | 2026-08-11 | 2026-08-13 | 2026-08-13 | 2026-08-19 | 2026-08-21 | 2026-08-22 | 2026-08-25 | 2026-08-28 |  |  |  |  | 2026-09-01 | 2026-09-03 |  |  | 2026-09-05 | 2026-09-08 | 2026-09-10 | 2026-09-21 | 2026-09-23 | 103 | Y | Sabikun | Chest |  | pink-605 pcs,,peyote-715 pcs bboth combo 4 clr rub print | AOP |  | NFL3 |  |  | Cut Ok | 193 | 188 | -5 | 1372 | 52 | [11 empty] | 39 | Aug'3 |  |  | 25.07.26
BS-ONS | 26828 73th | 22029226 | 2000 | 1321 | 2026-07-02 | 2026-07-06 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-07-16 | 2026-07-22 | 2026-08-01 | 2026-08-14 |  |  | 2026-08-13 | 2026-08-13 |  | 2026-08-17 | 2026-08-19 | [6 empty] | 2026-08-20 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-31 | 2026-09-02 | 60 | E | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 1321 | 1321 | 0 | 2035 | 35 | [11 empty] | 36 | Aug'2 |  |  | 18.07.26
BS-ONS | 45964 12th | 22039968 | 4000 | 2781 | 2026-07-02 | 2026-07-06 | LS High nk Haalf Zipp Swt shirt | Swt Shirt |  |  | 2026-07-14 | 2026-07-24 | 2026-07-25 | 2026-08-10 |  |  | 2026-08-10 | 2026-08-10 |  | 2026-08-15 | 2026-08-19 | [6 empty] | 2026-08-19 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-31 | 2026-09-02 | 60 | B | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 2782 | 2782 | 0 | 0 | -4000 | [11 empty] | 36 | Aug'2 |  |  | 27.07.26
BS-ONS | 48190 | 22040942 | 1247 | 636 | 2026-06-25 | 2026-07-06 | LS Swt hoody w rib and kangaroo pkt | Hoody |  |  | 2026-07-15 | 2026-07-22 | 2026-08-01 | 2026-08-14 |  |  | 2026-08-14 | 2026-08-14 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 2026-08-26 | 2026-08-29 |  |  |  |  | 2026-09-01 | 2026-09-03 |  |  | 2026-09-05 | 2026-09-07 | 2026-09-09 | 2026-09-14 | 2026-09-16 | 81 | B | Shovon | Fr,Bk |  | plaza-381 pcs,,navy-878 pcs both combo frt back 1 clr rub print |  |  | NFL1 |  |  | Cut Ok | 636 | 630 | -6 | 1301 | 54 | [11 empty] | 38 | Aug'3 |  |  | 25.08.26
BS-ONS | 48191 | 22040941 | 1647 | 610 | 2026-06-25 | 2026-07-06 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-07-18 | 2026-07-24 | 2026-08-01 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-22 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-29 |  |  |  |  | 2026-09-01 | 2026-09-02 |  |  | 2026-09-04 | 2026-09-07 | 2026-09-09 | 2026-09-14 | 2026-09-16 | 81 | A | Shovon | Fr,Bk |  | plaza-590 pcs frt 3 clr pig back 5 clr pig ,,egret-578 pcs frt 3 clr pig back 4 clr pig,,black-479 pcs frt back 2 clr rub print |  |  | NFL1 |  |  | Cut Ok | 611 | 607 | -4 | 1711 | 64 | [11 empty] | 38 | Aug'3 |  |  | 25.08.26
BS-ONL | 48299 | 15390922 | 640 | 140 | 2026-07-02 | 2026-07-04 | SS o nk TS | TS |  |  | 2026-07-16 | 2026-07-22 | 2026-08-01 | 2026-08-08 |  |  | 2026-08-10 | 2026-08-10 | 2026-08-15 | 2026-08-18 | 2026-08-19 | 2026-08-21 | 2026-08-25 |  |  |  |  | 2026-08-27 | 2026-08-28 |  |  | 2026-08-29 | 2026-08-29 | 2026-08-31 | 2026-09-05 | 2026-09-07 | 65 | O1 | Jannati | Chest |  | white-640 pcs 1 clr pig print |  |  | NFL2 |  |  | Cut Ok | 140 | 140 | 0 | 664 | 24 | [11 empty] | 37 | Aug'2 |  |  | 6.08.26
BS-ONL | 48158 | 15368187 | 13992 | 2143 | 2026-06-24 | 2026-06-30 | SS v nk TS | TS |  |  | 2026-07-15 | 2026-07-22 | 2026-07-23 | 2026-08-07 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-13 | 2026-08-15 | 2026-08-19 | 2026-08-19 | 2026-08-24 |  |  |  |  | 2026-08-24 | 2026-08-29 |  |  | 2026-09-02 | 2026-09-04 | 2026-09-07 | 2026-09-14 | 2026-09-16 | 82 | V | Mainul | Chest |  | black-6996 pcs,,c.dancer-6996 pcs all combo 3 clr rub 1 clr gltr |  |  | NFL3 |  |  | Cut Ok | 2144 | 2144 | 0 | 14028 | 36 | [11 empty] | 38 | Aug'2 |  |  | 25.07.26
BS-ONL | 46748 12th | 15244714 | 19872 | 253 | 2026-06-25 | 2026-06-30 | SS o nk TS | TS |  |  | 2026-07-12 | 2026-07-22 | 2026-07-22 | 2026-08-06 |  |  | 2026-08-06 | 2026-08-01 |  | 2026-08-10 | 2026-08-15 | 2026-08-14 | 2026-08-20 |  |  |  |  | 2026-08-20 | 2026-08-27 |  |  | 2026-08-29 | 2026-08-31 | 2026-09-05 | 2026-09-14 | 2026-09-16 | 81 | F | Imran | Chest |  | pink-7896 pcs,,anise-7896 pcs,,blue-4080 pcs all combo 1 clr gltr print |  |  | NFL1 |  |  | Cut Ok | 3032 | 3032 | 0 | 20249 | 377 | [11 empty] | 38 | Aug'1 |  |  | 17.07.26
BS-ONL | 22035 71th | 15095808 | 3096 | 442 | 2026-06-26 | 2026-07-04 | Tank Top | Tank Top |  |  | 2026-07-15 | 2026-07-22 | 2026-07-25 | 2026-08-08 |  |  | 2026-08-08 | 2026-08-08 |  | 2026-08-13 | 2026-08-14 | [6 empty] | 2026-08-17 | 2026-08-19 |  |  | 2026-08-22 | 2026-08-25 | 2026-08-27 | 2026-09-14 | 2026-09-16 | 80 | ZA2 | Imran | [5 empty] | NFL3 |  |  | Cut Ok | 441 | 441 | 0 | 3180 | 84 | [11 empty] | 38 | Aug'2 |  |  | 10.08.26
BS-ONL | 41875 15th | 15303956 | 1520 | 652 | 2026-06-30 | 2026-07-02 | PANT W PKT | PANT |  |  | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-08-03 |  |  | 2026-08-04 | 2026-07-25 |  | 2026-08-07 | 2026-08-08 |  |  |  |  | 2026-08-10 | 2026-08-11 | 2026-08-13 | 2026-08-17 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-22 | 2026-08-31 | 2026-09-02 | 62 | P | Khalid |  | LEG | BLACK 1520 PCS 1 CLR LETTERING EMB AT ONE LEG |  |  | NFL2 |  |  | Cut Ok | 652 | 652 | 0 | 0 | -1520 | [11 empty] | 36 | Aug'1 |  |  | 08.07.26
BS-ONL | 48186 | 15390588 | 1428 | 528 | 2026-06-24 | 2026-07-01 | SS O nk TS | TS |  |  | 2026-07-15 | 2026-07-23 | 2026-09-01 | 2026-09-10 |  |  | 2026-09-12 | 2026-09-12 | 2026-09-18 | 2026-09-21 | 2026-09-22 | 2026-09-24 | 2026-09-28 |  |  |  |  | 2026-10-01 | 2026-10-03 |  |  | 2026-10-06 | 2026-10-08 | 2026-10-15 | 2026-11-16 | 2026-11-18 | 145 | O2 | Zahirul | Chest |  | orchid-756 pcs 2 clr rub ,,pageant-672 pcs 1 clr rub |  |  | NFL2 |  |  | Cut Ok | 528 | 518 | -10 | 1476 | 48 | [11 empty] | 47 | Sep'3 |  |  | 25.08.26
BS-ONL | 48183 | 15373595 | 480 | 145 | 2026-06-24 | 2026-07-01 | SS o nk Rib TS | TS |  |  | 2026-07-18 | 2026-07-22 | 2026-08-04 | 2026-08-14 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-22 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-28 |  |  |  |  | 2026-09-01 | 2026-09-02 |  |  | 2026-09-04 | 2026-09-07 | 2026-09-10 | 2026-09-12 | 2026-09-14 | 80 | O2 | Zahirul | Nk |  | 1 combo nk 1 clr rub print print |  |  | NFL2 |  |  | Cut Ok | 145 | 145 | 0 | 499 | 19 | [11 empty] | 38 | Aug'3 |  |  | 29.07.26
BS-ONL | 46309 5th | 15188034 | 2000 | 520 | 2026-07-03 | 2026-07-06 | Legging w elatic waist belt | Legging |  |  | 2026-07-20 | 2026-07-24 | 2026-08-01 | 2026-08-08 |  |  | 2026-08-08 | 2026-08-08 |  | 2026-08-13 | 2026-08-14 | [6 empty] | 2026-08-17 | 2026-08-19 |  |  | 2026-08-21 | 2026-08-24 | 2026-08-26 | 2026-09-07 | 2026-09-09 | 66 | L2 | Zahirul | [5 empty] | NFL2 |  |  | Cut Ok | 520 | 520 | 0 | 2043 | 43 | [11 empty] | 37 | Aug'2 |  |  | 22.07.26
BS-ONL | 48189 | 15370026 | 4365 | 3020 | 2026-06-24 | 2026-07-06 | LS Swt hoody w cuff btm rib and drawstring | Hoody |  |  | 2026-07-12 | 2026-07-22 | 2026-07-23 | 2026-08-10 |  |  | 2026-08-10 | 2026-08-10 | 2026-08-15 | 2026-08-18 | 2026-08-21 |  |  |  |  | 2026-08-20 | 2026-08-24 | 2026-08-24 | 2026-08-29 |  |  | 2026-09-03 | 2026-09-05 | 2026-09-08 | 2026-09-14 | 2026-09-16 | 82 | J | Zahirul |  | Chest | c.dan-387 pcs,,pink-1464 pcs,,ether-867 pcs,,black-387 pcs,,flower-1260 pcs all combo 1 clr lurex heart emb |  |  | NFL2 |  |  | Cut Ok | 3020 | 3020 | 0 | 4469 | 104 | [11 empty] | 38 | Aug'2 |  |  | 11.08.26
BS-ONL | 42946 8th | 15360359 | 11958 | 4514 | 2026-07-03 | 2026-07-04 | YD loose pant w drawstring | Pant | 2026-07-16 | 2026-07-29 | 2026-07-25 | 2026-08-14 | 2026-08-08 | 2026-08-20 |  |  | 2026-08-20 | 2026-08-20 |  | 2026-08-25 | 2026-08-31 | [6 empty] | 2026-09-01 | 2026-09-10 |  |  | 2026-09-12 | 2026-09-15 | 2026-09-18 | 2026-09-28 | 2026-09-30 | 87 | P | Dalim |  |  |  | YD |  | NFL2 |  |  | Need Cut | 4515 | 3479 | -1036 | 0 | -11958 | [11 empty] | 40 | Aug'3 |  |  | 08.08.26
BS-ONL | 27204 58th | 15323159 | 7020 | 1697 | 2026-07-03 | 2026-07-06 | LS o nk TS | TS |  |  | 2026-07-20 | 2026-07-26 | 2026-08-01 | 2026-08-13 |  |  | 2026-08-12 | 2026-08-12 |  | 2026-08-17 | 2026-08-18 | [6 empty] | 2026-08-20 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-28 | 2026-08-31 | 2026-09-13 | 2026-09-15 | 72 | G2 | Dalim | [5 empty] | NFL1 |  |  | Cut Run | 1696 | 1683 | -13 | 6886 | -134 | [11 empty] | 38 | Aug'2 |  |  | 07.07.26
BS-ONL | 48202 | 15388786 | 21716 | 2715 | 2026-06-20 | 2026-07-01 | SS o nk TS w blind stitch | TS |  |  | 2026-07-05 | 2026-07-13 | 2026-07-13 | 2026-07-31 |  |  | 2026-08-01 | 2026-08-01 | 2026-08-10 | 2026-08-12 | 2026-08-17 | 2026-08-15 | 2026-08-24 |  |  |  |  | 2026-08-24 | 2026-09-02 |  |  | 2026-09-04 | 2026-09-07 | 2026-09-09 | 2026-09-19 | 2026-09-21 | 91 | G2 | Abid | Fr,Bk |  | C.dancer-6460 pcs frt 1 clr gltr and back 5 clr pig 1 clr gltr ,,ether-5812 pcs frt 2 clr pig 2 clr gltr back 6 clr pig 3 clr gltr ,,Navy-4360 pcs frt 2 clr pig 1 clr gltr and back 4 clr pig 2 clr gltr |  |  | NFL1 |  |  | Cut Ok | 2714 | 2714 | 0 | 22200 | 484 | [11 empty] | 39 | Aug'2 |  |  | 19.08.26
BS-ONL | 48203 | 15388785 | 6120 | 2705 | 2026-06-20 | 2026-07-01 | LS Swt hoody w cuff btm rib | Hoody |  |  | 2026-07-08 | 2026-07-18 | 2026-07-21 | 2026-08-07 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-12 | 2026-08-14 | 2026-08-17 | 2026-08-17 | 2026-08-22 |  |  |  |  | 2026-08-24 | 2026-08-29 |  |  | 2026-09-03 | 2026-09-05 | 2026-09-10 | 2026-09-21 | 2026-09-23 | 93 | K | Abid | Fr,Bk |  | c.dan-2868 pcs frt 2 clr pig 1 clr gltr and back 3 clr pig 3 clr gltr ,,Navy-3252 pcs frt 1 clr rub 1 clr gltr and back 4 clr rub 2 clr gltr print |  |  | NFL2 |  |  | Cut Ok | 2705 | 2705 | 0 | 6278 | 158 | [11 empty] | 39 | Aug'2 |  |  | 21.08.26
BS-ONL | 48201 | 15365507 | 13406 | 4781 | 2026-06-20 | 2026-07-01 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-07-07 | 2026-07-20 | 2026-07-22 | 2026-08-10 |  |  | 2026-08-10 | 2026-08-10 | 2026-08-15 | 2026-08-17 | 2026-08-21 | 2026-08-19 | 2026-08-26 |  |  |  |  | 2026-08-26 | 2026-09-01 |  |  | 2026-09-04 | 2026-09-07 | 2026-09-10 | 2026-09-19 | 2026-09-21 | 91 | E | Abid | Fr,Bk |  | ether-4192 pcs front 4 clr rub back 8 clr rub,,tofu-6582 pcs front 1 clr puff back 5 clr rub 1 clr puff ,,pink-2632 ps front 10 clr rub back no print |  |  | NFL1 |  |  | Cut Ok | 4781 | 4722 | -59 | 13785 | 379 | [11 empty] | 39 | Aug'2 |  |  | 19.08.26
OVS SPA | 47820 | 271HTS001SET-244 | 10310 | 580 | 2026-06-16 | 2026-06-29 | Hats and skirf set | Scarf & Hat |  |  | 2026-08-01 | 2026-08-08 | 2026-08-10 | 2026-08-22 |  |  | 2026-08-31 | 2026-08-28 | 2026-09-03 | 2026-09-04 | 2026-09-08 | [6 empty] | 2026-09-08 | 2026-09-14 |  |  | 2026-09-15 | 2026-09-17 | 2026-09-19 | 2026-09-21 | 2026-09-21 | 97 | N2 | Khairul | [5 empty] | NFL2 |  |  | Cut Ok | 580 | 580 | 0 | 10424 | 114 | [11 empty] | 39 | Sep'1 |  |  | 29.08.26
OVS SPA | 47821 | 271HTS002SET-244 | 10520 | 580 | 2026-06-16 | 2026-06-29 | AOP Hats and skirf set | Scarf & Hat |  |  | 2026-07-20 | 2026-08-05 | 2026-07-30 | 2026-08-15 | 2026-08-13 | 2026-08-22 | 2026-08-28 | 2026-08-29 | 2026-09-04 | 2026-09-05 | 2026-09-09 | [6 empty] | 2026-09-09 | 2026-09-16 |  |  | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-21 | 2026-09-21 | 97 | E | Khairul |  |  |  | AOP |  | NFL1 |  |  | Cut Ok | 580 | 580 | 0 | 10634 | 114 | [11 empty] | 39 | Sep'1 |  |  | 04.09.26
OVS SPA | 47822 | 271HTS501SET-5192 | 11696 | 660 | 2026-06-16 | 2026-06-29 | Hats and skirf set w jaquared label | Scarf & Hat |  |  | 2026-08-01 | 2026-08-08 | 2026-08-10 | 2026-08-22 |  |  | 2026-08-31 | 2026-08-28 | 2026-09-03 | 2026-09-04 | 2026-09-08 | [6 empty] | 2026-09-08 | 2026-09-14 |  |  | 2026-09-15 | 2026-09-17 | 2026-09-19 | 2026-09-21 | 2026-09-21 | 97 | N2 | Khairul | [5 empty] | NFL2 |  |  | Cut Run | 660 | 660 | 0 | 10344 | -1352 | [11 empty] | 39 | Sep'1 |  |  | 29.08.26
OVS SPA | 47823 | 271HTS610JB-5192 | 3440 | 200 | 2026-06-16 | 2026-06-29 | Double layer Hat | Hat |  |  | 2026-08-01 | 2026-08-08 | 2026-08-10 | 2026-08-22 |  |  | 2026-08-28 | 2026-08-29 | 2026-09-05 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-12 |  |  |  |  | 2026-09-11 | 2026-09-14 |  |  | 2026-09-15 | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-21 | 97 | N2 | Khairul | Heat Press/Heat Seal |  | LGM-3440 pcs HP sticker Print on Upper Layer Hat |  |  | NFL2 |  |  | Need Test Cut | 200 | 0 | -200 | 0 | -3440 | [11 empty] | 39 | Sep'1 |  |  | 05.09.26
OVS SPA | 47938 | 271HTS004JB-244 | 7200 | 450 | 2026-06-16 | 2026-06-29 | AOP Hat | Hat |  |  | 2026-07-20 | 2026-08-05 | 2026-08-01 | 2026-08-15 | 2026-08-13 | 2026-08-22 | 2026-08-28 | 2026-08-29 | 2026-09-03 | 2026-09-04 | 2026-09-07 | [6 empty] | 2026-09-07 | 2026-09-14 |  |  | 2026-09-15 | 2026-09-17 | 2026-09-19 | 2026-09-21 | 2026-09-21 | 97 | D1 | Khairul |  |  |  | AOP |  | NFL1 |  |  | Cut Ok | 450 | 450 | 0 | 7284 | 84 | [11 empty] | 39 | Sep'1 |  |  | 05.09.26
OVS SPA | 47939 | 271HTS005JB-244 | 6005 | 290 | 2026-06-16 | 2026-06-29 | Hat | Hat |  |  | 2026-08-01 | 2026-08-08 | 2026-08-10 | 2026-08-22 |  |  | 2026-08-31 | 2026-08-25 | 2026-09-01 | 2026-09-02 | 2026-09-04 | 2026-09-04 | 2026-09-08 |  |  |  |  | 2026-09-09 | 2026-09-14 |  |  | 2026-09-15 | 2026-09-17 | 2026-09-19 | 2026-09-21 | 2026-09-21 | 97 | G1 | Khairul | Hat |  | nosegay-6005 pcs 2 clr rub print |  |  | NFL1 |  |  | Need Cut | 290 | 290 | 0 | 0 | -6005 | [11 empty] | 39 | Sep'1 |  |  | 05.09.26
OVS SPA | 47940 | 271HTS007JB-244 | 5955 | 570 | 2026-06-16 | 2026-06-29 | AOP Hat | Hat |  |  | 2026-07-20 | 2026-07-31 | 2026-08-01 | 2026-08-11 | 2026-08-12 | 2026-08-20 | 2026-09-08 | 2026-09-04 | 2026-09-09 | 2026-09-10 | 2026-09-12 | [6 empty] | 2026-09-14 | 2026-09-17 |  |  | 2026-09-18 | 2026-09-18 | 2026-09-19 | 2026-09-21 | 2026-09-21 | 97 | G1 | Khairul |  |  |  | AOP |  | NFL1 |  |  | Cut Run | 570 | 570 | 0 | 2400 | -3555 | [11 empty] | 39 | Sep'1 |  |  | 05.09.26
OVS SPA | 47941 | 271HTS504JB-5192/271HTS505-5192 | 13572 | 745 | 2026-06-16 | 2026-06-29 | Hat w jaquared label | Hat |  |  | 2026-08-01 | 2026-08-08 | 2026-08-10 | 2026-08-22 |  |  | 2026-08-31 | 2026-08-28 | 2026-09-03 | 2026-09-04 | 2026-09-09 | [6 empty] | 2026-09-08 | 2026-09-14 |  |  | 2026-09-15 | 2026-09-17 | 2026-09-19 | 2026-09-21 | 2026-09-21 | 97 | G2 | Khairul | [5 empty] | NFL1 |  |  | Cut Run | 745 | 745 | 0 | 13437 | -135 | [11 empty] | 39 | Sep'1 |  |  | 29.08.26
OVS SPA | 47942 | 271HTS506JB-5192 | 3425 | 180 | 2026-06-16 | 2026-06-29 | Hat | Hat |  |  | 2026-08-01 | 2026-08-08 | 2026-08-10 | 2026-08-22 |  |  | 2026-08-31 | 2026-08-25 | 2026-09-02 | 2026-09-03 | 2026-09-05 | 2026-09-07 | 2026-09-10 |  |  |  |  | 2026-09-10 | 2026-09-14 |  |  | 2026-09-15 | 2026-09-17 | 2026-09-19 | 2026-09-21 | 2026-09-21 | 97 | G1 | Khairul | Hat |  | Black-3425 pcs 2 clr rub print |  |  | NFL1 |  |  | Need Cut | 180 | 180 | 0 | 0 | -3425 | [11 empty] | 39 | Sep'1 |  |  | 05.09.26
OVS SPA | 47943 | 271HTS507JB/508JB/613JB-5162 | 12659 | 820 | 2026-06-16 | 2026-06-29 | AOP Hat | Hat |  |  | 2026-07-20 | 2026-08-05 | 2026-08-01 | 2026-08-15 | 2026-08-13 | 2026-08-22 | 2026-08-28 | 2026-08-29 | 2026-09-03 | 2026-09-04 | 2026-09-07 | [6 empty] | 2026-09-07 | 2026-09-14 |  |  | 2026-09-15 | 2026-09-17 | 2026-09-19 | 2026-09-21 | 2026-09-21 | 97 | D1 | Khairul |  |  |  | AOP |  | NFL1 |  |  | Need Test Cut | 0 | 0 | 0 | 0 | -12659 | [11 empty] | 39 | Sep'1 |  |  | 05.09.26
OVS SPA | 47944 | 271HTS611JB-5192 | 7135 | 430 | 2026-06-16 | 2026-06-29 | Hat | Hat |  |  | 2026-08-01 | 2026-08-08 | 2026-08-10 | 2026-08-22 |  |  | 2026-08-31 | 2026-08-27 | 2026-09-02 | 2026-09-03 | 2026-09-05 | 2026-09-07 | 2026-09-11 |  |  |  |  | 2026-09-10 | 2026-09-15 |  |  | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-21 | 97 | G2 | Khairul | Hat |  | blue-7135 pcs 6 clr rub print |  |  | NFL1 |  |  | Size Set Run Print | 430 | 430 | 0 | 0 | -7135 | [11 empty] | 39 | Sep'1 |  |  | 05.09.26
OVS SPA | 47879 | 271HTS003JB-244 | 7205 | 450 | 2026-06-16 | 2026-06-29 | AOP Hat | Hat |  |  | 2026-07-20 | 2026-08-05 | 2026-08-01 | 2026-08-15 | 2026-08-13 | 2026-08-22 | 2026-08-31 | 2026-09-01 | 2026-09-05 | 2026-09-07 | 2026-09-09 | [6 empty] | 2026-09-10 | 2026-09-15 |  |  | 2026-09-16 | 2026-09-17 | 2026-09-19 | 2026-09-21 | 2026-09-21 | 97 | G2 | Khairul |  |  |  | AOP |  | NFL1 |  |  | Need Test Cut | 450 | 0 | -450 | 0 | -7205 | [11 empty] | 39 | Sep'1 |  |  | 05.09.26
OVS SPA | 47824 | 271TShH170-6154 | 2292 | 630 | 2026-06-16 | 2026-06-29 | YS SS drop shlder TS | TS | 2026-07-20 | 2026-07-31 | 2026-08-01 | 2026-08-11 | 2026-08-12 | 2026-08-21 |  |  | 2026-09-08 | 2026-09-02 | 2026-09-08 | 2026-09-09 | 2026-09-11 | 2026-09-11 | 2026-09-16 |  |  |  |  | 2026-09-17 | 2026-09-19 |  |  | 2026-09-21 | 2026-09-23 | 2026-09-25 | 2026-09-28 | 2026-09-28 | 104 | G1 | Khairul | Chest |  | off white-2292 pcs 1 clr rub print |  |  | NFL1 |  |  | Need Test Cut | 640 | 0 | -640 | 0 | -2292 | [11 empty] | 40 | Sep'1 |  |  | 12.09.26
OVS SPA | 48138 | 271TSH184-6154 | 4572 | 855 | 2026-06-16 | 2026-06-29 | SS o nk TS w nk rib | TS |  |  | 2026-08-01 | 2026-08-10 | 2026-08-11 | 2026-08-22 |  |  | 2026-09-05 | 2026-09-02 | 2026-09-07 | 2026-09-08 | 2026-09-10 | 2026-09-10 | 2026-09-16 |  |  |  |  | 2026-09-16 | 2026-09-21 |  |  | 2026-09-22 | 2026-09-24 | 2026-09-26 | 2026-09-28 | 2026-09-28 | 104 | G1 | Khairul | Chest |  | off white-4572 pcs 6 clr pig print |  |  | NFL1 |  |  | Cut Run | 875 | 875 | 0 | 4020 | -552 | [11 empty] | 40 | Sep'1 |  |  | 01.09.26
OVS SPA | 47838 | 271BDY090BDY90-6198 | 5080 | 895 | 2026-06-16 | 2026-06-29 | LS body w gusset tape at cross point and snap btn | Body |  |  | 2026-08-01 | 2026-08-10 | 2026-08-11 | 2026-08-24 |  |  | 2026-08-31 | 2026-09-01 | 2026-09-05 | 2026-09-07 | 2026-09-09 | [6 empty] | 2026-09-10 | 2026-09-18 |  |  | 2026-09-19 | 2026-09-22 | 2026-09-23 | 2026-09-28 | 2026-09-28 | 104 | N/3 | Khairul | [5 empty] | NCL |  |  | Ready Test Cut | 895 | 895 | 0 | 0 | -5080 | [11 empty] | 40 | Sep'1
OVS SPA | 47795 | 271SWT064-6156 | 2674 | 765 | 2026-06-29 | 2026-06-30 | LS YS polo shirt w collar cuff rib w placket btn | Polo | 2026-07-20 | 2026-07-31 | 2026-08-01 | 2026-08-12 | 2026-08-13 | 2026-08-22 |  |  | 2026-09-01 | 2026-09-01 | 2026-09-07 | 2026-09-08 | 2026-09-10 |  |  |  |  | 2026-09-11 | 2026-09-16 | 2026-09-17 | 2026-09-22 |  |  | 2026-09-23 | 2026-09-25 | 2026-09-26 | 2026-09-28 | 2026-09-28 | 91 | N/3 | Khairul |  | Chest | multi-2674 pcs patch attach emb if needed,and patch will be delivery from elegant supplier |  |  | NCL |  |  | Need Test Cut | 0 | 0 | 0 | 0 | -2674 | [11 empty] | 40 | Sep'1
UTG-(Even & Odd) | 30703 12th | BAD2640L | 2500 | 530 | 2026-06-27 | 2026-06-30 | BODYSUIT W ZIPPER | SUIT |  |  | 2026-08-01 | 2026-08-07 | 2026-08-08 | 2026-07-30 |  |  | 2026-08-02 | 2026-07-25 |  | 2026-08-06 | 2026-08-07 | [6 empty] | 2026-08-08 | 2026-08-12 |  |  | 2026-08-14 | 2026-08-18 | 2026-08-20 | 2026-08-29 | 2026-08-31 | 63 | N/3 | Rony |  |  |  |  | N/Cut | NCL |  |  | Cut Ok | 530 | 530 | 0 | 2542 | 42 | [11 empty] | 36 | Aug'1
UTG-(Even & Odd) | 41647 12th | BAD2678K | 2500 | 505 | 2026-06-27 | 2026-06-30 | LS BALLARINA KNOT TOP | DRESS | 2026-08-13: 2026-08-10; 2026-08-22: 2026-08-20 |  |  | 2026-08-26 | 2026-08-28 |  | 2026-09-01 | 2026-09-02 | [6 empty] | 2026-09-04 | 2026-09-08 |  |  | 2026-09-09 | 2026-09-11 | 2026-09-14 | 2026-09-19 | 2026-09-21 | 84 | N/3 | Rony |  |  |  |  | Imp Stock grey fab | NCL |  |  | Ready Test Cut | 505 | 505 | 0 | 0 | -2500 | [11 empty] | 39 | Sep'1
UTG-(Even & Odd) | 42353 6th | BAD2529I | 1500 | 310 | 2026-06-27 | 2026-07-02 | LDS LEGGING W LACE | LEGGING |  |  | 2026-07-20 | 2026-07-17 | 2026-07-25 | 2026-08-06 |  |  | 2026-08-01 | 2026-07-30 |  | 2026-08-12 | 2026-08-14 | [6 empty] | 2026-08-17 | 2026-08-20 |  |  | 2026-08-22 | 2026-08-25 | 2026-08-26 | 2026-08-29 | 2026-08-31 | 63 | N/1 | Rony |  |  |  |  | Lace | NCL |  |  | Ready Test Cut | 310 | 260 | -50 | 0 | -1500 | [11 empty] | 36 | Aug'2
UTG-(Even & Odd) | 24246 13th | BAD1449T | 2000 | 440 | 2026-06-27 | 2026-07-02 | LDS LS TS W FUNCTIONAL STRING | TS |  |  | 2026-07-21 | 2026-07-31 | 2026-08-01 | 2026-08-10 |  |  | 2026-08-01 | 2026-08-01 |  | 2026-08-13 | 2026-08-15 | [6 empty] | 2026-08-18 | 2026-08-21 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-27 | 2026-08-29 | 2026-08-31 | 63 | N/3 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 440 | 440 | 0 | 0 | -2000 | [11 empty] | 36 | Aug'2
UTG-(Even & Odd) | 22738 10th | BAD1131S | 2000 | 466 | 2026-06-27 | 2026-07-02 | LDS LS BODYSUIT | SUIT |  |  | 2026-07-20 | 2026-07-28 | 2026-08-01 | 2026-08-08 |  |  | 2026-08-01 | 2026-08-01 |  | 2026-08-15 | 2026-08-17 | [6 empty] | 2026-08-20 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-31 | 63 | N/3 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 466 | 466 | 0 | 0 | -2000 | [11 empty] | 36 | Aug'2
UTG-(Even & Odd) | 41318 17th | BAD1571AF | 2600 | 654 | 2026-06-27 | 2026-07-02 | LDS CROPPED WRAP OVERLAP LS TS | TS |  |  | 2026-07-20 | 2026-07-30 | 2026-08-01 | 2026-08-10 |  |  | 2026-08-08 | 2026-08-08 |  | 2026-08-13 | 2026-08-15 | [6 empty] | 2026-08-17 | 2026-08-20 |  |  | 2026-08-22 | 2026-08-24 | 2026-08-25 | 2026-08-29 | 2026-08-31 | 63 | N/3 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 654 | 654 | 0 | 0 | -2600 | [11 empty] | 36 | Aug'2
UTG-(Even & Odd) | 24229 9th | BAD0965P | 1300 | 335 | 2026-06-27 | 2026-07-02 | LS v Nk TS | TS |  |  | 2026-08-01 | 2026-07-17 | 2026-08-03 | 2026-08-13 |  |  | 2026-08-01 | 2026-08-01 |  | 2026-08-15 | 2026-08-17 | [6 empty] | 2026-08-18 | 2026-08-20 |  |  | 2026-08-22 | 2026-08-24 | 2026-08-25 | 2026-08-29 | 2026-08-31 | 63 | N/1 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 335 | 335 | 0 | 0 | -1300 | [11 empty] | 36 | Aug'2
UTG-(Even & Odd) | 23325 17th | BAD0960BD/BAD0960BE | 6500 | 1572 | 2026-06-27 | 2026-07-02 | LS HIGH NK TS | TS |  |  | 2026-07-22 | 2026-07-25 | 2026-08-03 | 2026-08-15 |  |  | 2026-08-01 | 2026-08-01 |  | 2026-08-18 | 2026-08-20 | [6 empty] | 2026-08-20 | 2026-08-24 |  |  | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-29 | 2026-08-31 | 63 | G1 | Rony | [5 empty] | NFL1 |  |  | Cut Ok | 1572 | 1572 | 0 | 6705 | 205 | [11 empty] | 36 | Aug'2 |  |  | 13.07.26
UTG-(Even & Odd) | 45963 11th | BAD0962BQ/BAD0962BR | 16800 | 3859 | 2026-06-27 | 2026-07-02 | LDS LS R NK TS | TS |  |  | 2026-07-15 | 2026-07-28 | 2026-08-01 | 2026-08-15 |  |  | 2026-08-01 | 2026-07-26 |  | 2026-08-13 | 2026-08-19 | [6 empty] | 2026-08-18 | 2026-08-25 |  |  | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-29 | 2026-08-31 | 63 | ZA2 | Rony | [5 empty] | NFL3 |  |  | Cut Ok | 3859 | 3859 | 0 | 17431 | 631 | [11 empty] | 36 | Aug'2 |  |  | 14.07.26
UTG-(Even & Odd) | 24297 12th | BAD1112U | 1700 | 402 | 2026-06-27 | 2026-07-02 | LS v nk TS w metal btn | TS |  |  | 2026-07-20 | 2026-07-29 | 2026-08-03 | 2026-08-15 |  |  | 2026-08-06 | 2026-08-06 |  | 2026-08-19 | 2026-08-20 | [6 empty] | 2026-08-12 | 2026-08-25 |  |  | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-31 | 63 | N/3 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 402 | 402 | 0 | 0 | -1700 | [11 empty] | 36 | Aug'2
UTG-(Even & Odd) | 22698 16th | BAD1675R | 2400 | 660 | 2026-06-27 | 2026-07-02 | LDS LONG SKIRT W CUT & SEW | SKIRT |  |  | 2026-08-01 | 2026-07-25 | 2026-08-01 | 2026-08-07 |  |  | 2026-08-01 | 2026-07-30 |  | 2026-08-08 | 2026-08-10 | [6 empty] | 2026-08-11 | 2026-08-14 |  |  | 2026-08-17 | 2026-08-19 | 2026-08-22 | 2026-08-29 | 2026-08-31 | 63 | N1 | Rony | [5 empty] | NFL2 |  |  | Cut Ok | 660 | 660 | 0 | 0 | -2400 | [11 empty] | 36 | Aug'1 |  |  | 28.07.26
UTG-(Even & Odd) | 41645 10th | BAD2681H | 6000 | 1356 | 2026-06-27 | 2026-07-02 | Cropped LS TS w placket | TS |  |  | 2026-08-01 | 2026-07-16 | 2026-08-01 | 2026-08-10 |  |  | 2026-08-01 | 2026-08-01 |  | 2026-08-10 | 2026-08-13 | [6 empty] | 2026-08-13 | 2026-08-20 |  |  | 2026-08-22 | 2026-08-24 | 2026-08-26 | 2026-08-29 | 2026-08-31 | 63 | N1 | Rony | [5 empty] | NFL2 |  |  | Cut Ok | 1356 | 1356 | 0 | 6131 | 131 | [11 empty] | 36 | Aug'1 |  |  | 15.07.26
UTG-(Even & Odd) | 44047 12th | BAD0982AO | 15000 | 3668 | 2026-06-27 | 2026-07-02 | LDS LS BODYSUIT | SUIT |  |  | 2026-07-20 | 2026-08-01 | 2026-08-01 | 2026-08-18 |  |  | 2026-08-24 | 2026-08-25 |  | 2026-08-27 | 2026-08-31 | [6 empty] | 2026-09-01 | 2026-09-12 |  |  | 2026-09-14 | 2026-09-15 | 2026-09-17 | 2026-09-19 | 2026-09-21 | 84 | Q | Rony | [5 empty] | NFL2 |  |  | Cut Ok | 3668 | 3668 | 0 | 15477 | 477 | [11 empty] | 39 | Aug'3 |  |  | 17.07.26
UTG-(Even & Odd) | 24230 23th | BAD0966AF/BAD0966AG | 5500 | 1186 | 2026-06-27 | 2026-07-02 | LS TS w letus stitch | TS |  |  | 2026-08-01 | 2026-07-29 | 2026-08-03 | 2026-08-15 |  |  | 2026-08-06 | 2026-08-06 |  | 2026-08-17 | 2026-08-20 | [6 empty] | 2026-08-21 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-27 | 2026-08-29 | 2026-08-29 | 2026-08-31 | 63 | D1 | Rony | [5 empty] | NFL1 |  |  | Cut Ok | 1186 | 1186 | 0 | 5765 | 265 | [11 empty] | 36 | Aug'2 |  |  | 17.07.26
UTG-(Even & Odd) | 24241 16th | BAD0981Y | 2000 | 370 | 2026-06-27 | 2026-07-02 | LDS LS OFF SHOULDER TS | TS |  |  | 2026-08-01 | 2026-07-16 | 2026-07-25 | 2026-08-06 |  |  | 2026-08-01 | 2026-08-01 |  | 2026-08-06 | 2026-08-07 | [6 empty] | 2026-08-11 | 2026-08-12 |  |  | 2026-08-15 | 2026-08-18 | 2026-08-20 | 2026-08-29 | 2026-08-31 | 63 | N/1 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 370 | 370 | 0 | 0 | -2000 | [11 empty] | 36 | Aug'1
UTG-(Even & Odd) | 27711 14th | BAD25221M | 2000 | 685 | 2026-06-27 | 2026-07-02 | LDS SKIRT | Skirt |  |  | 2026-08-01 | 2026-07-20 | 2026-07-22 | 2026-08-04 |  |  | 2026-08-01 | 2026-07-27 |  | 2026-08-08 | 2026-08-10 | [6 empty] | 2026-08-13 | 2026-08-17 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-22 | 2026-08-29 | 2026-08-31 | 63 | N1 | Rony | [5 empty] | NFL2 |  |  | Cut Ok | 685 | 685 | 0 | 0 | -2000 | [11 empty] | 36 | Aug'1 |  |  | 28.07.26
BS-ONS | 47819 2nd | 22040527 | 942 | 492 | 2026-06-19 | 2026-07-03 | YD LS O nk TS | TS | 2026-08-01 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-24 | 2026-08-29 |  |  | 2026-09-09 | 2026-09-09 |  | 2026-09-16 | 2026-09-17 | [6 empty] | 2026-09-21 | 2026-09-22 |  |  | 2026-09-24 | 2026-09-26 | 2026-09-30 | 2026-10-17 | 2026-10-19 | 120 | G1 | Shakel |  |  |  | YD |  | NFL1 |  |  | Need Test Cut | 491 | 0 | -491 | 0 | -942 | [11 empty] | 43 | Sep'2 |  |  | 14.09.26
BS-ONS | 48193 | 22040861 | 543 | 105 | 2026-06-25 | 2026-07-06 | SS o nk TS w nk rib | TS |  |  | 2026-08-01 | 2026-08-04 | 2026-08-11 | 2026-08-24 |  |  | 2026-08-27 | 2026-08-27 | 2026-09-03 | 2026-09-05 | 2026-09-05 | 2026-09-08 | 2026-09-10 |  |  |  |  | 2026-09-14 | 2026-09-14 |  |  | 2026-09-16 | 2026-09-18 | 2026-09-22 | 2026-10-19 | 2026-10-21 | 116 | F | Shovon | Chest |  | silver lining-201 pcs,,white-156 pcs,,black-186 pcs all combo 1 clr pig print |  |  | NFL1 |  |  | Need Cut | 105 | 67 | -38 | 0 | -543 | [11 empty] | 43 | Sep'1 |  |  | 28.08.26
BS-ONS | 48192 | 22041780 | 846 | 143 | 2026-06-25 | 2026-07-06 | SS o nk TS w nk rib | TS |  |  | 2026-08-01 | 2026-08-04 | 2026-08-10 | 2026-08-24 |  |  | 2026-08-28 | 2026-08-28 | 2026-09-04 | 2026-09-07 | 2026-09-07 | 2026-09-09 | 2026-09-10 |  |  |  |  | 2026-09-12 | 2026-09-12 |  |  | 2026-09-14 | 2026-09-16 | 2026-09-19 | 2026-10-19 | 2026-10-21 | 116 | F | Shovon | Chest |  | silver lining-846 pcs 1 clr pig print |  |  | NFL1 |  |  | Need Cut | 141 | 94 | -47 | 0 | -846 | [11 empty] | 43 | Sep'1 |  |  | 28.08.26
BS-ONL | 48160 | 15317989 | 4647 | 703 | 2026-06-24 | 2026-06-30 | SS o nk TS | TS |  |  | 2026-08-01 | 2026-08-06 | 2026-08-10 | 2026-08-25 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-31 | 2026-09-02 | 2026-09-04 |  |  |  |  | 2026-09-04 | 2026-09-09 | 2026-09-11 | 2026-09-16 |  |  | 2026-09-18 | 2026-09-21 | 2026-09-23 | 2026-10-12 | 2026-10-14 | 110 | N1 | Mainul |  | Chest | black-2199 pcs 6 clr flat emb at chest,,green-816 pcs 5 clr flat emb at pkt,,pink-816 pcs 6 clr flat emb at pkt ,,pumic-816 pcs 6 clr flat emb at pkt |  |  | NFL2 |  |  | Cut Ok | 702 | 696 | -6 | 4775 | 128 | [11 empty] | 42 | Sep'1 |  |  | 07.08.26
BS-ONL | 44114 7th | 15369240 | 4800 | 885 | 2026-06-26 | 2026-06-30 | SS o nk TS | TS | 2026-08-24: 2026-07-22; 2026-08-29: 2026-08-04 |  |  | 2026-08-08 | 2026-08-08 |  | 2026-08-12 | 2026-08-14 | 2026-08-15 | 2026-08-17 |  |  |  |  | 2026-08-18 | 2026-08-21 |  |  | 2026-08-24 | 2026-08-26 | 2026-08-31 | 2026-10-12 | 2026-10-14 | 108 | G1 | Imran | Nk |  | 5 combo label print |  |  | NFL1 |  |  | Cut Ok | 885 | 885 | 0 | 4934 | 134 | [11 empty] | 42 | Aug'2 |  |  | 07.08.26
BS-ONL | 44198 5th | 15337134 | 11871 | 4636 | 2026-06-26 | 2026-07-03 | YD LS o nk TS | TS | 2026-07-20 | 2026-08-04 | 2026-08-03 | 2026-08-20 | 2026-08-20 | 2026-08-31 |  |  | 2026-09-05 | 2026-09-05 |  | 2026-09-12 | 2026-09-18 | [6 empty] | 2026-09-18 | 2026-09-28 |  |  | 2026-09-30 | 2026-10-02 | 2026-10-05 | 2026-10-12 | 2026-10-14 | 108 | M | Imran |  |  |  | YD |  | NFL2 |  |  | Cut Run | 4638 | 3609 | -1029 | 9482 | -2389 | [11 empty] | 42 | Sep'2 |  |  | 13.08.26
BS-ONL | 48155 | 15390607 | 6836 | 2123 | 2026-06-24 | 2026-06-30 | LS o nk TS w btm Lace attach | TS |  |  | 2026-08-01 | 2026-08-08 | 2026-08-12 | 2026-08-31 |  |  | 2026-09-03 | 2026-09-03 | 2026-09-09 | 2026-09-12 | 2026-09-15 | [6 empty] | 2026-09-17 | 2026-09-23 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-30 | 2026-10-19 | 2026-10-21 | 117 | K | Zahirul |  |  |  |  | Lace | NFL2 |  |  | Cut Ok | 2113 | 2113 | 0 | 6936 | 100 | [11 empty] | 43 | Sep'2 |  |  | 27.08.26
BS-ONL | 48182 | 15342184 | 1782 | 1170 | 2026-06-24 | 2026-07-01 | Long loose ottoman rib pant | Pant |  |  | 2026-07-25 | 2026-08-14 | 2026-08-17 | 2026-09-02 |  |  | 2026-09-05 | 2026-09-05 | 2026-09-12 | 2026-09-16 | 2026-09-17 | [6 empty] | 2026-09-21 | 2026-09-24 |  |  | 2026-09-26 | 2026-09-29 | 2026-10-03 | 2026-10-19 | 2026-10-21 | 117 | M | Zahirul | [5 empty] | NFL2 |  |  | Need Test Cut | 0 | 0 | 0 | 0 | -1782 | [11 empty] | 43 | Sep'2 |  |  | 25.08.26
BS-ONL | 48184 | 15380916 | 3669 | 1805 | 2026-06-24 | 2026-07-01 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-07-13 | 2026-07-20 | 2026-07-23 | 2026-08-10 |  |  | 2026-08-12 | 2026-08-12 | 2026-08-18 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 2026-08-29 |  |  | 2026-09-01 | 2026-09-04 | 2026-09-05 | 2026-09-09 |  |  | 2026-09-10 | 2026-09-12 | 2026-09-15 | 2026-10-19 | 2026-10-21 | 117 | N2 | Zahirul | Chest | Chest | orchid-1299 pcs 1 clr HD print and 1 clr flat emb,,blue-975 pcs 1 clr HD print and 1 clr flat emb,,brown-1395 pcs 1 clr rub 1 clr puff and no emb |  |  | NFL2 |  |  | Cut Run | 1805 | 1784 | -21 | 3484 | -185 | [11 empty] | 43 | Aug'2 |  |  | 25.08.26
BS-ONL | 48129 | 15393712 | 600 | 160 | 2026-06-17 | 2026-06-30 | LS o nk TS w btm Lace attach | TS |  |  | 2026-08-01 | 2026-08-06 | 2026-08-15 | 2026-08-31 |  |  | 2026-09-05 | 2026-09-05 | 2026-09-11 | 2026-09-14 | 2026-09-14 | [6 empty] | 2026-09-17 | 2026-09-18 |  |  | 2026-09-21 | 2026-09-23 | 2026-09-26 | 2026-10-12 | 2026-10-14 | 117 | K | Zahirul |  |  |  |  | Lace | NFL2 |  |  | Cut Ok | 160 | 160 | 0 | 637 | 37 | [11 empty] | 42 | Sep'2 |  |  | 15.08.26
BS-ONL | 48126 | 15393661 | 324 | 200 | 2026-06-17 | 2026-07-01 | Elaste flared pant | Pant |  |  | 2026-08-04 | 2026-08-14 | 2026-08-18 | 2026-08-31 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-14 | 2026-09-17 | 2026-09-17 | [6 empty] | 2026-09-21 | 2026-09-22 |  |  | 2026-09-24 | 2026-09-26 | 2026-09-30 | 2026-10-12 | 2026-10-14 | 117 | M | Zahirul | [5 empty] | NFL2 |  |  | Need Test Cut | 200 | 0 | -200 | 0 | -324 | [11 empty] | 42 | Sep'2 |  |  | 27.08.26
BS-ONL | 48211 | 15387513 | 684 | 109 | 2026-06-19 | 2026-07-01 | LS o nk TS | TS |  |  | 2026-08-04 | 2026-08-07 | 2026-08-11 | 2026-08-25 |  |  | 2026-08-27 | 2026-08-27 | 2026-09-02 | 2026-09-05 | 2026-09-05 | [6 empty] | 2026-09-09 | 2026-09-10 |  |  | 2026-09-14 | 2026-09-16 | 2026-09-23 | 2026-10-19 | 2026-10-21 | 122 | O2 | Abid | [5 empty] | NFL2 |  |  | Cut Run | 109 | 109 | 0 | 397 | -287 | [11 empty] | 43 | Sep'1 |  |  | 31.08.26
BS-ONL | 48209 | 15364878 | 2592 | 238 | 2026-06-20 | 2026-07-01 | SS o nk TS w blind stitch | TS |  |  | 2026-07-20 | 2026-07-27 | 2026-08-01 | 2026-08-16 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-26 | 2026-08-28 | 2026-08-29 |  |  |  |  | 2026-09-01 | 2026-09-04 | 2026-09-07 | 2026-09-10 |  |  | 2026-09-12 | 2026-09-15 | 2026-09-19 | 2026-10-19 | 2026-10-21 | 121 | O2 | Abid |  | Chest | Orchid-422 pcs 2 clr flat emb ,,soft-386 pcs 6 clr flat emb ,,c.dancer-518 pcs 4-5 clr flat emb,,rose-578 pcs 5-6 clr flat emb ,,purple-698 pcs 7 clr flat emb |  | Emb Artwork due | NFL2 |  |  | PPM Due | 237 | 237 | 0 | 0 | -2592 | [11 empty] | 43 | Aug'3 |  |  | 31.08.26
BS-ONL | 48213 | 15387825 | 1216 | 433 | 2026-06-20 | 2026-07-01 | LS swt shirt w mk cuff bm rib | Swt Shirt |  |  | 2026-07-18 | 2026-07-24 | 2026-07-27 | 2026-08-15 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-22 | 2026-08-24 | 2026-08-25 | 2026-08-27 | 2026-08-31 |  |  |  |  | 2026-09-04 | 2026-09-07 |  |  | 2026-09-09 | 2026-09-12 | 2026-09-15 | 2026-10-19 | 2026-10-21 | 121 | N2 | Abid | Fr,Bk |  | voilet-694 pcs frt back 1 clr rub 2 clr High rub print ,,dream-526 pcs frt 1 clr high rub print back 2 clr rub 1 clr high rub |  |  | NFL2 |  |  | Cut Ok | 433 | 391 | -42 | 1265 | 49 | [11 empty] | 43 | Aug'3 |  |  | 21.08.26
BS-ONL | 48210 | 15383657 | 852 | 309 | 2026-06-20 | 2026-07-01 | Adjustable wiast belt rib legging | Legging |  |  | 2026-08-04 | 2026-08-10 | 2026-08-15 | 2026-08-27 |  |  | 2026-09-02 | 2026-09-02 | 2026-09-08 | 2026-09-11 | 2026-09-12 | [6 empty] | 2026-09-15 | 2026-09-16 |  |  | 2026-09-18 | 2026-09-22 | 2026-09-25 | 2026-10-19 | 2026-10-21 | 121 | P | Abid | [5 empty] | NFL2 |  |  | Cut Ok | 309 | 309 | 0 | 908 | 56 | [11 empty] | 43 | Sep'2 |  |  | 03.09.26
BS-ONL | 48207 | 15347335 | 2433 | 441 | 2026-06-20 | 2026-07-01 | SS o nk TS w blind stitch | TS |  |  | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-18 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-26 | 2026-08-28 | 2026-08-29 | 2026-09-02 | 2026-09-05 |  |  |  |  | 2026-09-08 | 2026-09-11 |  |  | 2026-09-14 | 2026-09-16 | 2026-09-18 | 2026-10-19 | 2026-10-21 | 121 | O2 | Abid | Fr,Bk |  | pink-1859 pcs frt 2 clr rub back 7 clr rub ,,c.dan-578 pcs frt 2 clr rub back 3 clr rub |  |  | NFL2 |  |  | Cut Ok | 441 | 417 | -24 | 2511 | 78 | [11 empty] | 43 | Aug'3 |  |  | 22.08.26
BS-ONL | 48208 | 15364629 | 780 | 301 | 2026-06-20 | 2026-07-01 | LS swt shirt cut&sew contrast at front back and slve w cuff btm rib | Swt Shirt |  |  | 2026-07-20 | 2026-07-26 | 2026-08-04 | 2026-08-20 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-28 | 2026-09-01 | 2026-09-02 | 2026-09-04 | 2026-09-07 |  |  |  |  | 2026-09-09 | 2026-09-11 |  |  | 2026-09-14 | 2026-09-17 | 2026-09-22 | 2026-10-19 | 2026-10-21 | 121 | R | Abid | Chest |  | black-780 pcs 1 clr rub on gltr print |  |  | NFL2 |  |  | CAD | 302 | 0 | -302 | 0 | -780 | [11 empty] | 43 | Sep'1 |  |  | 14.09.26
BS-ONL | 48206 | 15346421 | 23754 | 2969 | 2026-06-20 | 2026-07-06 | AOP SS o nk TS | TS |  |  | 2026-07-15 | 2026-08-06 | 2026-08-10 | 2026-08-24 | 2026-08-24 | 2026-09-05 | 2026-09-07 | 2026-09-07 | 2026-09-12 | 2026-09-16 | 2026-09-21 | [6 empty] | 2026-09-21 | 2026-09-28 |  |  | 2026-09-30 | 2026-10-03 | 2026-10-05 | 2026-10-17 | 2026-10-19 | 119 | ZA1 | Abid |  |  |  | AOP |  | NFL3 |  |  | CAD | 2971 | 2730 | -241 | 0 | -23754 | [11 empty] | 43 | Sep'2 |  |  | 15.09.26
OVS SPA | 47927 | 271TSH006-222 | 6549 | 966 | 2026-06-21 | 2026-07-04 | SS o nk TS w side shlder contrast cut & sew pannel | TS |  |  | 2026-08-15 | 2026-08-25 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-17 | 2026-09-09 | 2026-09-16 | 2026-09-17 | 2026-09-19 | 2026-09-21 | 2026-09-26 |  |  |  |  | 2026-09-26 | 2026-09-30 |  |  | 2026-10-01 | 2026-10-03 | 2026-10-05 | 2026-10-12 | 2026-10-12 | 113 | G1 | Shaker | Chest |  | Olive-6549 pcs 4 clr rub 2 clr HD print |  |  | NFL1 |  |  | Size Set Run S/J Fab Due | 998 | 755 | -243 | 0 | -6549 | [11 empty] | 42 | Sep'2 |  |  | 04.09.26
OVS SPA | 48142 | 271TROFTB90-6172 | 5339 | 2603 | 2026-06-24 | 2026-07-04 | Trouser w side pkt and drawstring w metal eyelet | Trouser |  |  | 2026-08-15 | 2026-08-27 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-12 | 2026-09-12 | 2026-09-17 | 2026-09-18 | 2026-09-21 | [6 empty] | 2026-09-22 | 2026-09-30 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-06 | 2026-10-06 | 104 | H | Shaker | [5 empty] | NFL1 |  |  | Need Cut | 2687 | 2486 | -201 | 0 | -5339 | [11 empty] | 41 | Sep'2 |  |  | 04.09.26
OVS SPA | 48143 | 271SWTFTT513-6172 | 6939 | 3921 | 2026-06-23 | 2026-07-04 | Ls High nk Full zipper Swt Shirt w side slit | Swt Shirt |  |  | 2026-08-15 | 2026-08-31 | 2026-08-31 | 2026-09-14 |  |  | 2026-09-10 | 2026-09-11 | 2026-09-17 | 2026-09-18 | 2026-09-19 | [6 empty] | 2026-09-22 | 2026-09-29 |  |  | 2026-09-30 | 2026-10-01 | 2026-10-03 | 2026-10-06 | 2026-10-06 | 105 | B | Shaker | [5 empty] | NFL1 |  |  | Need Cut | 3920 | 3478 | -442 | 0 | -6939 | [11 empty] | 41 | Sep'2 |  |  | 04.09.26
OVS SPA | 48144 | 271SWTFTT524-6172 | 3626 | 1525 | 2026-06-23 | 2026-07-04 | LS boat nk Swt Shirt w side slit | Swt Shirt |  |  | 2026-08-15 | 2026-08-27 | 2026-09-01 | 2026-09-14 |  |  | 2026-09-15 | 2026-09-14 | 2026-09-19 | 2026-09-21 | 2026-09-22 | [6 empty] | 2026-09-23 | 2026-09-29 |  |  | 2026-09-30 | 2026-10-01 | 2026-10-03 | 2026-10-06 | 2026-10-06 | 105 | A | Shaker | [5 empty] | NFL1 |  |  | Need Cut | 1622 | 1418 | -204 | 0 | -3626 | [11 empty] | 41 | Sep'3 |  |  | 04.09.26
OVS SPA | 48246 | 271SWTFTT521-6172 | 4239 | 885 | 2026-06-25 | 2026-07-04 | SS TS w side rib insert w gmts dye acid wash | TS |  |  | 2026-08-15 | 2026-08-25 | 2026-09-01 | 2026-09-14 |  |  | 2026-09-21 | 2026-09-17 | 2026-09-26 | 2026-09-28 | 2026-09-30 | [6 empty] | 2026-10-01 | 2026-10-05 | 2026-10-05 | 2026-10-12 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-16 | 2026-10-16 | 113 | G2 | Shaker |  |  |  |  | Gmts dye acid wash | NFL1 |  |  | Need Cut | 630 | 297 | -333 | 0 | -4239 | [11 empty] | 42 | Sep'3 |  |  | 04.09.26
BS-ONS | 48147 | 22039020 | 1662 | 1079 | 2026-06-19 | 2026-07-03 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-08-01 | 2026-08-10 | 2026-08-15 | 2026-08-31 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-14 | 2026-09-16 | 2026-09-17 | 2026-09-21 | 2026-09-24 |  |  |  |  | 2026-09-28 | 2026-09-30 |  |  | 2026-10-03 | 2026-10-06 | 2026-10-10 | 2026-11-08 | 2026-11-10 | 142 | A | Shakel | Fr,Bk |  | forest-617 pcs,,black-1061 pcs both combo frt back 1 clr puff print |  |  | NFL1 |  |  | CAD | 1079 | 0 | -1079 | 0 | -1662 | [11 empty] | 46 | Sep'2 |  |  | 12.09.26
BS-ONS | 48148 | 22040530 | 390 | 149 | 2026-06-19 | 2026-07-03 | Swt shorts pant w side back pkt | Shorts |  |  | 2026-08-04 | 2026-08-10 | 2026-08-15 | 2026-08-31 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-14 | 2026-09-17 | 2026-09-17 | 2026-09-21 | 2026-09-22 |  |  |  |  | 2026-09-25 | 2026-09-26 |  |  | 2026-06-29 | 2026-10-02 | 2026-10-06 | 2026-11-09 | 2026-11-11 | 143 | C | Shakel | Thigh |  | black-398 pcs 1 clr HD print |  |  | NFL1 |  |  | File Due | 149 | 0 | -149 | 0 | -390 | [11 empty] | 46 | Sep'2
BS-ONS | 48149 | 22040756 | 2146 | 472 | 2026-06-19 | 2026-07-03 | SS o nk TS w nk rib | TS |  |  | 2026-08-01 | 2026-08-07 | 2026-08-13 | 2026-08-28 |  |  | 2026-09-02 | 2026-09-02 | 2026-09-08 | 2026-09-11 | 2026-09-12 | 2026-09-15 | 2026-09-18 |  |  |  |  | 2026-09-21 | 2026-09-23 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-30 | 2026-11-09 | 2026-11-11 | 143 | D1 | Shakel | Chest |  | black-740 pcs,,silver lining-690 pcs,,white-740 pcs all combo 1 clr pig print |  |  | NFL1 |  |  | Need Cut | 472 | 150 | -322 | 0 | -2146 | [11 empty] | 46 | Sep'2 |  |  | 12.09.26
BS-ONS | 44076 18th | 22013782 | 14070 | 3097 | 2026-06-23 | 2026-07-03 | SS T Shirt | TS |  |  | 2026-07-16 | 2026-07-28 | 2026-08-03 | 2026-08-20 |  |  | 2026-08-20 | 2026-08-20 |  | 2026-08-25 | 2026-08-29 | [6 empty] | 2026-09-01 | 2026-09-07 |  |  | 2026-09-10 | 2026-09-12 | 2026-09-16 | 2026-11-09 | 2026-11-11 | 139 | F | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 3096 | 3084 | -12 | 14581 | 511 | [11 empty] | 46 | Aug'3 |  |  | 19.08.26
BS-ONS | 44076 19th | 22013782 | 9648 | 2113 | 2026-06-26 | 2026-07-03 | SS T Shirt | TS |  |  | 2026-07-18 | 2026-07-30 | 2026-08-06 | 2026-08-22 |  |  | 2026-08-22 | 2026-08-22 |  | 2026-08-27 | 2026-08-31 | [6 empty] | 2026-09-03 | 2026-09-07 |  |  | 2026-09-10 | 2026-09-12 | 2026-09-16 | 2026-11-09 | 2026-11-11 | 136 | F | Shakel | [5 empty] | NFL1 |  |  | Need Cut | 2115 | 2071 | -44 | 0 | -9648 | [11 empty] | 46 | Aug'3 |  |  | 19.08.26
BS-ONS | 44945 5th | 22036392 | 1876 | 700 | 2026-06-19 | 2026-07-03 | MENS BK & CUT SEW TS | TS |  |  | 2026-08-04 | 2026-08-15 | 2026-08-23 | 2026-09-08 |  |  | 2026-09-12 | 2026-09-12 |  | 2026-09-18 | 2026-09-19 | [6 empty] | 2026-09-23 | 2026-09-26 |  |  | 2026-09-29 | 2026-10-02 | 2026-10-08 | 2026-11-09 | 2026-11-11 | 143 | A | Shakel | [5 empty] | NFL1 |  |  | CAD | 700 | 700 | 0 | 0 | -1876 | [11 empty] | 46 | Sep'2 |  |  | 15.09.26
BS-ONS | 48146 | 22036387 | 7015 | 2932 | 2026-06-19 | 2026-07-03 | SS Shirt w frt collar placket btn | Shirt |  |  | 2026-08-01 | 2026-08-13 | 2026-08-18 | 2026-09-08 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-23 | 2026-09-26 | 2026-09-30 | [6 empty] | 2026-10-02 | 2026-10-10 |  |  | 2026-10-13 | 2026-10-15 | 2026-10-17 | 2026-11-28 | 2026-11-30 | 162 | B | Shakel | [5 empty] | NFL1 |  |  | CAD | 2932 | 2932 | 0 | 0 | -7015 | [11 empty] | 49 | Sep'3 |  |  | 15.09.26
BS-ONS | 48152 | 22028694 | 3168 | 1091 | 2026-06-19 | 2026-07-03 | SS Polo shirt w collar placket btn | Polo |  |  | 2026-08-01 | 2026-08-10 | 2026-08-18 | 2026-09-05 |  |  | 2026-09-12 | 2026-09-12 | 2026-09-19 | 2026-09-23 | 2026-09-26 | [6 empty] | 2026-10-01 | 2026-10-05 |  |  | 2026-10-07 | 2026-10-09 | 2026-10-13 | 2026-11-09 | 2026-11-11 | 143 | B | Shakel | [5 empty] | NFL1 |  |  | CAD | 1092 | 1092 | 0 | 0 | -3168 | [11 empty] | 46 | Sep'3 |  |  | 15.09.26
BS-ONS | 48153 | 22028692/22042219 | 33685 | 10086 | 2026-06-19 | 2026-07-03 | SS o nk TS w nk rib | TS |  |  | 2026-07-18 | 2026-08-04 | 2026-08-06 | 2026-08-25 |  |  | 2026-08-27 | 2026-08-27 | 2026-09-03 | 2026-09-05 | 2026-09-12 | [6 empty] | 2026-09-10 | 2026-09-22 |  |  | 2026-09-25 | 2026-09-28 | 2026-10-05 | 2026-11-09 | 2026-11-11 | 143 | F | Shakel | [5 empty] | NFL1 |  |  | Need Cut | 10086 | 10086 | 0 | 0 | -33685 | [11 empty] | 46 | Sep'1 |  |  | 12.09.26
BS-ONS | 48194 | 22040939 | 822 | 208 | 2026-06-25 | 2026-07-06 | Waist belt Shorts w side back pkt and tip drawstring | Shorts |  |  | 2026-08-01 | 2026-08-06 | 2026-08-13 | 2026-08-30 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-15 | 2026-09-18 | 2026-09-19 | 2026-09-22 | 2026-09-24 |  |  |  |  | 2026-09-26 | 2026-09-28 |  |  | 2026-09-30 | 2026-10-02 | 2026-10-06 | 2026-11-16 | 2026-11-18 | 144 | C | Shovon | Thigh |  | forest fog-822 pcs 1 clr HD print |  |  | NFL1 |  |  | Need Test Cut | 208 | 0 | -208 | 0 | -822 | [11 empty] | 47 | Sep'2 |  |  | 11.09.26
BS-ONL | 48173 | 15387024 | 7494 | 1874 | 2026-06-24 | 2026-07-03 | LS double layer o nk TS w dtm slvee lace | TS |  |  | 2026-07-25 | 2026-08-03 | 2026-08-10 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-26 | 2026-09-04 | 2026-09-07 | 2026-09-10 | [6 empty] | 2026-09-10 | 2026-09-18 |  |  | 2026-09-22 | 2026-09-24 | 2026-09-28 | 2026-11-09 | 2026-11-11 | 138 | J | Jannati |  |  |  |  | Lace | NFL2 |  |  | Cut Run | 1874 | 1262 | -612 | 5117 | -2377 | [11 empty] | 46 | Sep'1 |  |  | 12.08.26
BS-ONL | 48172 | 15388038 | 4023 | 978 | 2026-06-24 | 2026-07-03 | LS wrap cardigan w side waist self strap knot | Cardigan |  |  | 2026-07-25 | 2026-08-03 | 2026-08-08 | 2026-08-23 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-31 | 2026-09-02 | 2026-09-04 | 2026-09-04 | 2026-09-06 |  |  |  |  | 2026-09-07 | 2026-09-11 |  |  | 2026-09-14 | 2026-09-16 | 2026-09-22 | 2026-11-07 | 2026-11-09 | 136 | V | Jannati | Nk |  | 6 combo nk 1 clr rub print |  |  | NFL3 |  |  | Need Cut | 978 | 978 | 0 | 0 | -4023 | [11 empty] | 46 | Sep'1 |  |  | 14.07.26
BS-ONL | 44916 2nd | 15365759 | 5784 | 690 | 2026-06-24 | 2026-07-03 | SS V NK TS w lace at nk anf front ruching | TS |  |  | 2026-08-01 | 2026-08-07 | 2026-08-12 | 2026-08-28 |  |  | 2026-09-03 | 2026-09-03 | 2026-09-10 | 2026-09-14 | 2026-09-16 | 2026-09-16 | 2026-09-19 |  |  |  |  | 2026-09-18 | 2026-09-24 |  |  | 2026-09-26 | 2026-09-29 | 2026-10-02 | 2026-11-09 | 2026-11-11 | 138 | N2 | Jannati | Nk |  | 5 combo nk 1 clr rub print |  | Lace | NFL2 |  |  | Need Cut | 690 | 690 | 0 | 0 | -5784 | [11 empty] | 46 | Sep'2 |  |  | 23.07.26
BS-ONL | 48174 | 15389012 | 5838 | 866 | 2026-06-24 | 2026-07-03 | SS o nk TS | TS |  |  | 2026-07-25 | 2026-07-31 | 2026-08-04 | 2026-08-20 |  |  | 2026-08-27 | 2026-08-27 | 2026-09-02 | 2026-09-05 | 2026-09-08 | 2026-09-09 | 2026-09-14 |  |  |  |  | 2026-09-17 | 2026-09-22 |  |  | 2026-09-24 | 2026-09-26 | 2026-09-30 | 2026-11-07 | 2026-11-09 | 136 | L1 | Jannati | Chest |  | LGM-1424 pcs,,c.dan-2234 pcs,,black-2180 pcs all combo 1 clr rub print |  |  | NFL2 |  |  | Cut Ok | 866 | 866 | 0 | 6052 | 214 | [11 empty] | 46 | Sep'1 |  |  | 09.07.26
BS-ONL | 48166 | 15395552 | 1188 | 254 | 2026-06-24 | 2026-06-30 | SS o nk TS | TS |  |  | 2026-08-01 | 2026-08-04 | 2026-08-10 | 2026-08-22 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-27 | 2026-09-01 | 2026-09-02 | 2026-09-04 | 2026-09-07 |  |  |  |  | 2026-09-10 | 2026-09-12 |  |  | 2026-09-15 | 2026-09-17 | 2026-09-22 | 2026-11-09 | 2026-11-11 | 138 | O2 | Mainul | Chest |  | black-1188 pcs 1 clr pig 1 clr foil print |  |  | NFL2 |  |  | Ready Test Cut | 254 | 241 | -13 | 0 | -1188 | [11 empty] | 46 | Sep'1 |  |  | 04.09.26
BS-ONL | 48165 | 15395288 | 4450 | 690 | 2026-06-24 | 2026-06-30 | SS o nk TS w slve fold tuck | TS |  |  | 2026-08-01 | 2026-08-06 | 2026-08-13 | 2026-08-28 |  |  | 2026-09-01 | 2026-09-01 | 2026-09-07 | 2026-09-09 | 2026-09-11 | [6 empty] | 2026-09-14 | 2026-09-18 |  |  | 2026-09-22 | 2026-09-25 | 2026-09-30 | 2026-11-09 | 2026-11-11 | 138 | N1 | Mainul | [5 empty] | NFL2 |  |  | Need Cut | 690 | 273 | -417 | 0 | -4450 | [11 empty] | 46 | Sep'1 |  |  | 04.09.26
BS-ONL | 48163 | 15339894 | 2808 | 434 | 2026-06-24 | 2026-06-30 | SS o nk TS w slve fold tuck | TS |  |  | 2026-08-01 | 2026-08-06 | 2026-08-10 | 2026-08-25 |  |  | 2026-08-27 | 2026-08-27 | 2026-09-03 | 2026-09-05 | 2026-09-07 |  |  |  |  | 2026-09-09 | 2026-09-12 | 2026-09-16 | 2026-09-19 |  |  | 2026-09-22 | 2026-09-24 | 2026-09-28 | 2026-11-09 | 2026-11-11 | 138 | N1 | Mainul |  | Chest | c.dan-1404 pcs,,mermaid-1404 pcs both combo 1 clr flat emb |  |  | NFL2 |  |  | Cut Run | 434 | 416 | -18 | 684 | -2124 | [11 empty] | 46 | Sep'1 |  |  | 04.09.26
BS-ONL | 48164 | 15394945 | 4539 | 670 | 2026-06-24 | 2026-06-30 | SS o nk TS w slve fold tuck | TS |  |  | 2026-08-01 | 2026-08-06 | 2026-08-10 | 2026-08-24 |  |  | 2026-08-25 | 2026-08-25 | 2026-09-01 | 2026-09-03 | 2026-09-05 | 2026-09-07 | 2026-09-11 |  |  |  |  | 2026-09-14 | 2026-09-18 |  |  | 2026-09-21 | 2026-09-23 | 2026-09-26 | 2026-11-09 | 2026-11-11 | 138 | O2 | Mainul | Chest |  | black-1713 pcs,,c.dan pink-1413 pcs,,c.dan gold-1413 pcs all combo 2 clr gltr print |  |  | NFL2 |  |  | Cut Run | 670 | 634 | -36 | 4505 | -34 | [11 empty] | 46 | Sep'1 |  |  | 04.09.26
BS-ONL | 22035 72th | 15095808 | 2124 | 303 | 2026-06-26 | 2026-07-04 | Tank Top | Tank Top |  |  | 2026-08-01 | 2026-08-06 | 2026-08-13 | 2026-08-26 |  |  | 2026-09-01 | 2026-09-01 |  | 2026-09-09 | 2026-09-10 | [6 empty] | 2026-09-15 | 2026-09-17 |  |  | 2026-09-19 | 2026-09-22 | 2026-09-25 | 2026-11-09 | 2026-11-09 | 136 | ZA2 | Imran | [5 empty] | NFL3 |  |  | Need Cut | 303 | 303 | 0 | 0 | -2124 | [11 empty] | 46 | Sep'1 |  |  | 10.08.26
BS-ONL | 48187 | 15395066 | 504 | 150 | 2026-06-20 | 2026-07-06 | LS v nk TS w nk lace and front ruching | TS |  |  | 2026-08-06 | 2026-08-13 | 2026-08-18 | 2026-08-21 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-15 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-22 |  |  |  |  | 2026-09-23 | 2026-09-24 |  |  | 2026-09-26 | 2026-09-29 | 2026-10-05 | 2026-11-16 | 2026-11-18 | 149 | N1 | Zahirul | Nk |  | 1 combo nk 1 clr rub print print |  |  | NFL2 |  |  | Size Set Run | 150 | 150 | 0 | 0 | -504 | [11 empty] | 47 | Sep'2 |  |  | 12.09.26
BS-ONL | 48217 | 15368599 | 12636 | 1475 | 2026-06-20 | 2026-07-06 | SS TS w blind stitch | TS |  |  | 2026-07-23 | 2026-07-31 | 2026-08-06 | 2026-08-22 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-31 | 2026-09-02 | 2026-09-06 |  |  |  |  | 2026-09-03 | 2026-09-20 | 2026-09-18 | 2026-09-26 |  |  | 2026-09-28 | 2026-09-30 | 2026-10-07 | 2026-11-23 | 2026-11-25 | 156 | O2 | Abid |  | AOE | blue-698 pcs front both slve 1 clr flat all over emb ..c.dan-1754 pcs front both slve 2 clr flat all over emb ,,white heart -5762 pcs front both slve 2 clr flat all over emb ,,white cheery -4430 pcs front both slve 3 clr flat all over emb |  |  | NFL2 |  |  | Cut Run | 1476 | 1476 | 0 | 12161 | -475 | [11 empty] | 48 | Sep'1 |  |  | 21.08.26
BS-ONL | 48218 | 15387480 | 3884 | 467 | 2026-06-20 | 2026-07-06 | SS TS w both slve and front wovem emb lace | TS |  |  | 2026-08-01 | 2026-08-07 | 2026-08-15 | 2026-08-31 |  |  | 2026-09-06 | 2026-09-06 | 2026-09-12 | 2026-09-16 | 2026-09-19 | [6 empty] | 2026-09-21 | 2026-09-26 |  |  | 2026-09-29 | 2026-10-03 | 2026-10-10 | 2026-11-23 | 2026-11-25 | 156 | Q | Abid |  |  |  |  | Lace | NFL2 |  |  | File Due | 467 | 462 | -5 | 0 | -3884 | [11 empty] | 48 | Sep'2
BS-ONL | 48223 | 15387837 | 3255 | 452 | 2026-06-20 | 2026-07-06 | SS TS w blind stitch | TS |  |  | 2026-07-26 | 2026-08-03 | 2026-08-10 | 2026-08-25 |  |  | 2026-08-28 | 2026-08-28 | 2026-09-05 | 2026-09-08 | 2026-09-09 | 2026-09-11 | 2026-09-14 |  |  |  |  | 2026-09-17 | 2026-09-21 |  |  | 2026-09-23 | 2026-09-25 | 2026-09-28 | 2026-11-23 | 2026-11-25 | 156 | O2 | Abid | Fr,Bk |  | pink-1152 pcs frt 1 clr rub back 3 clr rub ,,c.dan-810 pcs frt 1 clr rub back 2 clr rub ,,orchid-1299 pcs frt 1 clr rub back 2 clr rub |  |  | NFL2 |  |  | Cut Ok | 453 | 453 | 0 | 3354 | 99 | [11 empty] | 48 | Sep'1 |  |  | 21.08.26
OVS SPA | 47775 | 271TROFTB114-6172 | 2800 | 1183 | 2026-06-24 | 2026-07-04 | Waist band rib legging | Legging |  |  | 2026-09-18 | 2026-09-30 | 2026-10-01 | 2026-10-13 |  |  | 2026-10-20 | 2026-10-17 | 2026-10-22 | 2026-10-23 | 2026-10-24 | [6 empty] | 2026-10-27 | 2026-10-31 |  |  | 2026-11-02 | 2026-11-04 | 2026-11-06 | 2026-11-09 | 2026-11-09 | 138 | E | Shaker | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -2800 | [11 empty] | 46 | Oct'3
OVS SPA | 48156 | 271TSHFTT102-6172 | 2813 | 455 | 2026-06-25 | 2026-07-04 | SS TS w mesh Fabric cut& sew | TS |  |  | 2026-09-18 | 2026-09-30 | 2026-10-01 | 2026-10-14 |  |  | 2026-10-17 | 2026-10-17 | 2026-10-22 | 2026-10-23 | 2026-10-24 | [6 empty] | 2026-10-26 | 2026-10-30 |  |  | 2026-10-31 | 2026-11-02 | 2026-11-04 | 2026-11-09 | 2026-11-09 | 137 | N/3 | Shaker |  |  |  |  | Mesh | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -2813 | [11 empty] | 46 | Oct'3
OVS SPA | 48157 | 271TSHFTT220-6172 | 2117 | 468 | 2026-06-25 | 2026-07-04 | SS TS w mesh Fabric cut& sew at nk | TS |  |  | 2026-09-18 | 2026-09-30 | 2026-10-01 | 2026-10-14 |  |  | 2026-10-17 | 2026-10-17 | 2026-10-22 | 2026-10-23 | 2026-10-24 | [6 empty] | 2026-10-26 | 2026-10-30 |  |  | 2026-11-02 | 2026-11-04 | 2026-11-06 | 2026-11-09 | 2026-11-09 | 137 | N/3 | Shaker |  |  |  |  | Mesh | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -2117 | [11 empty] | 46 | Oct'3
OVS SPA | 48282 | 271JOG603-6142 | 9000 | 1653 | 2026-06-29 | 2026-07-04 | LS drop shlder Swt shirt w rib and nk snap btn and Trouser w side pkt drawstring also both cotrast piping | Top & BTM |  |  | 2026-09-01 | 2026-09-11 | 2026-09-14 | 2026-09-28 |  |  | 2026-09-10 | 2026-09-23 | 2026-10-02 | 2026-10-03 | 2026-10-08 | 2026-10-08 | 2026-10-14 |  |  | 2026-10-14 | 2026-10-21 | 2026-10-21 | 2026-10-30 |  |  | 2026-10-31 | 2026-11-02 | 2026-11-04 | 2026-11-09 | 2026-11-09 | 133 | N/3 | Salam | Chest & Leg | Chest | stalacite top -4500 pcs chest 4 clr rub print and 5 clr flat 6 clr terry emb ,,coca mocha btm -4500 pcs one leg 1 clr rub print |  |  | NCL |  |  | File Due | 1653 | 0 | -1653 | 0 | -9000 | [11 empty] | 46 | Oct'1
BS-NMT | 48085 | 13251506 | 3636 | 334 | 2026-06-10 | 2026-07-01 | YD SS o nk TS w lace at nk And slve | TS | 2026-08-12 | 2026-08-20 | 2026-08-25 | 2026-09-07 | 2026-09-10 | 2026-09-18 |  |  | 2026-09-24 | 2026-09-24 | 2026-10-01 | 2026-10-03 | 2026-10-04 | 2026-10-06 | 2026-10-07 |  |  |  |  | 2026-10-10 | 2026-10-14 |  |  | 2026-10-17 | 2026-10-19 | 2026-10-25 | 2026-12-19 | 2026-12-21 | 192 | Z | Shamoly | Nk |  | 3 combo nk label print | YD | Lace | NFL3 |  |  | Need Cut FB | 333 | 0 | -333 | 0 | -3636 | [11 empty] | 52 | Oct'1 |  |  | 01.08.26
BS-NMT | 48087 | 13262930 | 4444 | 1019 | 2026-06-10 | 2026-07-01 | Elasted Shorts w drawstring | Pant |  |  | 2026-07-25 | 2026-08-06 | 2026-08-13 | 2026-08-28 |  |  | 2026-09-01 | 2026-09-01 | 2026-09-07 | 2026-09-10 | 2026-09-14 | 2026-09-15 | 2026-09-18 |  |  |  |  | 2026-09-21 | 2026-09-26 |  |  | 2026-09-30 | 2026-10-03 | 2026-10-07 | 2026-12-19 | 2026-12-21 | 192 | X | Shamoly |  | Thigh | Navy-2108 pcs,,papestry-1208 pcs,,carafe-at one leg 1128 pcs all combo 1 clr flat emb |  |  | NFL3 |  |  | Need Cut | 1020 | 1020 | 0 | 0 | -4444 | [11 empty] | 52 | Sep'1 |  |  | 01.08.26
BS-NMT | 48091 | 13262972 | 2272 | 249 | 2026-06-10 | 2026-07-01 | YD Tank top w nk and armhole lace attach | Tank Top | 2026-08-15 | 2026-08-22 | 2026-09-01 | 2026-09-10 | 2026-09-18 | 2026-09-26 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-09 | 2026-10-12 | 2026-10-14 | 2026-10-15 | 2026-10-17 |  |  |  |  | 2026-10-21 | 2026-10-24 |  |  | 2026-10-28 | 2026-10-30 | 2026-11-05 | 2026-12-19 | 2026-12-21 | 192 | W2 | Shamoly | Nk |  | 2 combo nk label print | YD | Lace | NFL3 |  |  | Need Test Cut | 248 | 0 | -248 | 0 | -2272 | [11 empty] | 52 | Oct'2 |  |  | 01.08.26
BS-NMT | 48092 | 13262973 | 2550 | 342 | 2026-06-10 | 2026-07-01 | YD SS o nk TS w lace at nk And slve | TS | 2026-08-15 | 2026-08-22 | 2026-09-01 | 2026-09-13 | 2026-09-19 | 2026-09-26 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-09 | 2026-10-12 | 2026-10-13 | 2026-10-15 | 2026-10-16 |  |  |  |  | 2026-10-20 | 2026-10-23 |  |  | 2026-10-26 | 2026-10-28 | 2026-11-05 | 2026-12-19 | 2026-12-21 | 192 | Z | Shamoly | Nk |  | 2 combo nk label print | YD | Lace | NFL3 |  |  | Need Test Cut | 342 | 0 | -342 | 0 | -2550 | [11 empty] | 52 | Oct'2 |  |  | 01.08.26
BS-NMT | 48094 | 13251273/13267083 | 6158 | 652 | 2026-06-10 | 2026-07-01 | SS o nk capsl TS w lace at slve | TS |  |  | 2026-08-20 | 2026-08-27 | 2026-09-05 | 2026-09-22 |  |  | 2026-10-01 | 2026-10-01 | 2026-10-07 | 2026-10-10 | 2026-10-13 | 2026-10-13 | 2026-10-16 |  |  |  |  | 2026-10-19 | 2026-10-24 |  |  | 2026-10-27 | 2026-10-29 | 2026-11-06 | 2027-01-17 | 2027-01-19 | 221 | Z | Shamoly | Nk |  | 3 combo nk label print |  | Lace | NFL3 |  |  | Need Cut FB | 653 | 0 | -653 | 0 | -6158 | [11 empty] | 4 | Oct'1 |  |  | 18.08.26
BS-NMT | 48095 | 13251275 | 2952 | 625 | 2026-06-10 | 2026-07-01 | AOP SL strap tank top long dress w side slit | Dress |  |  | 2026-08-15 | 2026-08-20 | 2026-09-05 | 2026-09-17 | 2026-09-22 | 2026-09-30 | 2026-10-06 | 2026-10-06 | 2026-10-13 | 2026-10-16 | 2026-10-17 | 2026-10-20 | 2026-10-22 |  |  |  |  | 2026-10-24 | 2026-10-28 |  |  | 2026-10-30 | 2026-11-06 | 2026-11-10 | 2027-01-17 | 2027-01-19 | 221 | Z | Shamoly | Nk |  | 2 combo nk label print | AOP |  | NFL3 |  |  | Need Cut FB | 625 | 0 | -625 | 0 | -2952 | [11 empty] | 4 | Oct'2 |  |  | 18.08.26
BS-NMT | 48096 | 13251521 | 6872 | 481 | 2026-06-10 | 2026-07-01 | SS o nk capsl TS w lace at slve | TS |  |  | 2026-08-20 | 2026-08-26 | 2026-09-05 | 2026-09-20 |  |  | 2026-09-25 | 2026-09-25 | 2026-10-03 | 2026-10-07 | 2026-10-10 | 2026-10-10 | 2026-10-13 |  |  |  |  | 2026-10-16 | 2026-10-22 |  |  | 2026-10-24 | 2026-10-27 | 2026-11-07 | 2027-01-17 | 2027-01-19 | 221 | Z | Shamoly | Nk |  | 3 combo nk label print |  | Lace | NFL3 |  |  | File Due | 482 | 0 | -482 | 0 | -6872 | [11 empty] | 4 | Oct'1
BS-NMT | 48097 | 13251523 | 6413 | 1930 | 2026-06-10 | 2026-07-01 | SS o nk Dress w top solid btm cut & sew AOP | Dress |  |  | 2026-08-04 | 2026-08-14 | 2026-08-20 | 2026-09-05 | 2026-09-08 | 2026-09-18 | 2026-09-22 | 2026-09-22 | 2026-09-28 | 2026-10-01 | 2026-10-03 | 2026-10-06 | 2026-10-09 |  |  |  |  | 2026-10-12 | 2026-10-17 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-27 | 2027-01-17 | 2027-01-19 | 221 | S | Shamoly | Nk |  | 3 combo nk label print | AOP |  | NFL3 |  |  | Need Cut | 1736 | 829 | -907 | 0 | -6413 | [11 empty] | 4 | Oct'1 |  |  | 18.08.26
BS-NMT | 48098 | 13262980 | 4200 | 655 | 2026-06-10 | 2026-07-01 | SS o nk TS | TS |  |  | 2026-08-01 | 2026-08-06 | 2026-08-15 | 2026-08-31 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-14 | 2026-09-17 | 2026-09-19 | 2026-09-22 | 2026-09-26 |  |  |  |  | 2026-10-01 | 2026-10-03 |  |  | 2026-10-06 | 2026-10-08 | 2026-10-15 | 2027-01-17 | 2027-01-19 | 221 | ZA1 | Shamoly | Fr & Bk & Nk |  | c.dan-2100 pcs frt 2 clr pig back 3 clr pig ,,strawberry-2100 pcs frt back 2 clr pig |  |  | NFL3 |  |  | Need Cut | 690 | 690 | 0 | 0 | -4200 | [11 empty] | 4 | Sep'2 |  |  | 18.08.26
BS-NMT | 48099 | 13263133/13256007 | 3406 | 395 | 2026-06-10 | 2026-07-01 | Rib Tank Top | Tank Top |  |  | 2026-08-20 | 2026-08-25 | 2026-09-06 | 2026-09-20 |  |  | 2026-09-25 | 2026-09-25 | 2026-10-03 | 2026-10-06 | 2026-10-07 | 2026-10-10 | 2026-10-14 | 2026-10-10 | 2026-10-14 |  |  | 2026-10-17 | 2026-10-20 |  |  | 2026-10-24 | 2026-10-26 | 2026-10-31 | 2027-01-17 | 2027-01-19 | 221 | W2 | Shamoly | Chest,Nk |  | lilac-1007 pcs,,c.dan-624 pcs,,strawberry-1151 pcs,,cream-624 pcs all combo chest studs HP stone |  |  | NFL3 |  |  | Size Set Run | 395 | 75 | -320 | 0 | -3406 | [11 empty] | 4 | Oct'1 |  |  | 18.08.26
BS-ONS | 48154 | 22029752/22042220 | 25307 | 6998 | 2026-06-19 | 2026-07-03 | Swt shorts pant w side pkt and back bon pkt and Drawstring | Shorts |  |  | 2026-08-15 | 2026-08-31 | 2026-09-08 | 2026-09-30 |  |  | 2026-10-12 | 2026-10-12 | 2026-10-19 | 2026-10-22 | 2026-10-29 | [6 empty] | 2026-11-02 | 2026-11-28 |  |  | 2026-11-30 | 2026-12-04 | 2026-12-08 | 2027-01-02 | 2027-01-04 | 197 | C | Shakel | [5 empty] | NFL1 |  |  | File Due | 6997 | 6048 | -949 | 0 | -25307 | [11 empty] | 2 | Oct'3
BS-ONL | 22035 73th | 15095808 | 2448 | 349 | 2026-06-26 | 2026-07-04 | Tank Top | Tank Top |  |  | 2026-09-15 | 2026-09-20 | 2026-10-01 | 2026-10-13 |  |  | 2026-10-17 | 2026-10-17 |  | 2026-10-26 | 2026-10-28 | [6 empty] | 2026-11-02 | 2026-11-04 |  |  | 2026-11-06 | 2026-11-10 | 2026-11-18 | 2027-01-11 | 2027-01-13 | 199 | ZA2 | Imran | [5 empty] | NFL3 |  |  | Need Cut FB | 0 | 0 | 0 | 0 | -2448 | [11 empty] | 3 | Oct'3 |  |  | 10.08.26
BS-ONL | 22036 37th | 15131538 | 4000 | 748 | 2026-07-09 | 2026-07-10 | LDS LEGGING | LEGGING | [8 empty] | 2026-07-16 | 2026-07-18 |  | 2026-07-15 | 2026-07-16 | [6 empty] | 2026-07-18 | 2026-07-22 |  |  | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-27 | 2026-07-29 | 18 | T1 | Imran |  |  |  |  | Stock fab from 43465 | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 4081 | 81 | [11 empty] | 31 | Jul'2 |  |  | 11.07.26
BS-ONL | 22036 38th | 15131538 | 10000 | 1870 | 2026-07-09 | 2026-07-10 | LDS LEGGING | LEGGING | [8 empty] | 2026-07-25 | 2026-07-18 |  | 2026-07-22 | 2026-07-25 | [6 empty] | 2026-08-01 | 2026-08-07 |  |  | 2026-08-10 | 2026-08-12 | 2026-08-14 | 2026-08-17 | 2026-08-19 | 39 | W2 | Imran |  |  |  |  | Stock fab from 43465 /VMI order | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 10110 | 110 | [11 empty] | 34 | Jul'3 |  |  | 11.07.26
BS-NMT | 41831 8th | 13239415 | 7080 | 1145 | 2026-07-09 | 2026-07-14 | GIRLS SOLID LEGGINGS | Legging |  |  | 2026-07-15 | 2026-07-22 | 2026-07-24 | 2026-08-08 |  |  | 2026-08-01 | 2026-08-01 | 2026-08-07 | 2026-08-12 | 2026-08-14 | [6 empty] | 2026-08-14 | 2026-08-18 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-24 | 2026-08-26 | 46 | W2 | Jafar | [5 empty] | NFL3 |  |  | Cut Ok | 1146 | 1146 | 0 | 21921 | 14841 | [11 empty] | 35 | Aug'2 |  |  | 25.07.26
BS-NMT | 44545 5th | 13236666 | 1520 | 215 | 2026-07-09 | 2026-07-14 | Legging w waist elastic | Legging |  |  | 2026-07-17 | 2026-07-20 | 2026-07-25 | 2026-08-03 |  |  | 2026-08-01 | 2026-08-01 | 2026-08-08 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 |  |  |  |  | 2026-08-14 | 2026-08-15 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-24 | 2026-08-26 | 46 | W2 | Jafar | Waist |  | 1 combo label print |  |  | NFL3 |  |  | Cut Ok | 215 | 215 | 0 | 0 | -1520 | [11 empty] | 35 | Aug'1 |  |  | 29.07.26
BS-ONS | 26828 74th | 22029226 | 6000 | 4028 | 2026-07-08 | 2026-07-14 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-07-15 | 2026-07-23 | 2026-07-25 | 2026-08-08 |  |  | 2026-08-06 | 2026-08-06 |  | 2026-08-11 | 2026-08-13 | [6 empty] | 2026-08-14 | 2026-08-18 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 2026-08-26 | 47 | E | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 4027 | 4023 | -4 | 0 | -6000 | [11 empty] | 35 | Aug'2 |  |  | 18.07.26
BS-ONS | 48309 | 22030372 | 8060 | 1777 | 2026-07-08 | 2026-07-09 | SS o nk TS | TS |  |  | 2026-07-13 | 2026-07-18 | 2026-07-20 | 2026-08-02 |  |  | 2026-07-30 | 2026-07-28 | 2026-08-06 | 2026-08-07 | 2026-08-10 | [6 empty] | 2026-08-10 | 2026-08-14 |  |  | 2026-08-16 | 2026-08-16 | 2026-08-17 | 2026-08-17 | 2026-08-19 | 40 | L1 | Shovon | [5 empty] | NFL2 |  |  | Cut Ok | 1778 | 1778 | 0 | 0 | -8060 | [11 empty] | 34 | Aug'1 |  |  | 27.07.26
BS-ONS | 48199 2nd | 22042193 | 20042 | 4952 | 2026-07-09 | 2026-07-10 | SS o nk TS w nk rib | TS |  |  | 2026-07-13 | 2026-07-18 | 2026-07-20 | 2026-08-03 |  |  | 2026-08-04 | 2026-07-28 |  | 2026-08-06 | 2026-08-10 | 2026-08-07 | 2026-08-12 |  |  |  |  | 2026-08-10 | 2026-08-17 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 2026-08-26 | 46 | ZA2 | Shovon | Heat Press/Heat Seal |  | 7 combo nk HP |  |  | NFL3 |  |  | Cut Ok | 4952 | 4952 | 0 | 0 | -20042 | [11 empty] | 35 | Aug'1 |  |  | 27.07.26
BS-ONL | 48302 | 15337134 | 1980 | 787 | 2026-07-04 | 2026-07-08 | YD LS o nk TS | TS | 2026-07-20 | 2026-07-25 | 2026-07-25 | 2026-08-03 | 2026-08-03 | 2026-08-08 |  |  | 2026-08-08 | 2026-08-08 | 2026-08-13 | 2026-08-15 | 2026-08-17 | [6 empty] | 2026-08-18 | 2026-08-20 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-24 | 2026-08-24 | 2026-08-26 | 51 | M | Mainul |  |  |  | YD |  | NFL2 |  |  | Cut Ok | 784 | 784 | 0 | 0 | -1980 | [11 empty] | 35 | Aug'2 |  |  | 25.07.26
BS-ONL | 48303 | 15397914 | 1980 | 1308 | 2026-07-04 | 2026-07-08 | LS Swt hoody w cuff btm rib | Hoody |  |  | 2026-07-13 | 2026-07-18 | 2026-07-20 | 2026-08-02 |  |  | 2026-08-01 | 2026-08-01 | 2026-08-08 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-15 |  |  |  |  | 2026-08-17 | 2026-08-19 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 2026-08-26 | 51 | J | Mainul | Fr & Bk & Slv |  | black-990 pcs frt back both slve 9 clr rub print ,,coffe-990 pcs frt back 1 clr rub print slve no print |  |  | NFL2 |  |  | Cut Ok | 1310 | 1310 | 0 | 2137 | 157 | [11 empty] | 35 | Aug'1 |  |  | 31.07.26
BS-ONL | 48304 | 15397938 | 1980 | 496 | 2026-07-04 | 2026-07-08 | LS boat nk TS w front ruching | TS |  |  | 2026-07-16 | 2026-07-22 | 2026-07-27 | 2026-08-06 |  |  | 2026-08-08 | 2026-08-08 | 2026-08-13 | 2026-08-15 | 2026-08-17 | [6 empty] | 2026-08-18 | 2026-08-20 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-24 | 2026-08-24 | 2026-08-26 | 51 | N2 | Mainul | [5 empty] | NFL2 |  |  | Cut Ok | 542 | 542 | 0 | 0 | -1980 | [11 empty] | 35 | Aug'2 |  |  | 07.08.26
BS-ONL | 30708 17th | 15201465 | 8280 | 1367 | 2026-07-08 | 2026-07-09 | Long Tank Top | Tank top |  |  | 2026-07-15 | 2026-07-23 | 2026-07-25 | 2026-08-08 |  |  | 2026-08-07 | 2026-08-07 |  | 2026-08-11 | 2026-08-14 | [6 empty] | 2026-08-14 | 2026-08-19 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 2026-08-26 | 47 | G1 | Mainul | [5 empty] | NFL1 |  |  | Cut Ok | 1368 | 1368 | 0 | 0 | -8280 | [11 empty] | 35 | Aug'2 |  |  | 25.07.26
BS-ONL | 30709 9th | 15209151 | 6660 | 1658 | 2026-07-08 | 2026-07-09 | Legging | Legging |  |  | 2026-07-16 | 2026-07-22 | 2026-07-25 | 2026-08-08 |  |  | 2026-08-07 | 2026-08-07 |  | 2026-08-12 | 2026-08-14 | [6 empty] | 2026-08-14 | 2026-08-19 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-24 | 2026-08-26 | 47 | L2 | Mainul | [5 empty] | NFL2 |  |  | Cut Ok | 1334 | 1334 | 0 | 6733 | 73 | [11 empty] | 35 | Aug'2 |  |  | 25.07.26
BS-ONL | 30711 8th | 15209156 | 6480 | 1331 | 2026-07-08 | 2026-07-09 | LS o nk TS | TS |  |  | 2026-07-15 | 2026-07-20 | 2026-07-25 | 2026-08-07 |  |  | 2026-08-08 | 2026-08-08 |  | 2026-08-11 | 2026-08-13 | [6 empty] | 2026-08-14 | 2026-08-17 |  |  | 2026-08-18 | 2026-08-20 | 2026-08-22 | 2026-08-24 | 2026-08-26 | 47 | ZA2 | Mainul | [5 empty] | NFL3 |  |  | Cut Ok | 1332 | 1332 | 0 | 6639 | 159 | [11 empty] | 35 | Aug'2 |  |  | 25.07.26
BS-ONL | 22041 64th | 15204712 | 10161 | 2097 | 2026-07-09 | 2026-07-13 | LS o nk TS | TS | [8 empty] | 2026-07-28 | 2026-07-21 |  | 2026-07-27 | 2026-07-30 | [6 empty] | 2026-08-07 | 2026-08-11 |  |  | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-17 | 2026-08-19 | 39 | G1 | Imran |  |  |  |  | Stock fab from 43465 /VMI order | NFL1 |  |  | Cut Ok | 0 | 0 | 0 | 10155 | -6 | [11 empty] | 34 | Jul'3 |  |  | 17.07.26
GBX-New Look | 48301 1st | 915-37618 | 11831 | 2587 | 2026-07-07 | 2026-07-07 | SS reglan contrast slve TS | TS |  |  | 2026-07-11 | 2026-07-22 | 2026-07-20 | 2026-08-04 |  |  | 2026-08-01 | 2026-08-01 | 2026-08-08 | 2026-08-11 | 2026-08-14 | [6 empty] | 2026-08-13 | 2026-08-19 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 46 | N/3 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 2588 | 2577 | -11 | 0 | -11831 | [11 empty] | 34 | Aug'2
GBX-New Look | 48310 | 915-34480 | 5250 | 610 | 2026-07-11 | 2026-07-13 | AOP SS reglan contrast slve TS | TS |  |  | 2026-07-15 | 2026-07-20 | 2026-07-22 | 2026-08-03 | 2026-08-03 | 2026-08-07 | 2026-08-06 | 2026-08-06 | 2026-08-10 | 2026-08-11 | 2026-08-14 | 2026-08-13 | 2026-08-17 |  |  |  |  | 2026-08-17 | 2026-08-20 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 42 | N/1 | Shofi | Chest |  | Blue pattern-5250 pcs 2 clr pig print | AOP |  | NCL |  |  | Ready Test Cut | 624 | 624 | 0 | 0 | -5250 | [11 empty] | 34 | Aug'2
UTG-(Even & Odd) | 41637 9th | BAD1502N | 1400 | 346 | 2026-07-09 | 2026-07-09 | LS ROLL NK TS | TS |  |  | 2026-07-13 | 2026-07-17 | 2026-07-18 | 2026-07-30 |  |  | 2026-08-01 | 2026-08-01 |  | 2026-08-07 | 2026-08-08 | [6 empty] | 2026-08-11 | 2026-08-13 |  |  | 2026-08-14 | 2026-08-17 | 2026-08-19 | 2026-08-22 | 2026-08-24 | 44 | Z | Rony | [5 empty] | NFL3 |  |  | Cut Ok | 346 | 346 | 0 | 1462 | 62 | [11 empty] | 35 | Aug'1 |  |  | 18.07.26
BS-NMT | 46491 5th | 13225095 | 2000 | 283 | 2026-07-08 | 2026-07-14 | YD LS o nk TS | TS | 2026-07-20 | 2026-07-25 | 2026-07-29 | 2026-08-06 | 2026-08-08 | 2026-08-13 |  |  | 2026-08-12 | 2026-08-12 |  | 2026-08-17 | 2026-08-18 | 2026-08-20 | 2026-08-21 |  |  |  |  | 2026-08-24 | 2026-08-25 |  |  | 2026-08-27 | 2026-08-29 | 2026-08-31 | 2026-09-07 | 2026-09-09 | 61 | L1 | Jafar | Chest,Nk |  | indigo-2000 pcs 1 clr puff print | YD |  | NFL2 |  |  | Cut Ok | 283 | 283 | 0 | 2091 | 91 | [11 empty] | 37 | Aug'2 |  |  | 27.07.26
BS-NMT | 48268 | 13265096 | 1285 | 512 | 2026-06-29 | 2026-07-07 | High waist legging lace attach w high waist | Legging |  |  | 2026-07-25 | 2026-08-04 | 2026-08-11 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-26 | 2026-09-02 | 2026-09-04 | 2026-09-05 | 2026-09-07 | 2026-09-08 |  |  |  |  | 2026-09-11 | 2026-09-12 |  |  | 2026-09-14 | 2026-09-16 | 2026-09-18 | 2026-09-21 | 2026-09-23 | 84 | U | Sanaul | Waist |  | 1 combo label print |  | Lace | NFL3 |  |  | Cut Ok | 512 | 512 | 0 | 1324 | 39 | [11 empty] | 39 | Sep'1 |  |  | 27.08.26
BS-NMT | 48266 | 13265086 | 754 | 298 | 2026-06-29 | 2026-07-07 | LS Swt shirt w cuff btm rib and front slve contrast cut&sew piping | Swt Shirt |  |  | 2026-07-25 | 2026-08-03 | 2026-08-10 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-26 | 2026-09-02 | 2026-09-04 | 2026-09-04 | 2026-09-07 | 2026-09-08 |  |  |  |  | 2026-09-10 | 2026-09-11 |  |  | 2026-09-14 | 2026-09-15 | 2026-09-17 | 2026-09-21 | 2026-09-23 | 84 | V | Sanaul | slv,Chest |  | mulled basil-754 pcs frt 1 clr rub one slve 2 clr rub print |  |  | NFL3 |  |  | Cut Ok | 297 | 289 | -8 | 784 | 30 | [11 empty] | 39 | Sep'1 |  |  | 23.07.26
BS-NMT | 48265 | 13265157 | 1264 | 309 | 2026-06-29 | 2026-07-07 | Trouser w waist btm rib and badge label and leg cut&sew and drawstring | Trouser |  |  | 2026-08-01 | 2026-08-07 | 2026-08-13 | 2026-08-25 |  |  | 2026-09-02 | 2026-09-02 | 2026-09-07 | 2026-09-09 | 2026-09-10 | [6 empty] | 2026-09-12 | 2026-09-14 |  |  | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-23 | 84 | X | Sanaul | [5 empty] | NFL3 |  |  | Cut Ok | 308 | 308 | 0 | 1294 | 30 | [11 empty] | 39 | Sep'1 |  |  | 14.08.26
BS-NMT | 48267 | 13265087 | 754 | 321 | 2026-06-29 | 2026-07-07 | Trouser w waist btm rib and side pkt side cut&sew contrast piping and drawstring | Trouser |  |  | 2026-07-25 | 2026-07-31 | 2026-08-08 | 2026-08-22 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-31 | 2026-09-02 | 2026-09-03 | 2026-09-05 | 2026-09-08 |  |  |  |  | 2026-09-10 | 2026-09-12 |  |  | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-21 | 2026-09-23 | 84 | X | Sanaul | leg |  | mulled basil-754 pcs one leg 2 clr rub print |  |  | NFL3 |  |  | Cut Ok | 321 | 312 | -9 | 797 | 43 | [11 empty] | 39 | Sep'1 |  |  | 23.07.26
BS-NMT | 48269 | 13265133 | 1500 | 305 | 2026-06-29 | 2026-07-07 | LS Swt shirt w cuff btm rib w chest chiifon flower | Swt Shirt |  |  | 2026-07-20 | 2026-07-24 | 2026-08-04 | 2026-08-18 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-27 | 2026-08-29 | 2026-08-31 | 2026-09-02 | 2026-09-04 |  |  | 2026-09-05 | 2026-09-10 | 2026-09-12 | 2026-09-14 |  |  | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-23 | 84 | W2 | Sanaul | Chest | Chest | violet Ice-1500 pcs 5 clr rub w 1 clr puff print and 1 clr terry emb |  | Chiffon flower attach at sewing | NFL3 |  |  | Cut Ok | 305 | 294 | -11 | 1557 | 57 | [11 empty] | 39 | Aug'3 |  |  | 23.07.26
BS-NMT | 48270 | 13265097 | 1261 | 194 | 2026-06-29 | 2026-07-07 | LS v nk TS w lace at nk and cuff | TS |  |  | 2026-08-01 | 2026-08-06 | 2026-08-12 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-26 | 2026-09-03 | 2026-09-05 | 2026-09-07 | 2026-09-09 | 2026-09-10 |  |  |  |  | 2026-09-12 | 2026-09-14 |  |  | 2026-09-16 | 2026-09-17 | 2026-09-19 | 2026-09-21 | 2026-09-23 | 84 | T2 | Sanaul | Nk |  | 1 combo label print |  | Lace | NFL3 |  |  | Cut Ok | 194 | 194 | 0 | 1296 | 35 | [11 empty] | 39 | Sep'1 |  |  | 23.07.26
BS-ONS | 26827 55th | 22029225 | 6100 | 5829 | 2026-07-08 | 2026-07-14 | LS Swt hoodie w kangaro pkt and drastring and cuff btm rib | HOODY |  |  | 2026-07-16 | 2026-07-28 | 2026-07-28 | 2026-08-14 |  |  | 2026-08-13 | 2026-08-10 |  | 2026-08-15 | 2026-08-19 | [6 empty] | 2026-08-19 | 2026-08-25 |  |  | 2026-08-27 | 2026-08-31 | 2026-09-02 | 2026-09-07 | 2026-09-09 | 61 | R | Shakel | [5 empty] | NFL2 |  |  | Cut Ok | 5830 | 5830 | 0 | 6242 | 142 | [11 empty] | 37 | Aug'2 |  |  | 18.07.26
BS-ONS | 41626 26th | 22031973 | 3030 | 2027 | 2026-07-08 | 2026-07-14 | MENS LONG SWT PANT W SIDE & BK PKT | PANT |  |  | 2026-07-20 | 2026-07-28 | 2026-08-01 | 2026-08-15 |  |  | 2026-08-15 | 2026-08-15 |  | 2026-08-20 | 2026-08-22 | [6 empty] | 2026-08-25 | 2026-08-29 |  |  | 2026-08-31 | 2026-09-02 | 2026-09-03 | 2026-09-07 | 2026-09-09 | 61 | C | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 2027 | 2027 | 0 | 3127 | 97 | [11 empty] | 37 | Aug'2 |  |  | 18.07.26
BS-ONS | 26828 75th | 22029226 | 10300 | 6878 | 2026-07-08 | 2026-07-14 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-07-18 | 2026-07-28 | 2026-08-01 | 2026-08-15 |  |  | 2026-08-15 | 2026-08-12 |  | 2026-08-17 | 2026-08-20 | [6 empty] | 2026-08-20 | 2026-08-27 |  |  | 2026-08-29 | 2026-08-31 | 2026-09-03 | 2026-09-07 | 2026-09-09 | 61 | E | Shakel | [5 empty] | NFL1 |  |  | Cut Ok | 6880 | 6863 | -17 | 10716 | 416 | [11 empty] | 37 | Aug'2 |  |  | 18.07.26
BS-ONL | 30710 12th | 15209153 | 4320 | 637 | 2026-07-08 | 2026-07-09 | SS o nk TS | TS |  |  | 2026-07-17 | 2026-07-23 | 2026-08-01 | 2026-08-12 |  |  | 2026-08-12 | 2026-08-12 |  | 2026-08-17 | 2026-08-18 | [6 empty] | 2026-08-20 | 2026-08-22 |  |  | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-31 | 2026-09-02 | 54 | D1 | Mainul | [5 empty] | NFL1 |  |  | Cut Ok | 637 | 637 | 0 | 4372 | 52 | [11 empty] | 36 | Aug'2 |  |  | 25.07.26
BS-ONL | 22041 63th | 15204712 | 1656 | 345 | 2026-07-09 | 2026-07-10 | LS o nk TS | TS |  |  | 2026-07-20 | 2026-07-25 | 2026-08-03 | 2026-08-15 |  |  | 2026-08-15 | 2026-08-15 |  | 2026-08-21 | 2026-08-22 | [6 empty] | 2026-08-25 | 2026-08-26 |  |  | 2026-08-28 | 2026-08-31 | 2026-09-03 | 2026-09-14 | 2026-09-16 | 67 | G1 | Imran | [5 empty] | NFL1 |  |  | Cut Ok | 345 | 345 | 0 | 1698 | 42 | [11 empty] | 38 | Aug'3 |  |  | 17.07.26
BS-ONL | 27204 59th | 15323159 | 14160 | 3404 | 2026-07-09 | 2026-07-10 | LS o nk TS | TS |  |  | 2026-07-16 | 2026-07-29 | 2026-08-01 | 2026-08-14 |  |  | 2026-08-10 | 2026-08-10 |  | 2026-08-15 | 2026-08-19 | [6 empty] | 2026-08-20 | 2026-08-26 |  |  | 2026-08-28 | 2026-08-31 | 2026-09-03 | 2026-09-07 | 2026-09-09 | 60 | G2 | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 3405 | 3405 | 0 | 14283 | 123 | [11 empty] | 37 | Aug'2 |  |  | 07.08.26
BS-ONL | 48204 | 15393547 | 1416 | 176 | 2026-06-20 | 2026-07-13 | SS o nk TS | TS |  |  | 2026-07-27 | 2026-07-31 | 2026-08-10 | 2026-08-24 |  |  | 2026-08-27 | 2026-08-27 | 2026-09-02 | 2026-09-04 | 2026-09-04 | 2026-09-07 | 2026-09-08 |  |  | 2026-09-10 | 2026-09-11 | 2026-09-14 | 2026-09-15 |  |  | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-21 | 2026-09-23 | 93 | O1 | Abid | Chest | Chest | c.dan bouquet-710 pcs,,orchid-bouquet-710 pcs |  | Print artwork due | NFL2 |  |  | Cut Run | 150 | 150 | 0 | 1286 | -130 | [11 empty] | 39 | Sep'1 |  |  | 21.08.26
BS-ONL | 48200 | 15286501 | 576 | 72 | 2026-06-20 | 2026-07-13 | SS o nk TS | TS |  |  | 2026-08-28 | 2026-08-31 | 2026-08-07 | 2026-08-20 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-31 | 2026-09-02 | 2026-09-02 | 2026-09-04 | 2026-09-05 |  |  | 2026-09-08 | 2026-09-09 | 2026-09-11 | 2026-09-12 |  |  | 2026-09-14 | 2026-09-16 | 2026-09-18 | 2026-09-19 | 2026-09-21 | 91 | O1 | Abid | Chest | Chest | c.dan bouquet-578 pcs |  | Print artwork due | NFL2 |  |  | Cut Ok | 72 | 72 | 0 | 613 | 37 | [11 empty] | 39 | Sep'1 |  |  | 21.08.26
BS-ONL | 48205 | 15395685 | 480 | 71 | 2026-06-20 | 2026-07-14 | SS o nk TS w blind stitch | TS |  |  | 2026-07-22 | 2026-07-25 | 2026-08-13 | 2026-08-18 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-25 | 2026-08-27 | 2026-08-27 | 2026-08-29 | 2026-09-02 |  |  |  |  | 2026-09-04 | 2026-09-04 |  |  | 2026-09-07 | 2026-09-09 | 2026-09-14 | 2026-09-21 | 2026-09-23 | 93 | O1 | Abid | Fr,Bk |  | c.dan -242 pcs frt 1 clr gltr back 1 clr gltr 5 clr pig ,,ether-242 pcs frt 2 clr pig 2 clr gltr back 6 clr pig 3 clr gltr |  |  | NFL2 |  |  | Cut Ok | 70 | 70 | 0 | 514 | 34 | [11 empty] | 39 | Aug'3 |  |  | 21.08.26
OVS SPA | 48284 | 271HTS104JB-244 | 2022 | 100 | 2026-07-01 | 2026-07-11 | Hat | Hat |  |  | 2026-08-01 | 2026-08-12 | 2026-08-10 | 2026-08-16 |  |  | 2026-09-01 | 2026-08-26 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-04 | 2026-09-07 |  |  |  |  | 2026-09-08 | 2026-09-10 |  |  | 2026-09-11 | 2026-09-12 | 2026-09-14 | 2026-09-15 | 2026-09-15 | 76 | G1 | Khairul | Hat |  | Black-2022 pcs 5 clr rub print |  |  | NFL1 |  |  | Cut Ok | 100 | 100 | 0 | 2077 | 55 | [11 empty] | 38 | Sep'1 |  |  | 05.09.26
GBX-Maurices | 48245 3rd | 2524991/4704991 | 13700 | 5367 | 2026-07-09 | 2026-07-10 | YD LS self nk binding TS W banded hem | TS | 2026-07-25 | 2026-08-06 | 2026-08-01 | 2026-08-13 | 2026-08-09 | 2026-08-22 |  |  | 2026-08-20 | 2026-08-18 |  | 2026-08-25 | 2026-08-31 | 2026-09-02 | 2026-09-11 |  |  |  |  | 2026-09-01 | 2026-09-11 |  |  | 2026-09-12 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-16 | 69 | N/1 | Mannan | Heat Press/Heat Seal |  | 4 combo nk HP | YD |  | NCL |  |  | Ready Test Cut | 4669 | 4196 | -473 | 0 | -13700 | [11 empty] | 38 | Aug'3
BS-ONL | 42946 9th | 15360359 | 4060 | 1533 | 2026-07-08 | 2026-07-08 | YD loose pant w drawstring | Pant | 2026-08-01 | 2026-08-10 | 2026-08-14 | 2026-08-26 | 2026-08-24 | 2026-09-03 |  |  | 2026-09-01 | 2026-09-01 |  | 2026-09-04 | 2026-09-07 | [6 empty] | 2026-09-09 | 2026-09-12 |  |  | 2026-09-15 | 2026-09-17 | 2026-09-22 | 2026-10-12 | 2026-10-14 | 96 | P | Dalim |  |  |  | YD |  | NFL2 |  |  | Need Cut FB | 1533 | 0 | -1533 | 0 | -4060 | [11 empty] | 42 | Sep'1 |  |  | 08.08.26
BS-ONL | 48212 | 15388120 | 1008 | 1244 | 2026-06-20 | 2026-07-13 | AOP & solid LS Swt shirt w shlder frill and nk rib | Swt Shirt |  |  | 2026-08-01 | 2026-08-06 | 2026-08-10 | 2026-08-24 | 2026-08-24 | 2026-08-29 | 2026-09-01 | 2026-09-01 | 2026-09-07 | 2026-09-09 | 2026-09-10 | 2026-09-12 | 2026-09-16 |  |  |  |  | 2026-09-18 | 2026-09-21 |  |  | 2026-09-23 | 2026-09-25 | 2026-09-30 | 2026-10-19 | 2026-10-21 | 121 | Q | Abid | Chest |  | lavender AOP-492 pcs no print ,,blue-516 pcs 8 clr rub 2 clr puff print | AOP |  | NFL2 |  |  | Size Set Run Rib Due | 217 | 207 | -10 | 0 | -1008 | [11 empty] | 43 | Sep'1 |  |  | 21.08.26
BS-ONL | 48202 2nd | 15388786 | 3000 | 375 | 2026-07-09 | 2026-07-13 | SS o nk TS w blind stitch | TS |  |  | 2026-08-03 | 2026-08-08 | 2026-08-15 | 2026-08-28 |  |  | 2026-09-03 | 2026-09-03 |  | 2026-09-09 | 2026-09-10 | 2026-09-12 | 2026-09-17 |  |  |  |  | 2026-09-21 | 2026-09-23 |  |  | 2026-09-25 | 2026-09-29 | 2026-10-03 | 2026-10-12 | 2026-10-14 | 95 | G2 | Abid | Fr,Bk |  | C.dancer-3002 pcs frt 1 clr gltr and back 5 clr pig 1 clr gltr |  |  | NFL1 |  |  | Cut Ok | 375 | 375 | 0 | 3082 | 82 | [11 empty] | 42 | Sep'1 |  |  | 19.08.26
BS-ONL | 48203 2nd | 15388785 | 1020 | 452 | 2026-07-09 | 2026-07-14 | LS Swt hoody w cuff btm rib | Hoody |  |  | 2026-08-01 | 2026-08-07 | 2026-08-12 | 2026-08-24 |  |  | 2026-08-25 | 2026-08-25 |  | 2026-09-02 | 2026-09-03 | 2026-09-05 | 2026-09-11 |  |  |  |  | 2026-09-14 | 2026-09-15 |  |  | 2026-09-17 | 2026-09-21 | 2026-09-26 | 2026-10-12 | 2026-10-14 | 95 | Q | Abid | Fr,Bk |  | Navy-1022 pcs frt 1 clr rub 1 clr gltr and back 4 clr rub 2 clr gltr print |  |  | NFL2 |  |  | Need Cut | 452 | 339 | -113 | 0 | -1020 | [11 empty] | 42 | Sep'1 |  |  | 21.08.26
OVS SPA | 47796 | 271TRO093-6156 | 2674 | 840 | 2026-07-06 | 2026-07-10 | Cut&sew elasted trouser w back pkt drawstring | Trouser |  |  | 2026-08-20 | 2026-08-31 | 2026-09-01 | 2026-09-14 |  |  | 2026-09-25 | 2026-09-10 | 2026-09-19 | 2026-09-21 | 2026-09-23 | 2026-09-25 | 2026-09-30 |  |  | 2026-10-01 | 2026-10-05 | 2026-10-05 | 2026-10-10 |  |  | 2026-10-12 | 2026-10-14 | 2026-10-16 | 2026-10-19 | 2026-10-19 | 105 | H | Khairul | Thigh | Thigh | blue-2674 pcs 4 clr rub and 2 clr terry emb |  |  | NFL1 |  |  | Size Set Run Emb | 840 | 840 | 0 | 0 | -2674 | [11 empty] | 43 | Sep'3 |  |  | 12.09.26
OVS SPA | 47880 | 271PJA506-224 | 10494 | 1865 | 2026-06-29 | 2026-07-10 | AOP LS nightwear Shirt w collar full placket btn and cuff elastic and Plazoo w btm frill | Top & BTM |  |  | 2026-08-18 | 2026-08-31 | 2026-09-01 | 2026-09-14 | 2026-09-15 | 2026-09-24 | 2026-09-30 | 2026-09-26 | 2026-10-02 | 2026-10-03 | 2026-10-08 | [6 empty] | 2026-10-08 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-19 | 112 | N/2 | Khairul |  |  |  | AOP |  | NCL |  |  | File Due | 1905 | 0 | -1905 | 0 | -10494 | [11 empty] | 43 | Oct'1
UTG-AF | 43337 6th | BAD1633AE | 6000 | 786 | 2026-07-01 | 2026-07-07 | LDS GROWING SLV O NK TS | TS |  |  | 2026-08-20 | 2026-07-25 | 2026-08-04 | 2026-08-18 |  |  | 2026-08-15 | 2026-08-15 |  | 2026-08-22 | 2026-08-26 | [6 empty] | 2026-09-02 | 2026-09-07 |  |  | 2026-09-09 | 2026-09-11 | 2026-09-14 | 2026-09-19 | 2026-09-21 | 80 | N1 | Rana | [5 empty] | NFL2 |  |  | Cut Run | 1047 | 964 | -83 | 5362 | -638 | [11 empty] | 39 | Aug'3 |  |  | 18.08.26
UTG-AF | 43430 6th | BAD2549E | 3000 | 758 | 2026-07-01 | 2026-07-07 | solid & YD LDS BOAT NK LS TS | TS | 2026-08-15 | 2026-08-25 | 2026-08-26 | 2026-08-02 | 2026-08-10 | 2026-08-20 |  |  | 2026-08-20 | 2026-08-18 |  | 2026-08-25 | 2026-08-30 | [6 empty] | 2026-09-05 | 2026-09-09 |  |  | 2026-09-11 | 2026-09-12 | 2026-09-15 | 2026-09-19 | 2026-09-21 | 80 | N1 | Rana |  |  |  | YD |  | NFL2 |  |  | Cut Ok | 758 | 758 | 0 | 3129 | 129 | [11 empty] | 39 | Aug'3 |  |  | 18.08.26
UTG-AF | 43333 5th | BAD1545mamaU | 4000 | 868 | 2026-07-01 | 2026-07-07 | SS nursiing TS solid YD | TS | 2026-08-15 | 2026-08-25 | 2026-08-26 | 2026-08-02 | 2026-08-08 | 2026-08-18 |  |  | 2026-08-18 | 2026-08-18 |  | 2026-08-24 | 2026-08-27 | [6 empty] | 2026-09-01 | 2026-09-04 |  |  | 2026-09-07 | 2026-09-09 | 2026-09-12 | 2026-09-19 | 2026-09-21 | 80 | V | Rana |  |  |  | YD |  | NFL3 |  |  | Cut Ok | 868 | 868 | 0 | 4152 | 152 | [11 empty] | 39 | Aug'3 |  |  | 18.08.26
UTG-AF | 41833 5th | BAD1056nursAJ | 4000 | 820 | 2026-07-01 | 2026-07-07 | O NK SS TS | TS |  |  | 2026-08-20 | 2026-07-22 | 2026-08-04 | 2026-08-18 |  |  | 2026-08-15 | 2026-08-15 |  | 2026-08-22 | 2026-08-25 | [6 empty] | 2026-09-04 | 2026-09-09 |  |  | 2026-09-11 | 2026-09-12 | 2026-09-15 | 2026-09-19 | 2026-09-21 | 80 | V | Rana | [5 empty] | NFL3 |  |  | Cut Ok | 820 | 820 | 0 | 4172 | 172 | [11 empty] | 39 | Aug'3 |  |  | 18.08.26
UTG-AF | 40675 11th | BAD1546mamaAA | 6000 | 1476 | 2026-07-01 | 2026-07-07 | LDS BOAT NK LS TS | TS |  |  | 2026-08-20 | 2026-07-22 | 2026-08-07 | 2026-08-18 |  |  | 2026-08-20 | 2026-08-20 |  | 2026-08-26 | 2026-08-29 | [6 empty] | 2026-09-01 | 2026-09-05 |  |  | 2026-09-08 | 2026-09-10 | 2026-09-14 | 2026-09-19 | 2026-09-21 | 80 | N1 | Rana | [5 empty] | NFL2 |  |  | Cut Ok | 1476 | 1476 | 0 | 6289 | 289 | [11 empty] | 39 | Aug'3 |  |  | 22.07.26
UTG-AF | 41948 5th | BAD0984mamaBL | 4500 | 882 | 2026-07-01 | 2026-07-07 | SS o nk TS | TS |  |  | 2026-08-20 | 2026-08-31 | 2026-08-01 | 2026-08-13 |  |  | 2026-08-17 | 2026-08-17 |  | 2026-08-24 | 2026-08-27 | [6 empty] | 2026-09-03 | 2026-09-08 |  |  | 2026-09-10 | 2026-09-15 | 2026-09-17 | 2026-09-19 | 2026-09-21 | 80 | N2 | Rana | [5 empty] | NFL2 |  |  | Cut Ok | 882 | 882 | 0 | 4591 | 91 | [11 empty] | 39 | Aug'3 |  |  | 18.08.26
UTG-AF | 44275 8th | BAD2731H | 4000 | 828 | 2026-07-01 | 2026-07-07 | LS o nk TS w lace | TS |  |  | 2026-08-20 | 2026-07-27 | 2026-08-10 | 2026-08-23 |  |  | 2026-08-20 | 2026-08-20 |  | 2026-09-01 | 2026-09-03 | [6 empty] | 2026-09-07 | 2026-09-11 |  |  | 2026-09-14 | 2026-09-16 | 2026-09-17 | 2026-09-19 | 2026-09-21 | 80 | N/1 | Rana |  |  |  |  | Lace | NCL |  |  | Ready Test Cut | 828 | 828 | 0 | 0 | -4000 | [11 empty] | 39 | Sep'1
UTG-AF | 44276 4th | BAD2480F | 2000 | 468 | 2026-07-01 | 2026-07-07 | LS v nk TS w nk lace | TS |  |  | 2026-08-20 | 2026-08-31 | 2026-08-03 | 2026-08-18 |  |  | 2026-08-20 | 2026-08-20 |  | 2026-08-26 | 2026-08-29 | [6 empty] | 2026-09-05 | 2026-09-09 |  |  | 2026-09-11 | 2026-09-12 | 2026-09-14 | 2026-09-19 | 2026-09-21 | 80 | N/1 | Rana |  |  |  |  | Lace | NCL |  |  | Ready Test Cut | 468 | 468 | 0 | 0 | -2000 | [11 empty] | 39 | Aug'3
UTG-AF | 43305 3rd | BAD0954T | 2000 | 782 | 2026-07-01 | 2026-07-07 | LDS 3/4 SLV DRESS | Dress |  |  | 2026-08-20 | 2026-08-31 | 2026-08-06 | 2026-08-14 |  |  | 2026-08-20 | 2026-08-20 |  | 2026-09-01 | 2026-09-02 | [6 empty] | 2026-09-05 | 2026-09-09 |  |  | 2026-09-11 | 2026-09-12 | 2026-09-15 | 2026-09-19 | 2026-09-21 | 80 | N/3 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 782 | 782 | 0 | 0 | -2000 | [11 empty] | 39 | Sep'1
UTG-AF | 44587 10th | BAD2548U | 2400 | 570 | 2026-07-01 | 2026-07-07 | LDS LS V NK TS | TS |  |  | 2026-08-20 | 2026-08-28 | 2026-08-06 | 2026-08-16 |  |  | 2026-08-14 | 2026-08-14 |  | 2026-08-21 | 2026-08-22 | [6 empty] | 2026-09-03 | 2026-09-05 |  |  | 2026-09-08 | 2026-09-10 | 2026-09-14 | 2026-09-19 | 2026-09-21 | 80 | D1 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 570 | 570 | 0 | 2529 | 129 | [11 empty] | 39 | Aug'3 |  |  | 22.07.26
UTG-AF | 46152 8th | BAD0985AM | 9000 | 2067 | 2026-07-01 | 2026-07-07 | LDS O NK LS TS | TS |  |  | 2026-08-18 | 2026-07-27 | 2026-08-03 | 2026-08-16 |  |  | 2026-08-15 | 2026-08-15 |  | 2026-08-20 | 2026-08-24 | [6 empty] | 2026-09-01 | 2026-09-05 |  |  | 2026-09-08 | 2026-09-10 | 2026-09-14 | 2026-09-19 | 2026-09-21 | 80 | D1 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 2066 | 2066 | 0 | 9532 | 532 | [11 empty] | 39 | Aug'2 |  |  | 22.07.26
UTG-AF | 40672 7th | BAD0934AE | 3000 | 686 | 2026-07-01 | 2026-07-07 | LDS O NK LS TS | TS |  |  | 2026-08-20 | 2026-08-29 | 2026-08-01 | 2026-08-12 |  |  | 2026-08-10 | 2026-08-10 |  | 2026-08-20 | 2026-08-22 | [6 empty] | 2026-09-03 | 2026-09-05 |  |  | 2026-09-08 | 2026-09-10 | 2026-09-14 | 2026-09-19 | 2026-09-21 | 80 | D1 | Rana | [5 empty] | NFL1 |  |  | Cut Ok | 686 | 686 | 0 | 3068 | 68 | [11 empty] | 39 | Aug'2 |  |  | 23.07.26
UTG-AF | 44277 4th | BAD2903E | 2400 | 660 | 2026-07-01 | 2026-07-07 | LS o nk TS | TS |  |  | 2026-08-20 | 2026-07-25 | 2026-08-10 | 2026-08-24 |  |  | 2026-08-20 | 2026-08-20 |  | 2026-08-28 | 2026-08-31 | [6 empty] | 2026-09-05 | 2026-09-08 |  |  | 2026-09-10 | 2026-09-12 | 2026-09-15 | 2026-09-19 | 2026-09-21 | 80 | V | Rana | [5 empty] | NFL3 |  |  | Cut Run | 660 | 440 | -220 | 855 | -1545 | [11 empty] | 39 | Aug'3 |  |  | 18.08.26
UTG-AF | 40671 12th | BAD1298AK | 7000 | 1741 | 2026-07-01 | 2026-07-07 | YD LS boat nk TS | TS | 2026-08-20 | 2026-08-31 | 2026-09-01 | 2026-08-02 | 2026-08-10 | 2026-08-20 |  |  | 2026-08-18 | 2026-08-18 |  | 2026-08-25 | 2026-08-29 | [6 empty] | 2026-09-01 | 2026-09-07 |  |  | 2026-09-09 | 2026-09-11 | 2026-09-15 | 2026-09-19 | 2026-09-21 | 80 | N1 | Rana |  |  |  | YD |  | NFL2 |  |  | Cut Run | 1463 | 1463 | 0 | 6009 | -991 | [11 empty] | 39 | Aug'3 |  |  | 18.08.26
BS-NMT | 48074 | 13267760 | 3819 | 328 | 2026-07-01 | 2026-07-08 | SS o nk TS | TS |  |  | 2026-08-03 | 2026-08-08 | 2026-08-15 | 2026-08-31 |  |  | 2026-09-05 | 2026-09-05 | 2026-09-10 | 2026-09-13 | 2026-09-15 | 2026-09-16 | 2026-09-21 |  |  |  |  | 2026-09-24 | 2026-09-29 |  |  | 2026-09-30 | 2026-10-05 | 2026-10-20 | 2026-11-02 | 2026-11-04 | 124 | ZA1 | Shamoly | Fr & Bk & Nk |  | blackberry-2046 pcs frt 2 clr gltr back 2 clr rub 2 clr gltr ,,pink-1773 pcs frt 3 clr rub 2 clr gltr back no print |  |  | NFL3 |  |  | File Due | 328 | 328 | 0 | 0 | -3819 | [11 empty] | 45 | Sep'2
BS-NMT | 48285 | 13256497 | 2112 | 175 | 2026-07-02 | 2026-07-10 | LS o nk TS w shlder snap btn | TS |  |  | 2026-08-03 | 2026-08-07 | 2026-08-15 | 2026-08-31 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-12 | 2026-09-15 | 2026-09-16 | 2026-09-18 | 2026-09-22 |  |  |  |  | 2026-09-24 | 2026-09-26 |  |  | 2026-09-29 | 2026-10-02 | 2026-10-10 | 2026-11-09 | 2026-11-11 | 130 | Y | Sabikun | Chest,Nk |  | green-1056 pcs ,,cashmere-1056 pcs both combo 3 clr rub 3 clr puff print |  | Outlet order | NFL3 |  |  | Cut Ok | 176 | 176 | 0 | 2244 | 132 | [11 empty] | 46 | Sep'2 |  |  | 01.08.26
BS-NMT | 48287 | 13267674 | 1543 | 382 | 2026-07-02 | 2026-07-10 | Wise waist belt Pant side pkt and drawstring | Pant |  |  | 2026-08-03 | 2026-08-08 | 2026-08-14 | 2026-08-31 |  |  | 2026-09-05 | 2026-09-05 | 2026-09-12 | 2026-09-15 | 2026-09-16 | 2026-09-18 | 2026-09-21 |  |  |  |  | 2026-09-23 | 2026-09-25 |  |  | 2026-09-29 | 2026-10-03 | 2026-10-07 | 2026-11-09 | 2026-11-11 | 130 | X | Sabikun | Waist & Thigh |  | sand-1543 pcs 3 clr gltr print |  | Outlet order | NFL3 |  |  | Need Cut | 382 | 382 | 0 | 0 | -1543 | [11 empty] | 46 | Sep'2 |  |  | 11.09.26
BS-NMT | 48286 | 13267673 | 1594 | 360 | 2026-07-02 | 2026-07-10 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-08-01 | 2026-08-07 | 2026-08-12 | 2026-08-25 |  |  | 2026-08-28 | 2026-08-28 | 2026-09-04 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-12 |  |  | 2026-09-14 | 2026-09-19 | 2026-09-22 | 2026-09-24 |  |  | 2026-09-26 | 2026-09-29 | 2026-10-08 | 2026-11-09 | 2026-11-11 | 130 | Z | Sabikun | Fr,Bk | Fr & Bk | summar sand-1594 pcs frt 1 clr gltr and 1 clr flat emb back 3 clr gltr and 4 clr flat emb |  | Outlet order | NFL3 |  |  | Need Cut | 360 | 360 | 0 | 0 | -1594 | [11 empty] | 46 | Sep'1 |  |  | 01.08.26
BS-NMT | 48307 | 13228342 | 1200 | 122 | 2026-07-08 | 2026-07-14 | SS o nk TS w woven fabric pkt | TS |  |  | 2026-08-15 | 2026-08-20 | 2026-09-01 | 2026-09-15 |  |  | 2026-09-18 | 2026-09-18 | 2026-09-25 | 2026-09-28 | 2026-09-29 | 2026-10-03 | 2026-10-05 |  |  |  |  | 2026-10-07 | 2026-10-10 |  |  | 2026-10-13 | 2026-10-15 | 2026-10-20 | 2026-11-23 | 2026-11-25 | 138 | T2 | Sabikun | Nk |  | 4 combo label print |  | Outlet order | NFL3 |  |  | Need Cut | 124 | 57 | -67 | 0 | -1200 | [11 empty] | 48 | Sep'3 |  |  | 01.08.26
BS-NMT | 48308 | 13269009 | 2800 | 280 | 2026-07-08 | 2026-07-14 | SS o nk TS w woven fabric pkt | TS |  |  | 2026-08-15 | 2026-08-20 | 2026-09-01 | 2026-09-15 |  |  | 2026-09-19 | 2026-09-19 | 2026-09-25 | 2026-09-29 | 2026-09-30 | 2026-10-02 | 2026-10-03 |  |  |  |  | 2026-10-06 | 2026-10-09 |  |  | 2026-10-12 | 2026-10-15 | 2026-10-22 | 2026-11-23 | 2026-11-25 | 138 | T2 | Sabikun | Nk |  | 4 combo label print |  | Outlet order | NFL3 |  |  | Need Cut | 280 | 140 | -140 | 0 | -2800 | [11 empty] | 48 | Sep'3 |  |  | 01.08.26
BS-NMT | 48277 | 13265143 | 807 | 263 | 2026-06-29 | 2026-07-07 | LS V nk Swt shirt w nk YD rib | Swt Shirt | 2026-07-20 | 2026-07-26 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-31 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-14 | 2026-09-16 | 2026-09-17 | 2026-09-19 | 2026-09-23 |  |  |  |  | 2026-09-25 | 2026-09-26 |  |  | 2026-09-29 | 2026-10-02 | 2026-10-10 | 2026-11-02 | 2026-11-04 | 126 | T2 | Sanaul | Chest,Nk |  | almond-807 pcs 1 clr rub print | YD |  | NFL3 |  |  | Need Test Cut | 262 | 0 | -262 | 0 | -807 | [11 empty] | 45 | Sep'2 |  |  | 25.08.26
BS-NMT | 48272 | 13265153 | 1440 | 338 | 2026-06-29 | 2026-07-09 | LS Swt shirt w nk btm cuff rib | Swt Shirt |  |  | 2026-08-04 | 2026-08-10 | 2026-08-15 | 2026-08-28 |  |  | 2026-09-01 | 2026-09-01 | 2026-09-05 | 2026-09-08 | 2026-09-09 | 2026-09-11 | 2026-09-15 |  |  |  |  | 2026-09-17 | 2026-09-19 |  |  | 2026-09-22 | 2026-09-24 | 2026-09-30 | 2026-11-02 | 2026-11-04 | 126 | V | Sanaul | Chest,Nk |  | spring lake-1440 pcs 4 clr rub print |  |  | NFL3 |  |  | Need Test Cut | 359 | 0 | -359 | 0 | -1440 | [11 empty] | 45 | Sep'1 |  |  | 25.08.26
BS-NMT | 48273 | 13265154 | 1450 | 306 | 2026-06-29 | 2026-07-09 | Elasted pant w cut& sew leg | Pant |  |  | 2026-08-06 | 2026-08-13 | 2026-08-18 | 2026-08-31 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-15 | 2026-09-18 | 2026-09-19 | 2026-09-22 | 2026-09-24 |  |  |  |  | 2026-09-26 | 2026-09-29 |  |  | 2026-10-02 | 2026-10-06 | 2026-10-13 | 2026-11-02 | 2026-11-04 | 126 | U | Sanaul | Waist & Thigh |  | spring lake-1450 pcs 4 clr rub print |  | same print as 48272 | NFL3 |  |  | Need Test Cut | 306 | 0 | -306 | 0 | -1450 | [11 empty] | 45 | Sep'2 |  |  | 25.08.26
BS-NMT | 48271 | 13265083 | 801 | 288 | 2026-06-29 | 2026-07-09 | LS Swt shirt w nk btm cuff rib and side cut&sew | Swt Shirt |  |  | 2026-08-04 | 2026-08-10 | 2026-08-15 | 2026-08-28 |  |  | 2026-09-01 | 2026-09-05 | 2026-09-08 | 2026-09-10 | 2026-09-11 | 2026-09-14 | 2026-09-16 |  |  |  |  | 2026-09-18 | 2026-09-19 |  |  | 2026-09-22 | 2026-09-24 | 2026-09-30 | 2026-11-02 | 2026-11-04 | 126 | V | Sanaul | Chest,Nk |  | lava-801 pcs 2 clr rub print |  |  | NFL3 |  |  | File Due | 288 | 0 | -288 | 0 | -801 | [11 empty] | 45 | Sep'1
BS-NMT | 48278 | 13265101 | 1210 | 474 | 2026-06-29 | 2026-07-09 | Trouser w side pkt and leg cut& sew | Trouser |  |  | 2026-08-08 | 2026-08-14 | 2026-08-18 | 2026-08-31 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-15 | 2026-09-18 | 2026-09-19 | 2026-09-22 | 2026-09-23 |  |  |  |  | 2026-09-25 | 2026-09-28 |  |  | 2026-09-30 | 2026-10-03 | 2026-10-08 | 2026-11-02 | 2026-11-04 | 126 | X | Sanaul | Waist |  | 1 combo label print |  |  | NFL3 |  |  | Need Test Cut | 474 | 0 | -474 | 0 | -1210 | [11 empty] | 45 | Sep'2 |  |  | 25.08.26
BS-NMT | 48274 | 13265084 | 1291 | 496 | 2026-06-29 | 2026-07-09 | Trouser w side pkt zipper and leg cut& sew and drawstring | Trouser |  |  | 2026-08-08 | 2026-08-15 | 2026-08-24 | 2026-09-07 |  |  | 2026-09-12 | 2026-09-12 | 2026-09-19 | 2026-09-23 | 2026-09-24 | [6 empty] | 2026-09-26 | 2026-09-29 |  |  | 2026-10-03 | 2026-10-06 | 2026-10-13 | 2026-11-02 | 2026-11-04 | 126 | X | Sanaul | [5 empty] | NFL3 |  |  | Need Test Cut | 486 | 0 | -486 | 0 | -1291 | [11 empty] | 45 | Sep'3 |  |  | 25.08.26
BS-NMT | 48276 | 13265120 | 880 | 122 | 2026-06-29 | 2026-07-09 | waist btm rib pant w leg cut&sew | Pant |  |  | 2026-08-06 | 2026-08-10 | 2026-08-17 | 2026-08-31 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-15 | 2026-09-18 | 2026-09-19 | [6 empty] | 2026-09-22 | 2026-09-24 |  |  | 2026-09-26 | 2026-09-29 | 2026-10-05 | 2026-11-02 | 2026-11-04 | 126 | U | Sanaul | [5 empty] | NFL3 |  |  | Need Cut | 122 | 122 | 0 | 0 | -880 | [11 empty] | 45 | Sep'2 |  |  | 25.08.26
BS-NMT | 48275 | 13265119 | 813 | 169 | 2026-06-29 | 2026-07-09 | Chest double layer overall w snap and wood btn | Overall |  |  | 2026-08-04 | 2026-08-10 | 2026-08-15 | 2026-08-31 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-14 | 2026-09-16 | 2026-09-17 |  |  |  |  | 2026-09-19 | 2026-09-24 | 2026-09-26 | 2026-09-29 |  |  | 2026-10-02 | 2026-10-06 | 2026-10-10 | 2026-11-02 | 2026-11-04 | 126 | S | Sanaul |  | Chest | spring lake-813 pcs self fab applique emb |  |  | NFL3 |  |  | Need Cut | 169 | 169 | 0 | 0 | -813 | [11 empty] | 45 | Sep'2 |  |  | 27.08.26
BS-NMT | 48306 | 13230335/13269016 | 3600 | 399 | 2026-07-08 | 2026-07-10 | SS o nk TS w frt pkt wood btn | TS |  |  | 2026-08-10 | 2026-08-15 | 2026-08-21 | 2026-09-07 |  |  | 2026-09-12 | 2026-09-12 | 2026-09-19 | 2026-09-22 | 2026-09-23 | 2026-09-25 | 2026-09-28 |  |  |  |  | 2026-10-01 | 2026-10-05 |  |  | 2026-10-07 | 2026-10-09 | 2026-10-14 | 2026-11-21 | 2026-11-23 | 136 | Y | Tomal | Nk |  | 3 combo label print |  |  | NFL3 |  |  | File Due | 400 | 400 | 0 | 0 | -3600 | [11 empty] | 48 | Sep'3
BS-ONS | 44076 20th | 22013782 | 4050 | 893 | 2026-07-11 | 2026-07-14 | SS T Shirt | TS |  |  | 2026-08-01 | 2026-08-07 | 2026-08-12 | 2026-08-25 |  |  | 2026-09-01: 2026-09-01; 2026-09-05: 2026-09-01; 2026-09-10: 2026-09-05; 2026-09-11: 2026-09-07 |  |  |  |  | 2026-09-10 | 2026-09-12 |  |  | 2026-09-15 | 2026-09-18 | 2026-09-25 | 2026-11-09 | 2026-11-11 | 121 | F | Shakel | [5 empty] | NFL1 |  |  | Need Cut | 894 | 881 | -13 | 0 | -4050 | [11 empty] | 46 | Sep'1 |  |  | 19.08.26
BS-ONS | 44077 9th | 22012786 | 101555 | 2253 | 2026-07-11 | 2026-07-13 | MENS R NK SS TS W SELF FABRIC NK BINDING | TS |  |  | 2026-08-01 | 2026-08-12 | 2026-08-18 | 2026-09-04 |  |  | 2026-09-01: 2026-09-09; 2026-09-05: 2026-09-09; 2026-09-10: 2026-09-14; 2026-09-11: 2026-09-17 |  |  |  |  | 2026-09-18 | 2026-09-24 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-30 | 2026-11-09 | 2026-11-11 | 121 | G2 | Shovon | [5 empty] | NFL1 |  |  | Cut Run | 2252 | 2203 | -49 | 5181 | -96374 | [11 empty] | 46 | Sep'2 |  |  | 15.08.26
BS-ONS | 48195 | 22040938 | 624 | 357 | 2026-06-25 | 2026-07-14 | LS Swt Hoody w kangaro pkt zipper and cuff btm rib | Hoody |  |  | 2026-08-20 | 2026-08-25 | 2026-09-02 | 2026-09-15 |  |  | 2026-09-19 | 2026-09-19 | 2026-09-26 | 2026-10-01 | 2026-10-02 | 2026-10-05 | 2026-10-09 |  |  |  |  | 2026-10-13 | 2026-10-15 |  |  | 2026-10-17 | 2026-10-21 | 2026-10-25 | 2026-11-16 | 2026-11-18 | 144 | B | Shovon | Fr,Bk |  | forest fog-618 pcs frt back 1 clr puff print |  |  | NFL1 |  |  | CAD | 356 | 0 | -356 | 0 | -624 | [11 empty] | 47 | Oct'1 |  |  | 11.09.26
BS-ONL | 48305 | 15395720 | 2940 | 444 | 2026-07-04 | 2026-07-08 | SS v nk TS | TS |  |  | 2026-08-02 | 2026-08-08 | 2026-08-15 | 2026-08-28 |  |  | 2026-09-01 | 2026-09-01 | 2026-09-05 | 2026-09-09 | 2026-09-11 | 2026-09-12 | 2026-09-15 |  |  | 2026-09-17 | 2026-09-21 | 2026-09-24 | 2026-09-28 |  |  | 2026-09-30 | 2026-10-02 | 2026-10-10 | 2026-11-09 | 2026-11-11 | 128 | O1 | Mainul | Chest | Chest | mermaid-2940 pcs 1 clr rub print and 1 clr lurex emb |  |  | NFL2 |  |  | Need Cut | 445 | 395 | -50 | 0 | -2940 | [11 empty] | 46 | Sep'1 |  |  | 04.09.26
BS-ONL | 48220 | 15387397 | 477 | 140 | 2026-06-20 | 2026-07-13 | SS o nk Dress w waist cut & sew and knot at one slve | Dress |  |  | 2026-08-06 | 2026-08-11 | 2026-08-18 | 2026-08-31 |  |  | 2026-09-05 | 2026-09-05 | 2026-09-11 | 2026-09-14 | 2026-09-15 | [6 empty] | 2026-09-17 | 2026-09-18 |  |  | 2026-09-21 | 2026-09-23 | 2026-09-30 | 2026-11-23 | 2026-11-25 | 156 | J | Abid | [5 empty] | NFL2 |  |  | File Due | 96 | 96 | 0 | 0 | -477 | [11 empty] | 48 | Sep'2
BS-ONL | 48219 | 15387508 | 780 | 101 | 2026-06-20 | 2026-07-13 | YD SS o nk TS | TS | 2026-08-06 | 2026-08-12 | 2026-08-17 | 2026-08-25 | 2026-09-02 | 2026-09-08 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-22 | 2026-09-24 | 2026-09-25 | [6 empty] | 2026-10-01 | 2026-10-02 |  |  | 2026-10-05 | 2026-10-07 | 2026-10-10 | 2026-11-23 | 2026-11-25 | 156 | O1 | Abid |  |  |  | YD |  | NFL2 |  |  | Need Test Cut | 101 | 0 | -101 | 0 | -780 | [11 empty] | 48 | Sep'3 |  |  | 31.08.26
BS-ONL | 48221 | 15387479 | 1875 | 342 | 2026-06-20 | 2026-07-13 | SS long dress w back nk cut out and woven and emb lace attach | Dress |  |  | 2026-08-07 | 2026-08-13 | 2026-08-20 | 2026-09-04 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-14 | 2026-09-16 | 2026-09-18 | [6 empty] | 2026-09-21 | 2026-09-24 |  |  | 2026-09-28 | 2026-09-30 | 2026-10-05 | 2026-11-23 | 2026-11-25 | 156 | J | Abid |  |  |  |  | Lace | NFL2 |  |  | File Due | 342 | 192 | -150 | 0 | -1875 | [11 empty] | 48 | Sep'2
BS-ONL | 48215 | 15388165 | 648 | 119 | 2026-06-20 | 2026-07-14 | Long elasted leggigng | Legging |  |  | 2026-08-10 | 2026-08-15 | 2026-08-24 | 2026-09-10 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-21 | 2026-09-23 | 2026-09-24 | [6 empty] | 2026-09-26 | 2026-09-28 |  |  | 2026-09-30 | 2026-10-02 | 2026-10-06 | 2026-11-23 | 2026-11-25 | 156 | P | Abid | [5 empty] | NFL2 |  |  | File Due | 119 | 119 | 0 | 0 | -648 | [11 empty] | 48 | Sep'3
OVS SPA | 48300 | 271PJA306-903 | 25484 | 5968 | 2026-07-08 | 2026-07-10 | LS boat nk TS and elasted AOP pant | Top & BTM |  |  | 2026-09-01 | 2026-09-14 | 2026-09-14 | 2026-09-30 | 2026-10-01 | 2026-10-12 | 2026-10-20 | 2026-10-09 | 2026-10-16 | 2026-10-17 | 2026-10-24 |  |  |  |  | 2026-10-23 | 2026-10-30 | 2026-10-30 | 2026-11-11 |  |  | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-16 | 2026-11-16 | 131 | A+E | Salam |  | Chest | c.dan top-7396 pcs 7 clr flat emb ,,aqua top -5347 pcs 5 clr flat emb ,,all btm AOP-12743 pcs no emb | AOP |  | NFL1 |  |  | File Due | 5979 | 767 | -5212 | 0 | -25484 | [11 empty] | 47 | Oct'2
BS-NMT | 48101 | 13251004 | 3346 | 583 | 2026-06-10 | 2026-07-08 | AOP SS o nk TS | TS |  |  | 2026-09-08 | 2026-09-15 | 2026-09-23 | 2026-10-05 | 2026-10-10 | 2026-10-17 | 2026-10-23 | 2026-10-23 | 2026-10-29 | 2026-11-02 | 2026-11-04 | 2026-11-06 | 2026-11-07 |  |  |  |  | 2026-11-11 | 2026-11-14 |  |  | 2026-11-17 | 2026-11-19 | 2026-11-28 | 2027-02-20 | 2027-02-22 | 255 | ZA1 | Shamoly | Nk |  | 3 combo nk label print | AOP |  | NFL3 |  |  | File Due | 583 | 0 | -583 | 0 | -3346 | [11 empty] | 9 | Nov'1
BS-NMT | 48102 | 13251005 | 3286 | 507 | 2026-06-10 | 2026-07-08 | AOP Swt Shorts w waist belt and side pkt contrast tape string | Shorts |  |  | 2026-09-02 | 2026-09-08 | 2026-09-14 | 2026-09-30 | 2026-10-06 | 2026-10-14 | 2026-10-17 | 2026-10-17 | 2026-10-24 | 2026-10-28 | 2026-10-30 | 2026-11-02 | 2026-11-04 |  |  |  |  | 2026-11-06 | 2026-11-11 |  |  | 2026-11-14 | 2026-11-17 | 2026-11-25 | 2027-02-20 | 2027-02-22 | 255 | X | Shamoly | Waist |  | 3 combo label print | AOP |  | NFL3 |  |  | File Due | 507 | 0 | -507 | 0 | -3286 | [11 empty] | 9 | Oct'3
BS-NMT | 48103 | 13251006/13267093 | 6413 | 988 | 2026-06-10 | 2026-07-08 | SS o nk TS | TS |  |  | 2026-09-15 | 2026-09-20 | 2026-09-25 | 2026-10-10 |  |  | 2026-10-17 | 2026-10-17 | 2026-10-24 | 2026-10-27 | 2026-10-30 | 2026-11-02 | 2026-11-07 |  |  |  |  | 2026-11-10 | 2026-11-13 |  |  | 2026-11-17 | 2026-11-20 | 2026-11-26 | 2027-02-20 | 2027-02-22 | 255 | ZA1 | Shamoly | Fr & Bk & Nk |  | feather grey-1830 pcs frt 2 clr pig back no print ,,chive-2042 pcs frt back 3 clr rub print ,,white-2541 pcs frt 6 clr pig back no print |  |  | NFL3 |  |  | File Due | 987 | 0 | -987 | 0 | -6413 | [11 empty] | 9 | Oct'3
BS-NMT | 48105 | 13251039 | 4888 | 538 | 2026-06-10 | 2026-07-08 | AOP SS o nk TS | TS |  |  | 2026-09-05 | 2026-09-10 | 2026-09-15 | 2026-09-30 | 2026-10-09 | 2026-10-19 | 2026-10-23 | 2026-10-23 | 2026-10-29 | 2026-11-02 | 2026-11-05 | 2026-11-05 | 2026-11-07 |  |  |  |  | 2026-11-10 | 2026-11-14 |  |  | 2026-11-17 | 2026-11-19 | 2026-11-25 | 2027-02-20 | 2027-02-22 | 255 | ZA1 | Shamoly | Nk |  | 3 combo nk label print | AOP |  | NFL3 |  |  | File Due | 537 | 0 | -537 | 0 | -4888 | [11 empty] | 9 | Nov'1
BS-NMT | 48107 | 13251505 | 10763 | 930 | 2026-06-10 | 2026-07-08 | AOP Swt Shorts w waist belt and side pkt draw string and btm letus frill | Shorts |  |  | 2026-09-03 | 2026-09-10 | 2026-09-15 | 2026-09-30 | 2026-10-06 | 2026-10-17 | 2026-10-22 | 2026-10-22 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2026-11-04 | 2026-11-07 |  |  |  |  | 2026-11-10 | 2026-11-21 |  |  | 2026-11-24 | 2026-11-28 | 2026-11-05 | 2027-02-20 | 2027-02-22 | 255 | X | Shamoly | Waist |  | 3 combo label print | AOP |  | NFL3 |  |  | File Due | 929 | 0 | -929 | 0 | -10763 | [11 empty] | 9 | Nov'1
BS-NMT | 48104 | 13251031 | 6204 | 610 | 2026-06-10 | 2026-07-10 | SS o nk TS and waist rib shorts w drawstring | Top & BTM |  |  | 2026-09-13 | 2026-09-20 | 2026-10-05 | 2026-10-20 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-10 | 2026-11-14 | 2026-11-17 | 2026-11-20 | 2026-11-24 |  |  |  |  | 2026-12-01 | 2026-12-04 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-15 | 2027-02-20 | 2027-02-22 | 255 | U+T1 | Shamoly | Chest,Nk |  | aquacade top -1551 pcs 3 clr rub print ,,LGM btm-1551 pcs no print ,,white top-1551 pcs 5 clr pig print ,,chive btm-1551 pcs no print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -6204 | [11 empty] | 9 | Nov'2
BS-NMT | 48106 | 13251045 | 5133 | 431 | 2026-06-10 | 2026-07-10 | AOP waist belt Shorts w side pkt drawstring | Shorts |  |  | 2026-09-05 | 2026-09-15 | 2026-09-25 | 2026-10-12 | 2026-10-17 | 2026-10-27 | 2026-11-05 | 2026-11-05 | 2026-11-12 | 2026-11-16 | 2026-11-19 | 2026-11-20 | 2026-11-24 |  |  |  |  | 2026-12-01 | 2026-12-07 |  |  | 2026-12-09 | 2026-12-12 | 2026-12-21 | 2027-02-20 | 2027-02-22 | 255 | X | Shamoly | Waist |  | 3 combo label print | AOP |  | NFL3 |  |  | File Due | 496 | 0 | -496 | 0 | -5133 | [11 empty] | 9 | Nov'2
BS-NMT | 48291 | 13267983 | 3658 | 268 | 2026-07-02 | 2026-07-10 | SS puff slve TS w shlder snap btn | TS |  |  | 2026-08-01 | 2026-08-07 | 2026-08-13 | 2026-08-31 |  |  | 2026-09-05 | 2026-09-05 | 2026-09-11 | 2026-09-14 | 2026-09-17 | 2026-09-17 | 2026-09-22 |  |  |  |  | 2026-09-24 | 2026-09-30 |  |  | 2026-10-03 | 2026-10-06 | 2026-10-13 | 2026-12-28 | 2026-12-30 | 179 | Y | Sabikun | Chest,Nk |  | pink-1056 pcs,,Aqua-1246 pcs,,c.dan-1356 pcs all combo 1 clr gltr print |  | Outlet order | NFL3 |  |  | Need Cut | 268 | 268 | 0 | 0 | -3658 | [11 empty] | 53 | Sep'2 |  |  | 10.08.26
BS-NMT | 48289 | 13268790 | 810 | 80 | 2026-07-02 | 2026-07-10 | SS o nk TS | TS |  |  | 2026-08-03 | 2026-08-06 | 2026-08-14 | 2026-08-27 |  |  | 2026-08-31 | 2026-08-31 | 2026-09-05 | 2026-09-08 | 2026-09-08 | 2026-09-10 | 2026-09-14 |  |  | 2026-09-16 | 2026-09-22 | 2026-09-25 | 2026-09-26 |  |  | 2026-09-29 | 2026-10-02 | 2026-10-10 | 2026-12-07 | 2026-12-09 | 158 | T1 | Sabikun | Chest,Nk | Chest | pink-405 pcs 2 clr puff 2 clr pig 1 clr gltr and chiffon flower tapping emb ,,white-405 pcs 2 clr pig 2 clr gltr gel print and plastic trasparent patch attach inside sequin emb w lurex thread |  | Outlet order | NFL3 |  |  | Need Cut | 80 | 80 | 0 | 0 | -810 | [11 empty] | 50 | Sep'1 |  |  | 01.08.26
BS-NMT | 48290 | 13267677 | 3723 | 316 | 2026-07-02 | 2026-07-10 | SS o nk TS | TS |  |  | 2026-08-01 | 2026-08-04 | 2026-08-10 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-26 | 2026-09-02 | 2026-09-04 | 2026-09-07 | 2026-09-07 | 2026-09-10 |  |  | 2026-09-10 | 2026-09-19 | 2026-09-23 | 2026-09-28 |  |  | 2026-10-02 | 2026-10-06 | 2026-10-12 | 2026-12-07 | 2026-12-09 | 158 | T1 | Sabikun | Chest,Nk | Chest | pink-1227 pcs 2 clr puff 2 clr pig 1 clr gltr and chiffon flower tapping emb,,vanilla-1248 pcs 5 clr pig 2 clr puff 2 clr gltr and 1 clr chiffon tapping emb ,,white-1248 pcs 2 clr pig 2 clr gltr gel print and plastic trasparent patch attach inside sequin emb w lurex |  | Outlet order | NFL3 |  |  | Need Cut | 316 | 316 | 0 | 0 | -3723 | [11 empty] | 50 | Sep'1 |  |  | 01.08.26
BS-NMT | 48288 | 13242502 | 4050 | 371 | 2026-07-02 | 2026-07-10 | SS TS w slve woven lace and btm knot | TS |  |  | 2026-08-04 | 2026-08-09 | 2026-08-15 | 2026-08-31 |  |  | 2026-09-05 | 2026-09-05 | 2026-09-12 | 2026-09-15 | 2026-09-18 | 2026-09-18 | 2026-09-22 |  |  |  |  | 2026-09-24 | 2026-09-30 |  |  | 2026-10-03 | 2026-10-06 | 2026-10-13 | 2026-11-30 | 2026-12-02 | 151 | S | Sabikun | Nk |  | 2 combo label print |  | Outlet order | NFL3 |  |  | Cut Run | 372 | 340 | -32 | 3930 | -120 | [11 empty] | 49 | Sep'2 |  |  | 01.08.26
BS-NMT | 48292 | 13256349 | 4284 | 436 | 2026-07-08 | 2026-07-10 | SS polo Shirt w flat knit collar cuff and placket w btn | Polo | 2026-08-01 | 2026-08-07 | 2026-08-10 | 2026-08-17 | 2026-08-20 | 2026-09-05 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-17 | 2026-09-19 | 2026-09-22 | 2026-09-24 | 2026-09-26 |  |  | 2026-09-24 | 2026-09-28 | 2026-10-01 | 2026-10-06 |  |  | 2026-10-08 | 2026-10-10 | 2026-10-13 | 2026-12-07 | 2026-12-09 | 152 | S | Tomal | Nk | Chest | Pure-1050 pcs,,aqua-1050 pcs,,blue-1113 pcs,,white-1071 pcs all combo 1 clr flat emb | YD |  | NFL3 |  |  | File Due | 436 | 0 | -436 | 0 | -4284 | [11 empty] | 50 | Sep'2
BS-NMT | 48293 | 13260882 | 2004 | 1027 | 2026-07-08 | 2026-07-10 | LS Swt hoody w full zipper cuff btm rib | Hoody |  |  | 2026-08-07 | 2026-08-12 | 2026-08-20 | 2026-09-05 |  |  | 2026-09-12 | 2026-09-12 | 2026-09-19 | 2026-09-23 | 2026-09-24 | 2026-09-26 | 2026-09-30 |  |  |  |  | 2026-10-05 | 2026-10-09 |  |  | 2026-10-12 | 2026-10-14 | 2026-10-20 | 2026-11-30 | 2026-12-02 | 145 | S | Tomal | Chest |  | pure-1002 pcs,,navy-1002 pcs both combo 1 clr puff print |  |  | NFL3 |  |  | File Due | 1026 | 513 | -513 | 0 | -2004 | [11 empty] | 49 | Sep'3
BS-NMT | 48294 | 13267868 | 4197 | 442 | 2026-07-08 | 2026-07-10 | SS o nk TS | TS |  |  | 2026-09-01 | 2026-09-06 | 2026-09-15 | 2026-09-30 |  |  | 2026-10-08 | 2026-10-08 | 2026-10-14 | 2026-10-17 | 2026-10-20 | 2026-10-22 | 2026-10-24 |  |  | 2026-10-26 | 2026-10-29 | 2026-11-02 | 2026-11-05 |  |  | 2026-11-07 | 2026-11-10 | 2026-11-18 | 2026-12-28 | 2026-12-30 | 173 | ZA1 | Tomal | Nk | Chest | shell-1539 pcs 2 clr flat emb ,,pearl-1539 pcs 3 clr flat emb ,,white-1119 pcs 1 clr flat emb |  |  | NFL3 |  |  | File Due | 442 | 313 | -129 | 0 | -4197 | [11 empty] | 53 | Oct'2
BS-NMT | 48295 | 13267869 | 2478 | 235 | 2026-07-08 | 2026-07-10 | SS o nk TS | TS |  |  | 2026-09-01 | 2026-09-05 | 2026-09-10 | 2026-09-25 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-12 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-21 |  |  | 2026-10-23 | 2026-10-28 | 2026-11-03 | 2026-11-05 |  |  | 2026-11-09 | 2026-11-12 | 2026-11-17 | 2026-12-28 | 2026-12-30 | 173 | ZA1 | Tomal | Chest,Nk | Chest | shell-1470 pcs..popcorn-1008 pcs both combo 1 clr rub and 3 type printed patch attach emb |  | Chest+Patch block print | NFL3 |  |  | File Due | 236 | 221 | -15 | 0 | -2478 | [11 empty] | 53 | Oct'2
BS-NMT | 48296 | 13267871 | 2238 | 302 | 2026-07-08 | 2026-07-10 | SS YD o nk TS | TS | 2026-08-26 | 2026-09-05 | 2026-09-10 | 2026-09-21 | 2026-09-25 | 2026-10-05 |  |  | 2026-10-13 | 2026-10-13 | 2026-10-20 | 2026-10-23 | 2026-10-24 | 2026-10-28 | 2026-10-29 |  |  |  |  | 2026-11-02 | 2026-11-04 |  |  | 2026-11-06 | 2026-11-10 | 2026-11-17 | 2026-12-28 | 2026-12-30 | 173 | Z | Tomal | Nk |  | 2 combo label print | YD |  | NFL3 |  |  | File Due | 302 | 0 | -302 | 0 | -2238 | [11 empty] | 53 | Oct'3
BS-ONS | 48197 | 22033202 | 10434 | 2163 | 2026-06-25 | 2026-07-08 | SS o nk TS | TS |  |  | 2026-08-13 | 2026-08-24 | 2026-09-05 | 2026-09-20 |  |  | 2026-09-25 | 2026-09-25 | 2026-10-02 | 2026-10-06 | 2026-10-10 | [6 empty] | 2026-10-12 | 2026-10-17 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-30 | 2026-12-14 | 2026-12-16 | 172 | D1 | Shovon | [5 empty] | NFL1 |  |  | File Due | 2163 | 2163 | 0 | 0 | -10434 | [11 empty] | 51 | Oct'1
BS-ONS | 48196 | 22040925 | 2094 | 613 | 2026-06-25 | 2026-07-08 | SS Shirt w full collar placket btn and frt pkt | Shirt |  |  | 2026-08-18 | 2026-08-25 | 2026-09-04 | 2026-09-19 |  |  | 2026-09-26 | 2026-09-26 | 2026-10-03 | 2026-10-07 | 2026-10-08 | [6 empty] | 2026-10-12 | 2026-10-15 |  |  | 2026-10-17 | 2026-10-20 | 2026-10-27 | 2026-12-14 | 2026-12-16 | 172 | B | Shovon | [5 empty] | NFL1 |  |  | File Due | 613 | 423 | -190 | 0 | -2094 | [11 empty] | 51 | Oct'1
BS-ONS | 48198 | 22033207 | 12586 | 2411 | 2026-06-25 | 2026-07-08 | Waist belt shorts w side pkt back bon pkt and fake fly | Shorts |  |  | 2026-08-25 | 2026-09-05 | 2026-09-10 | 2026-09-30 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-12 | 2026-10-14 | 2026-10-20 | [6 empty] | 2026-10-17 | 2026-10-31 |  |  | 2026-11-04 | 2026-11-06 | 2026-11-10 | 2026-12-14 | 2026-12-16 | 172 | C | Shovon | [5 empty] | NFL1 |  |  | File Due | 2410 | 1975 | -435 | 0 | -12586 | [11 empty] | 51 | Oct'2
BS-ONL | 22042 64th | 15205059 | 1224 | 189 | 2026-07-10 | 2026-07-13 | SS o nk TS | TS |  |  | 2026-09-01 | 2026-09-06 | 2026-09-15 | 2026-09-30 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-22 | 2026-10-26 | 2026-10-27 | [6 empty] | 2026-11-02 | 2026-11-03 |  |  | 2026-11-06 | 2026-11-10 | 2026-11-17 | 2027-01-11 | 2027-01-13 | 185 | O2 | Imran | [5 empty] | NFL2 |  |  | Po Sheet Due | 189 | 0 | -189 | 0 | -1224 | [11 empty] | 3 | Oct'3
BS-ONL | 48231 | 15324397 | 2772 | 512 | 2026-06-20 | 2026-07-13 | SL long Dress w side slit | Dress |  |  | 2026-08-03 | 2026-08-18 | 2026-08-25 | 2026-09-10 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-21 | 2026-09-23 | 2026-09-24 | [6 empty] | 2026-09-26 | 2026-09-30 |  |  | 2026-10-03 | 2026-10-06 | 2026-10-10 | 2026-12-21 | 2026-12-23 | 184 | O1 | Abid | [5 empty] | NFL2 |  |  | Need Cut | 511 | 125 | -386 | 0 | -2772 | [11 empty] | 52 | Sep'3 |  |  | 03.09.26
BS-ONL | 48229 | 15325769 | 2964 | 534 | 2026-06-20 | 2026-07-13 | SS Long dresss w shlder Woven emb lace | Dress |  |  | 2026-08-08 | 2026-08-16 | 2026-08-22 | 2026-09-11 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-22 | 2026-09-25 | 2026-09-28 | [6 empty] | 2026-10-01 | 2026-10-05 |  |  | 2026-10-07 | 2026-10-10 | 2026-10-13 | 2026-12-21 | 2026-12-23 | 184 | K | Abid |  |  |  |  | Lace | NFL2 |  |  | File Due | 534 | 231 | -303 | 0 | -2964 | [11 empty] | 52 | Sep'3
BS-ONL | 48226 | 15371458 | 8163 | 1088 | 2026-06-20 | 2026-07-14 | SS o nk TS | TS |  |  | 2026-08-01 | 2026-08-10 | 2026-08-13 | 2026-08-31 |  |  | 2026-09-05 | 2026-09-05 | 2026-09-12 | 2026-09-16 | 2026-09-19 | 2026-09-19 | 2026-09-26 |  |  |  |  | 2026-10-01 | 2026-10-07 |  |  | 2026-10-10 | 2026-10-13 | 2026-10-17 | 2026-12-21 | 2026-12-23 | 184 | O1 | Abid | Fr,Bk |  | air blue-2757 pcs frt 4 clr pig back 8 clr pig ,,c.dancer-2685 pcs frt 5 clr pig back 11 clr pig ,,pink-2721 pcs frt 4 clr pig back 8 clr pig |  |  | NFL2 |  |  | Need Cut | 1089 | 1089 | 0 | 0 | -8163 | [11 empty] | 52 | Sep'2 |  |  | 22.08.26
BS-ONL | 48230 | 15325767 | 5523 | 608 | 2026-06-20 | 2026-07-14 | SS TS w slve woven emb lace | TS |  |  | 2026-08-06 | 2026-08-15 | 2026-08-23 | 2026-09-10 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-22 | 2026-09-25 | 2026-09-28 | [6 empty] | 2026-10-01 | 2026-10-06 |  |  | 2026-10-09 | 2026-10-12 | 2026-10-16 | 2026-12-21 | 2026-12-23 | 184 | N1 | Abid |  |  |  |  | Lace | NFL2 |  |  | File Due | 609 | 609 | 0 | 0 | -5523 | [11 empty] | 52 | Sep'3
BS-ONL | 48235 | 15388150 | 1128 | 110 | 2026-06-20 | 2026-07-14 | SS o nk TS w chest woven emb lace | TS |  |  | 2026-08-25 | 2026-08-30 | 2026-09-10 | 2026-09-25 |  |  | 2026-10-06 | 2026-10-06 | 2026-10-13 | 2026-10-16 | 2026-10-17 | [6 empty] | 2026-10-21 | 2026-10-24 |  |  | 2026-10-27 | 2026-10-29 | 2026-11-05 | 2026-12-21 | 2026-12-23 | 184 | K | Abid |  |  |  |  | Lace | NFL2 |  |  | File Due | 110 | 110 | 0 | 0 | -1128 | [11 empty] | 52 | Oct'2
BS-ONL | 48206 2nd | 15346421 | 3500 | 438 | 2026-07-09 | 2026-07-14 | AOP SS o nk TS | TS |  |  | 2026-08-06 | 2026-08-16 | 2026-09-25 | 2026-10-10 | 2026-10-12 | 2026-10-20 | 2026-11-02 | 2026-11-02 |  | 2026-11-10 | 2026-11-13 | [6 empty] | 2026-11-18 | 2026-11-21 |  |  | 2026-11-24 | 2026-11-26 | 2026-11-30 | 2026-12-14 | 2026-12-16 | 158 | O1 | Abid |  |  |  | AOP |  | NFL2 |  |  | CAD | 438 | 438 | 0 | 0 | -3500 | [11 empty] | 51 | Sep'3 |  |  | 15.09.26
BS-ONS | 47818 3rd | 22041282 | 3051 | 1041 | 2026-07-15 | 2026-07-15 | SS TS w nk and arm hole contrast piping | TS |  |  | 2026-07-20 | 2026-07-24 | 2026-07-27 | 2026-08-06 |  |  | 2026-08-06 | 2026-08-01 |  | 2026-08-08 | 2026-08-10 | [6 empty] | 2026-08-11 | 2026-08-13 |  |  | 2026-08-15 | 2026-08-15 | 2026-08-17 | 2026-08-17 | 2026-08-19 | 33 | D1 | Shovon | [5 empty] | NFL1 |  |  | Cut Ok | 1041 | 1041 | 0 | 3153 | 102 | [11 empty] | 34 | Aug'1 |  |  | 27.07.26
BS-ONS | 48321 | 22042193 | 3990 | 1029 | 2026-07-15 | 2026-07-15 | SS o nk TS w nk rib | TS |  |  | 2026-07-17 | 2026-07-21 | 2026-07-24 | 2026-08-03 |  |  | 2026-08-01 | 2026-08-01 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-08 | 2026-08-10 |  |  |  |  | 2026-08-11 | 2026-08-13 |  |  | 2026-08-14 | 2026-08-15 | 2026-08-15 | 2026-08-17 | 2026-08-19 | 33 | O1 | Shovon | Heat Press/Heat Seal |  | 5 combo nk HP |  |  | NFL2 |  |  | Cut Ok | 1025 | 1025 | 0 | 0 | -3990 | [11 empty] | 34 | Aug'1 |  |  | 27.07.26
BS-ONL | 48139 2nd | 15397312 | 600 | 154 | 2026-07-15 | 2026-07-16 | LS v nk TS | TS |  |  | 2026-07-24 | 2026-07-28 | 2026-08-03 | 2026-08-10 |  |  | 2026-08-10 | 2026-08-10 |  | 2026-08-14 | 2026-08-14 | [6 empty] | 2026-08-17 | 2026-08-18 |  |  | 2026-08-20 | 2026-08-24 | 2026-08-25 | 2026-08-29 | 2026-08-31 | 45 | N1 | Mainul | [5 empty] | NFL2 |  |  | Cut Ok | 154 | 154 | 0 | 632 | 32 | [11 empty] | 36 | Aug'2 |  |  | 07.08.26
BS-NMT | 44842 10th | 13227981 | 1040 | 147 | 2026-07-22 | 2026-07-23 | GIRLS AOP LEGGING | LEGGING |  |  | 2026-08-01 | 2026-08-04 | 2026-08-10 | 2026-08-17 | 2026-08-20 | 2026-08-25 | 2026-08-25 | 2026-08-25 |  | 2026-09-01 | 2026-09-01 | 2026-09-03 | 2026-09-04 |  |  |  |  | 2026-09-07 | 2026-09-08 |  |  | 2026-09-09 | 2026-09-10 | 2026-09-12 | 2026-09-14 | 2026-09-16 | 54 | W2 | Jafar | WAIST |  | 1 combo label print | AOP |  | NFL3 |  |  | Cut Ok | 147 | 147 | 0 | 1079 | 39 | [11 empty] | 38 | Sep'1 |  |  | 21.08.26
BS-NMT | 43316 28th | 13234729 | 5040 | 867 | 2026-07-22 | 2026-07-23 | LS o nk TS | TS |  |  | 2026-08-01 | 2026-08-10 | 2026-08-12 | 2026-08-28 |  |  | 2026-09-03 | 2026-09-03 |  | 2026-09-08 | 2026-09-10 | 2026-09-11 | 2026-09-12 |  |  |  |  | 2026-09-15 | 2026-09-18 |  |  | 2026-09-21 | 2026-09-22 | 2026-09-24 | 2026-09-28 | 2026-09-30 | 68 | ZA2 | Jafar | Nk |  | 3 combo label print |  |  | NFL3 |  |  | Cut Ok | 867 | 867 | 0 | 5121 | 81 | [11 empty] | 40 | Sep'1 |  |  | 21.08.26
BS-ONL | 48335 | 15398492 | 810 | 402 | 2026-07-16 | 2026-07-18 | LS Swt Polo Shirt w collar cuff btm rib and frt placket btn | Polo |  |  | 2026-08-22 | 2026-08-28 | 2026-08-03 | 2026-08-14 |  |  | 2026-08-15 | 2026-08-15 | 2026-08-21 | 2026-08-22 | 2026-08-24 |  |  |  |  | 2026-08-26 | 2026-08-29 | 2026-09-01 | 2026-09-03 |  |  | 2026-09-04 | 2026-09-05 | 2026-09-05 | 2026-09-05 | 2026-09-07 | 51 | R | Mainul |  | Front,Slv | beech-810 pcs chest 1 clr flat one patch attach emb one slve 3 clr flat emb and another slvee patch attach emb |  |  | NFL2 |  |  | Cut Ok | 405 | 405 | 0 | 830 | 20 | [11 empty] | 37 | Aug'3 |  |  | 29.08.26
BS-ONL | 48238 | 15397105 | 516 | 64 | 2026-07-07 | 2026-07-17 | SS o nk TS | TS |  |  | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-25 |  |  | 2026-09-01 | 2026-09-01 | 2026-09-07 | 2026-09-10 | 2026-09-10 | 2026-09-12 | 2026-09-15 |  |  |  |  | 2026-09-17 | 2026-09-18 |  |  | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-28 | 2026-09-30 | 83 | M | Abid | Chest,Nk |  | pink-516 pcs photo print w 4 clr pig |  | License order | NFL2 |  |  | Cut Ok | 63 | 63 | 0 | 533 | 17 | [11 empty] | 40 | Sep'1 |  |  | 31.08.26
BS-ONL | 48239 | 15397108 | 504 | 179 | 2026-07-07 | 2026-07-17 | LS drop slve Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-08-01 | 2026-08-06 | 2026-08-14 | 2026-08-25 |  |  | 2026-08-28 | 2026-08-28 | 2026-09-04 | 2026-09-07 | 2026-09-07 | 2026-09-09 | 2026-09-11 |  |  |  |  | 2026-09-14 | 2026-09-15 |  |  | 2026-09-18 | 2026-09-22 | 2026-09-23 | 2026-09-28 | 2026-09-30 | 83 | N2 | Abid | Chest |  | tofu-504 pcs photo print w 1 clr pig |  | License order | NFL2 |  |  | Need Cut FB | 179 | 0 | -179 | 0 | -504 | [11 empty] | 40 | Sep'1 |  |  | 31.08.26
OVS SPA | 48261 | 271POL004-226 | 5537 | 1583 | 2026-07-15 | 2026-07-18 | YD LS Polo shirt w cuff rib and side slit and collar placket btn | Polo | 2026-08-01 | 2026-08-10 | 2026-08-11 | 2026-08-20 | 2026-08-21 | 2026-08-31 |  |  | 2026-09-10 | 2026-09-03 | 2026-09-09 | 2026-09-10 | 2026-09-12 |  |  |  |  | 2026-09-12 | 2026-09-17 | 2026-09-16 | 2026-09-23 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-28 | 2026-09-28 | 75 | N/2 | Sirajul |  | Fr & Bk | white stripe-5537 pcs frt 1 clr flat emb back 1 clr flat 3 clr twill fabric applique emb | YD |  | NCL |  |  | Need Test Cut | 1584 | 0 | -1584 | 0 | -5537 | [11 empty] | 40 | Sep'1
OVS SPA | 48262 | 271SWT028-226 | 7047 | 1680 | 2026-07-15 | 2026-07-18 | LS Half zipper Swt shirt w collar and cuff btm YD rib | Swt Shirt | 2026-07-22 | 2026-08-03 | 2026-08-01 | 2026-08-13 | 2026-08-14 | 2026-08-29 |  |  | 2026-09-08 | 2026-09-01 | 2026-09-07 | 2026-09-08 | 2026-09-11 |  |  |  |  | 2026-09-10 | 2026-09-15 | 2026-09-15 | 2026-09-23 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-28 | 2026-09-28 | 75 | N/2 | Sirajul |  | Chest | sugar swizzzle-7047 pcs 1 clr flat 1 clr twill fab applique emb | YD |  | NCL |  |  | Ready Test Cut | 1680 | 1641 | -39 | 0 | -7047 | [11 empty] | 40 | Sep'1
OVS SPA | 48263 | 271SWT029-226 | 4214 | 1838 | 2026-07-15 | 2026-07-18 | LS reglan full zipper Swt hoody w kangaro pkt and cuff btm rib | Hoody |  |  | 2026-08-01 | 2026-08-13 | 2026-08-14 | 2026-08-29 |  |  | 2026-09-10 | 2026-09-03 | 2026-09-09 | 2026-09-10 | 2026-09-12 | 2026-09-12 | 2026-09-17 |  |  |  |  | 2026-09-17 | 2026-09-23 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-28 | 2026-09-28 | 75 | N/3 | Sirajul | Bk |  | vista blue-4214 pcs 4 clr rub print |  |  | NCL |  |  | Ready Test Cut | 1820 | 1781 | -39 | 0 | -4214 | [11 empty] | 40 | Sep'1
GBX-New Look | 47424 3rd | 9646803 | 6060 | 1975 | 2026-07-18 | 2026-07-20 | YD legging w drawstring | Legging | 2026-07-25 | 2026-08-01 | 2026-08-01 | 2026-08-14 | 2026-08-12 | 2026-08-20 |  |  | 2026-08-22 | 2026-08-22 |  | 2026-08-27 | 2026-08-31 | [6 empty] | 2026-09-01 | 2026-09-05 |  |  | 2026-09-07 | 2026-09-08 | 2026-09-10 | 2026-09-12 | 2026-09-12 | 56 | N/1 | Sifat |  |  |  | YD |  | NCL |  |  | Ready Test Cut | 1975 | 1846 | -129 | 0 | -6060 | [11 empty] | 37 | Aug'3
GBX-New Look | 47403 4th | 9603199 | 6060 | 750 | 2026-07-18 | 2026-07-20 | YD SL TS w full placket btn | TS | 2026-07-28 | 2026-08-04 | 2026-08-06 | 2026-08-15 | 2026-08-17 | 2026-08-22 |  |  | 2026-08-22 | 2026-08-22 |  | 2026-08-28 | 2026-09-01 | [6 empty] | 2026-09-01 | 2026-09-05 |  |  | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-12 | 2026-09-12 | 56 | N/3 | Sifat |  |  |  | YD |  | NCL |  |  | Ready Test Cut | 751 | 751 | 0 | 0 | -6060 | [11 empty] | 37 | Aug'3
GBX-Anthony's | 47356 3rd | 67941/68173 | 5361 | 1365 | 2026-07-16 | 2026-07-16 | SS o nk TS | TS |  |  | 2026-07-24 | 2026-08-01 | 2026-08-01 | 2026-08-17 |  |  | 2026-08-17 | 2026-08-17 |  | 2026-08-22 | 2026-08-25 | [6 empty] | 2026-08-26 | 2026-08-31 |  |  | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-07 | 53 | N/1 | Shofi | [5 empty] | NCL |  |  | Ready Test Cut | 1362 | 1329 | -33 | 0 | -5361 | [11 empty] | 37 | Aug'3
BS-NMT | 48111 | 13264812 | 7620 | 775 | 2026-07-16 | 2026-07-20 | SS o nk TS | TS |  |  | 2026-08-01 | 2026-08-07 | 2026-08-17 | 2026-08-31 |  |  | 2026-09-01 | 2026-09-01 | 2026-09-05 | 2026-09-07 | 2026-09-10 | 2026-09-09 | 2026-09-14 |  |  |  |  | 2026-09-14 | 2026-09-19 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-26 | 2026-10-02 | 2026-10-04 | 78 | ZA2 | Shamoly | Fr & Bk & Nk |  | c.dan-7620 pcs frt 4 clr rub 1 clr puff back 6 clr rub 1 clr puff |  |  | NFL3 |  |  | Cut Run | 1435 | 1435 | 0 | 7596 | -24 | [11 empty] | 41 | Sep'1 |  |  | 27.08.26
BS-ONL | 48440 | 15388784 | 5736 | 813 | 2026-07-16 | 2026-07-22 | Short w ajustable waist elastic and self fab string | Shorts |  |  | 2026-08-01 | 2026-08-13 | 2026-08-16 | 2026-08-31 |  |  | 2026-09-05 | 2026-09-05 | 2026-09-11 | 2026-09-14 | 2026-09-16 | 2026-09-16 | 2026-09-19 |  |  |  |  | 2026-09-22 | 2026-09-28 |  |  | 2026-09-30 | 2026-10-03 | 2026-10-06 | 2026-10-19 | 2026-10-21 | 95 | P | Abid | Thigh |  | Navy-5736 pcs 1 clr gold foil print |  |  | NFL2 |  |  | File Due | 794 | 794 | 0 | 0 | -5736 | [11 empty] | 43 | Sep'2
BS-ONL | 48240 | 15388782 | 5964 | 696 | 2026-07-16 | 2026-07-22 | SS o nk TS | TS |  |  | 2026-08-01 | 2026-08-08 | 2026-08-14 | 2026-08-31 |  |  | 2026-09-05 | 2026-09-05 | 2026-09-12 | 2026-09-15 | 2026-09-18 | 2026-09-18 | 2026-09-22 |  |  |  |  | 2026-09-24 | 2026-09-29 |  |  | 2026-10-03 | 2026-10-05 | 2026-10-10 | 2026-10-19 | 2026-10-21 | 95 | O1 | Abid | Chest |  | c.dan-5968 pcs 1 clr gold foil print |  |  | NFL2 |  |  | Cut Ok | 697 | 697 | 0 | 6097 | 133 | [11 empty] | 43 | Sep'2 |  |  | 21.08.26
OVS SPA | 47926 | 271SWT005-222 | 3198 | 2271 | 2026-07-01 | 2026-07-16 | LS Swt hoody w chest slve zigzag stitch line and kangaro pkt and cuff btm rib | Hoody |  |  | 2026-08-10 | 2026-08-20 | 2026-08-21 | 2026-09-05 |  |  | 2026-09-19 | 2026-09-05 | 2026-09-14 | 2026-09-15 | 2026-09-17 | 2026-09-18 | 2026-09-23 |  |  | 2026-09-23 | 2026-09-28 | 2026-10-01 | 2026-10-06 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-10 | 2026-10-12 | 2026-10-12 | 103 | N/3 | Shaker | Chest | BK | black beauty-3198 pcs frt 1 clr HD print back self fabric applique emb |  |  | NCL |  |  | Ready Test Cut | 2347 | 1559 | -788 | 0 | -3198 | [11 empty] | 42 | Sep'2
OVS SPA | 47798 | 271TSH098-6156 | 2674 | 510 | 2026-06-29 | 2026-07-17 | SS Double layer slve TS | TS |  |  | 2026-08-20 | 2026-08-31 | 2026-09-01 | 2026-09-15 |  |  | 2026-10-01 | 2026-09-18 | 2026-09-26 | 2026-09-28 | 2026-09-30 | 2026-10-01 | 2026-10-05 |  |  | 2026-10-05 | 2026-10-10 | 2026-10-10 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-19 | 112 | N/3 | Khairul | Fr,Bk | Chest | milk-2674 pcs frt 1 clr pig 2 clr flat 1 clr terry emb and back 4 clr rub print |  |  | NCL |  |  | File Due | 510 | 470 | -40 | 0 | -2674 | [11 empty] | 43 | Sep'3
OVS SPA | 47799 | 271SWT100-6156 | 2674 | 1040 | 2026-06-29 | 2026-07-17 | LS Swt hoodie w contast cut& sew Slve w YD cuff btm rib | Hoody | 2026-08-18 | 2026-08-31 | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-09-23 |  |  | 2026-09-28 | 2026-09-24 | 2026-09-30 | 2026-10-01 | 2026-10-03 |  |  |  |  | 2026-10-03 | 2026-10-08 | 2026-10-08 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-17 | 2026-10-19 | 2026-10-19 | 112 | N/3 | Khairul |  | Chest | light blue-2674 pcs 2 clr flat 1 clr felt 1 clr chain stitch and 1 clr terry emb | YD |  | NCL |  |  | File Due | 990 | 0 | -990 | 0 | -2674 | [11 empty] | 43 | Oct'1
OVS SPA | 47810 | 271POLO081-6154 | 2292 | 735 | 2026-06-29 | 2026-07-17 | YD SS Polo shirt w flat knit collar placket btn | Polo | 2026-08-18 | 2026-08-31 | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-09-22 |  |  | 2026-09-28 | 2026-09-24 | 2026-09-30 | 2026-10-01 | 2026-10-03 | 2026-10-05 | 2026-10-09 |  |  |  |  | 2026-10-08 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-17 | 2026-10-19 | 2026-10-19 | 112 | N/2 | Khairul | Chest |  | multicolor-2292 pcs 1 clr rub print | YD |  | NCL |  |  | File Due | 735 | 0 | -735 | 0 | -2292 | [11 empty] | 43 | Oct'1
OVS SPA | 47797 | 271CAR094-6156 | 2674 | 865 | 2026-06-29 | 2026-07-17 | LS Swt cardigan w cut&sew cintrast slve and full placket btn and both side bon pkt | Cardigan | 2026-08-01 | 2026-08-10 | 2026-08-11 | 2026-08-20 | 2026-08-21 | 2026-09-03 |  |  | 2026-09-25 | 2026-09-14 | 2026-09-22 | 2026-09-23 | 2026-09-25 | 2026-09-26 | 2026-09-30 |  |  | 2026-10-01 | 2026-10-05 | 2026-10-05 | 2026-10-10 |  |  | 2026-10-12 | 2026-10-14 | 2026-10-16 | 2026-10-19 | 2026-10-19 | 112 | B | Khairul | Chest | Fr & Bk | light blue-2674 pcs frt left 4 clr rub print right side 1 clr felt 1 clr terry emb and back 1 clr felt 1 clr terry emb | YD |  | NFL1 |  |  | File Due | 865 | 0 | -865 | 0 | -2674 | [11 empty] | 43 | Sep'3
OVS SPA | 47800 | 271POL101-6156 | 2674 | 590 | 2026-06-29 | 2026-07-17 | YD SS Polo shirt w flat knit collar placket btn | Polo | 2026-08-18 | 2026-08-31 | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-09-22 |  |  | 2026-09-28 | 2026-09-24 | 2026-09-30 | 2026-10-01 | 2026-10-03 | 2026-10-05 | 2026-10-09 |  |  |  |  | 2026-10-08 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-17 | 2026-10-19 | 2026-10-19 | 112 | N/2 | Khairul | Chest |  | multicolar-2674 pcs 1 clr HD print | YD |  | NCL |  |  | File Due | 590 | 0 | -590 | 0 | -2674 | [11 empty] | 43 | Oct'1
OVS SPA | 47864 | 271TSH469-6084 | 5043 | 988 | 2026-07-12 | 2026-07-22 | LS v nk TS w side gathering | TS |  |  | 2026-09-01 | 2026-09-10 | 2026-09-11 | 2026-09-24 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-09 | 2026-10-08 | 2026-10-10 | [6 empty] | 2026-10-12 | 2026-10-20 |  |  | 2026-10-21 | 2026-10-23 | 2026-10-25 | 2026-10-26 | 2026-10-26 | 106 | K1 | Basir | [5 empty] | NFL2 |  |  | File Due | 988 | 0 | -988 | 0 | -5043 | [11 empty] | 44 | Oct'1
OVS SPA | 48297 | 271SET196-256 | 8528 | 899 | 2026-07-12 | 2026-07-22 | LS Swt shirt w collar and cut&sew elasted pant | Top & BTM |  |  | 2026-08-15 | 2026-08-31 | 2026-09-01 | 2026-09-15 |  |  | 2026-10-01 | 2026-09-17 | 2026-09-24 | 2026-09-25 | 2026-10-01 | 2026-10-01 | 2026-10-06 |  |  | 2026-10-05 | 2026-10-12 | 2026-10-10 | 2026-10-17 |  |  | 2026-10-19 | 2026-10-21 | 2026-10-23 | 2026-10-26 | 2026-10-26 | 106 | R+P | Basir | Fr,Bk | Chest | tea top-4264 pcs frt patch block wisee 5 clr rub print applique emb no print and back 7 clr pig print ,,ecru btm-4264 pcs no print emb |  |  | NFL2 |  |  | File Due | 899 | 344 | -555 | 0 | -8528 | [11 empty] | 44 | Sep'3
OVS SPA | 48298 | 271BDY197-256 | 3608 | 265 | 2026-07-12 | 2026-07-22 | YD SS body suit e btm snap btn and bk nk placke btn | Body | 2026-08-20 | 2026-08-31 | 2026-09-01 | 2026-09-10 | 2026-09-11 | 2026-09-21 |  |  | 2026-10-02 | 2026-09-25 | 2026-10-02 | 2026-10-03 | 2026-10-05 | 2026-10-06 | 2026-10-10 |  |  |  |  | 2026-10-12 | 2026-10-17 |  |  | 2026-10-19 | 2026-10-21 | 2026-10-23 | 2026-10-26 | 2026-10-26 | 106 | N/3 | Basir | Chest |  | multicolor-3608 pcs 6 clr rub print | YD |  | NCL |  |  | File Due | 264 | 0 | -264 | 0 | -3608 | [11 empty] | 44 | Oct'1
BS-ONL | 44672 5th | 15367075 | 7018 | 1402 | 2026-07-20 | 2026-07-21 | SS o nk TS | TS |  |  | 2026-08-03 | 2026-08-12 | 2026-08-17 | 2026-09-04 |  |  | 2026-09-08 | 2026-09-08 |  | 2026-09-14 | 2026-09-17 | 2026-09-17 | 2026-09-23 |  |  | 2026-09-23 | 2026-09-28 | 2026-10-01 | 2026-10-06 |  |  | 2026-10-08 | 2026-10-12 | 2026-10-16 | 2026-11-23 | 2026-11-25 | 126 | L1 | Jannati | Fr,Bk | Chest | purple-2693 pcs frt 3 clr rub w photo print w 4 clr puff and 1 clr flat emb back back 5 clr rub one slve 2 clr rub ,,corsage-1004 pcs frt 3 clr rub 4 clr puff and 3 clr flat emb back 3 clr rub print ,,magenta-2670 pcs frt back 1 clr rub and no emb ,,c.dan lemon-651 pcs chest 3 clr rub photo print w 3 clr puff and 1 clr flat emb |  |  | NFL2 |  |  | Cut Run | 1402 | 1392 | -10 | 3777 | -3241 | [11 empty] | 48 | Sep'2 |  |  | 25.07.26
BS-ONL | 48222 | 15387481 | 3162 | 351 | 2026-06-20 | 2026-07-17 | Skirt w waist smock and woven emb lace | Skirt |  |  | 2026-08-10 | 2026-08-15 | 2026-08-22 | 2026-09-08 |  |  | 2026-09-12 | 2026-09-12 | 2026-09-19 | 2026-09-26 | 2026-09-29 | [6 empty] | 2026-10-01 | 2026-10-05 |  |  | 2026-10-07 | 2026-10-09 | 2026-10-13 | 2026-11-23 | 2026-11-25 | 156 | L2 | Abid |  |  |  |  | Smock 22/09 to 25/09 | NFL2 |  |  | File Due | 351 | 339 | -12 | 0 | -3162 | [11 empty] | 48 | Sep'3
BS-ONL | 48214 | 15388800 | 2124 | 179 | 2026-06-20 | 2026-07-17 | Tank top w contrast piping | Tank Top |  |  | 2026-08-15 | 2026-08-20 | 2026-09-02 | 2026-09-15 |  |  | 2026-09-19 | 2026-09-19 | 2026-09-25 | 2026-09-28 | 2026-09-30 | 2026-10-03 | 2026-10-07 |  |  |  |  | 2026-10-09 | 2026-10-12 |  |  | 2026-10-15 | 2026-10-17 | 2026-10-22 | 2026-11-21 | 2026-11-23 | 154 | L2 | Abid | Chest |  | bracken-1130 pcs,,c.dan-998 pcs both 1 clr rub print |  |  | NFL2 |  |  | CAD | 179 | 0 | -179 | 0 | -2124 | [11 empty] | 48 | Sep'3 |  |  | 16.09.26
BS-ONL | 48224 | 15388160 | 396 | 94 | 2026-06-20 | 2026-07-17 | LS Swt shirt w contrast cut&sew front and slve | Swt Shirt |  |  | 2026-08-16 | 2026-08-20 | 2026-09-01 | 2026-09-15 |  |  | 2026-09-18 | 2026-09-18 | 2026-09-26 | 2026-09-29 | 2026-09-29 | 2026-10-03 | 2026-10-06 |  |  |  |  | 2026-10-09 | 2026-10-10 |  |  | 2026-10-13 | 2026-10-15 | 2026-10-20 | 2026-11-23 | 2026-11-25 | 156 | R | Abid | Chest |  | Tofu-398 pcs 3 clr HD print |  |  | NFL2 |  |  | File Due | 95 | 0 | -95 | 0 | -396 | [11 empty] | 48 | Sep'3
BS-ONL | 48216 | 15381667 | 4806 | 890 | 2026-06-20 | 2026-07-17 | SS o nk TS | TS |  |  | 2026-08-06 | 2026-08-15 | 2026-08-22 | 2026-09-10 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-22 | 2026-09-25 | 2026-09-28 | [6 empty] | 2026-10-01 | 2026-10-06 |  |  | 2026-10-09 | 2026-10-12 | 2026-10-20 | 2026-11-23 | 2026-11-25 | 156 | Q | Abid | [5 empty] | NFL2 |  |  | Need Test Cut | 891 | 0 | -891 | 0 | -4806 | [11 empty] | 48 | Sep'3 |  |  | 03.09.26
OVS SPA | 48320 | 271TSH160-227 | 20380 | 1072 | 2026-07-10 | 2026-07-16 | SS o nk TS | TS |  |  | 2026-09-01 | 2026-09-17 | 2026-09-14 | 2026-09-29 |  |  | 2026-10-13 | 2026-10-06 | 2026-10-12 | 2026-10-13 | 2026-10-17 | 2026-10-17 | 2026-10-24 |  |  |  |  | 2026-10-24 | 2026-10-31 |  |  | 2026-11-02 | 2026-11-04 | 2026-11-06 | 2026-11-09 | 2026-11-09 | 122 | G1 | Salam | Chest |  | green-8076 pcs,,yellow-9254 pcs,,bonbom-3050 pcs all combo 2 clr puff print |  |  | NFL1 |  |  | File Due | 1060 | 0 | -1060 | 0 | -20380 | [11 empty] | 46 | Oct'2
OVS SPA | 48339 | 271DRS169-6140 | 8916 | 1510 | 2026-07-20 | 2026-07-23 | AOP SL frock Dress w shlder btn and frill and with btm side pkt | Dress |  |  | 2026-09-10 | 2026-09-19 | 2026-09-21 | 2026-09-30 | 2026-10-01 | 2026-10-10 | 2026-10-20 | 2026-10-12 | 2026-10-19 | 2026-10-20 | 2026-10-24 |  |  |  |  | 2026-10-24 | 2026-10-31 | 2026-11-02 | 2026-11-16 |  |  | 2026-11-17 | 2026-11-19 | 2026-11-21 | 2026-11-23 | 2026-11-23 | 126 | N/3 | Salam |  | Pkt | Navy-5352 pcs,,red-3564 pcs both combo two pkt 1 clr flat emb | AOP |  | NCL |  |  | File Due | 1554 | 578 | -976 | 0 | -8916 | [11 empty] | 48 | Oct'2
OVS SPA | 48311 | 271VST009UTPC2-6110 | 9065 | 1020 | 2026-07-12 | 2026-07-22 | Tank top w nk arm hole lace | Tank Top |  |  | 2026-10-01 | 2026-10-10 | 2026-10-12 | 2026-10-24 |  |  | 2026-10-28 | 2026-10-26 | 2026-11-02 | 2026-11-03 | 2026-11-06 | [6 empty] | 2026-11-07 | 2026-11-14 |  |  | 2026-11-14 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-18 | 129 | A | Basir |  |  |  |  | Lace | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -9065 | [11 empty] | 47 | Nov'1
BS-NMT | 48108 | 13251508 | 7579 | 1070 | 2026-06-10 | 2026-07-17 | AOP SS o nk Dress slve gathering | Dress |  |  | 2026-09-12 | 2026-09-20 | 2026-10-01 | 2026-10-15 | 2026-10-17 | 2026-10-30 | 2026-11-10 | 2026-11-10 | 2026-11-17 | 2026-11-20 | 2026-11-24 | 2026-11-25 | 2026-11-28 |  |  |  |  | 2026-12-01 | 2026-12-07 |  |  | 2026-12-09 | 2026-12-12 | 2026-12-18 | 2027-02-20 | 2027-02-22 | 255 | S | Shamoly | Nk |  | 3 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -7579 | [11 empty] | 9 | Nov'2
BS-NMT | 48109 | 13262997 | 5232 | 532 | 2026-06-10 | 2026-07-17 | AOP SS o nk TS w woven label attach | TS |  |  | 2026-09-15 | 2026-09-20 | 2026-10-01 | 2026-10-15 | 2026-10-20 | 2026-10-30 | 2026-11-07 | 2026-10-07 | 2026-11-16 | 2026-11-19 | 2026-11-21 | 2026-11-24 | 2026-11-27 |  |  |  |  | 2026-12-01 | 2026-12-04 |  |  | 2026-12-07 | 2026-12-10 | 2026-12-15 | 2027-02-20 | 2027-02-22 | 255 | ZA1 | Shamoly | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -5232 | [11 empty] | 9 | Nov'2
BS-NMT | 48110 | 13262999 | 5262 | 504 | 2026-06-10 | 2026-07-17 | Elasted Shorts w side pkt drawstring w woven label | Shorts |  |  | 2026-09-20 | 2026-09-26 | 2026-10-08 | 2026-10-25 |  |  | 2026-11-06 | 2026-11-06 | 2026-11-14 | 2026-11-18 | 2026-11-23 | 2026-11-24 | 2026-11-27 |  |  |  |  | 2026-12-03 | 2026-12-09 |  |  | 2026-12-11 | 2026-12-15 | 2026-12-25 | 2027-02-20 | 2027-02-22 | 255 | X | Shamoly | Waist |  | 2 combo label print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -5262 | [11 empty] | 9 | Nov'2
BS-ONL | 48234 | 15388149 | 624 | 54 | 2026-06-20 | 2026-07-17 | Skirt w waist smock and woven emb lace | Skirt |  |  | 2026-08-15 | 2026-08-18 | 2026-09-01 | 2026-09-10 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-09-29 | [6 empty] | 2026-10-03 | 2026-10-05 |  |  | 2026-10-07 | 2026-10-09 | 2026-10-15 | 2026-12-21 | 2026-12-23 | 184 | L2 | Abid |  |  |  |  | smock T&A 24/09 to 25/09 | NFL2 |  |  | File Due | 54 | 0 | -54 | 0 | -624 | [11 empty] | 52 | Sep'3
BS-ONL | 48230 2nd | 15325767 | 1500 | 165 | 2026-07-09 | 2026-07-17 | SS TS w slve woven emb lace | TS |  |  | 2026-09-05 | 2026-09-10 | 2026-09-18 | 2026-09-30 |  |  | 2026-10-08 | 2026-10-08 | 2026-10-16 | 2026-10-20 | 2026-10-22 | [6 empty] | 2026-10-24 | 2026-10-27 |  |  | 2026-10-29 | 2026-10-31 | 2026-11-05 | 2027-01-11 | 2027-01-13 | 186 | K | Abid |  |  |  |  | Lace | NFL2 |  |  | Po Sheet Due | 165 | 0 | -165 | 0 | -1500 | [11 empty] | 3 | Oct'2
BS-ONL | 48237 | 15388151 | 732 | 111 | 2026-06-20 | 2026-07-17 | SL frock dress w front placket btn and front woven emb lace attach | Dress |  |  | 2026-08-25 | 2026-08-30 | 2026-09-05 | 2026-09-20 |  |  | 2026-09-25 | 2026-09-25 | 2026-10-03 | 2026-10-07 | 2026-10-09 | [6 empty] | 2026-10-12 | 2026-10-15 |  |  | 2026-10-17 | 2026-10-20 | 2026-10-28 | 2026-12-21 | 2026-12-23 | 184 | J | Abid |  |  |  |  | Lace | NFL2 |  |  | File Due | 111 | 0 | -111 | 0 | -732 | [11 empty] | 52 | Oct'1
BS-ONL | 48228 | 15395680 | 672 | 79 | 2026-06-20 | 2026-07-17 | SS TS w slve woven emb lace | TS |  |  | 2026-09-05 | 2026-09-10 | 2026-09-20 | 2026-10-05 |  |  | 2026-10-10 | 2026-10-10 | 2026-10-17 | 2026-10-20 | 2026-10-21 | [6 empty] | 2026-10-23 | 2026-10-24 |  |  | 2026-10-27 | 2026-10-29 | 2026-11-05 | 2026-12-21 | 2026-12-23 | 184 | K | Abid |  |  |  |  | Lace | NFL2 |  |  | File Due | 78 | 0 | -78 | 0 | -672 | [11 empty] | 52 | Oct'2
BS-ONL | 48225 | 15374431 | 2586 | 324 | 2026-06-20 | 2026-07-17 | Tank Top | Tank Top |  |  | 2026-08-22 | 2026-08-28 | 2026-09-06 | 2026-09-20 |  |  | 2026-09-28 | 2026-09-28 | 2026-10-05 | 2026-10-08 | 2026-10-09 | [6 empty] | 2026-10-12 | 2026-10-15 |  |  | 2026-10-17 | 2026-10-20 | 2026-10-27 | 2026-12-19 | 2026-12-21 | 182 | L2 | Abid | [5 empty] | NFL2 |  |  | PPM Due | 324 | 94 | -230 | 0 | -2586 | [11 empty] | 52 | Oct'1 |  |  | 22.08.26
BS-ONL | 48227 | 15387380 | 5028 | 650 | 2026-06-20 | 2026-07-17 | SL dress w btm woven poplin fab w V shape waist | Dress |  |  | 2026-08-15 | 2026-08-20 | 2026-09-01 | 2026-09-15 |  |  | 2026-09-20 | 2026-09-20 | 2026-09-26 | 2026-10-01 | 2026-10-03 | [6 empty] | 2026-10-05 | 2026-10-10 |  |  | 2026-10-13 | 2026-10-15 | 2026-10-20 | 2026-12-19 | 2026-12-21 | 182 | K | Abid | [5 empty] | NFL2 |  |  | File Due | 651 | 300 | -351 | 0 | -5028 | [11 empty] | 52 | Oct'1
BS-ONL | 48233 | 15388155 | 468 | 87 | 2026-06-20 | 2026-07-17 | SS AOP dress w waist elastic w self fab string | Dress |  |  | 2026-08-25 | 2026-08-28 | 2026-09-07 | 2026-09-18 | 2026-09-24 | 2026-09-30 | 2026-10-05 | 2026-10-05 | 2026-10-12 | 2026-10-15 | 2026-10-16 | [6 empty] | 2026-10-20 | 2026-10-21 |  |  | 2026-10-23 | 2026-10-27 | 2026-10-31 | 2026-12-21 | 2026-12-23 | 184 | J | Abid |  |  |  | AOP |  | NFL2 |  |  | File Due | 87 | 0 | -87 | 0 | -468 | [11 empty] | 52 | Oct'2
BS-ONL | 48236 | 15388156 | 1392 | 142 | 2026-06-20 | 2026-07-17 | SS AOP TS w slve slit twisting | TS |  |  | 2026-08-20 | 2026-08-24 | 2026-09-06 | 2026-09-18 | 2026-09-22 | 2026-09-28 | 2026-10-03 | 2026-10-03 | 2026-10-10 | 2026-10-14 | 2026-10-15 | [6 empty] | 2026-10-17 | 2026-10-20 |  |  | 2026-10-22 | 2026-10-24 | 2026-10-30 | 2026-12-21 | 2026-12-23 | 184 | K | Abid |  |  |  | AOP |  | NFL2 |  |  | Need Test Cut | 142 | 0 | -142 | 0 | -1392 | [11 empty] | 52 | Oct'2 |  |  | 03.09.26
BS-ONL | 48232 | 15388158 | 1188 | 101 | 2026-06-20 | 2026-07-17 | AOP Shorts w side pkt and waist elastic Side slit twist and tape drawstringstring | Shorts |  |  | 2026-08-26 | 2026-08-31 | 2026-09-10 | 2026-09-20 | 2026-09-24 | 2026-09-30 | 2026-10-07 | 2026-10-07 | 2026-10-14 | 2026-10-17 | 2026-10-19 | [6 empty] | 2026-10-23 | 2026-10-26 |  |  | 2026-10-28 | 2026-11-04 | 2026-11-10 | 2026-12-21 | 2026-12-23 | 184 | P | Abid |  |  |  | AOP |  | NFL2 |  |  | File Due | 101 | 0 | -101 | 0 | -1188 | [11 empty] | 52 | Oct'2
BS-ONS | 48199 3rd | 22042193 | 64084 | 15834 | 2026-07-09 | 2026-07-10 | SS o nk TS w nk rib | TS |  |  | 2026-07-13 | 2026-07-22 | 2026-07-18 | 2026-08-10 |  |  | 2026-08-05 | 2026-07-30 |  | 2026-08-07 | 2026-08-17 | 2026-08-10 | 2026-08-20 |  |  |  |  | 2026-08-17 | 2026-08-31 |  |  | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-09 | 60 | ZA2 | Shovon | Heat Press/Heat Seal |  | 14 combo nk HP |  |  | NFL3 |  |  | Cut Ok | 15834 | 15834 | 0 | 65559 | 1475 | [11 empty] | 37 | Aug'1 |  |  | 27.07.26
UTG-(Even & Odd) | 27711 15th | BAD25221N | 2000 | 687 | 2026-07-23 | 2026-07-25 | LDS SKIRT w side slit | Skirt |  |  | 2026-08-11 | 2026-08-20 | 2026-08-21 | 2026-08-31 |  |  | 2026-09-07 | 2026-09-08 |  | 2026-09-11 | 2026-09-12 | [6 empty] | 2026-09-15 | 2026-09-17 |  |  | 2026-09-18 | 2026-09-21 | 2026-09-23 | 2026-10-03 | 2026-10-05 | 72 | G2 | Rony | [5 empty] | NFL1 |  |  | Need Cut | 687 | 323 | -364 | 0 | -2000 | [11 empty] | 41 | Sep'2 |  |  | 28.07.26
BS-ONL | 22041 65th | 15204712 | 9070 | 1890 | 2026-07-27 | 2026-07-28 | LS o nk TS | TS | [8 empty] | 2026-08-01 | 2026-08-01 |  | 2026-08-01 | 2026-08-07 | [6 empty] | 2026-08-06 | 2026-08-10 |  |  | 2026-08-12 | 2026-08-13 | 2026-08-15 | 2026-08-17 | 2026-08-19 | 21 | O1 | Imran |  |  |  |  | Stock fab from 43465 /VMI order | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 9184 | 114 | [11 empty] | 34 | Aug'1 |  |  | 30.07.26
GBX-New Look | 48301 2nd | 9672271 | 8700 | 1910 | 2026-07-27 | 2026-07-28 | SS reglan contrast slve TS | TS |  |  | 2026-07-30 | 2026-08-06 | 2026-08-06 | 2026-08-18 |  |  | 2026-08-15 | 2026-08-14 |  | 2026-08-18 | 2026-08-21 | [6 empty] | 2026-08-20 | 2026-08-26 |  |  | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-29 | 2026-08-30 | 33 | N/3 | Sifat | [5 empty] | NCL |  |  | Ready Test Cut | 1850 | 1838 | -12 | 0 | -8700 | [11 empty] | 36 | Aug'2
BS-NMT | 43323 34th | 13180124 | 7600 | 939 | 2026-07-22 | 2026-07-24 | GIRLS SOLID LEGGINGS | Legging |  |  | 2026-08-01 | 2026-08-07 | 2026-08-10 | 2026-08-27 |  |  | 2026-08-27 | 2026-08-27 |  | 2026-09-02 | 2026-09-04 | 2026-09-04 | 2026-09-07 |  |  |  |  | 2026-09-09 | 2026-09-12 |  |  | 2026-09-15 | 2026-09-17 | 2026-09-21 | 2026-09-28 | 2026-09-30 | 68 | W2 | Jafar | WAIST |  | 3 combo label print |  |  | NFL3 |  |  | Cut Run | 939 | 881 | -58 | 7349 | -251 | [11 empty] | 40 | Sep'1 |  |  | 21.08.26
BS-ONL | 27204 60th | 15323159 | 9600 | 2296 | 2026-07-24 | 2026-07-25 | LS o nk TS | TS |  |  | 2026-08-01 | 2026-08-13 | 2026-08-12 | 2026-08-25 |  |  | 2026-08-24 | 2026-08-24 |  | 2026-08-28 | 2026-08-31 | [6 empty] | 2026-09-01 | 2026-09-04 |  |  | 2026-09-07 | 2026-09-09 | 2026-09-12 | 2026-09-21 | 2026-09-23 | 59 | G1 | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 2296 | 2280 | -16 | 9709 | 109 | [11 empty] | 39 | Aug'3 |  |  | 07.08.26
GBX-New Look | 47376 2nd | 9602963 | 16200 | 2205 | 2026-07-27 | 2026-07-28 | Open sholder YD SS TS | TS | 2026-08-04 | 2026-08-14 | 2026-08-10 | 2026-08-18 | 2026-08-15 | 2026-08-22 |  |  | 2026-08-17 | 2026-08-17 |  | 2026-08-22 | 2026-08-27 | [6 empty] | 2026-08-26 | 2026-09-03 |  |  | 2026-09-04 | 2026-09-05 | 2026-09-05 | 2026-09-05 | 2026-09-06 | 40 | N/1 | Sifat |  |  |  | YD |  | NCL |  |  | Ready Test Cut | 2205 | 2205 | 0 | 0 | -16200 | [11 empty] | 37 | Aug'3
GBX-New Look | 47936 4th | 9657695 | 25048 | 2862 | 2026-07-25 | 2026-07-28 | SS reglan contrast slve TS | TS |  |  | 2026-07-31 | 2026-08-06 | 2026-08-06 | 2026-08-20 |  |  | 2026-08-17 | 2026-08-17 |  | 2026-08-21 | 2026-08-26 | [6 empty] | 2026-08-24 | 2026-09-03 |  |  | 2026-09-04 | 2026-09-05 | 2026-09-05 | 2026-09-05 | 2026-09-06 | 42 | N/2 | Sifat | [5 empty] | NCL |  |  | Ready Test Cut | 2862 | 2642 | -220 | 0 | -25048 | [11 empty] | 37 | Aug'3
GBX-New Look | 46804 3rd | 9602962 | 17675 | 2279 | 2026-07-27 | 2026-07-28 | SL TS w btm boulson | TS |  |  | 2026-07-30 | 2026-08-07 | 2026-08-07 | 2026-08-19 |  |  | 2026-08-17 | 2026-08-17 |  | 2026-08-21 | 2026-08-25 | [6 empty] | 2026-08-24 | 2026-09-02 |  |  | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-05 | 2026-09-06 | 40 | N/1 | Sifat | [5 empty] | NCL |  |  | Ready Test Cut | 2279 | 2279 | 0 | 0 | -17675 | [11 empty] | 37 | Aug'3
GBX-New Look | 48326 | 9426700 | 808 | 375 | 2026-07-18 | 2026-07-24 | Waist belt shorts w side bon pkt and back pkt w drawstring | Shorts |  |  | 2026-08-08 | 2026-08-14 | 2026-08-17 | 2026-08-31 |  |  | 2026-09-01 | 2026-09-01 | 2026-09-07 | 2026-09-09 | 2026-09-10 | [6 empty] | 2026-09-12 | 2026-09-15 |  |  | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-26 | 2026-09-27 | 70 | N/2 | Morad | [5 empty] | NCL |  |  | Need Test Cut | 374 | 0 | -374 | 0 | -808 | [11 empty] | 40 | Sep'1
GBX-New Look | 48324 | 9426701 | 606 | 309 | 2026-07-18 | 2026-07-24 | Waist belt shorts w front cargo pkt and drawstring | Shorts |  |  | 2026-08-07 | 2026-08-12 | 2026-08-17 | 2026-08-29 |  |  | 2026-09-01 | 2026-09-01 | 2026-09-07 | 2026-09-10 | 2026-09-11 | [6 empty] | 2026-09-14 | 2026-09-17 |  |  | 2026-09-19 | 2026-09-21 | 2026-09-23 | 2026-09-26 | 2026-09-27 | 70 | N/2 | Morad | [5 empty] | NCL |  |  | Need Test Cut | 310 | 10 | -300 | 0 | -606 | [11 empty] | 40 | Sep'1
GBX-New Look | 48325 | 9359337 | 1515 | 617 | 2026-07-18 | 2026-07-24 | Waist belt shorts w side pkt and drawstring | Shorts |  |  | 2026-08-06 | 2026-08-12 | 2026-08-15 | 2026-08-29 |  |  | 2026-09-02 | 2026-09-02 | 2026-09-07 | 2026-09-10 | 2026-09-11 | [6 empty] | 2026-09-14 | 2026-09-16 |  |  | 2026-09-18 | 2026-09-21 | 2026-09-23 | 2026-09-26 | 2026-09-27 | 70 | N/3 | Morad | [5 empty] | NCL |  |  | Need Test Cut | 618 | 197 | -421 | 0 | -1515 | [11 empty] | 40 | Sep'1
GBX-New Look | 48331 | 9668372 | 2981 | 947 | 2026-07-18 | 2026-07-24 | Waist belt shorts w side pkt back pkt and drawstring | Shorts |  |  | 2026-08-01 | 2026-08-13 | 2026-08-12 | 2026-08-29 |  |  | 2026-09-01 | 2026-09-01 | 2026-09-05 | 2026-09-07 | 2026-09-10 | [6 empty] | 2026-09-10 | 2026-09-14 |  |  | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 63 | N/3 | Morad | [5 empty] | NCL |  |  | Ready Test Cut | 947 | 727 | -220 | 0 | -2981 | [11 empty] | 39 | Sep'1
GBX-New Look | 48330 | 9668400 | 758 | 448 | 2026-07-17 | 2026-07-24 | LS Double layer Slve TS | TS |  |  | 2026-08-04 | 2026-08-10 | 2026-08-15 | 2026-08-29 |  |  | 2026-09-01 | 2026-09-01 | 2026-09-05 | 2026-09-08 | 2026-09-09 | [6 empty] | 2026-09-11 | 2026-09-12 |  |  | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-19 | 2026-09-20 | 64 | N/1 | Morad | [5 empty] | NCL |  |  | Need Test Cut | 448 | 0 | -448 | 0 | -758 | [11 empty] | 39 | Sep'1
GBX-New Look | 48332 | 9668430 | 1566 | 430 | 2026-07-17 | 2026-07-24 | SS TS w contrast nk | TS |  |  | 2026-08-04 | 2026-08-10 | 2026-08-15 | 2026-08-29 |  |  | 2026-09-01 | 2026-09-01 | 2026-09-05 | 2026-09-07 | 2026-09-08 | [6 empty] | 2026-09-10 | 2026-09-12 |  |  | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-19 | 2026-09-20 | 64 | N/1 | Morad | [5 empty] | NCL |  |  | Need Test Cut | 470 | 0 | -470 | 0 | -1566 | [11 empty] | 39 | Sep'1
GBX-New Look | 48334 | 9668425 | 3284 | 1102 | 2026-07-17 | 2026-07-24 | SS o nk TS w frt pkt | TS |  |  | 2026-08-01 | 2026-08-12 | 2026-08-13 | 2026-08-28 |  |  | 2026-09-01 | 2026-09-01 | 2026-09-05 | 2026-09-08 | 2026-09-10 | [6 empty] | 2026-09-11 | 2026-09-15 |  |  | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 64 | N/1 | Morad | [5 empty] | NCL |  |  | Ready Test Cut | 1199 | 913 | -286 | 0 | -3284 | [11 empty] | 39 | Sep'1
GBX-New Look | 48329 | 9328977 | 2020 | 567 | 2026-07-17 | 2026-07-24 | SS o nk TS | TS |  |  | 2026-08-01 | 2026-08-06 | 2026-08-12 | 2026-08-22 |  |  | 2026-08-25 | 2026-08-25 | 2026-09-01 | 2026-09-03 | 2026-09-04 | 2026-09-04 | 2026-09-05 |  |  |  |  | 2026-09-07 | 2026-09-08 |  |  | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 57 | N/1 | Morad | Nk |  | 4 combo size nk label print |  |  | NCL |  |  | Ready Test Cut | 566 | 558 | -8 | 0 | -2020 | [11 empty] | 38 | Sep'1
GBX-New Look | 48323 | 9328960/9328781 | 2121 | 669 | 2026-07-17 | 2026-07-24 | SS o nk TS | TS |  |  | 2026-08-01 | 2026-08-06 | 2026-08-12 | 2026-08-24 |  |  | 2026-08-25 | 2026-08-25 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 |  |  |  |  | 2026-09-07 | 2026-09-08 |  |  | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 57 | N/1 | Morad | Nk |  | 4 combo size nk label print |  |  | NCL |  |  | Ready Test Cut | 669 | 442 | -227 | 0 | -2121 | [11 empty] | 38 | Sep'1
GBX-New Look | 48322 | 9328950/9426478 | 6969 | 1504 | 2026-07-17 | 2026-07-24 | Tank Top | Tank Top |  |  | 2026-08-01 | 2026-08-10 | 2026-08-12 | 2026-08-25 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-29 | 2026-09-01 | 2026-09-03 | 2026-09-02 | 2026-09-04 |  |  |  |  | 2026-09-05 | 2026-09-09 |  |  | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-12 | 2026-09-13 | 57 | N/1 | Morad | Nk |  | 5 combo size nk label print |  |  | NCL |  |  | Ready Test Cut | 1503 | 953 | -550 | 0 | -6969 | [11 empty] | 38 | Sep'1
GBX-New Look | 48333 | 9668427 | 758 | 384 | 2026-07-17 | 2026-07-24 | LS reglan contrast slve TS w cuff rib | TS |  |  | 2026-08-06 | 2026-08-12 | 2026-08-15 | 2026-08-31 |  |  | 2026-09-03 | 2026-09-03 | 2026-09-09 | 2026-09-11 | 2026-09-12 | [6 empty] | 2026-09-15 | 2026-09-16 |  |  | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-19 | 2026-09-20 | 64 | N/1 | Morad | [5 empty] | NCL |  |  | Need Test Cut | 384 | 0 | -384 | 0 | -758 | [11 empty] | 39 | Sep'2
UTG-(Even & Odd) | 42250 4th | BAD2728C | 1500 | 302 | 2026-07-24 | 2026-07-25 | LDS V NK TS W YD COLLAR | TS | 2026-07-30 | 2026-08-08 | 2026-08-08 | 2026-08-15 | 2026-08-15 | 2026-08-22 |  |  | 2026-08-21 | 2026-08-21 |  | 2026-08-24 | 2026-08-25 | [6 empty] | 2026-08-26 | 2026-08-29 |  |  | 2026-08-31 | 2026-09-01 | 2026-09-03 | 2026-09-05 | 2026-09-07 | 43 | N/1 | Rony |  |  |  | YD |  | NCL |  |  | Ready Test Cut | 302 | 302 | 0 | 0 | -1500 | [11 empty] | 37 | Aug'3
UTG-(Even & Odd) | 43039 7th | BAD2853F | 1500 | 680 | 2026-07-24 | 2026-07-25 | LDS LONG DRESS | DRESS |  |  | 2026-07-30 | 2026-08-06 | 2026-08-07 | 2026-08-18 |  |  | 2026-08-21 | 2026-08-21 |  | 2026-08-24 | 2026-08-25 | [6 empty] | 2026-08-26 | 2026-08-29 |  |  | 2026-08-31 | 2026-09-02 | 2026-09-04 | 2026-09-05 | 2026-09-07 | 43 | N/2 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 680 | 680 | 0 | 0 | -1500 | [11 empty] | 37 | Aug'3
BS-ONL | 48168 | 15395613 | 13245 | 1896 | 2026-07-24 | 2026-07-27 | SS o nk TS | TS |  |  | 2026-08-01 | 2026-08-10 | 2026-08-13 | 2026-08-31 |  |  | 2026-09-05 | 2026-09-05 | 2026-09-11 | 2026-09-14 | 2026-09-18 |  |  |  |  | 2026-09-17 | 2026-09-22 | 2026-09-23 | 2026-09-29 |  |  | 2026-09-30 | 2026-10-02 | 2026-10-05 | 2026-10-12 | 2026-10-14 | 80 | V | Mainul |  | Chest | white-6840 pcs,,green-6405 pcs both combo 3 clr flat emb |  |  | NFL3 |  |  | Cut Run | 1897 | 980 | -917 | 6600 | -6645 | [11 empty] | 42 | Sep'2 |  |  | 26.08.26
BS-ONL | 47709 2nd | 15299770 | 1610 | 225 | 2026-07-24 | 2026-07-27 | LS o nk TS w blind hem | TS |  |  | 2026-08-07 | 2026-08-11 | 2026-08-20 | 2026-08-31 |  |  | 2026-09-04 | 2026-09-04 |  | 2026-09-09 | 2026-09-10 | [6 empty] | 2026-09-12 | 2026-09-14 |  |  | 2026-09-16 | 2026-09-18 | 2026-09-19 | 2026-09-21 | 2026-09-23 | 59 | N1 | Abid | [5 empty] | NFL2 |  |  | Cut Ok | 225 | 217 | -8 | 1628 | 18 | [11 empty] | 39 | Sep'1 |  |  | 05.09.26
OVS SPA | 48260 | 271TRO014-226 | 8362 | 3170 | 2026-07-10 | 2026-07-24 | Waist belt trouser w side back pkt and drawstring w gmts dye acid wash | Trouser |  |  | 2026-08-01 | 2026-08-15 | 2026-08-15 | 2026-08-31 |  |  | 2026-09-10 | 2026-09-01 | 2026-09-09 | 2026-09-10 | 2026-09-12 |  |  |  |  | 2026-09-14 | 2026-09-19 | 2026-09-18 | 2026-09-26 | 2026-09-25 | 2026-10-05 | 2026-10-06 | 2026-10-08 | 2026-10-10 | 2026-10-12 | 2026-10-12 | 94 | N/2 | Sirajul |  | Pkt | tanzine-8362 pcs 3 clr flat emb patch make and patch applique attach emb |  | Gmts dye acid wash | NCL |  |  | File Due | 3170 | 2923 | -247 | 0 | -8362 | [11 empty] | 42 | Sep'1
OVS SPA | 48259 | 271TSH004-226 | 5607 | 1044 | 2026-07-10 | 2026-07-24 | LS double layer contrast slve and contrast nk TS | TS |  |  | 2026-08-10 | 2026-08-20 | 2026-08-21 | 2026-09-05 |  |  | 2026-09-21 | 2026-09-09 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-28 |  |  |  |  | 2026-10-01 | 2026-10-05 |  |  | 2026-10-06 | 2026-10-08 | 2026-10-10 | 2026-10-12 | 2026-10-12 | 94 | F | Sirajul | Fr & Bk & Slv |  | c.dan-5607 pcs frt 3 clr rub back 2 clr rub one slve 1 clr rub print |  |  | NFL1 |  |  | File Due | 1044 | 1016 | -28 | 0 | -5607 | [11 empty] | 42 | Sep'2
OVS SPA | 48249 | 271TSH008-223 | 8116 | 1782 | 2026-07-15 | 2026-07-24 | LS double layer contrast slve TS | TS |  |  | 2026-08-01 | 2026-08-13 | 2026-08-14 | 2026-08-28 |  |  | 2026-09-10 | 2026-09-02 | 2026-09-08 | 2026-09-09 | 2026-09-12 | 2026-09-12 | 2026-09-19 |  |  |  |  | 2026-09-19 | 2026-09-26 |  |  | 2026-09-28 | 2026-09-30 | 2026-10-02 | 2026-10-05 | 2026-10-05 | 82 | N2 | Sirajul | Chest,HP |  | magnet gray-4828 pcs,,tomato-3288 pcs both combo 1 clr rub print |  |  | NFL2 |  |  | CAD | 1780 | 1780 | 0 | 0 | -8116 | [11 empty] | 41 | Sep'1 |  |  | 12.09.26
OVS SPA | 48254 | 271SWT010-223 | 5229 | 3562 | 2026-07-15 | 2026-07-24 | LS Swt full zipper hoody w contrast cut & sew and reglan slve and cuff btm rib | Hoody |  |  | 2026-08-01 | 2026-08-14 | 2026-08-15 | 2026-08-31 |  |  | 2026-09-11 | 2026-09-05 | 2026-09-12 | 2026-09-14 | 2026-09-16 | 2026-09-16 | 2026-09-21 |  |  |  |  | 2026-09-21 | 2026-09-29 |  |  | 2026-09-30 | 2026-10-02 | 2026-10-05 | 2026-10-12 | 2026-10-12 | 89 | X | Sirajul | Fr,Bk |  | black beauty-5229 pcs frt two side 1 clr rub back back 2 clr rub print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -5229 | [11 empty] | 42 | Sep'2
OVS SPA | 48253 | 271SWT009-223 | 5209 | 3430 | 2026-07-15 | 2026-07-24 | LS cut Sew Swt hoody w kangaro pkt and cuff btm rib | Hoody |  |  | 2026-08-01 | 2026-09-04 | 2026-08-14 | 2026-09-11 |  |  | 2026-09-11 | 2026-09-03 | 2026-09-09 | 2026-09-10 | 2026-09-10 | 2026-09-11 | 2026-09-16 |  |  | 2026-09-16 | 2026-09-21 | 2026-09-21 | 2026-09-30 |  |  | 2026-10-01 | 2026-10-03 | 2026-10-05 | 2026-10-12 | 2026-10-12 | 89 | J | Sirajul | Chest | Fr & Bk | gray-5209 pcs 4 clr rub print 1 clr flat emb and back self fabric emb patch attach 2 clr flat emb |  |  | NFL2 |  |  | CAD | 3363 | 3363 | 0 | 0 | -5209 | [11 empty] | 42 | Sep'1 |  |  | 15.09.26
OVS SPA | 48257 | 271TRO023PF-223 | 5105 | 2490 | 2026-07-15 | 2026-07-24 | waist belt trouser side bon pkt and w side contrast cut & sew and drawstring | Trouser |  |  | 2026-08-10 | 2026-08-22 | 2026-08-24 | 2026-09-10 |  |  | 2026-09-14 | 2026-09-12 | 2026-09-18 | 2026-09-19 | 2026-09-22 | [6 empty] | 2026-09-23 | 2026-10-01 |  |  | 2026-10-02 | 2026-10-05 | 2026-10-07 | 2026-10-12 | 2026-10-12 | 89 | H | Sirajul | [5 empty] | NFL1 |  |  | File Due | 2490 | 1733 | -757 | 0 | -5105 | [11 empty] | 42 | Sep'2
OVS SPA | 48256 | 271TRO021PF-223 | 6391 | 3663 | 2026-07-15 | 2026-07-24 | waist belt trouser side bon pkt back pkt and w side cut & sew and drawstring | Trouser |  |  | 2026-08-10 | 2026-08-25 | 2026-08-26 | 2026-09-12 |  |  | 2026-09-21 | 2026-09-12 | 2026-09-18 | 2026-09-19 | 2026-09-22 | 2026-09-23 | 2026-09-28 |  |  |  |  | 2026-10-01 | 2026-10-08 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-12 | 2026-10-12 | 89 | N/2 | Sirajul | leg |  | gray-6391 pcs one leg 2 clr rub print |  |  | NCL |  |  | File Due | 3634 | 3634 | 0 | 0 | -6391 | [11 empty] | 42 | Sep'2
OVS SPA | 48457 | 271MMP320-903 | 16772 | 6835 | 2026-07-24 | 2026-07-27 | Elasted pant w self fab drawstring and lace at waistband | Pant |  |  | 2026-08-15 | 2026-09-07 | 2026-09-01 | 2026-09-29 |  |  | 2026-10-03 | 2026-10-02 | 2026-10-07 | 2026-10-08 | 2026-10-13 | [6 empty] | 2026-10-12 | 2026-10-24 |  |  | 2026-10-26 | 2026-10-27 | 2026-10-29 | 2026-11-10 | 2026-11-10 | 109 | N/2 | Salam |  |  |  |  | Lace | NCL |  |  | File Due | 6834 | 0 | -6834 | 0 | -16772 | [11 empty] | 46 | Oct'1
OVS SPA | 48458 | 271MMP321-903 | 15304 | 3813 | 2026-07-24 | 2026-07-27 | SS o nk TS w lace at bttm hem | TS |  |  | 2026-08-15 | 2026-09-07 | 2026-09-01 | 2026-09-29 |  |  | 2026-10-03 | 2026-10-02 | 2026-10-07 | 2026-10-08 | 2026-10-13 | [6 empty] | 2026-10-12 | 2026-10-24 |  |  | 2026-10-26 | 2026-10-27 | 2026-10-29 | 2026-11-10 | 2026-11-10 | 109 | T2 | Salam |  |  |  |  | Lace | NFL3 |  |  | File Due | 3813 | 0 | -3813 | 0 | -15304 | [11 empty] | 46 | Oct'1
OVS SPA | 48461 | 271NDG319-903 | 9804 | 3480 | 2026-07-24 | 2026-07-27 | SS o nk TS w lace at bttm hem | TS |  |  | 2026-08-15 | 2026-09-07 | 2026-09-01 | 2026-09-29 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-08 | 2026-10-09 | 2026-10-14 | [6 empty] | 2026-10-13 | 2026-10-22 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-28 | 2026-11-10 | 2026-11-10 | 109 | N/1 | Salam |  |  |  |  | Lace | NCL |  |  | File Due | 3480 | 0 | -3480 | 0 | -9804 | [11 empty] | 46 | Oct'1
UTG-AF | 44586 4th | BAD2940C | 800 | 182 | 2026-07-23 | 2026-07-25 | LDS LS TS W SHLDR PLKT | TS |  |  | 2026-08-20 | 2026-08-31 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-23 | 2026-09-24 |  | 2026-09-29 | 2026-09-30 | [6 empty] | 2026-10-01 | 2026-10-03 |  |  | 2026-10-05 | 2026-10-07 | 2026-10-09 | 2026-10-17 | 2026-10-19 | 86 | N/3 | Rana | [5 empty] | NCL |  |  | Need Test Cut | 182 | 0 | -182 | 0 | -800 | [11 empty] | 43 | Sep'3
UTG-AF | 45092 9th | BAD1468mamaAI | 9000 | 2204 | 2026-07-23 | 2026-07-25 | Long legging | Legging |  |  | 2026-08-18 | 2026-08-31 | 2026-09-01 | 2026-09-15 |  |  | 2026-09-23 | 2026-09-24 |  | 2026-09-28 | 2026-09-30 | [6 empty] | 2026-10-01 | 2026-10-05 |  |  | 2026-10-06 | 2026-10-08 | 2026-10-10 | 2026-10-17 | 2026-10-19 | 86 | ZA1 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 2202 | 2202 | 0 | 0 | -9000 | [11 empty] | 43 | Sep'3
UTG-AF | 44587 11th | BAD2548V | 3000 | 690 | 2026-07-26 | 2026-07-29 | LDS LS V NK TS | TS |  |  | 2026-08-20 | 2026-08-29 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-24 | 2026-09-25 |  | 2026-09-28 | 2026-09-29 | [6 empty] | 2026-10-01 | 2026-10-05 |  |  | 2026-10-06 | 2026-10-08 | 2026-10-10 | 2026-10-17 | 2026-10-19 | 83 | G1 | Rana | [5 empty] | NFL1 |  |  | CAD | 690 | 683 | -7 | 0 | -3000 | [11 empty] | 43 | Sep'3 |  |  | 15.09.26
UTG-AF | 43663 9th | BAD1634U | 15600 | 3654 | 2026-07-26 | 2026-07-29 | LS o nk TS | TS |  |  | 2026-08-10 | 2026-08-25 | 2026-08-25 | 2026-09-10 |  |  | 2026-09-19 | 2026-09-22 |  | 2026-09-24 | 2026-09-30 | [6 empty] | 2026-10-01 | 2026-10-09 |  |  | 2026-10-10 | 2026-10-12 | 2026-10-14 | 2026-10-17 | 2026-10-19 | 83 | G1 | Rana | [5 empty] | NFL1 |  |  | CAD | 3654 | 3414 | -240 | 0 | -15600 | [11 empty] | 43 | Sep'3 |  |  | 15.09.26
UTG-AF | 40671 13th | BAD1298AL | 2000 | 517 | 2026-07-25 | 2026-07-29 | YD LS boat nk TS | TS | 2026-08-20 | 2026-08-31 | 2026-09-01 | 2026-09-11 | 2026-09-12 | 2026-09-22 |  |  | 2026-09-28 | 2026-09-30 |  | 2026-10-02 | 2026-10-03 | [6 empty] | 2026-10-06 | 2026-10-08 |  |  | 2026-10-09 | 2026-10-12 | 2026-10-14 | 2026-10-17 | 2026-10-19 | 84 | G2 | Rana |  |  |  | YD |  | NFL1 |  |  | Need Cut FB | 516 | 0 | -516 | 0 | -2000 | [11 empty] | 43 | Oct'1 |  |  | 18.08.26
UTG-AF | 40668 9th | BAD1630T | 6000 | 1144 | 2026-07-26 | 2026-07-29 | LS o nk TS | TS |  |  | 2026-08-20 | 2026-08-31 | 2026-09-01 | 2026-09-14 |  |  | 2026-09-25 | 2026-09-28 |  | 2026-10-01 | 2026-10-03 | [6 empty] | 2026-10-03 | 2026-10-08 |  |  | 2026-10-09 | 2026-10-12 | 2026-10-14 | 2026-10-17 | 2026-10-19 | 83 | G2 | Rana | [5 empty] | NFL1 |  |  | CAD | 1144 | 902 | -242 | 0 | -6000 | [11 empty] | 43 | Oct'1 |  |  | 15.09.26
UTG-AF | 40665 8th | BAD1123U | 2000 | 475 | 2026-07-26 | 2026-07-29 | LDS LS WRAP TS W LACE | TS |  |  | 2026-08-20 | 2026-08-31 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-24 | 2026-09-25 |  | 2026-09-28 | 2026-09-29 | [6 empty] | 2026-10-01 | 2026-10-05 |  |  | 2026-10-06 | 2026-10-08 | 2026-10-10 | 2026-10-17 | 2026-10-19 | 83 | N/3 | Rana |  |  |  |  | Lace | NCL |  |  | Need Test Cut | 475 | 0 | -475 | 0 | -2000 | [11 empty] | 43 | Sep'3
UTG-AF | 45396 2nd | BAD2999mamaA | 700 | 254 | 2026-07-26 | 2026-07-29 | LS dress w side slit | Dress |  |  | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-09-25 |  |  | 2026-10-01 | 2026-10-02 |  | 2026-10-05 | 2026-10-06 | [6 empty] | 2026-10-07 | 2026-10-09 |  |  | 2026-10-10 | 2026-10-12 | 2026-10-14 | 2026-10-24 | 2026-10-26 | 90 | N/3 | Rana | [5 empty] | NCL |  |  | Po Sheet Due | 254 | 0 | -254 | 0 | -700 | [11 empty] | 44 | Oct'1
UTG-AF | 41711 4th | BAD1529mamaI | 4000 | 890 | 2026-07-26 | 2026-07-29 | Legging | Legging |  |  | 2026-08-10 | 2026-08-20 | 2026-08-21 | 2026-09-05 |  |  | 2026-09-09 | 2026-09-10 |  | 2026-09-14 | 2026-09-15 | [6 empty] | 2026-09-16 | 2026-09-21 |  |  | 2026-09-22 | 2026-09-24 | 2026-09-26 | 2026-10-10 | 2026-10-12 | 76 | N/1 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 890 | 890 | 0 | 0 | -4000 | [11 empty] | 42 | Sep'2
UTG-(Even & Odd) | 45142 3rd | BAD2970B/BAD2970C | 800 | 920 | 2026-07-24 | 2026-07-25 | LS midi dress w side slit | Dress |  |  | 2026-08-20 | 2026-08-31 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-15 | 2026-09-16 |  | 2026-09-18 | 2026-09-19 | [6 empty] | 2026-09-21 | 2026-09-24 |  |  | 2026-09-25 | 2026-09-28 | 2026-10-01 | 2026-10-03 | 2026-10-05 | 71 | N/3 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 920 | 834 | -86 | 0 | -800 | [11 empty] | 41 | Sep'2
UTG-(Even & Odd) | 45244 3rd | BAD2996B | 1000 | 450 | 2026-07-24 | 2026-07-25 | LDS LKS MINI DRESS | DRESS |  |  | 2026-09-01 | 2026-09-08 | 2026-09-10 | 2026-09-22 |  |  | 2026-09-21 | 2026-09-22 |  | 2026-09-25 | 2026-09-26 | [6 empty] | 2026-09-28 | 2026-09-30 |  |  | 2026-10-02 | 2026-10-05 | 2026-10-08 | 2026-10-17 | 2026-10-19 | 85 | N/3 | Rony | [5 empty] | NCL |  |  | Need Test Cut | 450 | 0 | -450 | 0 | -1000 | [11 empty] | 43 | Sep'3
UTG-(Even & Odd) | 44268 2nd | BAD2928A | 1000 | 515 | 2026-07-24 | 2026-07-25 | LDS MINI DRESS | DRESS |  |  | 2026-09-01 | 2026-09-08 | 2026-09-10 | 2026-09-22 |  |  | 2026-09-21 | 2026-09-22 |  | 2026-09-25 | 2026-09-26 | [6 empty] | 2026-09-28 | 2026-09-30 |  |  | 2026-10-02 | 2026-10-05 | 2026-10-08 | 2026-10-17 | 2026-10-19 | 85 | N/3 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 515 | 515 | 0 | 0 | -1000 | [11 empty] | 43 | Sep'3
UTG-(Even & Odd) | 46615 8th | BAD1318AB | 3300 | 992 | 2026-07-23 | 2026-07-25 | AOP SKIRT W SIDE SLIT | Skirt |  |  | 2026-08-01 | 2026-08-10 | 2026-08-11 | 2026-08-20 | 2026-08-21 | 2026-08-28 | 2026-09-07 | 2026-09-08 |  | 2026-09-11 | 2026-09-12 | [6 empty] | 2026-09-15 | 2026-09-17 |  |  | 2026-09-18 | 2026-09-21 | 2026-09-23 | 2026-10-03 | 2026-10-05 | 72 | G2 | Rony |  |  |  | AOP |  | NFL1 |  |  | PPM Due | 992 | 970 | -22 | 0 | -3300 | [11 empty] | 41 | Sep'2 |  |  | 05.09.26
UTG-(Even & Odd) | 30777 7th | BAD2651F | 1500 | 662 | 2026-07-23 | 2026-07-25 | SS Square nk long dress w side slit | Dress |  |  | 2026-08-05 | 2026-08-14 | 2026-08-15 | 2026-08-28 |  |  | 2026-09-07 | 2026-09-08 |  | 2026-09-11 | 2026-09-12 | [6 empty] | 2026-09-15 | 2026-09-18 |  |  | 2026-09-19 | 2026-09-21 | 2026-09-24 | 2026-10-03 | 2026-10-05 | 72 | N/2 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 662 | 662 | 0 | 0 | -1500 | [11 empty] | 41 | Sep'2
BS-NMT | 48494 | 13269381 | 500 | 609 | 2026-07-22 | 2026-07-29 | LS full zipper Swt Hoody w cuff btm rib and kangaro pkt | Hoody |  |  | 2026-08-25 | 2026-08-31 | 2026-09-05 | 2026-09-17 |  |  | 2026-09-19 | 2026-09-19 | 2026-09-26 | 2026-09-30 | 2026-09-30 | 2026-10-02 | 2026-10-05 |  |  |  |  | 2026-10-07 | 2026-10-08 |  |  | 2026-10-10 | 2026-10-13 | 2026-10-16 | 2026-11-09 | 2026-11-11 | 110 | S | Sanaul | Fr,Bk,Nk & Slv |  | black-500 pcs frt back both slve 1 clr rub print |  |  | NFL3 |  |  | File Due | 609 | 0 | -609 | 0 | -500 | [11 empty] | 46 | Sep'3
BS-NMT | 48511 | 13269404 | 2000 | 1487 | 2026-07-22 | 2026-07-29 | LS Swt Hoody w cuff btm rib and kangaro pkt | Hoody |  |  | 2026-08-22 | 2026-08-31 | 2026-09-04 | 2026-09-19 |  |  | 2026-09-21 | 2026-09-21 | 2026-09-26 | 2026-09-29 | 2026-09-30 | [6 empty] | 2026-10-07 | 2026-10-10 |  |  | 2026-10-13 | 2026-10-15 | 2026-10-20 | 2026-11-09 | 2026-11-11 | 110 | S | Sanaul | [5 empty] | NFL3 |  |  | File Due | 1486 | 0 | -1486 | 0 | -2000 | [11 empty] | 46 | Sep'3
BS-NMT | 48498 | 13269380 | 500 | 550 | 2026-07-22 | 2026-07-29 | LS Swt Hoody w cuff btm rib and kangaro pkt | Hoody |  |  | 2026-08-25 | 2026-08-31 | 2026-09-05 | 2026-09-19 |  |  | 2026-09-23 | 2026-09-23 | 2026-09-29 | 2026-10-02 | 2026-10-03 | 2026-10-05 | 2026-10-08 |  |  |  |  | 2026-10-10 | 2026-10-11 |  |  | 2026-10-14 | 2026-10-16 | 2026-10-22 | 2026-11-09 | 2026-11-11 | 110 | S | Sanaul | Fr & Bk & Nk |  | black-500 pcs frt 2 clr rub back 1 clr rub |  |  | NFL3 |  |  | File Due | 550 | 0 | -550 | 0 | -500 | [11 empty] | 46 | Oct'1
BS-NMT | 48497 | 13269379 | 500 | 558 | 2026-07-22 | 2026-07-29 | LS Swt Hoody w cuff btm rib and kangaro pkt | Hoody |  |  | 2026-08-25 | 2026-09-02 | 2026-09-05 | 2026-09-19 |  |  | 2026-09-23 | 2026-09-23 | 2026-09-29 | 2026-10-01 | 2026-10-01 | 2026-10-03 | 2026-10-06 |  |  |  |  | 2026-10-08 | 2026-10-10 |  |  | 2026-10-12 | 2026-10-14 | 2026-10-20 | 2026-11-09 | 2026-11-11 | 110 | S | Sanaul | Patch,Chest,Hood |  | white-500 pcs frt 5 clr rub print and hood 3 clr rub print and back nk label print |  |  | NFL3 |  |  | File Due | 558 | 0 | -558 | 0 | -500 | [11 empty] | 46 | Oct'1
BS-NMT | 48505 | 13269407 | 3000 | 848 | 2026-07-22 | 2026-07-29 | SS o nk TS w nk Rib | TS |  |  | 2026-08-20 | 2026-08-25 | 2026-09-05 | 2026-09-18 |  |  | 2026-09-23 | 2026-09-23 | 2026-09-28 | 2026-10-01 | 2026-10-02 | [6 empty] | 2026-10-08 | 2026-10-10 |  |  | 2026-10-13 | 2026-10-15 | 2026-10-20 | 2026-11-09 | 2026-11-11 | 110 | ZA1 | Sanaul | [5 empty] | NFL3 |  |  | File Due | 828 | 276 | -552 | 0 | -3000 | [11 empty] | 46 | Oct'1
BS-NMT | 48518 | 13269403 | 3000 | 535 | 2026-07-22 | 2026-07-29 | SS o nk TS w nk Rib | TS |  |  | 2026-08-20 | 2026-08-25 | 2026-09-05 | 2026-09-19 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-29 | 2026-10-02 | 2026-10-03 | [6 empty] | 2026-10-07 | 2026-10-09 |  |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-09 | 2026-11-11 | 110 | ZA1 | Sanaul | [5 empty] | NFL3 |  |  | File Due | 535 | 528 | -7 | 0 | -3000 | [11 empty] | 46 | Oct'1
BS-NMT | 48512 | 13269387 | 600 | 106 | 2026-07-22 | 2026-07-29 | SS o nk TS w nk Rib | TS |  |  | 2026-08-20 | 2026-08-24 | 2026-09-05 | 2026-09-17 |  |  | 2026-09-21 | 2026-09-21 | 2026-09-26 | 2026-09-29 | 2026-09-29 | 2026-10-02 | 2026-10-05 |  |  |  |  | 2026-10-07 | 2026-10-08 |  |  | 2026-10-10 | 2026-10-13 | 2026-10-16 | 2026-11-09 | 2026-11-11 | 110 | T1 | Sanaul | Fr & Bk & Nk |  | black-600 pcs frt back 3 clr rub print |  |  | NFL3 |  |  | File Due | 106 | 106 | 0 | 0 | -600 | [11 empty] | 46 | Sep'3
BS-NMT | 48501 | 13269375 | 700 | 198 | 2026-07-22 | 2026-07-29 | SS o nk TS w nk Rib | TS |  |  | 2026-08-20 | 2026-08-25 | 2026-09-04 | 2026-09-17 |  |  | 2026-09-21 | 2026-09-21 | 2026-09-26 | 2026-09-28 | 2026-09-28 | 2026-10-01 | 2026-10-04 |  |  |  |  | 2026-10-07 | 2026-10-08 |  |  | 2026-10-10 | 2026-10-14 | 2026-10-16 | 2026-11-09 | 2026-11-11 | 110 | T1 | Sanaul | Fr & Bk & Nk |  | black-700 pcs frt back 3 clr rub print |  |  | NFL3 |  |  | File Due | 198 | 198 | 0 | 0 | -700 | [11 empty] | 46 | Sep'3
BS-NMT | 48516 | 13269384 | 600 | 108 | 2026-07-22 | 2026-07-29 | SS o nk TS w nk Rib | TS |  |  | 2026-08-17 | 2026-08-20 | 2026-09-02 | 2026-09-14 |  |  | 2026-09-19 | 2026-09-19 | 2026-09-25 | 2026-09-28 | 2026-09-28 | 2026-10-02 | 2026-10-05 |  |  |  |  | 2026-10-08 | 2026-10-09 |  |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-09 | 2026-11-11 | 110 | T1 | Sanaul | Fr & Bk & Nk |  | black-600 pcs frt 3 clr rub back 4 clr rub print |  |  | NFL3 |  |  | File Due | 108 | 108 | 0 | 0 | -600 | [11 empty] | 46 | Sep'3
BS-NMT | 48504 | 13269376 | 700 | 202 | 2026-07-22 | 2026-07-29 | SS o nk TS w nk Rib | TS |  |  | 2026-08-20 | 2026-08-25 | 2026-09-05 | 2026-09-16 |  |  | 2026-09-21 | 2026-09-21 | 2026-09-26 | 2026-09-29 | 2026-09-29 | 2026-10-02 | 2026-10-05 |  |  |  |  | 2026-10-08 | 2026-10-09 |  |  | 2026-10-11 | 2026-10-14 | 2026-10-16 | 2026-11-09 | 2026-11-11 | 110 | T1 | Sanaul | Fr & Bk & Nk |  | black-700 pcs frt back 3 clr rub print |  |  | NFL3 |  |  | File Due | 202 | 202 | 0 | 0 | -700 | [11 empty] | 46 | Sep'3
BS-NMT | 48517 | 13269385 | 500 | 87 | 2026-07-22 | 2026-07-29 | SS o nk TS w nk Rib | TS |  |  | 2026-08-20 | 2026-08-24 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-19 | 2026-09-19 | 2026-09-25 | 2026-09-28 | 2026-09-28 | 2026-10-01 | 2026-10-03 |  |  |  |  | 2026-10-07 | 2026-10-08 |  |  | 2026-10-10 | 2026-10-13 | 2026-10-16 | 2026-11-09 | 2026-11-11 | 110 | T1 | Sanaul | Fr & Bk & Nk |  | white-500 pcs frt 12 clr pig photo print and back 2 clr pig print |  |  | NFL3 |  |  | File Due | 87 | 87 | 0 | 0 | -500 | [11 empty] | 46 | Sep'3
BS-NMT | 48515 | 13269386 | 600 | 108 | 2026-07-22 | 2026-07-29 | SS o nk TS w nk Rib | TS |  |  | 2026-08-17 | 2026-08-20 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-19 | 2026-09-19 | 2026-09-25 | 2026-09-28 | 2026-09-28 | 2026-10-01 | 2026-10-03 |  |  |  |  | 2026-10-07 | 2026-10-07 |  |  | 2026-10-10 | 2026-10-13 | 2026-10-16 | 2026-11-09 | 2026-11-11 | 110 | T1 | Sanaul | Fr & Bk & Nk |  | black-600 pcs frt 7 clr rub photo print and back 3 clr rub print |  |  | NFL3 |  |  | CAD | 108 | 108 | 0 | 0 | -600 | [11 empty] | 46 | Sep'3 |  |  | 14.09.26
BS-NMT | 48514 | 13269382 | 800 | 137 | 2026-07-22 | 2026-07-29 | SS o nk TS w nk Rib | TS |  |  | 2026-08-17 | 2026-08-20 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-18 | 2026-09-18 | 2026-09-25 | 2026-09-28 | 2026-09-29 | 2026-10-02 | 2026-10-05 |  |  |  |  | 2026-10-08 | 2026-10-08 |  |  | 2026-10-11 | 2026-10-13 | 2026-10-15 | 2026-11-09 | 2026-11-11 | 110 | T1 | Sanaul | Fr & Bk & Nk |  | black-800 pcs frt 1 clr rubt and back 4 clr rub digital photo print |  |  | NFL3 |  |  | File Due | 143 | 143 | 0 | 0 | -800 | [11 empty] | 46 | Sep'3
BS-NMT | 48513 | 13269383 | 500 | 89 | 2026-07-22 | 2026-07-29 | SS o nk TS w nk Rib | TS |  |  | 2026-08-17 | 2026-08-20 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-19 | 2026-09-19 | 2026-09-26 | 2026-09-29 | 2026-09-29 | 2026-10-02 | 2026-10-05 |  |  |  |  | 2026-10-09 | 2026-10-09 |  |  | 2026-10-13 | 2026-10-15 | 2026-10-20 | 2026-11-09 | 2026-11-11 | 110 | T1 | Sanaul | Fr & Bk & Nk |  | white-500 pcs frt back 5 clr rub print |  |  | NFL3 |  |  | File Due | 89 | 89 | 0 | 0 | -500 | [11 empty] | 46 | Sep'3
BS-NMT | 48503 | 13269374 | 700 | 202 | 2026-07-22 | 2026-07-29 | SS o nk TS w nk Rib | TS |  |  | 2026-08-15 | 2026-08-20 | 2026-09-05 | 2026-09-15 |  |  | 2026-09-22 | 2026-09-22 | 2026-09-28 | 2026-09-30 | 2026-09-30 | 2026-10-03 | 2026-10-06 |  |  |  |  | 2026-10-10 | 2026-10-10 |  |  | 2026-10-13 | 2026-10-15 | 2026-10-19 | 2026-11-09 | 2026-11-11 | 110 | T1 | Sanaul | Fr & Bk & Nk |  | black-700 pcs frt back 2 clr rub print |  |  | NFL3 |  |  | File Due | 202 | 202 | 0 | 0 | -700 | [11 empty] | 46 | Sep'3
BS-NMT | 48502 | 13269373 | 700 | 201 | 2026-07-22 | 2026-07-29 | SS o nk TS w nk Rib | TS |  |  | 2026-08-15 | 2026-08-20 | 2026-09-05 | 2026-09-15 |  |  | 2026-09-22 | 2026-09-22 | 2026-09-28 | 2026-10-01 | 2026-10-01 | 2026-10-04 | 2026-10-07 |  |  |  |  | 2026-10-10 | 2026-10-10 |  |  | 2026-10-12 | 2026-10-15 | 2026-10-21 | 2026-11-09 | 2026-11-11 | 110 | T1 | Sanaul | Fr & Bk & Nk |  | black-700 pcs frt 14 clr rub photo print back 2 clr rub print |  |  | NFL3 |  |  | File Due | 201 | 201 | 0 | 0 | -700 | [11 empty] | 46 | Oct'1
BS-NMT | 48500 | 13269363 | 500 | 145 | 2026-07-22 | 2026-07-29 | SS o nk TS w nk Rib | TS |  |  | 2026-08-17 | 2026-08-22 | 2026-09-05 | 2026-09-17 |  |  | 2026-09-21 | 2026-09-21 | 2026-09-26 | 2026-09-30 | 2026-09-30 | 2026-10-02 | 2026-10-05 |  |  |  |  | 2026-10-09 | 2026-10-09 |  |  | 2026-10-12 | 2026-10-14 | 2026-10-22 | 2026-11-09 | 2026-11-11 | 110 | T1 | Sanaul | Fr & Bk & Nk |  | White-500 pcs frt back 5 clr rub print |  |  | NFL3 |  |  | File Due | 145 | 145 | 0 | 0 | -500 | [11 empty] | 46 | Sep'3
BS-NMT | 48496 | 13269378 | 600 | 652 | 2026-07-22 | 2026-07-29 | LS Swt Hoody w cuff btm rib and kangaro pkt | Hoody |  |  | 2026-08-24 | 2026-08-31 | 2026-09-05 | 2026-09-19 |  |  | 2026-09-23 | 2026-09-23 | 2026-09-28 | 2026-10-01 | 2026-10-01 | 2026-10-03 | 2026-10-07 |  |  |  |  | 2026-10-09 | 2026-10-10 |  |  | 2026-10-12 | 2026-10-14 | 2026-10-17 | 2026-11-09 | 2026-11-11 | 110 | S | Sanaul | Fr,Bk,Nk & Slv |  | Black-600 pcs frt 14 clr rub photo print back 2 clr rub both slve 3 clr rub print |  |  | NFL3 |  |  | File Due | 652 | 427 | -225 | 0 | -600 | [11 empty] | 46 | Oct'1
BS-NMT | 48499 | 13269406 | 1000 | 1024 | 2026-07-22 | 2026-07-29 | LS Swt Hoody w cuff btm rib and kangaro pkt | Hoody |  |  | 2026-08-15 | 2026-08-22 | 2026-09-02 | 2026-09-16 |  |  | 2026-09-18 | 2026-09-18 | 2026-09-24 | 2026-09-26 | 2026-09-28 | [6 empty] | 2026-10-07 | 2026-10-08 |  |  | 2026-10-10 | 2026-10-13 | 2026-10-16 | 2026-11-09 | 2026-11-11 | 110 | S | Sanaul | [5 empty] | NFL3 |  |  | File Due | 1024 | 0 | -1024 | 0 | -1000 | [11 empty] | 46 | Sep'3
BS-NMT | 48508 | 13269399 | 600 | 514 | 2026-07-22 | 2026-07-29 | LS full zipper Swt Hoody w cuff btm rib and kangaro pkt | Hoody |  |  | 2026-08-15 | 2026-08-20 | 2026-09-02 | 2026-09-14 |  |  | 2026-09-18 | 2026-09-18 | 2026-09-25 | 2026-09-28 | 2026-09-28 | 2026-10-01 | 2026-10-03 |  |  |  |  | 2026-10-07 | 2026-10-09 |  |  | 2026-10-12 | 2026-10-14 | 2026-10-17 | 2026-11-09 | 2026-11-11 | 110 | S | Sanaul | Fr & Bk & Nk |  | black-600 pcs frt 2 clr rub back 4 clr rub print |  |  | NFL3 |  |  | CAD | 515 | 0 | -515 | 0 | -600 | [11 empty] | 46 | Sep'3 |  |  | 16.09.26
BS-NMT | 48506 | 13269391 | 600 | 458 | 2026-07-22 | 2026-07-29 | LS Swt Hoody w cuff btm rib and kangaro pkt | Hoody |  |  | 2026-08-20 | 2026-08-26 | 2026-09-05 | 2026-09-17 |  |  | 2026-09-19 | 2026-09-19 | 2026-09-25 | 2026-09-28 | 2026-09-29 | 2026-10-02 | 2026-10-05 |  |  |  |  | 2026-10-08 | 2026-10-09 |  |  | 2026-10-12 | 2026-10-14 | 2026-10-22 | 2026-11-09 | 2026-11-11 | 110 | S | Sanaul | Fr & Bk & Nk |  | black-600 pcs frt 1 clr rub back 4 clr rub digital photo print |  |  | NFL3 |  |  | CAD | 459 | 0 | -459 | 0 | -600 | [11 empty] | 46 | Sep'3 |  |  | 16.09.26
BS-NMT | 48507 | 13269394 | 500 | 385 | 2026-07-22 | 2026-07-29 | LS Swt Hoody w cuff btm rib and kangaro pkt | Hoody |  |  | 2026-08-23 | 2026-08-31 | 2026-09-05 | 2026-09-19 |  |  | 2026-09-22 | 2026-09-22 | 2026-09-28 | 2026-10-01 | 2026-10-01 | 2026-10-03 | 2026-10-07 |  |  |  |  | 2026-10-09 | 2026-10-10 |  |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-09 | 2026-11-11 | 110 | S | Sanaul | Fr,Bk,Nk & Slv |  | black-500 pcs frt 2 clr rub back 14 clr rub photo print and both slve 3 clr rub print |  |  | NFL3 |  |  | File Due | 385 | 0 | -385 | 0 | -500 | [11 empty] | 46 | Oct'1
OVS SPA | 48255 | 271SWT009-223 | 7643 | 5422 | 2026-07-15 | 2026-07-24 | LS Swt hoody w kangaro pkt and cuff btm belt gmts dye acid wash | Hoody |  |  | 2026-08-15 | 2026-09-03 | 2026-09-01 | 2026-09-19 |  |  | 2026-10-15 | 2026-10-01 | 2026-10-09 | 2026-10-10 | 2026-10-13 | 2026-10-30 | 2026-11-10 |  |  |  |  | 2026-10-19 | 2026-10-28 | 2026-10-26 | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-14 | 2026-11-16 | 2026-11-16 | 124 | J | Sirajul | Chest |  | black-7643 pcs 4 clr rub print |  | Gmts dye acid wash | NFL2 |  |  | File Due | 5422 | 4352 | -1070 | 0 | -7643 | [11 empty] | 47 | Oct'1
OVS SPA | 48251 | 271TSH011-223 | 3910 | 914 | 2026-07-15 | 2026-07-24 | YD SS O nk TS w cuff nk rib | TS | 2026-08-20 | 2026-08-31 | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-09-23 |  |  | 2026-10-10 | 2026-09-03 | 2026-10-09 | 2026-10-10 | 2026-10-12 | 2026-10-13 | 2026-10-17 |  |  |  |  | 2026-10-19 | 2026-10-21 |  |  | 2026-10-22 | 2026-10-24 | 2026-10-26 | 2026-11-02 | 2026-11-02 | 110 | G1 | Sirajul | Chest,HP |  | multicolor-3910 pcs 2 clr rub print | YD |  | NFL1 |  |  | File Due | 914 | 0 | -914 | 0 | -3910 | [11 empty] | 45 | Oct'1
OVS SPA | 48252 | 271SWT008-223 | 5783 | 3055 | 2026-07-15 | 2026-07-24 | LS half zipper swt shirt w slve cut& sewand kangaro pkt and collar cuff btm rib | Swt Shirt |  |  | 2026-08-25 | 2026-09-08 | 2026-09-10 | 2026-09-25 |  |  | 2026-10-06 | 2026-09-25 | 2026-10-03 | 2026-10-05 | 2026-10-07 |  |  |  |  | 2026-10-12 | 2026-10-17 | 2026-10-16 | 2026-10-24 |  |  | 2026-10-26 | 2026-10-28 | 2026-10-30 | 2026-11-02 | 2026-11-02 | 110 | B | Sirajul |  | Fr & Bk | white-5783 pcs frt back 1 clr flat emb |  |  | NFL1 |  |  | File Due | 3055 | 2857 | -198 | 0 | -5783 | [11 empty] | 45 | Oct'1
OVS SPA | 48250 | 271TSH009-223 | 4158 | 1020 | 2026-07-15 | 2026-07-24 | YD SS o nk TS w nk Rib | TS | 2026-08-20 | 2026-08-31 | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-09-23 |  |  | 2026-10-10 | 2026-10-03 | 2026-10-09 | 2026-10-10 | 2026-10-12 | 2026-10-13 | 2026-10-17 |  |  |  |  | 2026-10-19 | 2026-10-21 |  |  | 2026-10-22 | 2026-10-24 | 2026-10-26 | 2026-11-02 | 2026-11-02 | 110 | G1 | Sirajul | Chest,HP |  | multicolor-4158 pcs 1 clr rub print | YD |  | NFL1 |  |  | File Due | 1021 | 0 | -1021 | 0 | -4158 | [11 empty] | 45 | Oct'1
OVS SPA | 48248 | 271TRO022-6155 | 11851 | 3028 | 2026-07-15 | 2026-07-24 | Waist belt trouser w side pkt and drawstring | Trouser |  |  | 2026-09-05 | 2026-09-14 | 2026-09-18 | 2026-10-05 |  |  | 2026-10-10 | 2026-10-09 | 2026-10-14 | 2026-10-15 | 2026-10-19 | [6 empty] | 2026-10-20 | 2026-10-30 |  |  | 2026-10-31 | 2026-11-02 | 2026-11-04 | 2026-11-09 | 2026-11-09 | 117 | N/3 | Sirajul | [5 empty] | NCL |  |  | File Due | 3027 | 0 | -3027 | 0 | -11851 | [11 empty] | 46 | Oct'2
OVS SPA | 48242 | 271TNKT101-6084 | 5030 | 570 | 2026-07-22 | 2026-07-28 | Tank Top w front placket btn | Tank Top |  |  | 2026-10-01 | 2026-10-12 | 2026-10-14 | 2026-10-28 |  |  | 2026-11-04 | 2026-11-05 | 2026-11-10 | 2026-11-11 | 2026-11-13 | [6 empty] | 2026-11-14 | 2026-11-20 |  |  | 2026-11-22 | 2026-11-24 | 2026-11-26 | 2026-11-30 | 2026-11-30 | 131 | N/2 | Basir | [5 empty] | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -5030 | [11 empty] | 49 | Nov'2
OVS SPA | 47895 | 271TSHT111-6084 | 5030 | 856 | 2026-07-22 | 2026-07-28 | SS TS w slve frill w lurex rib | TS |  |  | 2026-10-01 | 2026-10-13 | 2026-10-14 | 2026-10-28 |  |  | 2026-11-04 | 2026-11-05 | 2026-11-10 | 2026-11-11 | 2026-11-13 | [6 empty] | 2026-11-14 | 2026-11-21 |  |  | 2026-11-23 | 2026-11-25 | 2026-11-27 | 2026-11-30 | 2026-11-30 | 131 | A | Basir | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -5030 | [11 empty] | 49 | Nov'2
GBX-New Look | 48327 | 9155325 | 2020 | 562 | 2026-07-17 | 2026-07-24 | SS o nk TS | TS |  |  | 2026-09-15 | 2026-09-20 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-20 | 2026-10-22 | 2026-10-23 | [6 empty] | 2026-10-26 | 2026-10-28 |  |  | 2026-10-31 | 2026-11-03 | 2026-11-05 | 2026-11-14 | 2026-11-15 | 120 | N/1 | Morad | [5 empty] | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -2020 | [11 empty] | 47 | Oct'3
GBX-New Look | 48328 | 9668391 | 4141 | 1070 | 2026-07-17 | 2026-07-24 | SL o nk TS | TS |  |  | 2026-09-10 | 2026-09-15 | 2026-09-25 | 2026-10-08 |  |  | 2026-10-12 | 2026-10-12 | 2026-10-17 | 2026-10-19 | 2026-10-20 | 2026-10-22 | 2026-10-23 |  |  |  |  | 2026-10-26 | 2026-10-29 |  |  | 2026-10-31 | 2026-11-02 | 2026-11-04 | 2026-11-14 | 2026-11-15 | 120 | N/1 | Morad | Nk |  | 2 combo nk size label print |  |  | NCL |  |  | File Due | 1070 | 0 | -1070 | 0 | -4141 | [11 empty] | 47 | Oct'2
UTG-AF | 42965 17th | BAD2530mamaAF | 6000 | 2462 | 2026-07-26 | 2026-07-29 | Long Plazoo | Plazo |  |  | 2026-09-01 | 2026-09-08 | 2026-09-10 | 2026-09-22 |  |  | 2026-10-01 | 2026-10-02 |  | 2026-10-06 | 2026-10-07 | [6 empty] | 2026-10-08 | 2026-10-15 |  |  | 2026-10-16 | 2026-10-19 | 2026-10-19 | 2026-11-07 | 2026-11-09 | 104 | K1 | Rana | [5 empty] | NFL2 |  |  | Po Sheet Due | 2464 | 1184 | -1280 | 0 | -6000 | [11 empty] | 46 | Oct'1
UTG-AF | 42480 5th | BAD1059mamaAN | 2000 | 390 | 2026-07-26 | 2026-07-29 | maternity legging | Legging |  |  | 2026-09-01 | 2026-09-07 | 2026-09-10 | 2026-09-21 |  |  | 2026-10-05 | 2026-10-06 |  | 2026-10-08 | 2026-10-09 | [6 empty] | 2026-10-10 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-17 | 2026-10-19 | 2026-11-07 | 2026-11-09 | 104 | N/1 | Rana | [5 empty] | NCL |  |  | Po Sheet Due | 390 | 390 | 0 | 0 | -2000 | [11 empty] | 46 | Oct'1
UTG-(Even & Odd) | 41647 13th | BAD2678L | 600 | 135 | 2026-07-24 | 2026-07-25 | LS BALLARINA KNOT TOP | DRESS |  |  | 2026-08-11: 2026-09-01; 2026-08-20: 2026-09-12; 2026-09-07: 2026-09-26; 2026-09-08: 2026-09-28 |  | 2026-10-01 | 2026-10-02 | [6 empty] | 2026-10-05 | 2026-10-07 |  |  | 2026-10-08 | 2026-10-10 | 2026-10-12 | 2026-10-31 | 2026-11-02 | 99 | N/3 | Rony |  |  |  |  | Imp Stock grey fab | NCL |  |  | Po Sheet Due | 135 | 0 | -135 | 0 | -600 | [11 empty] | 45 | Oct'1
OVS SPA | 48459 | 271MMP420-903 | 16985 | 2378 | 2026-07-24 | 2026-07-28 | Elasted Shorts w lace at opening | Shorts |  |  | 2026-10-20 | 2026-11-05 | 2026-11-06 | 2026-11-24 |  |  | 2026-12-02 | 2026-12-03 | 2026-12-08 | 2026-12-09 | 2026-12-15 | [6 empty] | 2026-12-12 | 2026-12-25 |  |  | 2026-12-26 | 2026-12-28 | 2026-12-30 | 2027-01-05 | 2027-01-05 | 165 | E | Salam |  |  |  |  | Lace | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -16985 | [11 empty] | 2 | Dec'1
OVS SPA | 48460 | 271MMP421-903 | 14160 | 2136 | 2026-07-24 | 2026-07-28 | Tank top w armhole self fab binding and lace at front collar | Tank Top |  |  | 2026-10-20 | 2026-11-05 | 2026-11-06 | 2026-11-24 |  |  | 2026-12-02 | 2026-12-03 | 2026-12-08 | 2026-12-09 | 2026-12-14 | [6 empty] | 2026-12-12 | 2026-12-25 |  |  | 2026-12-26 | 2026-12-28 | 2026-12-30 | 2027-01-05 | 2027-01-05 | 165 | A | Salam |  |  |  |  | Lace | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -14160 | [11 empty] | 2 | Dec'1
UTG-(Even & Odd) | 45827 3rd | BAD3042B | 2000 | 260 | 2026-07-29 | 2026-07-29 | Double layer sqred nk line strap Tank top | TANK TOP |  |  | 2026-08-01 | 2026-08-06 | 2026-08-08 | 2026-08-20 |  |  | 2026-08-20 | 2026-08-21 |  | 2026-08-24 | 2026-08-25 | [6 empty] | 2026-08-26 | 2026-08-29 |  |  | 2026-08-31 | 2026-09-01 | 2026-09-03 | 2026-09-05 | 2026-09-07 | 38 | N/2 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 260 | 260 | 0 | 0 | -2000 | [11 empty] | 37 | Aug'3
UTG-(Even & Odd) | 46706 3rd | BAD3157B | 4000 | 660 | 2026-07-29 | 2026-07-29 | SS o nk TS | TS |  |  | 2026-08-01 | 2026-08-06 | 2026-08-08 | 2026-08-20 |  |  | 2026-08-20 | 2026-08-21 |  | 2026-08-24 | 2026-08-25 | [6 empty] | 2026-08-26 | 2026-08-29 |  |  | 2026-08-31 | 2026-09-02 | 2026-09-04 | 2026-09-05 | 2026-09-07 | 38 | N/3 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 660 | 660 | 0 | 0 | -4000 | [11 empty] | 37 | Aug'3
UTG-(Even & Odd) | 43040 3rd | BAD2854C | 1800 | 565 | 2026-07-29 | 2026-07-29 | SL LONG DRESS W CUT OUT | Dress |  |  | 2026-08-01 | 2026-08-06 | 2026-08-08 | 2026-08-20 |  |  | 2026-08-19 | 2026-08-20 |  | 2026-08-24 | 2026-08-25 | [6 empty] | 2026-08-26 | 2026-08-29 |  |  | 2026-08-31 | 2026-09-02 | 2026-09-04 | 2026-09-05 | 2026-09-07 | 38 | N/3 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 565 | 565 | 0 | 0 | -1800 | [11 empty] | 37 | Aug'3
UTG-(Even & Odd) | 47083 2nd | BAD3210A | 1800 | 255 | 2026-07-29 | 2026-07-29 | SS V nk Polo w YD collar placket | Polo | 2026-08-03 | 2026-08-11 | 2026-08-11 | 2026-08-15 | 2026-08-15 | 2026-08-22 |  |  | 2026-08-18 | 2026-08-19 |  | 2026-08-21 | 2026-08-22 |  |  |  |  | 2026-08-24 | 2026-08-26 | 2026-08-27 | 2026-08-31 |  |  | 2026-08-31 | 2026-09-01 | 2026-09-03 | 2026-09-05 | 2026-09-07 | 38 | N/2 | Rony |  | Chest | sky captain-1800 pcs 1 clr flat emb | YD |  | NCL |  |  | Ready Test Cut | 255 | 255 | 0 | 0 | -1800 | [11 empty] | 37 | Aug'3
BS-ONL | 29402 44th | 15312874 | 3024 | 1712 | 2026-08-05 | 2026-08-06 | LS Swt hoodie w drawstring | Hoody |  |  | 2026-08-10 | 2026-08-20 | 2026-08-22 | 2026-09-05 |  |  | 2026-09-04 | 2026-09-04 |  | 2026-09-09 | 2026-09-11 |  |  |  |  | 2026-09-11 | 2026-09-12 | 2026-09-15 | 2026-09-18 |  |  | 2026-09-21 | 2026-09-23 | 2026-09-24 | 2026-09-28 | 2026-09-30 | 54 | H | Imran |  | Chest,Pkt | black heart-3024 pcs chest and btm side 1 CLR FLAT EMB |  |  | NFL1 |  |  | Need Cut FB | 1712 | 0 | -1712 | 0 | -3024 | [11 empty] | 40 | Sep'1 |  |  | 07.08.26
BS-ONL | 29402 45th | 15312874 | 6048 | 3425 | 2026-08-05 | 2026-08-06 | LS Swt hoodie w drawstring | Hoody |  |  | 2026-08-13 | 2026-08-26 | 2026-08-25 | 2026-09-10 |  |  | 2026-09-09 | 2026-09-09 |  | 2026-09-12 | 2026-09-15 |  |  |  |  | 2026-09-15 | 2026-09-18 | 2026-09-21 | 2026-09-24 |  |  | 2026-09-26 | 2026-09-29 | 2026-10-05 | 2026-10-12 | 2026-10-14 | 68 | H | Imran |  | Chest,Pkt | Anise -3024 pcs,,pink-3024 pcs all combo chest and btm side 1 CLR FLAT EMB |  |  | NFL1 |  |  | Cut Run | 3424 | 1969 | -1455 | 1806 | -4242 | [11 empty] | 42 | Sep'2 |  |  | 07.08.26
BS-ONL | 29402 46th | 15312874 | 4032 | 2283 | 2026-08-05 | 2026-08-06 | LS Swt hoodie w drawstring | Hoody |  |  | 2026-08-20 | 2026-08-27 | 2026-09-01 | 2026-09-15 |  |  | 2026-09-18 | 2026-09-18 |  | 2026-09-23 | 2026-09-24 |  |  |  |  | 2026-09-26 | 2026-09-28 | 2026-10-01 | 2026-10-03 |  |  | 2026-10-06 | 2026-10-08 | 2026-10-13 | 2026-11-16 | 2026-11-18 | 103 | E | Imran |  | Chest,Pkt | Anise -2016 pcs,,pink-2016 pcs all combo chest and btm side 1 CLR FLAT EMB |  |  | NFL1 |  |  | Need Cut | 2282 | 1225 | -1057 | 0 | -4032 | [11 empty] | 47 | Sep'3 |  |  | 07.08.26
BS-ONL | 27204 61th | 15323159 | 10720 | 2573 | 2026-07-30 | 2026-07-31 | LS o nk TS | TS |  |  | 2026-08-10 | 2026-08-20 | 2026-08-24 | 2026-09-08 |  |  | 2026-09-07 | 2026-09-07 |  | 2026-09-12 | 2026-09-15 | [6 empty] | 2026-09-16 | 2026-09-21 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-25 | 2026-09-28 | 2026-09-30 | 60 | G1 | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 2573 | 2573 | 0 | 10815 | 95 | [11 empty] | 40 | Sep'2 |  |  | 07.08.26
BS-ONL | 27204 62th | 15323159 | 7840 | 1893 | 2026-07-30 | 2026-07-31 | LS o nk TS | TS |  |  | 2026-08-15 | 2026-08-24 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-10 | 2026-09-10 |  | 2026-09-14 | 2026-09-17 | [6 empty] | 2026-09-17 | 2026-09-22 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-28 | 2026-09-30 | 60 | G1 | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 1893 | 1865 | -28 | 7905 | 65 | [11 empty] | 40 | Sep'2 |  |  | 07.08.26
BS-ONL | 42946 10th | 15360359 | 4060 | 1533 | 2026-07-31 | 2026-08-01 | YD loose pant w drawstring | Pant | 2026-08-06 | 2026-08-15 | 2026-08-17 | 2026-08-28 | 2026-08-28 | 2026-09-07 |  |  | 2026-09-04 | 2026-09-04 |  | 2026-09-09 | 2026-09-11 | [6 empty] | 2026-09-14 | 2026-09-18 |  |  | 2026-09-21 | 2026-09-23 | 2026-09-24 | 2026-09-28 | 2026-09-30 | 59 | P | Dalim |  |  |  | YD |  | NFL2 |  |  | Need Cut FB | 1533 | 0 | -1533 | 0 | -4060 | [11 empty] | 40 | Sep'1 |  |  | 08.08.26
BS-ONS | 30588 20th | 22031724 | 14000 | 5752 | 2026-07-31 | 2026-08-01 | SS o nk TS | TS |  |  | 2026-08-06 | 2026-08-18 | 2026-08-12 | 2026-08-31 |  |  | 2026-08-24 | 2026-08-24 |  | 2026-08-28 | 2026-09-01 | [6 empty] | 2026-09-01 | 2026-09-05 |  |  | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-14 | 2026-09-16 | 45 | F | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 5754 | 5734 | -20 | 14301 | 301 | [11 empty] | 38 | Aug'3 |  |  | 08.08.26
BS-ONL | 45313 10th | 15311584 | 1520 | 253 | 2026-07-29 | 2026-07-30 | High waist shorts | Shorts |  |  | 2026-08-01 | 2026-08-06 | 2026-08-10 | 2026-08-18 |  |  | 2026-08-15 | 2026-08-15 |  | 2026-08-21 | 2026-08-22 | 2026-08-22 | 2026-08-24 |  |  |  |  | 2026-08-26 | 2026-08-27 |  |  | 2026-08-28 | 2026-08-29 | 2026-08-31 | 2026-08-31 | 2026-09-02 | 33 | L2 | Khalid | WAIST |  | 1 combo label print |  |  | NFL2 |  |  | Cut Ok | 253 | 129 | -124 | 0 | -1520 | [11 empty] | 36 | Aug'3 |  |  | 10.08.26
BS-ONL | 45317 5th | 15084518 | 1500 | 389 | 2026-07-29 | 2026-07-30 | LDS 3/4 FOLD LEGGING | Legging |  |  | 2026-08-04 | 2026-08-08 | 2026-08-12 | 2026-08-22 |  |  | 2026-08-20 | 2026-08-20 |  | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 |  |  |  |  | 2026-09-01 | 2026-09-02 |  |  | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-07 | 2026-09-09 | 40 | O1 | Khalid | WAIST |  | 1 combo waist print |  |  | NFL2 |  |  | Cut Ok | 389 | 389 | 0 | 1537 | 37 | [11 empty] | 37 | Aug'3 |  |  | 10.08.26
BS-ONL | 45315 5th | 15206049 | 1520 | 196 | 2026-07-29 | 2026-07-30 | High waist shorts | Shorts |  |  | 2026-08-01 | 2026-08-06 | 2026-08-10 | 2026-08-18 |  |  | 2026-08-15 | 2026-08-15 |  | 2026-08-21 | 2026-08-22 | 2026-08-24 | 2026-08-25 |  |  |  |  | 2026-08-26 | 2026-08-27 |  |  | 2026-08-28 | 2026-08-29 | 2026-08-31 | 2026-08-31 | 2026-09-02 | 33 | L2 | Khalid | WAIST |  | 1 combo logo print |  |  | NFL2 |  |  | Cut Ok | 196 | 196 | 0 | 1568 | 48 | [11 empty] | 36 | Aug'3 |  |  | 10.08.26
BS-ONL | 41875 16th | 15303956 | 1520 | 636 | 2026-07-29 | 2026-07-30 | PANT W PKT | PANT |  |  | 2026-08-04 | 2026-08-10 | 2026-08-12 | 2026-08-26 |  |  | 2026-08-25 | 2026-08-25 |  | 2026-09-02 | 2026-09-03 |  |  |  |  | 2026-09-04 | 2026-09-05 | 2026-09-08 | 2026-09-10 |  |  | 2026-09-12 | 2026-09-14 | 2026-09-16 | 2026-09-21 | 2026-09-23 | 54 | P | Khalid |  | LEG | BLACK 1520 PCS 1 CLR LETTERING EMB AT ONE LEG |  |  | NFL2 |  |  | Cut Ok | 636 | 636 | 0 | 1546 | 26 | [11 empty] | 39 | Sep'1 |  |  | 10.08.26
BS-ONS | 47818 4th | 22041282 | 11524 | 3952 | 2026-08-03 | 2026-07-31 | SS TS w nk and arm hole contrast piping | TS |  |  | 2026-08-01 | 2026-08-07 | 2026-08-06 | 2026-08-13 |  |  | 2026-08-11 | 2026-08-11 |  | 2026-08-13 | 2026-08-16 | [6 empty] | 2026-08-15 | 2026-08-20 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-24 | 2026-08-24 | 2026-08-26 | 21 | V | Shovon | [5 empty] | NFL3 |  |  | Cut Ok | 3952 | 3952 | 0 | 0 | -11524 | [11 empty] | 35 | Aug'2 |  |  | 10.08.26
BS-NMT | 46491 6th | 13225095 | 1520 | 215 | 2026-07-31 | 2026-08-01 | YD LS o nk TS | TS | 2026-09-07 | 2026-09-13 | 2026-09-17 | 2026-09-25 | 2026-08-29 | 2026-09-04 |  |  | 2026-09-07 | 2026-09-07 |  | 2026-09-11 | 2026-09-12 | 2026-09-15 | 2026-09-16 |  |  |  |  | 2026-09-18 | 2026-09-19 |  |  | 2026-09-22 | 2026-09-24 | 2026-09-25 | 2026-09-28 | 2026-09-30 | 59 | L1 | Jafar | Chest,Nk |  | indigo-1520 pcs 1 clr puff print | YD |  | NFL2 |  |  | Cut Ok | 214 | 214 | 0 | 1587 | 67 | [11 empty] | 40 | Sep'2 |  |  | 24.08.26
BS-NMT | 43321 26th | 13205781 | 11160 | 1424 | 2026-08-06 | 2026-08-10 | Legging | Legging |  |  | 2026-08-10 | 2026-08-15 | 2026-08-15 | 2026-08-28 |  |  | 2026-08-28 | 2026-08-28 |  | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 |  |  |  |  | 2026-09-05 | 2026-09-08 |  |  | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-14 | 2026-09-16 | 39 | W2 | Jafar | Waist |  | 3 combo label print |  |  | NFL3 |  |  | Cut Ok | 1424 | 1424 | 0 | 11373 | 213 | [11 empty] | 38 | Sep'1 |  |  | 21.08.26
BS-NMT | 43325 15th | 13224921 | 2000 | 927 | 2026-08-06 | 2026-08-10 | LS Swt full Zip hoodie | Hoody |  |  | 2026-08-15 | 2026-08-21 | 2026-08-28 | 2026-09-10 |  |  | 2026-09-10 | 2026-09-10 |  | 2026-09-14 | 2026-09-15 | [6 empty] | 2026-09-17 | 2026-09-21 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-25 | 2026-09-28 | 2026-09-30 | 53 | S | Jafar | [5 empty] | NFL3 |  |  | Cut Run | 928 | 768 | -160 | 1909 | -91 | [11 empty] | 40 | Sep'2 |  |  | 21.08.26
BS-NMT | 43327 16th | 13235093 | 1200 | 395 | 2026-08-06 | 2026-08-10 | Swt Pant w pkt waist belt drawstring | Pant |  |  | 2026-08-17 | 2026-08-22 | 2026-09-01 | 2026-09-11 |  |  | 2026-09-10 | 2026-09-10 |  | 2026-09-15 | 2026-09-16 | [6 empty] | 2026-09-18 | 2026-09-21 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-28 | 2026-09-30 | 53 | X | Jafar | [5 empty] | NFL3 |  |  | Need Cut FB | 395 | 0 | -395 | 0 | -1200 | [11 empty] | 40 | Sep'2 |  |  | 21.08.26
BS-NMT | 44023 13th | 13246492 | 2080 | 121 | 2026-08-06 | 2026-08-10 | AOP Legging | Legging |  |  | 2026-08-19 | 2026-08-22 | 2026-08-26 | 2026-09-03 | 2026-09-05 | 2026-09-12 | 2026-09-12 | 2026-09-10 |  | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 |  |  |  |  | 2026-09-21 | 2026-09-22 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-28 | 2026-09-30 | 53 | W1 | Jafar | waist |  | 2 combo label print | AOP |  | NFL3 |  |  | Need Cut FB | 122 | 0 | -122 | 0 | -2080 | [11 empty] | 40 | Sep'2 |  |  | 21.08.26
BS-ONS | 26827 56th | 22029225 | 1000 | 912 | 2026-07-29 | 2026-07-30 | LS Swt hoodie w kangaro pkt and drastring and cuff btm rib | HOODY |  |  | 2026-08-06 | 2026-08-10 | 2026-08-14 | 2026-08-25 |  |  | 2026-08-22 | 2026-08-22 |  | 2026-08-28 | 2026-08-29 | [6 empty] | 2026-09-01 | 2026-09-02 |  |  | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-07 | 2026-09-09 | 40 | J | Shakel | [5 empty] | NFL2 |  |  | Cut Ok | 912 | 912 | 0 | 1037 | 37 | [11 empty] | 37 | Aug'1 |  |  | 22.08.26
BS-ONS | 26970 60th | 22002973 | 2000 | 431 | 2026-08-01 | 2026-08-06 | SS o nk TS | TS |  |  | 2026-08-17 | 2026-08-22 | 2026-09-01 | 2026-09-10 |  |  | 2026-09-12 | 2026-09-12 |  | 2026-09-17 | 2026-09-18 | [6 empty] | 2026-09-21 | 2026-09-22 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-28 | 2026-09-30 | 58 | G1 | Shakel | [5 empty] | NFL1 |  |  | Size Set Run PC | 431 | 418 | -13 | 0 | -2000 | [11 empty] | 40 | Sep'2 |  |  | 14.09.26
BS-ONS | 26828 78th | 22029226 | 11000 | 7051 | 2026-07-31 | 2026-08-06 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-08-10 | 2026-08-22 | 2026-08-20 | 2026-09-08 |  |  | 2026-09-04 | 2026-09-04 |  | 2026-09-08 | 2026-09-12 | [6 empty] | 2026-09-11 | 2026-09-17 |  |  | 2026-09-18 | 2026-09-19 | 2026-09-21 | 2026-09-21 | 2026-09-23 | 52 | H | Shakel | [5 empty] | NFL1 |  |  | Cut Run | 7049 | 6796 | -253 | 10914 | -86 | [11 empty] | 39 | Sep'1 |  |  | 25.08.26
BS-ONS | 46616 4th | 22039183 | 5500 | 4968 | 2026-08-07 | 2026-08-08 | LS Swt Hoody | Hoody |  |  | 2026-08-12 | 2026-08-17 | 2026-08-17 | 2026-08-31 |  |  | 2026-08-28 | 2026-08-26 |  | 2026-08-31 | 2026-09-03 | 2026-09-02 | 2026-09-05 |  |  |  |  | 2026-09-05 | 2026-09-11 |  |  | 2026-09-12 | 2026-09-12 | 2026-09-14 | 2026-09-14 | 2026-09-16 | 38 | B | Shakel | Fr,Bk |  | black-2008 pcs frt back 1 clr rub 1 clr puff print,,beluga-2008 pccs frt back 1 clr rub 1 clr puff print,,silver-1508 pcs frt back 1 clr rub 1 clr puff print |  |  | NFL1 |  |  | Cut Ok | 4971 | 4922 | -49 | 5638 | 138 | [11 empty] | 38 | Aug'1 |  |  | 25.08.26
GBX-New Look | 48543 1st | 9148519 | 7070 | 1683 | 2026-08-01 | 2026-08-01 | Skirt w three layer frill | Skirt |  |  | 2026-08-04 | 2026-08-10 | 2026-08-11 | 2026-08-21 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-26 | 2026-08-28 | 2026-09-02 | [6 empty] | 2026-09-01 | 2026-09-10 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-12 | 2026-09-12 | 2026-09-12 | 42 | N/3 | Sifat | [5 empty] | NCL |  |  | Ready Test Cut | 1683 | 1683 | 0 | 0 | -7070 | [11 empty] | 37 | Aug'1
UTG-AF | 45092 10th | BAD1058mamaBR | 2000 | 520 | 2026-08-01 | 2026-08-01 | Long legging | Legging |  |  | 2026-08-04 | 2026-08-10 | 2026-08-14 | 2026-08-25 |  |  | 2026-08-28 | 2026-08-29 |  | 2026-09-01 | 2026-09-02 | [6 empty] | 2026-09-03 | 2026-09-05 |  |  | 2026-09-07 | 2026-09-09 | 2026-09-11 | 2026-09-12 | 2026-09-14 | 42 | N/1 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 520 | 520 | 0 | 0 | -2000 | [11 empty] | 38 | Sep'1
UTG-(Even & Odd) | 41705 5th | BAD1138H | 1000 | 490 | 2026-08-06 | 2026-08-10 | Lds Pant W Zipper | Pant |  |  | 2026-09-07: 2026-08-27; 2026-09-08: 2026-08-28 |  | 2026-08-31 | 2026-08-31 | [6 empty] | 2026-09-01 | 2026-09-03 |  |  | 2026-09-04 | 2026-09-04 | 2026-09-07 | 2026-09-12 | 2026-09-15 | 37 | N/3 | Rony |  |  |  |  | Imp fabric | NCL |  |  | Need Test Cut | 0 | 0 | 0 | 0 | -1000 | [11 empty] | 38 | Aug'1
UTG-(Even & Odd) | 43624 5th | BAD2888E | 2000 | 396 | 2026-08-06 | 2026-08-10 | Lds Bodysuit | Bodycon |  |  | 2026-08-12 | 2026-08-17 | 2026-08-18 | 2026-08-29 |  |  | 2026-08-31 | 2026-09-01 |  | 2026-09-04 | 2026-09-05 | [6 empty] | 2026-09-07 | 2026-09-10 |  |  | 2026-09-11 | 2026-09-14 | 2026-09-16 | 2026-09-19 | 2026-09-22 | 44 | N/3 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 396 | 198 | -198 | 0 | -2000 | [11 empty] | 39 | Sep'1
BS-NMT | 43316 29th | 13234729 | 2040 | 347 | 2026-08-06 | 2026-08-10 | LS o nk TS | TS |  |  | 2026-08-17 | 2026-08-21 | 2026-09-01 | 2026-09-09 |  |  | 2026-09-18 | 2026-09-08 |  | 2026-09-12 | 2026-09-14 | 2026-09-16 | 2026-09-17 |  |  |  |  | 2026-09-19 | 2026-09-21 |  |  | 2026-09-23 | 2026-09-25 | 2026-09-28 | 2026-10-12 | 2026-10-14 | 67 | ZA2 | Jafar | Nk |  | 1 combo label print |  |  | NFL3 |  |  | Cut Ok | 346 | 293 | -53 | 2091 | 51 | [11 empty] | 42 | Sep'2 |  |  | 21.08.26
BS-NMT | 43323 35th | 13180124 | 3600 | 404 | 2026-08-06 | 2026-08-10 | GIRLS SOLID LEGGINGS | Legging |  |  | 2026-08-17 | 2026-08-21 | 2026-08-28 | 2026-09-10 |  |  | 2026-09-10 | 2026-09-10 |  | 2026-09-14 | 2026-09-15 | 2026-09-17 | 2026-09-18 |  |  |  |  | 2026-09-21 | 2026-09-23 |  |  | 2026-09-24 | 2026-09-26 | 2026-09-29 | 2026-10-12 | 2026-10-14 | 67 | W2 | Jafar | WAIST |  | 3 combo label print |  |  | NFL3 |  |  | Cut Run | 404 | 385 | -19 | 3560 | -40 | [11 empty] | 42 | Sep'2 |  |  | 21.08.26
BS-NMT | 46491 7th | 13225095 | 4080 | 519 | 2026-08-06 | 2026-08-10 | YD LS o nk TS | TS | 2026-08-17 | 2026-08-25 | 2026-08-26 | 2026-09-05 | 2026-09-08 | 2026-09-16 |  |  | 2026-09-17 | 2026-09-17 |  | 2026-09-23 | 2026-09-26 | 2026-09-26 | 2026-09-29 |  |  |  |  | 2026-10-01 | 2026-10-05 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-10 | 2026-10-12 | 2026-10-14 | 67 | Z | Jafar | Chest,Nk |  | indigo-2560 pcs,,green-1520 pcs both combo 1 clr puff print | YD |  | NFL3 |  |  | Need Cut | 517 | 517 | 0 | 0 | -4080 | [11 empty] | 42 | Sep'3 |  |  | 24.08.26
BS-ONL | 44115 15th | 15315687 | 2016 | 935 | 2026-07-30 | 2026-07-31 | Ls Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-08-10 | 2026-08-15 | 2026-08-27 | 2026-09-07 |  |  | 2026-09-15 | 2026-09-07 |  | 2026-09-12 | 2026-09-14 |  |  |  |  | 2026-09-16 | 2026-09-30 | 2026-10-05 | 2026-10-07 |  |  | 2026-10-09 | 2026-10-12 | 2026-10-15 | 2026-10-26 | 2026-10-28 | 88 | A | Imran |  | Slv | c.dan-2016 pcs both slve CUTOUT EMB |  |  | NFL1 |  |  | Cut Ok | 935 | 935 | 0 | 2080 | 64 | [11 empty] | 44 | Sep'2 |  |  | 07.08.26
BS-ONL | 41787 33th | 15288473 | 31578 | 4877 | 2026-08-15 | 2026-08-06 | LDS SS TS | TS |  |  | 2026-08-10 | 2026-08-20 | 2026-08-18 | 2026-09-02 |  |  | 2026-09-10 | 2026-08-11 | 2026-08-13 | 2026-08-14 | 2026-09-05 |  |  |  |  | 2026-08-20 | 2026-09-16 | 2026-09-16 | 2026-09-26 |  |  | 2026-09-28 | 2026-09-30 | 2026-10-01 | 2026-10-05 | 2026-10-07 | 51 | V | Imran |  | Front,Slv | anise daisy-11601 pcs,,white cherries-960 pcs,white strawberry-270 pcss,,white bees-120 pcs,,white shell ice-10020 pcs,,ice water shell-8607 pcs all combo front both slve 3 clr flat all over emb |  | stock fab from 41787 27th | NFL3 |  |  | Cut Run | 4878 | 4851 | -27 | 24460 | -7118 | [11 empty] | 41 | Aug'1 |  |  | 12.08.26
BS-ONL | 46748 13th | 15244714 | 11232 | 1735 | 2026-08-05 | 2026-08-06 | SS o nk TS | TS |  |  | 2026-08-15 | 2026-08-24 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-10 | 2026-09-10 |  | 2026-09-14 | 2026-09-17 | 2026-09-17 | 2026-09-21 |  |  |  |  | 2026-09-22 | 2026-09-26 |  |  | 2026-09-29 | 2026-10-01 | 2026-10-05 | 2026-10-12 | 2026-10-14 | 68 | D1 | Imran | Chest |  | pink-5616 pcs,,anise-5616 pcs all combo 1 clr gltr print |  |  | NFL1 |  |  | Cut Ok | 1734 | 1734 | 0 | 11426 | 194 | [11 empty] | 42 | Sep'2 |  |  | 13.08.26
BS-ONL | 48158 2nd | 15368187 | 8160 | 1250 | 2026-08-03 | 2026-08-06 | SS v nk TS | TS |  |  | 2026-08-15 | 2026-08-22 | 2026-08-25 | 2026-09-10 |  |  | 2026-09-10 | 2026-09-10 |  | 2026-09-14 | 2026-09-17 | 2026-09-17 | 2026-09-21 |  |  | 2026-09-21 | 2026-09-24 | 2026-09-25 | 2026-09-30 |  |  | 2026-10-02 | 2026-10-05 | 2026-10-07 | 2026-10-12 | 2026-10-14 | 70 | U | Imran | Chest | Chest | black-4080 pcs,,c.dancer-4080 pcs all combo 3 clr rub print 1 clr Lurex emb |  |  | NFL3 |  |  | Cut Run | 1250 | 625 | -625 | 4050 | -4110 | [11 empty] | 42 | Sep'2 |  |  | 03.09.26
OVS SPA | 48453 | 271TSH048-226 | 6858 | 1022 | 2026-07-27 | 2026-07-31 | SS TS w nk triangle rib and slve contrast piping | TS |  |  | 2026-09-01 | 2026-09-11 | 2026-09-12 | 2026-09-25 |  |  | 2026-10-02 | 2026-09-25 | 2026-10-02 | 2026-10-03 | 2026-10-06 | 2026-10-06 | 2026-10-12 |  |  | 2026-10-10 | 2026-10-14 | 2026-10-12 | 2026-10-17 |  |  | 2026-10-17 | 2026-10-19 | 2026-10-21 | 2026-10-26 | 2026-10-26 | 91 | G1 | Sirajul | Fr,Bk,Nk & Slv | Chest | blanc-6858 pcs frt 9 clr pig and 1 clr flat emb back 5 clr pig print both slve 1 clr pig print and nk HP sticker |  |  | NFL1 |  |  | File Due | 1002 | 0 | -1002 | 0 | -6858 | [11 empty] | 44 | Oct'1
OVS SPA | 48455 | 271TSH051-226 | 6116 | 1256 | 2026-07-25 | 2026-07-31 | LS double slve contrast cut&sew TS w front back yoke | TS |  |  | 2026-09-01 | 2026-09-11 | 2026-09-12 | 2026-09-25 |  |  | 2026-10-06 | 2026-09-30 | 2026-10-05 | 2026-10-06 | 2026-10-08 | 2026-10-09 | 2026-10-14 |  |  |  |  | 2026-10-14 | 2026-10-19 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-24 | 2026-10-26 | 2026-10-26 | 93 | G1 | Sirajul | Fr & Bk & Nk |  | blanc-6116 pcs frt one part 2 clr pig 2nd part 8 clr pig back one part 3 clr pig 2nd part 8 clr pig print and nk HP sticker |  |  | NFL1 |  |  | File Due | 1235 | 0 | -1235 | 0 | -6116 | [11 empty] | 44 | Oct'1
OVS SPA | 48454 | 271TSH049-226 | 6554 | 895 | 2026-07-25 | 2026-07-31 | SS o nk TS w nk rib | TS |  |  | 2026-08-25 | 2026-09-08 | 2026-09-10 | 2026-09-23 |  |  | 2026-10-05 | 2026-09-23 | 2026-09-30 | 2026-10-01 | 2026-10-03 | 2026-10-03 | 2026-10-09 |  |  | 2026-10-09 | 2026-10-14 | 2026-10-14 | 2026-10-17 |  |  | 2026-10-19 | 2026-10-21 | 2026-10-23 | 2026-10-26 | 2026-10-26 | 93 | F | Sirajul | Fr & Bk & Nk | Fr & Bk | drill green-6554 pcs frt 8 clr rub 1 clr flat emb and back photo print w 8 clr rub 1 clr flat emb and nk label HP sticker |  |  | NFL1 |  |  | File Due | 896 | 0 | -896 | 0 | -6554 | [11 empty] | 44 | Oct'1
OVS SPA | 48451 | 271SHR010-226 | 7576 | 1435 | 2026-07-25 | 2026-07-31 | Waist belt shorts w side pkt and side contrast cut&sew and piping and drawstring | Shorts |  |  | 2026-08-25 | 2026-09-08 | 2026-09-10 | 2026-09-24 |  |  | 2026-09-28 | 2026-09-23 | 2026-09-30 | 2026-10-01 | 2026-10-03 | 2026-10-02 | 2026-10-07 |  |  |  |  | 2026-10-07 | 2026-10-15 |  |  | 2026-10-16 | 2026-10-19 | 2026-10-21 | 2026-10-26 | 2026-10-26 | 93 | H | Sirajul | leg |  | dill green-7576 pcs one leg 8 clr rub 2nd leg 2 clr HD print |  |  | NFL1 |  |  | File Due | 1435 | 0 | -1435 | 0 | -7576 | [11 empty] | 44 | Oct'1
OVS SPA | 48448 | 271SWT017-6155 | 9261 | 3254 | 2026-07-27 | 2026-07-31 | LS full zipper reglan slve Swt hoody slve shlder contrast piping | Hoody |  |  | 2026-08-18 | 2026-09-05 | 2026-09-01 | 2026-09-21 |  |  | 2026-09-25 | 2026-09-18 | 2026-09-25 | 2026-09-26 | 2026-09-30 | 2026-10-01 | 2026-10-06 |  |  |  |  | 2026-10-05 | 2026-10-17 |  |  | 2026-10-19 | 2026-10-21 | 2026-10-23 | 2026-10-26 | 2026-10-26 | 91 | R | Sirajul | Chest |  | LGM-2422 pcs,,bonbon-6839 pcs both combo two part 2 clr puff print |  |  | NFL2 |  |  | File Due | 3265 | 2313 | -952 | 0 | -9261 | [11 empty] | 44 | Sep'3
OVS SPA | 48449 | 271LEG021-6155 | 10556 | 2464 | 2026-07-20 | 2026-07-31 | Elasted legging w side contrast piping | Legging |  |  | 2026-08-24 | 2026-09-12 | 2026-09-14 | 2026-09-28 |  |  | 2026-09-28 | 2026-09-25 | 2026-10-02 | 2026-10-03 | 2026-10-09 | [6 empty] | 2026-10-08 | 2026-10-17 |  |  | 2026-10-17 | 2026-10-19 | 2026-10-21 | 2026-10-26 | 2026-10-26 | 98 | E | Sirajul | [5 empty] | NFL1 |  |  | File Due | 2464 | 0 | -2464 | 0 | -10556 | [11 empty] | 44 | Oct'1
OVS SPA | 48463 | 271PJLRNUNIT-906 | 22912 | 5542 | 2026-07-25 | 2026-07-31 | LS o nk TS and waist belt pant | Top & BTM |  |  | 2026-08-14 | 2026-08-31 | 2026-08-28 | 2026-09-15 |  |  | 2026-09-18 | 2026-09-09 | 2026-09-15 | 2026-09-16 | 2026-09-23 | 2026-09-22 | 2026-09-28 |  |  |  |  | 2026-09-29 | 2026-10-10 |  |  | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-15 | 82 | O1+P | Sirajul | Heat Press/Heat Seal |  | TOP 2 combo nk HP label |  |  | NFL2 |  |  | File Due | 5542 | 3208 | -2334 | 0 | -22912 | [11 empty] | 42 | Sep'2
OVS SPA | 48464 | 271PJLRNSTRYD-906 | 31078 | 7925 | 2026-07-25 | 2026-07-31 | YD LS o nk TS and solid waist belt pant | Top & BTM | 2026-08-08 | 2026-08-22 | 2026-08-18 | 2026-09-02 | 2026-08-28 | 2026-09-14 |  |  | 2026-09-18 | 2026-09-09 | 2026-09-16 | 2026-09-17 | 2026-09-25 | 2026-09-22 | 2026-09-28 |  |  |  |  | 2026-09-26 | 2026-10-09 |  |  | 2026-10-10 | 2026-10-12 | 2026-10-14 | 2026-10-15 | 2026-10-15 | 82 | N/2 | Sirajul | Heat Press/Heat Seal |  | TOP 3 combo nk HP label | YD |  | NCL |  |  | File Due | 7925 | 872 | -7053 | 0 | -31078 | [11 empty] | 42 | Sep'2
OVS SPA | 48456 | 271TRO051-226 | 5071 | 1481 | 2026-07-27 | 2026-08-01 | Waist belt trouser w side pkt leg cut&sew and drawstring | Trouser |  |  | 2026-08-20 | 2026-09-03 | 2026-09-05 | 2026-09-22 |  |  | 2026-10-01 | 2026-09-18 | 2026-09-26 | 2026-09-28 | 2026-09-30 | 2026-10-01 | 2026-10-05 |  |  | 2026-10-05 | 2026-10-10 | 2026-10-09 | 2026-10-16 |  |  | 2026-10-17 | 2026-10-19 | 2026-10-21 | 2026-10-26 | 2026-10-26 | 91 | N/2 | Sirajul | leg | Leg | dill green-5071 pcs front leg one part 5 clr rub print another part 8 clr rub print back leg 1 clr pig and 3 clr flat emb |  |  | NCL |  |  | File Due | 1468 | 0 | -1468 | 0 | -5071 | [11 empty] | 44 | Sep'3
OVS SPA | 47850 | 271TSH177-6156 | 5831 | 655 | 2026-07-20 | 2026-07-30 | YD SS o nk TS | TS | 2026-08-20 | 2026-08-31 | 2026-09-01 | 2026-09-10 | 2026-09-10 | 2026-09-19 |  |  | 2026-09-17 | 2026-09-16 | 2026-09-21 | 2026-09-22 | 2026-09-24 | [6 empty] | 2026-09-25 | 2026-09-30 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-05 | 2026-10-05 | 77 | N/1 | Khairul |  |  |  | YD |  | NCL |  |  | File Due | 655 | 0 | -655 | 0 | -5831 | [11 empty] | 41 | Sep'3
OVS SPA | 48520 | 271JOG139-6156 | 22008 | 5400 | 2026-07-29 | 2026-08-08 | LS High nk Full zipper Swt shirt w kangaroo pkt and swt pant w drawstring | Top & BTM | 2026-08-15 | 2026-08-28 | 2026-08-24 | 2026-09-05 | 2026-09-01 | 2026-09-17 |  |  | 2026-09-21 | 2026-09-08 | 2026-09-14 | 2026-09-15 | 2026-09-23 | 2026-09-21 | 2026-09-30 |  |  |  |  | 2026-10-01 | 2026-10-15 |  |  | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-20 | 2026-10-20 | 83 | N/3 | Khairul | Chest & Leg |  | white top-6909 pcs 1 clr rub print ,,dk blue btm-6909 pcs no print ,,blue top-4095 pcs 1 clr rub print ,,blue btm-4095 pcs 2 clr rub print | YD |  | NCL |  |  | File Due | 5400 | 0 | -5400 | 0 | -22008 | [11 empty] | 43 | Sep'2
UTG-AF | 40671 14th | BAD1298AM | 2400 | 618 | 2026-08-01 | 2026-08-07 | LDS LS TS | TS | 2026-08-20 | 2026-08-31 | 2026-09-01 | 2026-09-10 | 2026-09-11 | 2026-09-22 |  |  | 2026-09-26 | 2026-09-28 |  | 2026-10-01 | 2026-10-03 | [6 empty] | 2026-10-05 | 2026-10-08 |  |  | 2026-10-09 | 2026-10-12 | 2026-10-14 | 2026-10-24 | 2026-10-26 | 84 | N1 | Rana | [5 empty] | NFL2 |  |  | Cut Run | 618 | 292 | -326 | 1242 | -1158 | [11 empty] | 44 | Oct'1 |  |  | 18.08.26
UTG-(Even & Odd) | 48533 | BAD3265 | 600 | 320 | 2026-07-31 | 2026-08-08 | LS Dress w side slit | Dress |  |  | 2026-08-13 | 2026-08-19 | 2026-08-20 | 2026-08-31 |  |  | 2026-09-04 | 2026-09-05 | 2026-09-10 | 2026-09-11 | 2026-09-12 | [6 empty] | 2026-09-14 | 2026-09-16 |  |  | 2026-09-17 | 2026-09-19 | 2026-09-21 | 2026-10-03 | 2026-10-05 | 64 | N/3 | Rony | [5 empty] | NCL |  |  | Need Test Cut | 320 | 0 | -320 | 0 | -600 | [11 empty] | 41 | Sep'2
UTG-(Even & Odd) | 48535 | BAD3268 | 3000 | 634 | 2026-07-31 | 2026-08-08 | LS boat nk TS | TS |  |  | 2026-08-12 | 2026-08-17 | 2026-08-18 | 2026-08-31 |  |  | 2026-09-05 | 2026-09-07 | 2026-09-10 | 2026-09-11 | 2026-09-12 | [6 empty] | 2026-09-15 | 2026-09-17 |  |  | 2026-09-18 | 2026-09-21 | 2026-09-23 | 2026-10-03 | 2026-10-05 | 64 | N/1 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 634 | 317 | -317 | 0 | -3000 | [11 empty] | 41 | Sep'2
UTG-(Even & Odd) | 48537 | BAD3266 | 800 | 169 | 2026-07-31 | 2026-08-08 | LS double layer contrast slve TS | TS |  |  | 2026-08-12 | 2026-08-17 | 2026-08-18 | 2026-08-31 |  |  | 2026-09-05 | 2026-09-07 | 2026-09-10 | 2026-09-11 | 2026-09-12 | [6 empty] | 2026-09-15 | 2026-09-17 |  |  | 2026-09-18 | 2026-09-21 | 2026-09-23 | 2026-10-03 | 2026-10-05 | 64 | N/1 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 169 | 59 | -110 | 0 | -800 | [11 empty] | 41 | Sep'2
UTG-(Even & Odd) | 48538 | BAD3263 | 2000 | 500 | 2026-07-31 | 2026-08-08 | LS o nk TS | TS |  |  | 2026-08-12 | 2026-08-17 | 2026-08-18 | 2026-08-31 |  |  | 2026-09-05 | 2026-09-07 | 2026-09-10 | 2026-09-11 | 2026-09-12 | [6 empty] | 2026-09-15 | 2026-09-17 |  |  | 2026-09-18 | 2026-09-21 | 2026-09-23 | 2026-10-03 | 2026-10-05 | 64 | N/1 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 500 | 250 | -250 | 0 | -2000 | [11 empty] | 41 | Sep'2
UTG-(Even & Odd) | 48534 | BAD3264 | 2000 | 563 | 2026-07-31 | 2026-08-08 | LS o nk TS | TS | 2026-08-12 | 2026-08-20 | 2026-08-20 | 2026-08-27 | 2026-08-27 | 2026-09-05 |  |  | 2026-09-05 | 2026-09-07 | 2026-09-12 | 2026-09-14 | 2026-09-15 | [6 empty] | 2026-09-16 | 2026-09-18 |  |  | 2026-09-19 | 2026-09-21 | 2026-09-23 | 2026-10-03 | 2026-10-05 | 64 | N/1 | Rony |  |  |  | YD |  | NCL |  |  | Need Test Cut | 563 | 0 | -563 | 0 | -2000 | [11 empty] | 41 | Sep'2
UTG-(Even & Odd) | 48536 | BAD3267 | 1200 | 296 | 2026-07-31 | 2026-08-08 | LS Polo Shirt w YD collar placket and | Polo | 2026-08-12 | 2026-08-20 | 2026-08-20 | 2026-08-27 | 2026-08-27 | 2026-09-05 |  |  | 2026-09-05 | 2026-09-07 | 2026-09-12 | 2026-09-14 | 2026-09-15 | [6 empty] | 2026-09-16 | 2026-09-18 |  |  | 2026-09-19 | 2026-09-21 | 2026-09-23 | 2026-10-03 | 2026-10-05 | 64 | N/3 | Rony |  |  |  | YD |  | NCL |  |  | Need Test Cut | 296 | 0 | -296 | 0 | -1200 | [11 empty] | 41 | Sep'2
BS-NMT | 48510 | 13269388 | 500 | 385 | 2026-07-22 | 2026-07-30 | LS Swt Hoody w cuff btm rib and kangaro pkt | Hoody |  |  | 2026-08-25 | 2026-09-01 | 2026-09-05 | 2026-09-19 |  |  | 2026-09-23 | 2026-09-23 | 2026-09-29 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-08 |  |  |  |  | 2026-10-12 | 2026-10-13 |  |  | 2026-10-15 | 2026-10-17 | 2026-10-22 | 2026-11-09 | 2026-11-11 | 110 | S | Sanaul | Fr,Bk,Nk & Slv |  | white-500 pcs frt 11 clr rub back 6 clr rub and one slve 6 clr rub print |  |  | NFL3 |  |  | File Due | 385 | 0 | -385 | 0 | -500 | [11 empty] | 46 | Oct'1
BS-NMT | 48509 | 13269395 | 500 | 403 | 2026-07-22 | 2026-07-30 | LS Swt Hoody w cuff btm rib and kangaro pkt | Hoody |  |  | 2026-08-25 | 2026-08-30 | 2026-09-05 | 2026-09-19 |  |  | 2026-09-22 | 2026-09-22 | 2026-09-28 | 2026-10-01 | 2026-10-02 | 2026-10-05 | 2026-10-09 |  |  |  |  | 2026-10-12 | 2026-10-13 |  |  | 2026-10-15 | 2026-10-17 | 2026-10-22 | 2026-11-09 | 2026-11-11 | 110 | S | Sanaul | Fr & Bk & Nk |  | black-500 pcs frt 7 clr rub print and back 8 clr rub print and back side two self fabric ear 1 clr rub print |  |  | NFL3 |  |  | File Due | 403 | 0 | -403 | 0 | -500 | [11 empty] | 46 | Oct'1
BS-NMT | 48495 | 13269980 | 500 | 546 | 2026-07-22 | 2026-07-30 | LS Swt Hoody w cuff btm rib and kangaro pkt | Hoody |  |  | 2026-08-20 | 2026-08-26 | 2026-09-05 | 2026-09-19 |  |  | 2026-09-22 | 2026-09-22 | 2026-09-28 | 2026-10-01 | 2026-10-01 | 2026-10-03 | 2026-10-08 |  |  |  |  | 2026-10-10 | 2026-10-12 |  |  | 2026-10-14 | 2026-10-16 | 2026-10-22 | 2026-11-09 | 2026-11-11 | 110 | S | Sanaul | Fr & Bk & Nk |  | black-500 pcs frt back 3 clr rub print |  |  | NFL3 |  |  | File Due | 546 | 0 | -546 | 0 | -500 | [11 empty] | 46 | Oct'1
BS-ONS | 26582 9th | 22027015 | 4672 | 1072 | 2026-08-06 | 2026-08-10 | SS o nk TS | TS |  |  | 2026-08-22 | 2026-08-27 | 2026-09-05 | 2026-09-17 |  |  | 2026-09-20 | 2026-09-18 | 2026-09-23 | 2026-09-25 | 2026-09-26 | 2026-10-01 | 2026-10-05 |  |  |  |  | 2026-10-08 | 2026-10-12 |  |  | 2026-10-14 | 2026-10-16 | 2026-10-20 | 2026-11-09 | 2026-11-11 | 95 | F | Shovon | Fr,Bk |  | c.dan-1118 pcs,,black-2756 pcs ,, c.dan mojave-798 pcs all combo frt 1 clr rub/pig back 7 clr rub/pig |  |  | NFL1 |  |  | PPM Due | 1072 | 626 | -446 | 0 | -4672 | [11 empty] | 46 | Sep'3 |  |  | 11.09.26
OVS SPA | 48446 | 271SHR009-6153 | 5250 | 1199 | 2026-07-20 | 2026-07-31 | Waist belt shorts w side bon pkt and drawstring | Shorts |  |  | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-09-30 |  |  | 2026-10-14 | 2026-10-07 | 2026-10-13 | 2026-10-14 | 2026-10-17 | 2026-10-17 | 2026-10-23 |  |  |  |  | 2026-10-22 | 2026-10-31 |  |  | 2026-11-02 | 2026-11-04 | 2026-11-06 | 2026-11-09 | 2026-11-09 | 112 | N/3 | Sirajul | Thigh |  | lollipop-5250 pcs 1 clr rub print |  |  | NCL |  |  | File Due | 1199 | 0 | -1199 | 0 | -5250 | [11 empty] | 46 | Oct'2
OVS SPA | 48467 | 271PJSRNUNST-906 | 32250 | 5509 | 2026-07-25 | 2026-07-31 | YD SS o nk TS and solid Shorts w elastic | Top & BTM | 2026-08-20 | 2026-09-04 | 2026-09-01 | 2026-09-17 | 2026-09-14 | 2026-09-30 |  |  | 2026-10-10 | 2026-10-02 | 2026-10-07 | 2026-10-08 | 2026-10-17 | 2026-10-15 | 2026-10-24 |  |  |  |  | 2026-10-21 | 2026-11-03 |  |  | 2026-11-04 | 2026-11-06 | 2026-11-09 | 2026-11-12 | 2026-11-12 | 110 | H+E | Sirajul | Heat Press/Heat Seal |  | TOP 3 combo nk HP label | YD |  | NFL1 |  |  | File Due | 5509 | 0 | -5509 | 0 | -32250 | [11 empty] | 46 | Oct'1
OVS SPA | 48466 | 271PJSVNUNIT-906 | 18616 | 2827 | 2026-07-25 | 2026-07-31 | SS v nk TS and solid Shorts w elastic | Top & BTM |  |  | 2026-09-01 | 2026-09-17 | 2026-09-21 | 2026-10-05 |  |  | 2026-10-17 | 2026-10-08 | 2026-10-14 | 2026-10-15 | 2026-10-23 | 2026-10-21 | 2026-10-28 |  |  |  |  | 2026-10-26 | 2026-11-06 |  |  | 2026-11-07 | 2026-11-09 | 2026-11-11 | 2026-11-12 | 2026-11-12 | 110 | N/2 | Sirajul | Heat Press/Heat Seal |  | TOP 2 combo nk HP label |  |  | NCL |  |  | File Due | 2826 | 688 | -2138 | 0 | -18616 | [11 empty] | 46 | Oct'2
OVS SPA | 48465 | 271PJRNUNIT-906 | 21820 | 3296 | 2026-07-25 | 2026-07-31 | SS o nk TS and solid Shorts w elastic | Top & BTM |  |  | 2026-09-01 | 2026-09-17 | 2026-09-15 | 2026-10-05 |  |  | 2026-10-15 | 2026-10-05 | 2026-10-10 | 2026-10-12 | 2026-10-20 | 2026-10-19 | 2026-10-26 |  |  |  |  | 2026-10-24 | 2026-11-05 |  |  | 2026-11-06 | 2026-11-09 | 2026-11-11 | 2026-11-12 | 2026-11-12 | 110 | N/2 | Sirajul | Heat Press/Heat Seal |  | TOP 2 combo nk HP label |  |  | NCL |  |  | File Due | 3296 | 3252 | -44 | 0 | -21820 | [11 empty] | 46 | Oct'2
OVS SPA | 48452 | 271TSH015-226 | 5411 | 1373 | 2026-07-25 | 2026-07-31 | SS frt cut & sew Swt hoody w contrast hood | Hoody |  |  | 2026-09-21 | 2026-09-30 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-22 | 2026-10-09 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 2026-10-27 |  |  | 2026-10-27 | 2026-10-31 | 2026-11-02 | 2026-11-06 |  |  | 2026-11-07 | 2026-11-09 | 2026-11-11 | 2026-11-16 | 2026-11-16 | 114 | N/2 | Sirajul | Chest,HP | Chest | coconut milk-5411 pcs fr 2 clr flat w self fabric applique emb no print back 3 clr rub print |  |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -5411 | [11 empty] | 47 | Oct'2
OVS SPA | 48450 | 271SWT008-226 | 2351 | 985 | 2026-07-25 | 2026-07-31 | LS Full zipper Swt hoody w front pkt and cuff btm rib | Hoody |  |  | 2026-09-15 | 2026-09-26 | 2026-09-28 | 2026-10-10 |  |  | 2026-10-23 | 2026-10-17 | 2026-10-23 | 2026-10-24 | 2026-10-26 | 2026-10-28 | 2026-11-03 |  |  |  |  | 2026-11-03 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-11 | 2026-11-13 | 2026-11-16 | 2026-11-16 | 114 | N/2 | Sirajul | Bk |  | blue-2351 pcs 6 clr rub print |  |  | NCL |  |  | File Due | 1682 | 0 | -1682 | 0 | -2351 | [11 empty] | 47 | Oct'3
OVS SPA | 48447 | 271SHR010-6153 | 7788 | 2439 | 2026-07-25 | 2026-07-31 | Waist belt shorts w side bon pkt and drawstring | Shorts |  |  | 2026-09-01 | 2026-09-15 | 2026-09-15 | 2026-10-06 |  |  | 2026-10-17 | 2026-10-15 | 2026-10-20 | 2026-10-21 | 2026-10-23 | [6 empty] | 2026-10-26 | 2026-11-06 |  |  | 2026-11-06 | 2026-11-07 | 2026-11-07 | 2026-11-09 | 2026-11-09 | 107 | H | Sirajul | [5 empty] | NFL1 |  |  | File Due | 2901 | 1645 | -1256 | 0 | -7788 | [11 empty] | 46 | Oct'3
OVS SPA | 48550 | 271NDG340SB-903 | 6176 | 2059 | 2026-07-30 | 2026-08-08 | SS Dress w full placket btn and collar | Dress |  |  | 2026-09-01 | 2026-09-18 | 2026-09-21 | 2026-10-09 |  |  | 2026-10-20 | 2026-10-14 | 2026-10-20 | 2026-10-21 | 2026-10-24 |  |  |  |  | 2026-10-26 | 2026-10-31 | 2026-11-02 | 2026-11-10 |  |  | 2026-11-11 | 2026-11-12 | 2026-11-14 | 2026-11-16 | 2026-11-16 | 109 | B | Salam |  | Chest | rose-3094 pcs,,blue-3082 pcs both combo 1 clr flat emb |  |  | NFL1 |  |  | File Due | 2058 | 0 | -2058 | 0 | -6176 | [11 empty] | 47 | Oct'3
OVS SPA | 47849 | 271TSH253-6156 | 15453 | 1765 | 2026-07-27 | 2026-08-08 | SS V nk TS | TS |  |  | 2026-09-01 | 2026-09-14 | 2026-09-15 | 2026-09-30 |  |  | 2026-10-14 | 2026-10-06 | 2026-10-12 | 2026-10-13 | 2026-10-19 | 2026-10-17 | 2026-10-26 |  |  |  |  | 2026-10-24 | 2026-11-02 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-07 | 2026-11-09 | 2026-11-09 | 105 | G2 | Khairul | slv,Chest |  | butter-7641 pcs,,navy-7812 pcs both combo frt both slve 1 clr rub print |  |  | NFL1 |  |  | File Due | 1765 | 0 | -1765 | 0 | -15453 | [11 empty] | 46 | Oct'2
OVS SPA | 48442 | 271NDG013MZ2-6111 | 4828 | 1320 | 2026-07-27 | 2026-08-01 | AOP SS dress w full placket btn collar w front pkt | Dress |  |  | 2026-08-18 | 2026-08-31 | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-09-23 | 2026-09-28 | 2026-09-23 | 2026-09-29 | 2026-09-30 | 2026-10-02 |  |  |  |  | 2026-10-02 | 2026-10-07 | 2026-10-07 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-16 | 2026-10-17 | 2026-11-20 | 2026-11-20 | 116 | N/2 | Basir |  | Pkt | pastel-3016 pcs,,blue-1812 pcs both combo 1 clr flat emb at pkt | AOP |  | NCL |  |  | File Due | 1319 | 0 | -1319 | 0 | -4828 | [11 empty] | 47 | Sep'3
OVS SPA | 48443 | 271PJA030MZ3-6111 | 12456 | 3083 | 2026-07-27 | 2026-08-01 | Solid LS key hole nk TS and AOP elasted pant w tussel string | Top & BTM |  |  | 2026-08-15 | 2026-08-31 | 2026-09-01 | 2026-09-14 | 2026-09-14 | 2026-09-24 | 2026-09-24 | 2026-09-25 | 2026-10-01 | 2026-10-02 | 2026-10-07 | [6 empty] | 2026-10-06 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-16 | 2026-10-17 | 2026-11-20 | 2026-11-20 | 116 | N/3 | Basir |  |  |  | AOP |  | NCL |  |  | File Due | 3082 | 0 | -3082 | 0 | -12456 | [11 empty] | 47 | Oct'1
UTG-AF | 42566 9th | BAD2784I | 3400 | 900 | 2026-07-29 | 2026-08-01 | SS POLO SHIRT W LACE | POLO |  |  | 2026-09-01 | 2026-09-14 | 2026-09-15 | 2026-10-03 |  |  | 2026-10-09 | 2026-10-10 |  | 2026-10-14 | 2026-10-15 | [6 empty] | 2026-10-16 | 2026-10-19 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-24 | 2026-11-14 | 2026-11-16 | 108 | N/2 | Rana | [5 empty] | NCL |  |  | Po Sheet Due | 900 | 0 | -900 | 0 | -3400 | [11 empty] | 47 | Oct'2
UTG-AF | 45104 3rd | BAD2966B | 500 | 122 | 2026-07-29 | 2026-08-01 | LS polo w tipping collar placket | Polo |  |  | 2026-09-01 | 2026-09-19 | 2026-09-21 | 2026-09-29 |  |  | 2026-10-08 | 2026-10-10 |  | 2026-10-14 | 2026-10-15 | [6 empty] | 2026-10-16 | 2026-10-19 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-24 | 2026-11-14 | 2026-11-16 | 108 | N/2 | Rana | [5 empty] | NCL |  |  | Po Sheet Due | 122 | 0 | -122 | 0 | -500 | [11 empty] | 47 | Oct'2
UTG-AF | 42349 3rd | BAD2758C | 900 | 430 | 2026-07-29 | 2026-08-01 | LS DRESS W FULL PLACKET AND BTN | Dress |  |  | 2026-10-01 | 2026-10-08 | 2026-10-10 | 2026-10-20 |  |  | 2026-11-04 | 2026-11-05 |  | 2026-11-07 | 2026-11-09 | [6 empty] | 2026-11-10 | 2026-11-13 |  |  | 2026-11-14 | 2026-11-16 | 2026-11-18 | 2026-11-21 | 2026-11-23 | 115 | N/3 | Rana | [5 empty] | NCL |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -900 | [11 empty] | 48 | Nov'1
UTG-AF | 43310 4th | BAD2862C | 700 | 265 | 2026-07-29 | 2026-08-01 | LDS PUNTI DRESS | DRESS |  |  | 2026-10-10 | 2026-10-20 | 2026-11-02 | 2026-11-07 |  |  | 2026-11-04 | 2026-11-05 |  | 2026-11-07 | 2026-11-09 | [6 empty] | 2026-11-10 | 2026-11-13 |  |  | 2026-11-14 | 2026-11-16 | 2026-11-18 | 2026-11-21 | 2026-11-23 | 115 | N/3 | Rana | [5 empty] | NCL |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -700 | [11 empty] | 48 | Nov'1
UTG-(Even & Odd) | 30777 8th | BAD2651G | 1400 | 620 | 2026-07-28 | 2026-08-01 | SS Square nk long dress w side slit | Dress |  |  | 2026-09-01 | 2026-09-08 | 2026-09-15 | 2026-09-25 |  |  | 2026-10-08 | 2026-10-09 |  | 2026-10-13 | 2026-10-14 | [6 empty] | 2026-10-15 | 2026-10-17 |  |  | 2026-10-19 | 2026-10-21 | 2026-10-23 | 2026-11-14 | 2026-11-16 | 109 | N/2 | Rony | [5 empty] | NCL |  |  | Need Test Cut | 620 | 0 | -620 | 0 | -1400 | [11 empty] | 47 | Oct'2
UTG-(Even & Odd) | 46615 9th | BAD1318AC/BAD2287F | 7000 | 2010 | 2026-07-28 | 2026-08-01 | AOP SKIRT W SIDE SLIT | Skirt |  |  | 2026-08-25 | 2026-09-08 | 2026-09-10 | 2026-09-22 | 2026-09-23 | 2026-10-03 | 2026-10-09 | 2026-10-10 |  | 2026-10-14 | 2026-10-15 | [6 empty] | 2026-10-16 | 2026-10-22 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-28 | 2026-11-14 | 2026-11-16 | 109 | G2 | Rony |  |  |  | AOP |  | NFL1 |  |  | Need Test Cut | 2010 | 0 | -2010 | 0 | -7000 | [11 empty] | 47 | Oct'2 |  |  | 05.09.26
UTG-(Even & Odd) | 24239 12th | BAD1109R | 1000 | 182 | 2026-07-28 | 2026-08-01 | LDS SS BODYSUIT | SUIT |  |  | 2026-09-01 | 2026-09-07 | 2026-09-15 | 2026-09-25 |  |  | 2026-10-09 | 2026-10-10 |  | 2026-10-14 | 2026-10-15 | [6 empty] | 2026-10-16 | 2026-10-19 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-24 | 2026-11-14 | 2026-11-16 | 109 | N/2 | Rony | [5 empty] | NCL |  |  | Po Sheet Due | 182 | 182 | 0 | 0 | -1000 | [11 empty] | 47 | Oct'2
UTG-(Even & Odd) | 22738 11th | BAD1131T | 800 | 198 | 2026-07-28 | 2026-08-01 | LDS LS BODYSUIT | SUIT |  |  | 2026-09-01 | 2026-09-08 | 2026-09-15 | 2026-09-26 |  |  | 2026-10-07 | 2026-10-08 |  | 2026-10-12 | 2026-10-13 | [6 empty] | 2026-10-14 | 2026-10-16 |  |  | 2026-10-17 | 2026-10-19 | 2026-10-21 | 2026-11-07 | 2026-11-09 | 102 | N/2 | Rony | [5 empty] | NCL |  |  | Po Sheet Due | 198 | 0 | -198 | 0 | -800 | [11 empty] | 46 | Oct'2
UTG-(Even & Odd) | 26835 12th | BAD2361N | 6000 | 540 | 2026-07-28 | 2026-08-01 | LDS 3 STYLE TANK TOP | TANK TOP |  |  | 2026-09-01 | 2026-09-09 | 2026-06-15 | 2026-09-26 |  |  | 2026-10-08 | 2026-10-10 |  | 2026-10-13 | 2026-10-15 | [6 empty] | 2026-10-16 | 2026-10-22 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-28 | 2026-11-14 | 2026-11-16 | 109 | G2 | Rony | [5 empty] | NFL1 |  |  | Po Sheet Due | 540 | 540 | 0 | 0 | -6000 | [11 empty] | 47 | Oct'2
UTG-(Even & Odd) | 29929 10th | BAD2594I | 4000 | 311 | 2026-07-28 | 2026-08-01 | LDS TANK TOP W LACE | TANK TOP |  |  | 2026-09-01 | 2026-09-10 | 2026-09-15 | 2026-09-26 |  |  | 2026-10-07 | 2026-10-08 |  | 2026-10-12 | 2026-10-13 | [6 empty] | 2026-10-14 | 2026-10-17 |  |  | 2026-10-19 | 2026-10-21 | 2026-10-23 | 2026-11-14 | 2026-11-16 | 109 | N/1 | Rony | [5 empty] | NCL |  |  | Po Sheet Due | 312 | 0 | -312 | 0 | -4000 | [11 empty] | 47 | Oct'2
UTG-(Even & Odd) | 42408 8th | BAD2764G | 1200 | 370 | 2026-07-28 | 2026-08-01 | Wrap mini Skirt | Skirt |  |  | 2026-10-09: 2026-10-05; 2026-10-10: 2026-10-06 |  | 2026-10-09 | 2026-10-10 | [6 empty] | 2026-10-12 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-17 | 2026-10-20 | 2026-11-14 | 2026-11-16 | 109 | G2 | Rony |  |  |  |  | Imp fab stock | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1200 | [11 empty] | 47 | Oct'1
UTG-(Even & Odd) | 41897 8th | BAD1286AF | 2000 | 215 | 2026-07-28 | 2026-08-01 | LDS MIDI SKIRT | Skirt |  |  | 2026-09-01 | 2026-09-09 | 2026-09-15 | 2026-09-25 |  |  | 2026-10-12 | 2026-10-13 |  | 2026-10-16 | 2026-10-17 | [6 empty] | 2026-10-19 | 2026-10-22 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-28 | 2026-11-14 | 2026-11-16 | 109 | G2 | Rony | [5 empty] | NFL1 |  |  | Po Sheet Due | 215 | 0 | -215 | 0 | -2000 | [11 empty] | 47 | Oct'2
UTG-(Even & Odd) | 45963 12th | BAD0962BS | 600 | 146 | 2026-07-28 | 2026-08-01 | LDS LS R NK TS | TS |  |  | 2026-09-01 | 2026-09-11 | 2026-09-14 | 2026-09-26 |  |  | 2026-10-09 | 2026-10-10 |  | 2026-10-14 | 2026-10-15 | [6 empty] | 2026-10-16 | 2026-10-19 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-24 | 2026-11-14 | 2026-11-16 | 109 | N/1 | Rony | [5 empty] | NCL |  |  | Need Test Cut | 146 | 0 | -146 | 0 | -600 | [11 empty] | 47 | Oct'2
UTG-(Even & Odd) | 24232 9th | BAD1287Q | 1000 | 165 | 2026-07-28 | 2026-08-01 | LDS LONG SKIRT W SIDE SLIT | Skirt |  |  | 2026-09-01 | 2026-09-09 | 2026-09-14 | 2026-09-26 |  |  | 2026-10-10 | 2026-10-12 |  | 2026-10-15 | 2026-10-16 | [6 empty] | 2026-10-19 | 2026-10-21 |  |  | 2026-10-22 | 2026-10-24 | 2026-10-26 | 2026-11-14 | 2026-11-16 | 109 | G2 | Rony | [5 empty] | NFL1 |  |  | Po Sheet Due | 165 | 165 | 0 | 0 | -1000 | [11 empty] | 47 | Oct'2
UTG-(Even & Odd) | 42250 5th | BAD2728D,BAD2728E | 1700 | 354 | 2026-08-06 | 2026-08-07 | LDS LS TS | TS | 2026-08-20 | 2026-08-31 | 2026-09-01 | 2026-09-11 | 2026-09-12 | 2026-09-22 |  |  | 2026-10-03 | 2026-10-05 |  | 2026-10-08 | 2026-10-09 | [6 empty] | 2026-10-10 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-17 | 2026-10-19 | 2026-11-07 | 2026-11-09 | 93 | N/1 | Rony |  |  |  | YD |  | NCL |  |  | Po Sheet Due | 354 | 0 | -354 | 0 | -1700 | [11 empty] | 46 | Oct'1
BS-ONS | 48154 2nd | 22029752 | 405 | 115 | 2026-07-25 | 2026-07-30 | Swt shorts pant w side pkt and back bon pkt and Drawstring | Shorts |  |  | 2026-09-25 | 2026-09-30 | 2026-10-10 | 2026-10-26 |  |  | 2026-11-06 | 2026-11-06 |  | 2026-11-16 | 2026-11-17 | [6 empty] | 2026-11-23 | 2026-11-25 |  |  | 2026-11-28 | 2026-11-30 | 2026-12-05 | 2027-01-04 | 2027-01-06 | 163 | C | Shakel | [5 empty] | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -405 | [11 empty] | 2 | Nov'2
BS-ONS | 48153 2nd | 22028692 | 450 | 138 | 2026-07-25 | 2026-07-30 | SS o nk TS w nk rib | TS |  |  | 2026-08-15 | 2026-08-20 | 2026-08-26 | 2026-09-08 |  |  | 2026-09-12 | 2026-09-12 |  | 2026-09-18 | 2026-09-18 | [6 empty] | 2026-09-22 | 2026-09-22 |  |  | 2026-09-24 | 2026-09-28 | 2026-10-08 | 2027-01-04 | 2027-01-06 | 163 | F | Shakel | [5 empty] | NFL1 |  |  | Size Set Run | 138 | 138 | 0 | 0 | -450 | [11 empty] | 2 | Sep'2 |  |  | 12.09.26
OVS SPA | 48519 | 271TNK007-6155 | 9093 | 924 | 2026-07-27 | 2026-07-31 | Tank top w sholder mesh and fake mother of pearl batch | Tank Top |  |  | 2026-10-01 | 2026-10-15 | 2026-10-20 | 2026-11-05 |  |  | 2026-11-20 | 2026-11-19 | 2026-11-24 | 2026-11-25 | 2026-11-28 | [6 empty] | 2026-12-01 | 2026-12-09 |  |  | 2026-12-10 | 2026-12-11 | 2026-12-12 | 2026-12-14 | 2026-12-14 | 140 | A | Sirajul |  |  |  |  | Mesh | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -9093 | [11 empty] | 51 | Nov'3
OVS SPA | 48542 | 271TSH046-6155 | 9558 | 1705 | 2026-07-31 | 2026-08-08 | SS TS w slve frill | TS |  |  | 2026-10-01 | 2026-10-13 | 2026-10-14 | 2026-10-31 |  |  | 2026-11-16 | 2026-11-14 | 2026-11-19 | 2026-11-20 | 2026-11-24 | [6 empty] | 2026-11-25 | 2026-12-04 |  |  | 2026-12-05 | 2026-12-07 | 2026-12-09 | 2026-12-14 | 2026-12-14 | 136 | K1 | Sirajul | [5 empty] | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -9558 | [11 empty] | 51 | Nov'2
OVS SPA | 48336 | 271PJA416-903 | 86732 | 12648 | 2026-07-30 | 2026-08-08 | SS o nk TS and AOP elasted Shorts w self drawstring | Top & BTM |  |  | 2026-08-18 | 2026-09-10 | 2026-09-05 | 2026-09-30 | 2026-09-21 | 2026-10-08 | 2026-10-20 | 2026-09-25 | 2026-09-30 | 2026-10-01 | 2026-10-20 |  |  |  |  | 2026-10-14 | 2026-11-11 | 2026-11-05 | 2026-12-04 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-11 | 2026-12-14 | 2026-12-14 | 137 | NFL1+N/2 | Salam |  | Chest | lavender top-9307 pcs 1 clr cording emb ,,naval top-9454 pcs 1 clr flat emb,,pink top-9420 pcs 1 clr flat emb,,marshmello-8194 pcs 1 clr flat emb,,white top-6991 pcs 1 clr flat emb ,All btm AOP-43366 pcs no emb | AOP | 1 combo cording emb | NFL1 |  |  | File Due | 12646 | 7080 | -5566 | 0 | -86732 | [11 empty] | 51 | Oct'1
OVS SPA | 48337 | 271NDG417-903 | 4914 | 1343 | 2026-07-30 | 2026-08-08 | SS U nk TS dress w frt AOP Pkt | Dress |  |  | 2026-10-01 | 2026-10-10 | 2026-10-12 | 2026-10-23 | 2026-10-24 | 2026-11-05 | 2026-11-18 | 2026-11-19 | 2026-11-24 | 2026-11-25 | 2026-11-27 | [6 empty] | 2026-11-28 | 2026-12-05 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-11 | 2026-12-14 | 2026-12-14 | 137 | N/3 | Salam |  |  |  | AOP |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -4914 | [11 empty] | 51 | Nov'3
OVS SPA | 48338 | 271NDG418-903 | 7546 | 2000 | 2026-07-30 | 2026-08-08 | SS U nk TS dress w side slit | Dress |  |  | 2026-09-25 | 2026-10-10 | 2026-10-12 | 2026-10-30 |  |  | 2026-11-20 | 2026-11-11 | 2026-11-18 | 2026-11-19 | 2026-11-21 |  |  |  |  | 2026-11-23 | 2026-11-30 | 2026-12-01 | 2026-12-05 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-11 | 2026-12-14 | 2026-12-14 | 137 | D1 | Salam |  | Chest | Naval academy-7546 pcs 1 clr flat emb |  |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -7546 | [11 empty] | 51 | Nov'2
BS-ONS | 26828 79th | 22029226 | 1500 | 971 | 2026-08-14 | 2026-08-17 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-08-24 | 2026-08-27 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-12 | 2026-09-12 |  | 2026-09-16 | 2026-09-17 | [6 empty] | 2026-09-19 | 2026-09-21 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-28 | 2026-09-30 | 45 | H | Shakel | [5 empty] | NFL1 |  |  | Need Cut FB | 971 | 0 | -971 | 0 | -1500 | [11 empty] | 40 | Sep'2 |  |  | 25.08.26
BS-ONS | 41626 27th | 22031973 | 1020 | 697 | 2026-08-14 | 2026-08-17 | MENS LONG SWT PANT W SIDE & BK PKT | PANT |  |  | 2026-08-20 | 2026-08-25 | 2026-08-27 | 2026-09-09 |  |  | 2026-09-07 | 2026-09-07 |  | 2026-09-11 | 2026-09-12 | [6 empty] | 2026-09-14 | 2026-09-16 |  |  | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-21 | 2026-09-23 | 38 | B | Shakel | [5 empty] | NFL1 |  |  | Cut Run | 697 | 476 | -221 | 745 | -275 | [11 empty] | 39 | Sep'2 |  |  | 11.09.26
BS-ONL | 43102 7th | 15366301 | 1500 | 235 | 2026-08-10 | 2026-08-11 | SS o nk TS | TS |  |  | 2026-08-14 | 2026-08-18 | 2026-09-23 | 2026-09-01 |  |  | 2026-09-02 | 2026-08-27 |  | 2026-09-01 | 2026-09-01 | 2026-09-03 | 2026-09-04 |  |  |  |  | 2026-09-07 | 2026-09-08 |  |  | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-14 | 2026-09-16 | 35 | K | Mainul | Chest |  | c.dan-750 pcs,,green-375 pcs,,brown-375 pcs both combo 1 clr gltr |  |  | NFL2 |  |  | Cut Ok | 234 | 234 | 0 | 1568 | 68 | [11 empty] | 38 | Sep'1 |  |  | 04.09.26
BS-ONL | 48170 | 15396533 | 25552 | 9506 | 2026-08-13 | 2026-08-15 | YD SS o nk TS | TS | 2026-08-19 | 2026-08-31 | 2026-08-26 | 2026-09-08 | 2026-09-01 | 2026-09-13 |  |  | 2026-09-05 | 2026-09-05 | 2026-09-10 | 2026-09-12 | 2026-09-17 | [6 empty] | 2026-09-14 | 2026-09-24 |  |  | 2026-09-25 | 2026-09-26 | 2026-09-28 | 2026-09-28 | 2026-09-30 | 46 | T1+Y | Imran |  |  |  | YD |  | NFL3 |  |  | Need Test Cut | 9852 | 0 | -9852 | 0 | -25552 | [11 empty] | 40 | Sep'2 |  |  | 12.09.26
BS-ONL | 21004 36th | 15245901 | 6250 | 931 | 2026-08-12 | 2026-08-13 | Tank Top | Tank Top |  |  | 2026-08-17 | 2026-08-22 | 2026-08-26 | 2026-09-05 |  |  | 2026-09-05 | 2026-09-05 |  | 2026-09-10 | 2026-09-11 | [6 empty] | 2026-09-14 | 2026-09-17 |  |  | 2026-09-18 | 2026-09-19 | 2026-09-21 | 2026-09-21 | 2026-09-23 | 40 | G2 | Dalim | [5 empty] | NFL1 |  |  | Cut Ok | 931 | 931 | 0 | 6287 | 37 | [11 empty] | 39 | Sep'1 |  |  | 02.09.26
GBX-New Look | 48551 1st | 9686529 | 5304 | 545 | 2026-08-06 | 2026-08-11 | AOP SS reglan contrast slve TS | TS |  |  | 2026-08-15 | 2026-08-20 | 2026-08-22 | 2026-09-01 | 2026-09-02 | 2026-09-08 | 2026-09-07 | 2026-09-07 | 2026-09-11 | 2026-09-12 | 2026-09-15 | 2026-09-15 | 2026-09-18 |  |  |  |  | 2026-09-18 | 2026-09-23 |  |  | 2026-09-25 | 2026-09-25 | 2026-09-26 | 2026-09-26 | 2026-09-27 | 51 | N/3 | Sifat | Fr,Bk |  | pink-5150 pcs frt back 1 clr rub print | AOP |  | NFL3 |  |  | Need Test Cut | 595 | 0 | -595 | 0 | -5304 | [11 empty] | 40 | Sep'2 |  |  | 12.09.26
GBX-New Look | 48551 2nd | 9686529 | 8083 | 1057 | 2026-08-06 | 2026-08-11 | YD SS reglan contrast slve TS | TS | 2026-08-25 | 2026-08-31 | 2026-09-01 | 2026-09-07 | 2026-09-07 | 2026-09-12 |  |  | 2026-09-05 | 2026-09-05 | 2026-09-10 | 2026-09-12 | 2026-09-15 | 2026-09-14 | 2026-09-18 |  |  |  |  | 2026-09-18 | 2026-09-24 |  |  | 2026-09-25 | 2026-09-25 | 2026-09-26 | 2026-09-26 | 2026-09-27 | 51 | N/3 | Sifat | Fr,Bk |  | pink-8200 pcs frt back 2 clr rub print | YD |  | NCL |  |  | Need Test Cut | 1057 | 0 | -1057 | 0 | -8083 | [11 empty] | 40 | Sep'2
GBX-New Look | 48551 3rd | 9686529 | 5304 | 672 | 2026-08-06 | 2026-08-11 | YD SS reglan contrast slve TS | TS | 2026-08-25 | 2026-08-31 | 2026-09-01 | 2026-09-07 | 2026-09-07 | 2026-09-12 |  |  | 2026-09-05 | 2026-09-05 |  | 2026-09-12 | 2026-09-15 | 2026-09-14 | 2026-09-18 |  |  |  |  | 2026-09-18 | 2026-09-24 |  |  | 2026-09-25 | 2026-09-25 | 2026-09-26 | 2026-09-26 | 2026-09-27 | 51 | N/3 | Sifat | Fr,Bk |  | blue-5051 pcs frt back 2 clr rub print | YD |  | NCL |  |  | Need Test Cut | 672 | 0 | -672 | 0 | -5304 | [11 empty] | 40 | Sep'2
GBX-New Look | 48588 1st | 915-9672271 | 2550 | 588 | 2026-08-13 | 2026-08-12 | LS reglan TS w w contrast slve and slve strpie self fabric attach | TS |  |  | 2026-08-18 | 2026-08-22 | 2026-08-25 | 2026-09-09 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 |  |  |  |  | 2026-09-19 | 2026-09-22 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-25 | 2026-09-27 | 43 | N/1 | Sifat | Chest |  | Navy-2550 pcs 1 clr rub print |  |  | NCL |  |  | Ready Test Cut | 588 | 553 | -35 | 0 | -2550 | [11 empty] | 40 | Sep'2
GBX-New Look | 48552 | 9686536 | 13887 | 1552 | 2026-07-26 | 2026-08-14 | AOP SS reglan contrast slve TS | TS |  |  | 2026-08-12 | 2026-08-20 | 2026-08-20 | 2026-09-03 | 2026-09-03 | 2026-09-09 | 2026-09-08 | 2026-09-08 | 2026-09-12 | 2026-09-15 | 2026-09-18 | [6 empty] | 2026-09-17 | 2026-09-23 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 62 | N/1 | Sifat |  |  |  | AOP |  | NCL |  |  | Need Test Cut | 1552 | 100 | -1452 | 0 | -13887 | [11 empty] | 40 | Sep'2
GBX-New Look | 48553 | CNOFJTKL38744 | 1920 | 235 | 2026-08-06 | 2026-08-14 | SS cross v nk TS | TS |  |  | 2026-08-18 | 2026-08-22 | 2026-09-01 | 2026-09-10 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-15 | 2026-09-17 | 2026-09-18 | [6 empty] | 2026-09-21 | 2026-09-23 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-26 | 2026-09-27 | 51 | N/1 | Sifat | [5 empty] | NFL3 |  |  | Need Test Cut | 235 | 0 | -235 | 0 | -1920 | [11 empty] | 40 | Sep'2 |  |  | 12.09.26
GBX-New Look | 48329 2nd | 9328977 | 1313 | 355 | 2026-08-15 | 2026-08-13 | SS o nk TS | TS |  |  | 2026-08-22 | 2026-08-26 | 2026-09-01 | 2026-09-10 |  |  | 2026-09-07 | 2026-09-07 |  | 2026-09-12 | 2026-09-12 | 2026-09-15 | 2026-09-16 |  |  |  |  | 2026-09-18 | 2026-09-19 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 41 | N/1 | Morad | Nk |  | 2 combo size nk label print |  |  | NCL |  |  | Need Test Cut | 355 | 0 | -355 | 0 | -1313 | [11 empty] | 39 | Sep'2
GBX-New Look | 48323 2nd | 9328960 | 808 | 241 | 2026-08-15 | 2026-08-13 | SS o nk TS | TS |  |  | 2026-08-24 | 2026-08-28 | 2026-09-01 | 2026-09-10 |  |  | 2026-09-09 | 2026-09-09 |  | 2026-09-14 | 2026-09-14 | 2026-09-15 | 2026-09-16 |  |  |  |  | 2026-09-18 | 2026-09-19 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 41 | N/1 | Morad | Nk |  | 1 combo size nk label print |  |  | NCL |  |  | Need Test Cut | 241 | 0 | -241 | 0 | -808 | [11 empty] | 39 | Sep'2
GBX-New Look | 48322 2nd | 9328950 | 505 | 105 | 2026-08-15 | 2026-08-13 | Tank Top | Tank Top |  |  | 2026-08-20 | 2026-08-24 | 2026-09-03 | 2026-09-10 |  |  | 2026-09-06 | 2026-09-06 |  | 2026-09-12 | 2026-09-12 | 2026-09-14 | 2026-09-15 |  |  |  |  | 2026-09-17 | 2026-09-18 |  |  | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-25 | 2026-09-26 | 41 | N/1 | Morad | Nk |  | 1 combo size nk label print |  |  | NCL |  |  | Need Test Cut | 105 | 0 | -105 | 0 | -505 | [11 empty] | 39 | Sep'2
BS-NMT | 46491 8th | 13225095 | 2560 | 340 | 2026-08-13 | 2026-08-14 | YD LS o nk TS | TS | 2026-08-27 | 2026-09-03 | 2026-09-07 | 2026-09-12 | 2026-09-15 | 2026-09-21 |  |  | 2026-09-23 | 2026-09-23 |  | 2026-09-28 | 2026-09-29 | 2026-10-01 | 2026-10-02 |  |  |  |  | 2026-10-05 | 2026-10-08 |  |  | 2026-10-10 | 2026-10-13 | 2026-10-15 | 2026-10-26 | 2026-10-28 | 74 | Z | Jafar | Chest,Nk |  | indigo-2560 pcs 1 clr puff print | YD |  | NFL3 |  |  | Need Cut FB | 340 | 0 | -340 | 0 | -2560 | [11 empty] | 44 | Sep'3 |  |  | 24.08.26
BS-NMT | 43327 17th | 13235093 | 1020 | 362 | 2026-08-13 | 2026-08-14 | Swt Pant w pkt waist belt drawstring | Pant |  |  | 2026-08-28 | 2026-09-02 | 2026-09-08 | 2026-09-19 |  |  | 2026-09-22 | 2026-09-22 |  | 2026-09-26 | 2026-09-28 | [6 empty] | 2026-10-01 | 2026-10-03 |  |  | 2026-10-05 | 2026-10-07 | 2026-10-08 | 2026-10-12 | 2026-10-14 | 60 | X | Jafar | [5 empty] | NFL3 |  |  | Need Cut FB | 362 | 0 | -362 | 0 | -1020 | [11 empty] | 42 | Sep'3 |  |  | 21.08.26
BS-ONS | 26970 61th | 22002973 | 1040 | 228 | 2026-08-10 | 2026-08-13 | SS o nk TS | TS |  |  | 2026-08-21 | 2026-08-25 | 2026-09-03 | 2026-09-12 |  |  | 2026-09-14 | 2026-09-14 |  | 2026-09-19 | 2026-09-21 | [6 empty] | 2026-09-24 | 2026-09-25 |  |  | 2026-09-28 | 2026-09-30 | 2026-10-01 | 2026-10-05 | 2026-10-07 | 56 | G1 | Shakel | [5 empty] | NFL1 |  |  | Size Set Run PC | 228 | 228 | 0 | 0 | -1040 | [11 empty] | 41 | Sep'2 |  |  | 14.09.26
BS-ONS | 26827 57th | 22029225 | 1200 | 1075 | 2026-08-13 | 2026-08-15 | LS Swt hoodie w kangaro pkt and drawstring and cuff btm rib | HOODY |  |  | 2026-08-25 | 2026-08-30 | 2026-09-03 | 2026-09-16 |  |  | 2026-09-14 | 2026-09-14 |  | 2026-09-19 | 2026-09-21 | [6 empty] | 2026-09-23 | 2026-09-25 |  |  | 2026-09-28 | 2026-09-29 | 2026-10-01 | 2026-10-05 | 2026-10-07 | 53 | J | Shakel | [5 empty] | NFL2 |  |  | Need Cut FB | 1075 | 0 | -1075 | 0 | -1200 | [11 empty] | 41 | Sep'2 |  |  | 22.08.26
BS-ONS | 48283 2nd | 22042341 | 6000 | 4057 | 2026-08-13 | 2026-08-14 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-08-18 | 2026-08-26 | 2026-08-25 | 2026-09-10 |  |  | 2026-09-10 | 2026-09-07 |  | 2026-09-12 | 2026-09-15 | 2026-09-14 | 2026-09-18 |  |  |  |  | 2026-09-18 | 2026-09-22 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-28 | 2026-09-30 | 46 | H | Shakel | Fr,Bk |  | Mulch-3008 pcs,,milk-3008 pcs both combo frt back 2 clr pig 1 clr puff |  |  | NFL1 |  |  | Need Cut FB | 4056 | 0 | -4056 | 0 | -6000 | [11 empty] | 40 | Sep'2 |  |  | 12.09.26
BS-ONL | 48299 2nd | 15390922 | 13359 | 3067 | 2026-08-15 | 2026-08-15 | SS o nk TS | TS |  |  | 2026-08-22 | 2026-09-02 | 2026-09-04 | 2026-09-21 |  |  | 2026-09-21 | 2026-09-21 |  | 2026-09-26 | 2026-09-30 | 2026-10-01 | 2026-10-07 |  |  |  |  | 2026-10-07 | 2026-10-15 |  |  | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-19 | 2026-10-21 | 65 | L1 | Jannati | Fr,Bk |  | air blue-3522 pcs frt 1 clr pig back photo print w 2 clr pig ,,ice water-1275 pcs frt 1 clr pig back no print ,,white universe-1230 pcs frt back 1 clr pig ,,lollipop-1022 pcs frt photo print w 2 clr pig back no print ,,white self-734 pcs frt 1 clr pig back no print ,,corage-1424 pcs frt 2 clr pig back no print ,,white pastry-4152 pcs frt back photo print |  |  | NFL2 |  |  | Need Cut | 3079 | 1400 | -1679 | 0 | -13359 | [11 empty] | 43 | Sep'3 |  |  | 07.09.26
BS-ONL | 48614 | 15391466 | 2340 | 484 | 2026-08-15 | 2026-08-15 | SS U nk TS w front woven frog closure button | TS |  |  | 2026-09-01 | 2026-09-05 | 2026-09-12 | 2026-09-25 |  |  | 2026-09-29 | 2026-09-29 | 2026-10-05 | 2026-10-07 | 2026-10-08 | [6 empty] | 2026-10-10 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-21 | 65 | M | Jannati | [5 empty] | NFL2 |  |  | Need Test Cut | 484 | 0 | -484 | 0 | -2340 | [11 empty] | 43 | Oct'1 |  |  | 04.09.26
BS-ONL | 48618 | 15390921 | 1032 | 156 | 2026-08-15 | 2026-08-17 | SS o nk TS | TS |  |  | 2026-08-26 | 2026-08-30 | 2026-09-05 | 2026-09-18 |  |  | 2026-09-21 | 2026-09-21 | 2026-09-26 | 2026-09-28 | 2026-09-29 | 2026-10-01 | 2026-10-02 |  |  |  |  | 2026-10-05 | 2026-10-06 |  |  | 2026-10-08 | 2026-10-10 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 65 | M | Jannati | Chest |  | LGM-516 pcs photo print w 7 clr rub,,pink-516 pcs photo print w 6 clr rub |  |  | NFL2 |  |  | File Due | 156 | 78 | -78 | 0 | -1032 | [11 empty] | 43 | Sep'3
BS-ONL | 48617 | 15390892 | 11940 | 2576 | 2026-08-15 | 2026-08-17 | YD SS boat nk TS | TS | 2026-08-25 | 2026-09-03 | 2026-08-24 | 2026-09-14 | 2026-09-04 | 2026-09-24 | 2026-09-18 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-29 | 2026-09-30 | 2026-10-04 | 2026-10-02 | 2026-10-04 |  |  |  |  | 2026-10-05 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 65 | M | Jannati | Nk |  | 9 combo nk 1 clr rub print | YD & AOP |  | NFL2 |  |  | Need Test Cut | 2576 | 0 | -2576 | 0 | -11940 | [11 empty] | 43 | Oct'1 |  |  | 04.09.26
BS-ONL | 48623 | 15391339 | 2274 | 1176 | 2026-08-15 | 2026-08-15 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-08-25 | 2026-09-02 | 2026-09-05 | 2026-09-20 |  |  | 2026-09-21 | 2026-09-21 | 2026-09-26 | 2026-09-29 | 2026-09-30 | 2026-10-02 | 2026-10-07 |  |  |  |  | 2026-10-08 | 2026-10-12 |  |  | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 65 | N2 | Jannati | slv,Chest |  | black-1569 pcs chest 1 clr puff print slve no print ,,beetroot-705 pcs chest no print both slvee 1 clr puff print |  |  | NFL2 |  |  | File Due | 1176 | 0 | -1176 | 0 | -2274 | [11 empty] | 43 | Sep'3
BS-ONL | 48626 | 15391961 | 1149 | 529 | 2026-08-15 | 2026-08-15 | AOP and Solid LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-08-25 | 2026-08-30 | 2026-09-05 | 2026-09-18 | 2026-09-18 | 2026-09-24 | 2026-09-25 | 2026-09-25 | 2026-09-30 | 2026-10-02 | 2026-10-03 | 2026-10-05 | 2026-10-07 | 2026-10-12 | 2026-10-14 |  |  | 2026-10-09 | 2026-10-10 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 65 | N2 | Jannati | Chest |  | white smily AOP-540 pcs no print no pearl ,,lollipop-609 pcs 1 clr rub and pearl attach |  |  | NFL2 |  |  | CAD | 529 | 0 | -529 | 0 | -1149 | [11 empty] | 43 | Oct'1 |  |  | 15.09.26
BS-ONL | 48625 | 15391436 | 672 | 376 | 2026-08-15 | 2026-08-17 | LS Frt slve Cut&sew contrast Swt Shirt | Swt Shirt |  |  | 2026-08-25 | 2026-09-01 | 2026-09-05 | 2026-09-19 |  |  | 2026-09-22 | 2026-09-22 | 2026-09-29 | 2026-10-01 | 2026-10-02 | [6 empty] | 2026-10-05 | 2026-10-07 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-14 | 2026-10-19 | 2026-10-21 | 65 | R | Jannati | [5 empty] | NFL2 |  |  | File Due | 376 | 0 | -376 | 0 | -672 | [11 empty] | 43 | Oct'1
BS-ONL | 48532 | 15391922 | 12633 | 2855 | 2026-08-15 | 2026-08-17 | YD SS O nk TS w Hand sewn beads | TS | 2026-08-20 | 2026-08-27 | 2026-08-25 | 2026-09-04 | 2026-08-30 | 2026-09-06 |  |  | 2026-09-20 | 2026-08-28 | 2026-09-02 | 2026-09-04 | 2026-09-10 | 2026-09-07 | 2026-09-14 | 2026-09-10 | 2026-10-06 |  |  | 2026-10-08 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-21 | 65 | F | Jannati | Fr,Bk |  | phanthom stripe -5073 pcs frt 2 clr rub back photo print w 2 clr rub hand sewn beads,, Primrose pink-4419 pcs frt photo print w 2 clr rub and hand sewn beads back no print ,,Bel Air Blue-3141 pcs frt photo print w 1 clr pig back photo print w 1 clr pig w hand sewn beads or stone |  | Hand sewn beads | NFL1 |  |  | Cut Run | 2855 | 1634 | -1221 | 6190 | -6443 | [11 empty] | 43 | Sep'1 |  |  | 31.08.26
BS-ONL | 48169 | 15399193 | 816 | 166 | 2026-08-06 | 2026-08-13 | SS dress w upper part mesh and bk nk zipper | Dress |  |  | 2026-08-20 | 2026-08-25 | 2026-09-02 | 2026-09-12 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-19 | 2026-09-21 | 2026-09-22 | [6 empty] | 2026-09-24 | 2026-09-26 |  |  | 2026-09-28 | 2026-09-30 | 2026-10-01 | 2026-10-05 | 2026-10-07 | 60 | J | Mainul |  |  |  |  | Mesh | NFL2 |  |  | CAD | 166 | 0 | -166 | 0 | -816 | [11 empty] | 41 | Sep'3 |  |  | 16.09.26
BS-ONL | 48302 2nd | 15337134 | 24000 | 9167 | 2026-08-13 | 2026-08-14 | YD LS o nk TS | TS | 2026-08-18 | 2026-08-31 | 2026-08-27 | 2026-09-12 | 2026-09-05 | 2026-09-17 |  |  | 2026-09-12 | 2026-09-12 |  | 2026-09-17 | 2026-09-24 | [6 empty] | 2026-09-21 | 2026-10-02 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-05 | 2026-10-05 | 2026-10-07 | 53 | N1+L1 | Imran |  |  |  | YD |  | NFL2 |  |  | Need Cut FB | 9093 | 0 | -9093 | 0 | -24000 | [11 empty] | 41 | Sep'2 |  |  | 02.09.26
BS-ONL | 48160 2nd | 15317989 | 8463 | 1343 | 2026-08-13 | 2026-08-15 | SS o nk TS w frt pkt | TS |  |  | 2026-08-25 | 2026-09-02 | 2026-09-05 | 2026-09-19 |  |  | 2026-09-21 | 2026-09-17 |  | 2026-09-23 | 2026-09-26 |  |  | 2026-10-05 | 2026-10-10 | 2026-09-25 | 2026-09-30 | 2026-10-01 | 2026-10-07 |  |  | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 67 | N1 | Mainul |  | Chest | black lovely-2027 pcs no print 6 clr flat emb at chest 1 clr flat emb at pkt and flower hand sewing at chest,,white cattitate-1119 pcs chest and pkt 1 clr pig print no emb ,,white apologies-1119 pcs chest and pkt 1 clr pig print no emb ,,c.and wild-2357 pcs no print pkt 6 clr flat emb ,,anise wild-1841 pcs no print 8 clr flat emb at pkt |  | 1 combo hand sewing flower | NFL2 |  |  | CAD | 1345 | 1023 | -322 | 0 | -8463 | [11 empty] | 43 | Sep'3 |  |  | 16.09.26
BS-ONL | 46205 5th | 15382230 | 14523 | 2167 | 2026-08-13 | 2026-08-17 | SS o nk TS | TS |  |  | 2026-08-20 | 2026-08-28 | 2026-09-01 | 2026-09-15 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-19 | 2026-09-22 | 2026-09-26 | 2026-09-24 | 2026-09-30 |  |  | 2026-09-28 | 2026-10-06 | 2026-10-06 | 2026-10-15 |  |  | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-19 | 2026-10-21 | 67 | N1 | Mainul | Chest | Chest | black flower-75 pcs 6 clr rub 3 clr seq emb ,,black perfect-2758 pcs 4 clr rub 1 clr gltr and 1 clr seq emb ,,black bear-1883 pcs photo print and 1 clr seq emb ,,c.dan flower-75 pcs 6 clr pig 4 clr seq emb ,,c.dan scooter-925 pcs 9 clr pig 1 clr seq emb ,,c.dan new scooter-2371 pcs,,c.dan flamingo-75 pcs photo print and 1 clr seq emb ,,c.dan mini flowwer-75 pcs 4 clr pig print and 2 clr seq emb ,,c.dan bear iconic-2150 pcs photo print and 3 clr seq emb ,,anise mini flower-75 pcs 4 clr pig 2 clr seq emb ,,jadeite flamingo-75 pcs photo print 1 clr seq emb ,,blue flower-75 pcs 6 clr pig 3 clr seq emb ,,pink mini flower-75 pcs 4 clr pig 3 clr seq emb ,,pink flamingo-75 pcs photo print 1 clr seq emb ,,pink bear iconic-1853 pcs photo print and 1 clr seq emb ,,pink bicycle-1908 pcs 3 clr pg 2 clr gltr and 1 clr seq emb |  |  | NFL2 |  |  | CAD | 2166 | 1423 | -743 | 0 | -14523 | [11 empty] | 43 | Sep'3 |  |  | 16.09.26
BS-ONL | 48631 | 15392772 | 4599 | 1003 | 2026-08-12 | 2026-08-17 | SS o nk TS | TS |  |  | 2026-08-26 | 2026-09-02 | 2026-09-05 | 2026-09-18 |  |  | 2026-09-19 | 2026-09-19 | 2026-09-23 | 2026-09-25 | 2026-09-28 | 2026-09-28 | 2026-10-03 |  |  |  |  | 2026-10-05 | 2026-10-09 |  |  | 2026-10-10 | 2026-10-12 | 2026-10-14 | 2026-10-18 | 2026-10-20 | 67 | M | Zahirul | Chest |  | begula-2148 pcs 1 clr rub 1 clr gltr ,,p.stone-2451 pcs 1 clr rub 1 clr foil |  |  | NFL2 |  |  | File Due | 1003 | 0 | -1003 | 0 | -4599 | [11 empty] | 43 | Sep'3
BS-ONL | 45941 2nd | 15379280 | 3378 | 705 | 2026-08-12 | 2026-08-17 | SS o nk TS | TS |  |  | 2026-08-25 | 2026-08-31 | 2026-09-05 | 2026-09-16 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-21 | 2026-09-23 | 2026-09-25 |  |  |  |  | 2026-09-26 | 2026-10-06 | 2026-10-08 | 2026-10-12 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-21 | 68 | T1 | Zahirul |  | AOE | c.dan shell ice-1377 pcs,,c.dna lemon-2001 pcs both combo frt both slve 1 clr flat All over emb |  |  | NFL3 |  |  | Po Sheet Due | 705 | 705 | 0 | 0 | -3378 | [11 empty] | 43 | Sep'3
BS-ONL | 47066 4th | 15384652 | 616 | 220 | 2026-08-12 | 2026-08-17 | LS o nk TS | TS |  |  | 2026-09-05 | 2026-09-08 | 2026-09-14 | 2026-09-24 |  |  | 2026-09-26 | 2026-09-26 |  | 2026-10-02 | 2026-10-02 | [6 empty] | 2026-10-06 | 2026-10-07 |  |  | 2026-10-09 | 2026-10-12 | 2026-10-14 | 2026-10-19 | 2026-10-21 | 68 | T1 | Zahirul | [5 empty] | NFL3 |  |  | Need Test Cut | 220 | 0 | -220 | 0 | -616 | [11 empty] | 43 | Oct'1 |  |  | 12.09.26
BS-ONL | 44700 5th | 15315774 | 720 | 451 | 2026-08-12 | 2026-08-17 | LS O NK SWT SHIRT | Swt Shirt |  |  | 2026-08-26 | 2026-08-31 | 2026-09-05 | 2026-09-17 |  |  | 2026-09-21 | 2026-09-21 |  | 2026-09-25 | 2026-09-25 |  |  |  |  | 2026-09-28 | 2026-10-06 | 2026-10-09 | 2026-10-10 |  |  | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 68 | T2 | Zahirul |  | Slv | lollipop-720 pcs BOTH SLV CUT OUT EMB |  |  | NFL3 |  |  | Need Test Cut | 451 | 0 | -451 | 0 | -720 | [11 empty] | 43 | Sep'3 |  |  | 12.09.26
GBX-New Look | 47424 4th | 9646803 | 6264 | 2049 | 2026-08-08 | 2026-08-14 | legging w drawstring | Legging |  |  | 2026-08-25 | 2026-09-07 | 2026-09-07 | 2026-09-14 |  |  | 2026-09-14 | 2026-09-14 |  | 2026-09-19 | 2026-09-22 | [6 empty] | 2026-09-23 | 2026-09-28 |  |  | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-03 | 2026-10-04 | 56 | N/1 | Sifat | [5 empty] | NCL |  |  | Need Test Cut | 2049 | 0 | -2049 | 0 | -6264 | [11 empty] | 41 | Sep'2
GBX-New Look | 47403 5th | 9603199 | 6263 | 781 | 2026-08-08 | 2026-08-14 | YD SL TS w full placket btn | TS | 2026-08-18 | 2026-08-24 | 2026-08-25 | 2026-09-04 | 2026-09-05 | 2026-09-12 |  |  | 2026-09-12 | 2026-09-12 |  | 2026-09-18 | 2026-09-22 | [6 empty] | 2026-09-22 | 2026-09-28 |  |  | 2026-09-29 | 2026-09-30 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 56 | N/2 | Sifat |  |  |  | YD |  | NCL |  |  | Need Test Cut | 781 | 0 | -781 | 0 | -6263 | [11 empty] | 41 | Sep'2
GBX-New Look | 48608 | 9686507 | 6567 | 714 | 2026-08-14 | 2026-08-15 | SS o nk TS w seq and pompom at chest | TS |  |  | 2026-08-25 | 2026-08-29 | 2026-09-02 | 2026-09-14 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-21 | 2026-09-23 | 2026-09-26 |  |  |  |  | 2026-09-25 | 2026-09-02 | 2026-10-02 | 2026-10-06 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-10 | 57 | N/1 | Sifat |  | Chest | pink-6567 pcs 2 clr seq and pompom attach emb |  |  | NCL |  |  | File Due | 714 | 0 | -714 | 0 | -6567 | [11 empty] | 41 | Sep'3
GBX-New Look | 48609 | 9686518 | 3537 | 387 | 2026-08-14 | 2026-08-15 | SS o nk TS | TS |  |  | 2026-08-24 | 2026-08-29 | 2026-09-02 | 2026-09-12 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-19 | 2026-09-21 | 2026-09-22 | 2026-09-22 | 2026-09-26 |  |  | 2026-09-26 | 2026-09-30 | 2026-10-01 | 2026-10-03 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-10 | 2026-10-10 | 57 | N/1 | Sifat | Chest | Chest | Navy-3537 pcs 7 clr rub print and 2 clr seq emb |  |  | NCL |  |  | File Due | 387 | 0 | -387 | 0 | -3537 | [11 empty] | 41 | Sep'3
GBX-New Look | 47936 5th | 9657695 | 4250 | 461 | 2026-08-18 | 2026-08-17 | SS reglan contrast slve TS | TS |  |  | 2026-08-22 | 2026-08-27 | 2026-09-02 | 2026-09-14 |  |  | 2026-09-14 | 2026-09-14 |  | 2026-09-19 | 2026-09-22 | [6 empty] | 2026-09-23 | 2026-09-28 |  |  | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-03 | 2026-10-04 | 46 | N/2 | Sifat | [5 empty] | NCL |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -4250 | [11 empty] | 41 | Sep'2
UTG-AF | 46346 2nd | BAD3144mamaA | 2400 | 495 | 2026-08-10 | 2026-08-14 | SS V nk TS | TS |  |  | 2026-08-25 | 2026-09-02 | 2026-09-07 | 2026-09-21 |  |  | 2026-09-23 | 2026-09-23 |  | 2026-09-28 | 2026-09-29 | [6 empty] | 2026-10-01 | 2026-10-03 |  |  | 2026-10-06 | 2026-10-08 | 2026-10-13 | 2026-10-24 | 2026-10-26 | 75 | N/1 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 495 | 495 | 0 | 0 | -2400 | [11 empty] | 44 | Sep'3
UTG-AF | 48557 | BAD3283Nurs | 1600 | 290 | 2026-08-10 | 2026-08-14 | SS V nk TS | TS |  |  | 2026-08-25 | 2026-08-31 | 2026-09-04 | 2026-09-18 |  |  | 2026-09-29 | 2026-09-29 | 2026-09-25 | 2026-09-28 | 2026-09-29 | [6 empty] | 2026-10-01 | 2026-10-03 |  |  | 2026-10-06 | 2026-10-08 | 2026-10-10 | 2026-10-24 | 2026-10-26 | 75 | N/2 | Rana | [5 empty] | NCL |  |  | File Due | 290 | 0 | -290 | 0 | -1600 | [11 empty] | 44 | Sep'3
UTG-AF | 43663 10th | BAD1634V | 2700 | 645 | 2026-08-09 | 2026-08-14 | LS o nk TS | TS |  |  | 2026-08-25 | 2026-09-02 | 2026-09-08 | 2026-09-22 |  |  | 2026-09-24 | 2026-09-24 |  | 2026-10-01 | 2026-10-02 | [6 empty] | 2026-10-05 | 2026-10-08 |  |  | 2026-10-10 | 2026-10-13 | 2026-10-15 | 2026-10-24 | 2026-10-26 | 76 | D1 | Rana | [5 empty] | NFL1 |  |  | CAD | 645 | 215 | -430 | 0 | -2700 | [11 empty] | 44 | Oct'1 |  |  | 15.09.26
UTG-AF | 48541 | BAD3254 | 2400 | 465 | 2026-08-09 | 2026-08-14 | LS o nk TS | TS |  |  | 2026-08-26 | 2026-08-31 | 2026-09-05 | 2026-09-18 |  |  | 2026-09-21 | 2026-09-21 | 2026-09-26 | 2026-09-29 | 2026-09-30 | [6 empty] | 2026-10-01 | 2026-10-03 |  |  | 2026-10-06 | 2026-10-08 | 2026-10-13 | 2026-10-24 | 2026-10-26 | 76 | D1 | Rana | [5 empty] | NFL1 |  |  | CAD | 465 | 155 | -310 | 0 | -2400 | [11 empty] | 44 | Sep'3 |  |  | 15.09.26
UTG-AF | 41947 27th | BAD0984CF+2554AR | 22900 | 3941 | 2026-08-09 | 2026-08-14 | LDS O NK SS TS | TS |  |  | 2026-08-24 | 2026-09-03 | 2026-09-04 | 2026-09-26 |  |  | 2026-09-26 | 2026-09-26 |  | 2026-10-01 | 2026-10-06 | [6 empty] | 2026-10-05 | 2026-10-15 |  |  | 2026-10-17 | 2026-10-19 | 2026-10-20 | 2026-10-24 | 2026-10-26 | 76 | D1 | Rana | [5 empty] | NFL1 |  |  | CAD | 3942 | 836 | -3106 | 0 | -22900 | [11 empty] | 44 | Oct'1 |  |  | 15.09.26
UTG-AF | 41712 15th | BAD2323mamaAA | 3000 | 786 | 2026-08-09 | 2026-08-14 | LDS LONG LEGGINGS | LEGGING |  |  | 2026-08-25 | 2026-08-31 | 2026-09-05 | 2026-09-17 |  |  | 2026-09-17 | 2026-09-17 |  | 2026-09-26 | 2026-09-28 | [6 empty] | 2026-10-01 | 2026-10-03 |  |  | 2026-10-06 | 2026-10-08 | 2026-10-12 | 2026-10-17 | 2026-10-19 | 69 | L2 | Rana | [5 empty] | NFL2 |  |  | Cut Run | 786 | 524 | -262 | 2084 | -916 | [11 empty] | 43 | Sep'3 |  |  | 02.09.26
UTG-AF | 48539 | BAD3252 | 1600 | 280 | 2026-08-09 | 2026-08-14 | SS Scallop nk TS w lace | TS |  |  | 2026-09-01 | 2026-09-07 | 2026-09-08 | 2026-09-19 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-28 | 2026-09-29 | 2026-09-30 | [6 empty] | 2026-10-01 | 2026-10-03 |  |  | 2026-10-05 | 2026-10-07 | 2026-10-09 | 2026-10-24 | 2026-10-26 | 76 | N/2 | Rana | [5 empty] | NCL |  |  | File Due | 280 | 0 | -280 | 0 | -1600 | [11 empty] | 44 | Sep'3
UTG-AF | 48540 | BAD3253 | 550 | 150 | 2026-08-09 | 2026-08-14 | LS bk waterfall style nk TS | TS |  |  | 2026-09-01 | 2026-09-07 | 2026-09-08 | 2026-09-19 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-28 | 2026-09-29 | 2026-09-30 | [6 empty] | 2026-10-01 | 2026-10-02 |  |  | 2026-10-03 | 2026-10-05 | 2026-10-07 | 2026-10-24 | 2026-10-26 | 76 | N/2 | Rana | [5 empty] | NCL |  |  | File Due | 150 | 0 | -150 | 0 | -550 | [11 empty] | 44 | Sep'3
UTG-AF | 46885 5th | BAD3195mamaD | 2000 | 652 | 2026-08-09 | 2026-08-14 | Long legging | Legging |  |  | 2026-08-25 | 2026-08-31 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-25 | 2026-09-26 |  | 2026-09-29 | 2026-09-30 | [6 empty] | 2026-10-01 | 2026-10-05 |  |  | 2026-10-06 | 2026-10-08 | 2026-10-10 | 2026-10-17 | 2026-10-19 | 69 | N/1 | Rana | [5 empty] | NCL |  |  | Need Test Cut | 652 | 0 | -652 | 0 | -2000 | [11 empty] | 43 | Sep'3 |  |  | 07.09.26
UTG-AF | 46839 2nd | BAD3183MamaA | 600 | 175 | 2026-08-09 | 2026-08-14 | LS love nk TS | TS |  |  | 2026-09-01 | 2026-09-09 | 2026-09-10 | 2026-09-22 |  |  | 2026-09-29 | 2026-09-30 |  | 2026-10-02 | 2026-10-03 | [6 empty] | 2026-10-05 | 2026-10-06 |  |  | 2026-10-07 | 2026-10-09 | 2026-10-12 | 2026-10-24 | 2026-10-26 | 76 | N/1 | Rana | [5 empty] | NCL |  |  | Need Test Cut | 175 | 0 | -175 | 0 | -600 | [11 empty] | 44 | Oct'1
UTG-(Even & Odd) | 41318 19th | BAD1571AI | 1500 | 385 | 2026-08-06 | 2026-08-14 | CROPPED WRAP OVERLAP LS TS | TS |  |  | 2026-08-22 | 2026-08-26 | 2026-09-02 | 2026-09-12 |  |  | 2026-09-12 | 2026-09-12 |  | 2026-09-18 | 2026-09-19 | [6 empty] | 2026-09-22 | 2026-09-24 |  |  | 2026-09-26 | 2026-09-29 | 2026-09-30 | 2026-10-03 | 2026-10-05 | 58 | N/2 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 385 | 385 | 0 | 0 | -1500 | [11 empty] | 41 | Sep'2
UTG-(Even & Odd) | 27136 21th | BAD2497T | 3000 | 462 | 2026-08-06 | 2026-08-14 | LDS SS BODYSUIT | SUIT |  |  | 2026-08-20 | 2026-08-26 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-12 | 2026-09-12 |  | 2026-09-17 | 2026-09-18 | [6 empty] | 2026-09-21 | 2026-09-25 |  |  | 2026-09-26 | 2026-09-29 | 2026-09-30 | 2026-10-03 | 2026-10-05 | 58 | N/2 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 462 | 231 | -231 | 0 | -3000 | [11 empty] | 41 | Sep'2
UTG-(Even & Odd) | 45963 13th | BAD0962BT | 2000 | 472 | 2026-08-06 | 2026-08-14 | LDS LS R NK TS | TS |  |  | 2026-08-25 | 2026-08-31 | 2026-09-08 | 2026-09-21 |  |  | 2026-09-24 | 2026-09-24 |  | 2026-09-26 | 2026-09-30 | [6 empty] | 2026-10-05 | 2026-10-07 |  |  | 2026-10-08 | 2026-10-10 | 2026-10-12 | 2026-10-17 | 2026-10-19 | 72 | N/1 | Rony | [5 empty] | NCL |  |  | Need Test Cut | 472 | 0 | -472 | 0 | -2000 | [11 empty] | 43 | Sep'3
UTG-(Even & Odd) | 44262 8th | BAD2927G | 2200 | 409 | 2026-08-06 | 2026-08-14 | LS TS W LACE | TS |  |  | 2026-08-24 | 2026-08-28 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-12 | 2026-09-12 |  | 2026-09-17 | 2026-09-18 | [6 empty] | 2026-09-22 | 2026-09-25 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-03 | 2026-10-05 | 58 | Q | Rony |  |  |  |  | Lace | NFL2 |  |  | Need Test Cut | 409 | 0 | -409 | 0 | -2200 | [11 empty] | 41 | Sep'2 |  |  | 12.09.26
UTG-(Even & Odd) | 44047 13th | BAD0982AP | 4000 | 984 | 2026-08-06 | 2026-08-14 | LDS LS BODYSUIT | SUIT |  |  | 2026-08-22 | 2026-08-31 | 2026-09-01 | 2026-09-14 |  |  | 2026-09-12 | 2026-09-12 |  | 2026-09-17 | 2026-09-19 | [6 empty] | 2026-09-19 | 2026-09-24 |  |  | 2026-09-26 | 2026-09-28 | 2026-09-30 | 2026-10-03 | 2026-10-05 | 58 | Q | Rony | [5 empty] | NFL2 |  |  | Need Cut | 984 | 492 | -492 | 0 | -4000 | [11 empty] | 41 | Sep'2 |  |  | 11.09.26
UTG-(Even & Odd) | 45150 5th | BAD2992E | 1400 | 240 | 2026-08-06 | 2026-08-14 | LS WRAP TOP | Dress | 2026-09-05: 2026-09-04; 2026-09-12: 2026-09-14 |  |  | 2026-09-12 | 2026-09-12 |  | 2026-09-17 | 2026-09-19 | [6 empty] | 2026-09-21 | 2026-09-23 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-30 | 2026-10-03 | 2026-10-05 | 58 | N2 | Rony |  |  |  |  | Imp Grey Fab stock | NFL2 |  |  | Need Cut FB | 240 | 0 | -240 | 0 | -1400 | [11 empty] | 41 | Sep'2 |  |  | 11.09.26
BS-NMT | 48112 | 13269965 | 2853 | 344 | 2026-08-06 | 2026-08-14 | SS o nk TS | TS |  |  | 2026-09-01 | 2026-09-06 | 2026-09-15 | 2026-09-30 |  |  | 2026-10-06 | 2026-10-06 | 2026-10-12 | 2026-10-14 | 2026-10-15 | 2026-10-17 | 2026-10-21 |  |  |  |  | 2026-10-23 | 2026-10-26 |  |  | 2026-10-28 | 2026-10-30 | 2026-11-05 | 2026-11-20 | 2026-11-22 | 106 | T1 | Shamoly | Chest,Nk |  | white-951 pcs 4 clr pig print ,,swamp-951 pcs 1 clr pig print ,,Navy-951 pcs 1 clr rub print |  |  | NFL3 |  |  | File Due | 345 | 232 | -113 | 0 | -2853 | [11 empty] | 48 | Oct'2
BS-ONS | 48554 | 22037874 | 3044 | 2507 | 2026-08-05 | 2026-08-11 | LS Swt hoody w cuff btm rib | Hoody |  |  | 2026-08-25 | 2026-09-03 | 2026-09-05 | 2026-09-24 |  |  | 2026-09-28 | 2026-09-28 | 2026-10-05 | 2026-10-08 | 2026-10-10 | 2026-10-10 | 2026-10-17 |  |  |  |  | 2026-10-20 | 2026-10-26 |  |  | 2026-10-28 | 2026-10-30 | 2026-10-31 | 2026-11-09 | 2026-11-11 | 96 | R | Shakel | Fr,Bk,Nk & Slv |  | black-1003 pcs frt back 1 clr rub slve no print ,,jet black-1310 pcs frt both slve 3 clr rub back 1 clr rub print ,,SLG-803 pcs frt back 2 clr rub both slve 1 clr rub print |  | License order | NFL2 |  |  | File Due | 2507 | 0 | -2507 | 0 | -3044 | [11 empty] | 46 | Oct'1
BS-ONS | 48555 | 22037681 | 3816 | 1206 | 2026-08-05 | 2026-08-11 | SS o nk TS w nk rib | TS |  |  | 2026-09-01 | 2026-09-09 | 2026-09-14 | 2026-09-29 |  |  | 2026-10-01 | 2026-10-01 | 2026-10-06 | 2026-10-08 | 2026-10-10 | 2026-10-12 | 2026-10-16 |  |  |  |  | 2026-10-19 | 2026-10-22 |  |  | 2026-10-24 | 2026-10-27 | 2026-10-30 | 2026-11-09 | 2026-11-11 | 96 | D1 | Shakel | Fr & Bk & Nk |  | black kanto-548 pcs frt 3 clr rub back 6 clr rub,,silver pikasu-524 pcs frt back 4 clr rub,,white gotta-524 pcs frt 5 clr pig back no print ,,black-1316 pcs frt 1 clr rub back 7 clr rub,,white pkemon-524 pcs,frt back 3 clr pig ,white charizard-524 pcs frt back 5 clr pig |  | License order | NFL1 |  |  | File Due | 1207 | 157 | -1050 | 0 | -3816 | [11 empty] | 46 | Oct'1
BS-ONS | 45750 3rd | 22037659 | 1472 | 444 | 2026-08-05 | 2026-08-11 | SS o nk TS w nk rib | TS |  |  | 2026-09-10 | 2026-09-15 | 2026-09-19 | 2026-09-30 |  |  | 2026-10-05 | 2026-10-02 |  | 2026-10-09 | 2026-10-10 | 2026-10-13 | 2026-10-15 |  |  | 2026-10-13 | 2026-10-17 | 2026-10-20 | 2026-10-21 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-30 | 2026-11-09 | 2026-11-11 | 96 | D1 | Shakel | Nk | Chest | white genger-1472 pcs 4 clr flat emb |  | License order | NFL1 |  |  | Po Sheet Due | 444 | 0 | -444 | 0 | -1472 | [11 empty] | 46 | Oct'1
BS-ONS | 48556 | 22042437 | 2284 | 1903 | 2026-08-05 | 2026-08-11 | LS Swt hoody w cuff btm rib | Hoody |  |  | 2026-08-25 | 2026-09-07 | 2026-09-12 | 2026-09-30 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-09 | 2026-10-12 | 2026-10-13 | 2026-10-15 | 2026-10-19 |  |  |  |  | 2026-10-21 | 2026-10-24 |  |  | 2026-10-27 | 2026-10-29 | 2026-11-05 | 2026-11-09 | 2026-11-11 | 96 | R | Shakel | Chest,Nk |  | black charizard-1166 pcs 4 clr rub ,,black snorlaxy-1166 pcs 3 clr rub |  | License order | NFL2 |  |  | File Due | 1904 | 1387 | -517 | 0 | -2284 | [11 empty] | 46 | Oct'2
BS-ONL | 48621 | 15394365 | 3874 | 540 | 2026-08-15 | 2026-08-15 | Elasted Legging | Legging |  |  | 2026-09-03 | 2026-09-08 | 2026-09-16 | 2026-09-28 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-09 | 2026-10-12 | 2026-10-14 | [6 empty] | 2026-10-16 | 2026-10-21 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-28 | 2026-11-09 | 2026-11-11 | 86 | L2 | Jannati | [5 empty] | NFL2 |  |  | File Due | 540 | 540 | 0 | 0 | -3874 | [11 empty] | 46 | Oct'2
BS-ONL | 48620 | 15391460 | 6063 | 958 | 2026-08-15 | 2026-08-17 | SS V nk TS w nk Lace and slve btm letus stich | TS |  |  | 2026-09-01 | 2026-09-12 | 2026-09-15 | 2026-09-30 |  |  | 2026-10-06 | 2026-10-06 | 2026-10-12 | 2026-10-14 | 2026-10-17 | [6 empty] | 2026-10-17 | 2026-10-24 |  |  | 2026-10-27 | 2026-10-28 | 2026-10-31 | 2026-11-09 | 2026-11-11 | 86 | K | Jannati | [5 empty] | NFL2 |  |  | Need Test Cut | 958 | 0 | -958 | 0 | -6063 | [11 empty] | 46 | Oct'2 |  |  | 07.09.26
BS-ONL | 45228 2nd | 15357482 | 1440 | 202 | 2026-08-15 | 2026-08-17 | SS o nk TS w btm double shell tussle lace attach | TS |  |  | 2026-09-08 | 2026-09-13 | 2026-09-20 | 2026-10-05 |  |  | 2026-10-13 | 2026-10-13 | 2026-10-19 | 2026-10-21 | 2026-10-22 | [6 empty] | 2026-10-24 | 2026-10-27 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-09 | 2026-11-11 | 86 | K | Jannati | [5 empty] | NFL2 |  |  | CAD | 202 | 101 | -101 | 0 | -1440 | [11 empty] | 46 | Oct'3 |  |  | 15.09.26
BS-ONL | 48624 | 15391423 | 564 | 293 | 2026-08-15 | 2026-08-17 | LS Swt shirt w front double pkt w flap | Swt Shirt |  |  | 2026-09-05 | 2026-09-10 | 2026-09-15 | 2026-09-30 |  |  | 2026-10-04 | 2026-10-04 | 2026-10-10 | 2026-10-13 | 2026-10-14 | [6 empty] | 2026-10-16 | 2026-10-17 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-26 | 2026-11-09 | 2026-11-11 | 86 | R | Jannati | [5 empty] | NFL2 |  |  | Need Test Cut | 293 | 0 | -293 | 0 | -564 | [11 empty] | 46 | Oct'2 |  |  | 04.09.26
BS-ONL | 30011 22th | 15318144 | 3966 | 595 | 2026-08-13 | 2026-08-17 | SS o nk TS | TS |  |  | 2026-09-01 | 2026-09-07 | 2026-09-13 | 2026-09-30 |  |  | 2026-10-01 | 2026-10-01 |  | 2026-10-06 | 2026-10-08 | 2026-10-09 | 2026-10-13 |  |  | 2026-10-13 | 2026-10-17 | 2026-10-20 | 2026-10-23 |  |  | 2026-10-26 | 2026-10-28 | 2026-10-30 | 2026-11-09 | 2026-11-11 | 88 | L1 | Mainul | Chest | Chest | C.dan scooter-1233 pcs 2 clr pig 1 clr gltr and 1 clr seq emb ,,green waterfall-1545 pcs photo print no emb ,,walnut eternal-1188 pcs 1 clr rub 1 clr foil and no emb |  |  | NFL2 |  |  | Po Sheet Due | 596 | 183 | -413 | 0 | -3966 | [11 empty] | 46 | Oct'1
BS-ONL | 45347 2nd | 15368855 | 1908 | 445 | 2026-08-13 | 2026-08-17 | SS v nK TS | TS |  |  | 2026-09-02 | 2026-09-08 | 2026-09-14 | 2026-09-28 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-08 | 2026-10-10 | 2026-10-12 | 2026-10-14 | 2026-10-19 |  |  |  |  | 2026-10-21 | 2026-10-23 |  |  | 2026-10-26 | 2026-10-28 | 2026-10-31 | 2026-11-16 | 2026-11-18 | 95 | F | Zahirul | Chest |  | corsage-900 pcs ,,black-1008 pcs both combo 1 clr rub 1 clr gltr print |  |  | NFL1 |  |  | Po Sheet Due | 445 | 190 | -255 | 0 | -1908 | [11 empty] | 47 | Oct'1
OVS SPA | 48314 | 271PJA027PYJ7-6111 | 14678 | 2581 | 2026-07-28 | 2026-08-11 | SS TS w frt placket btn and AOP elated pajama set | Top & BTM |  |  | 2026-09-10 | 2026-09-24 | 2026-09-25 | 2026-10-09 | 2026-10-10 | 2026-10-20 | 2026-10-23 | 2026-10-16 | 2026-10-23 | 2026-10-24 | 2026-10-31 | 2026-10-30 | 2026-11-06 |  |  |  |  | 2026-11-04 | 2026-11-13 |  |  | 2026-11-14 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-18 | 113 | N/2 | Basir | Chest |  | ochid top-3013 pcs 2 clr pig ,,orchid btm-3013 pcs no print ,,azure top-2613 pcs 3 clr pig ,,white btm-2613 pcs no print ,,blue top-1713 pcs 3 clr pig ,,white btm-1713 pcs no print | AOP |  | NCL |  |  | File Due | 2581 | 0 | -2581 | 0 | -14678 | [11 empty] | 47 | Oct'3
OVS SPA | 48315 | 271PJA026PYJ12-6111 | 11512 | 2043 | 2026-07-28 | 2026-08-11 | SS TS w frill at slve and AOP elated pajama set | Top & BTM |  |  | 2026-09-10 | 2026-09-24 | 2026-09-22 | 2026-10-09 | 2026-10-10 | 2026-10-22 | 2026-10-27 | 2026-10-20 | 2026-10-26 | 2026-10-27 | 2026-11-02 | 2026-11-02 | 2026-11-07 |  |  |  |  | 2026-11-06 | 2026-11-12 |  |  | 2026-11-13 | 2026-11-14 | 2026-11-16 | 2026-11-18 | 2026-11-18 | 113 | N/2 | Basir | Chest |  | violet top-3043 pcs 4 clr pig print ,pink btm-3043 pcs no print ,,rose top-3043 pcs no print ,,taupe btm- 2713 pcs no print | AOP |  | NCL |  |  | File Due | 2043 | 0 | -2043 | 0 | -11512 | [11 empty] | 47 | Oct'3
OVS SPA | 48312 | 271NDG009DRS-6111 | 11482 | 3665 | 2026-07-28 | 2026-08-11 | SS TS long dress w side pkt | Dress |  |  | 2026-09-14 | 2026-09-30 | 2026-10-01 | 2026-10-17 |  |  | 2026-10-27 | 2026-10-26 | 2026-11-02 | 2026-11-03 | 2026-11-07 | [6 empty] | 2026-11-06 | 2026-11-13 |  |  | 2026-11-14 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-18 | 113 | N/2 | Basir | [5 empty] | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -11482 | [11 empty] | 47 | Nov'1
OVS SPA | 48313 | 271NDG012PRLR2-6111 | 9472 | 2257 | 2026-07-28 | 2026-08-11 | AOP Dress w front placket btm pkt and btm cut&sew | Dress |  |  | 2026-09-10 | 2026-09-22 | 2026-09-24 | 2026-10-09 | 2026-10-10 | 2026-10-21 | 2026-10-26 | 2026-10-24 | 2026-10-29 | 2026-10-30 | 2026-11-04 | [6 empty] | 2026-11-04 | 2026-11-12 |  |  | 2026-11-13 | 2026-11-14 | 2026-11-16 | 2026-11-18 | 2026-11-18 | 113 | N/3 | Basir |  |  |  | AOP |  | NCL |  |  | File Due | 2257 | 0 | -2257 | 0 | -9472 | [11 empty] | 47 | Oct'3
OVS SPA | 48316 | 271NDG010LDY6-6111 | 4404 | 1343 | 2026-07-28 | 2026-08-11 | AOP SS Dress w front placket chest pleat and btn | Dress |  |  | 2026-09-18 | 2026-09-30 | 2026-10-01 | 2026-10-13 | 2026-10-14 | 2026-10-24 | 2026-10-26 | 2026-10-28 | 2026-11-02 | 2026-11-03 | 2026-11-04 | [6 empty] | 2026-11-05 | 2026-11-11 |  |  | 2026-11-12 | 2026-11-14 | 2026-11-16 | 2026-11-18 | 2026-11-18 | 113 | N/3 | Basir |  |  |  | AOP |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -4404 | [11 empty] | 47 | Nov'1
OVS SPA | 48317 | 271NDG010LDY13-6111 | 6051 | 2108 | 2026-07-28 | 2026-08-11 | AOP SS cut & sew dress w lace and key hole self string gathering hem | Dress |  |  | 2026-09-10 | 2026-09-22 | 2026-09-23 | 2026-10-09 | 2026-10-10 | 2026-10-22 | 2026-10-26 | 2026-10-24 | 2026-10-29 | 2026-10-30 | 2026-11-03 | [6 empty] | 2026-11-04 | 2026-11-11 |  |  | 2026-11-12 | 2026-11-14 | 2026-11-16 | 2026-11-18 | 2026-11-18 | 113 | N/3 | Basir |  |  |  | AOP | Lace | NCL |  |  | File Due | 2108 | 0 | -2108 | 0 | -6051 | [11 empty] | 47 | Oct'3
OVS SPA | 48318 | 271PJA025SB1L-6111 | 16678 | 2717 | 2026-07-28 | 2026-08-11 | SS TS w slve lace and elated legging w btm laace | Top & BTM |  |  | 2026-09-14 | 2026-09-30 | 2026-10-01 | 2026-10-17 |  |  | 2026-10-24 | 2026-10-21 | 2026-10-26 | 2026-10-27 | 2026-11-04 | [6 empty] | 2026-11-03 | 2026-11-13 |  |  | 2026-11-14 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-18 | 113 | Q1+P | Basir |  |  |  |  | Lace | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -16678 | [11 empty] | 47 | Oct'3
OVS SPA | 48441 | 271PJA031MZ1-6111 | 4438 | 703 | 2026-07-28 | 2026-08-11 | AOP SS Shirt w front pkt collar full placket btn and waist belt shorts w tussel string | Top & BTM |  |  | 2026-09-21 | 2026-09-30 | 2026-10-01 | 2026-10-13 | 2026-10-14 | 2026-10-24 | 2026-11-02 | 2026-10-31 | 2026-11-05 | 2026-11-06 | 2026-11-09 | [6 empty] | 2026-11-10 | 2026-11-14 |  |  | 2026-11-16 | 2026-11-17 | 2026-11-19 | 2026-11-20 | 2026-11-20 | 115 | N/2 | Basir |  |  |  | AOP |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -4438 | [11 empty] | 47 | Nov'1
OVS SPA | 48445 | 271NDG028MCH5-6111 | 4616 | 1289 | 2026-07-28 | 2026-08-11 | SS TS w front poket | TS |  |  | 2026-09-25 | 2026-10-09 | 2026-10-10 | 2026-10-22 |  |  | 2026-10-26 | 2026-10-28 | 2026-11-02 | 2026-11-03 | 2026-11-04 | [6 empty] | 2026-11-05 | 2026-11-11 |  |  | 2026-11-12 | 2026-11-14 | 2026-11-16 | 2026-11-20 | 2026-11-20 | 115 | N/2 | Basir | [5 empty] | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -4616 | [11 empty] | 47 | Nov'1
OVS SPA | 48444 | 271PJA047MCH4-6111 | 9244 | 2471 | 2026-08-07 | 2026-08-17 | SS TS w Pkt applique flower and AOP elasted legging w self drawstring | Top & BTM |  |  | 2026-09-17 | 2026-09-30 | 2026-10-01 | 2026-10-13 | 2026-10-14 | 2026-10-23 | 2026-10-24 | 2026-10-26 | 2026-10-31 | 2026-11-02 | 2026-11-05 | [6 empty] | 2026-11-05 | 2026-11-12 |  |  | 2026-11-13 | 2026-11-16 | 2026-11-18 | 2026-11-20 | 2026-11-20 | 105 | N/2 | Basir |  |  |  | AOP |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -9244 | [11 empty] | 47 | Nov'1
GBX-New Look | 48543 2nd | 9148519 | 14870 | 3491 | 2026-08-20 | 2026-08-14 | Skirt w three layer frill | Skirt |  |  | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-10-03 |  |  | 2026-10-03 | 2026-10-03 |  | 2026-10-08 | 2026-10-14 | [6 empty] | 2026-10-12 | 2026-10-30 |  |  | 2026-10-31 | 2026-11-02 | 2026-11-03 | 2026-11-07 | 2026-11-08 | 79 | N/2 | Sifat | [5 empty] | NCL |  |  | Po Sheet Due | 3491 | 0 | -3491 | 0 | -14870 | [11 empty] | 46 | Oct'1
GBX-TM Lewin | 48560 | Herringbone QZIP Polo | 2100 | 1176 | 2026-08-10 | 2026-08-17 | LS mens Polo Shirt w half zipper | Polo |  |  | 2026-09-01 | 2026-09-13 | 2026-09-15 | 2026-10-04 |  |  | 2026-10-07 | 2026-10-07 | 2026-10-14 | 2026-10-16 | 2026-10-19 | [6 empty] | 2026-10-19 | 2026-10-23 |  |  | 2026-10-26 | 2026-10-28 | 2026-10-30 | 2026-11-05 | 2026-11-05 | 87 | N/1 | Shofi | [5 empty] | NCL |  |  | File Due | 1336 | 0 | -1336 | 0 | -2100 | [11 empty] | 45 | Oct'2
GBX-TM Lewin | 48563 | LS Slve Rugby Polo | 1590 | 1113 | 2026-08-12 | 2026-08-17 | LS cut&sew Polo w placket btn bon collar slve cuff & side slit | Polo |  |  | 2026-09-01 | 2026-09-10 | 2026-09-13 | 2026-09-30 |  |  | 2026-10-09 | 2026-10-09 | 2026-10-15 | 2026-10-17 | 2026-10-20 | [6 empty] | 2026-10-20 | 2026-10-24 |  |  | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-11-05 | 2026-11-05 | 85 | N/3 | Shofi | [5 empty] | NCL |  |  | File Due | 742 | 0 | -742 | 0 | -1590 | [11 empty] | 45 | Oct'2
GBX-TM Lewin | 48562 | SS KNIT POLO | 2650 | 1176 | 2026-08-10 | 2026-08-17 | SS POLO Shirt w Placket btn side slit | Polo |  |  | 2026-09-05 | 2026-09-15 | 2026-09-20 | 2026-10-04 |  |  | 2026-10-08 | 2026-10-08 | 2026-10-15 | 2026-10-17 | 2026-10-19 | [6 empty] | 2026-10-21 | 2026-10-24 |  |  | 2026-10-27 | 2026-10-28 | 2026-10-30 | 2026-11-05 | 2026-11-05 | 87 | N/1 | Shofi | [5 empty] | NCL |  |  | File Due | 1175 | 0 | -1175 | 0 | -2650 | [11 empty] | 45 | Oct'2
GBX-TM Lewin | 48564 | SS Rugby Polo | 1590 | 940 | 2026-08-10 | 2026-08-17 | SS Polo Shirt w bon collar placket btn | Polo |  |  | 2026-09-03 | 2026-09-12 | 2026-09-17 | 2026-10-02 |  |  | 2026-10-06 | 2026-10-06 | 2026-10-13 | 2026-10-15 | 2026-10-16 | [6 empty] | 2026-10-19 | 2026-10-23 |  |  | 2026-10-26 | 2026-10-28 | 2026-10-30 | 2026-11-05 | 2026-11-05 | 87 | N/3 | Shofi | [5 empty] | NCL |  |  | File Due | 939 | 0 | -939 | 0 | -1590 | [11 empty] | 45 | Oct'2
GBX-TM Lewin | 48559 | LS Testured Zip Polo | 1995 | 1334 | 2026-08-10 | 2026-08-17 | LS Polo Shirt w half zipper collar placket btn and side slit | Polo |  |  | 2026-09-05 | 2026-09-15 | 2026-09-20 | 2026-10-05 |  |  | 2026-10-10 | 2026-10-10 | 2026-10-16 | 2026-10-19 | 2026-10-20 | [6 empty] | 2026-10-22 | 2026-10-26 |  |  | 2026-10-28 | 2026-10-30 | 2026-10-31 | 2026-11-05 | 2026-11-05 | 87 | N/1 | Shofi | [5 empty] | NCL |  |  | File Due | 1335 | 0 | -1335 | 0 | -1995 | [11 empty] | 45 | Oct'2
BS-ONL | 48622 | 15391921 | 5490 | 802 | 2026-08-15 | 2026-08-15 | SS O nk TS w metal buckle and mesh bow attach | TS |  |  | 2026-09-10 | 2026-09-16 | 2026-09-23 | 2026-10-10 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-26 | 2026-10-28 | 2026-10-30 | 2026-11-01 | 2026-11-06 | 2026-11-06 | 2026-11-09 | 2026-11-12 | 2026-11-20 | 2026-11-09 | 2026-11-12 |  |  | 2026-11-23 | 2026-11-25 | 2026-11-28 | 2026-12-14 | 2026-12-16 | 121 | O2 | Jannati | Chest,HP |  | c.dan-2478 pcs 1 clr pig print and 1 size HP Stone and 2 metal buckle Hand sewing ,,LGM-1590 pcs photo print w 2 clr gltr no stone,,pink-1422 pcs photo print w 2 clr gltr and 1 mesh bow attach at sewing |  | 1 combo Hand sewing ring buckle | NFL2 |  |  | CAD | 802 | 570 | -232 | 0 | -5490 | [11 empty] | 51 | Oct'3 |  |  | 15.09.26
BS-ONL | 48160 3rd | 15317989 | 18968 | 3010 | 2026-08-13 | 2026-08-15 | SS o nk TS w frt pkt | TS |  |  | 2026-09-12 | 2026-09-22 | 2026-10-05 | 2026-10-20 |  |  | 2026-10-25 | 2026-10-25 |  | 2026-11-02 | 2026-11-07 |  |  | 2026-11-23 | 2026-11-30 | 2026-11-05 | 2026-11-16 | 2026-11-16 | 2026-11-26 |  |  | 2026-12-02 | 2026-12-04 | 2026-12-07 | 2026-12-14 | 2026-12-16 | 123 | N1 | Mainul |  | Chest | black lovely-6520 pcs no print 6 clr flat emb at chest 1 clr flat emb at pkt and flower hand sewing at chest,,white cattitate-1008 pcs chest and pkt 1 clr pig print no emb ,,white apologies-1008 pcs chest and pkt 1 clr pig print no emb ,,c.and wild-6712 pcs no print pkt 6 clr flat emb ,,anise wild-3720 pcs no print 8 clr flat emb at pkt |  | 1 combo hand sewing flower | NFL2 |  |  | CAD | 0 | 0 | 0 | 0 | -18968 | [11 empty] | 51 | Nov'1 |  |  | 16.09.26
BS-ONL | 46205 6th | 15382230 | 20382 | 3041 | 2026-08-13 | 2026-08-17 | SS o nk TS | TS |  |  | 2026-08-25 | 2026-09-06 | 2026-09-12 | 2026-09-30 |  |  | 2026-10-01 | 2026-10-01 |  | 2026-10-08 | 2026-10-14 | 2026-10-12 | 2026-10-20 |  |  | 2026-10-17 | 2026-11-02 | 2026-11-02 | 2026-11-14 |  |  | 2026-11-17 | 2026-11-19 | 2026-11-24 | 2026-12-14 | 2026-12-16 | 123 | N1 | Mainul | Chest | Chest | black flower-1976 pcs 6 clr rub 3 clr seq emb ,,c.dan flower-1976 pcs 6 clr pig 4 clr seq emb ,,,c.dan flamingo-3898 pcs photo print and 1 clr seq emb ,,c.dan mini flowwer-920 pcs 4 clr pig print and 2 clr seq emb,,anise mini flower-920 pcs 4 clr pig 2 clr seq emb ,,jadeite flamingo-3898 pcs photo print 1 clr seq emb ,,blue flower-1976 pcs 6 clr pig 3 clr seq emb ,,pink mini flower-920 pcs 4 clr pig 3 clr seq emb ,,pink flamingo-3898 pcs photo print 1 clr seq emb |  |  | NFL2 |  |  | CAD | 3042 | 2171 | -871 | 0 | -20382 | [11 empty] | 51 | Oct'1 |  |  | 16.09.26
BS-ONL | 44932 2nd | 15372417/15378313 | 18324 | 3793 | 2026-08-13 | 2026-08-17 | SS TS W SLV CUFF FOLDTUCK & BTM raw edge | TS |  |  | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-10-05 |  |  | 2026-10-09 | 2026-10-09 | 2026-10-15 | 2026-10-17 | 2026-10-24 |  |  |  |  | 2026-10-21 | 2026-11-02 | 2026-11-02 | 2026-11-16 |  |  | 2026-11-19 | 2026-11-20 | 2026-11-25 | 2026-12-14 | 2026-12-16 | 123 | K | Mainul |  | CHEST | anise-6180 pcs,,candy-6180 pcs,,coral-5964 pcs all combo patch attach applique emb |  |  | NFL2 |  |  | Po Sheet Due | 3795 | 3019 | -776 | 0 | -18324 | [11 empty] | 51 | Oct'2
BS-ONL | 45199 2nd | 15372216/15378312 | 17664 | 4135 | 2026-08-13 | 2026-08-17 | SWTY PANT W PKT & drawstring | PANT |  |  | 2026-09-10 | 2026-09-22 | 2026-10-01 | 2026-10-18 |  |  | 2026-10-21 | 2026-10-21 | 2026-10-27 | 2026-10-30 | 2026-11-05 |  |  |  |  | 2026-11-03 | 2026-11-11 | 2026-11-11 | 2026-11-20 |  |  | 2026-11-23 | 2026-11-25 | 2026-11-28 | 2026-12-14 | 2026-12-16 | 123 | H | Mainul |  | Thigh | anise-5952 pcs,,candy-5952 pcs,,coral-5760 pcs all combo patch attach applique emb |  | po rev 15/08 | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -17664 | [11 empty] | 51 | Oct'3
BS-ONL | 45200 2nd | 15372414 | 4164 | 1923 | 2026-08-13 | 2026-08-17 | LS o nk Swt Shirt w cuff btm rib | Swt Shirt |  |  | 2026-09-10 | 2026-09-17 | 2026-09-22 | 2026-10-10 |  |  | 2026-10-17 | 2026-10-17 | 2026-10-24 | 2026-10-27 | 2026-10-30 |  |  |  |  | 2026-11-03 | 2026-11-07 | 2026-11-10 | 2026-11-14 |  |  | 2026-11-17 | 2026-11-20 | 2026-11-24 | 2026-12-14 | 2026-12-16 | 123 | N2 | Mainul |  | Chest | anise-1460 pcs,,candy-1460 pcs,,coral-1244 pcs all combo patch attach applique emb |  |  | NFL2 |  |  | Po Sheet Due | 1922 | 0 | -1922 | 0 | -4164 | [11 empty] | 51 | Oct'3
BS-ONL | 45357 2nd | 15367767 | 5082 | 1070 | 2026-08-12 | 2026-08-17 | SS o nk TS | TS |  |  | 2026-10-03 | 2026-10-12 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-04 | 2026-11-04 | 2026-11-10 | 2026-11-12 | 2026-11-14 | 2026-11-14 | 2026-11-19 |  |  | 2026-11-18 | 2026-11-28 | 2026-12-01 | 2026-12-05 |  |  | 2026-12-08 | 2026-12-10 | 2026-12-14 | 2026-12-21 | 2026-12-23 | 131 | ZA2 | Zahirul | Chest | Chest | Anise-1928 pcss photo print w 1 clr pig and 3 size seq emb ,,white -1820 pcs photo print w 1 clr pig and 3 size seq emb,,brown-1334 pcs chest all over photo print w 1 clr pig and 3 size seq emb | YD |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -5082 | [11 empty] | 52 | Nov'2
BS-ONL | 48641 | 15392866 | 526 | 120 | 2026-08-12 | 2026-08-17 | SS o nk TS | TS |  |  | 2026-10-01 | 2026-10-05 | 2026-10-12 | 2026-10-24 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-07 | 2026-11-11 | 2026-11-12 | 2026-11-14 | 2026-11-17 |  |  |  |  | 2026-11-19 | 2026-11-20 |  |  | 2026-11-23 | 2026-11-25 | 2026-11-28 | 2026-12-21 | 2026-12-23 | 131 | T1 | Zahirul | Chest |  | pink-526 pcs 1 clr pig print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -526 | [11 empty] | 52 | Nov'2
BS-ONL | 48188 3rd | 15299502 | 2080 | 410 | 2026-08-19 | 2026-08-20 | SS O nk TS | TS |  |  | 2026-08-22 | 2026-08-25 | 2026-08-28 | 2026-09-02 |  |  | 2026-09-01 | 2026-09-01 |  | 2026-09-04 | 2026-09-05 | 2026-09-05 | 2026-09-07 |  |  |  |  | 2026-09-08 | 2026-09-11 |  |  | 2026-09-12 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-16 | 26 | O1 | Zahirul | Chest |  | black-1040 pcs,,C.dan-1040 pcs all combo chest 1 clr gltr print |  |  | NFL2 |  |  | Cut Ok | 410 | 410 | 0 | 2142 | 62 | [11 empty] | 38 | Sep'1 |  |  | 22.08.26
BS-ONL | 29251 14th | 15247223 | 300 | 160 | 2026-08-18 | 2026-08-19 | MATERNITY CUT & SEW LEGGING | LEGGING |  |  | 2026-08-24 | 2026-08-27 | 2026-09-01 | 2026-09-09 |  |  | 2026-09-05 | 2026-09-05 |  | 2026-09-11 | 2026-09-11 | [6 empty] | 2026-09-14 | 2026-09-15 |  |  | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-23 | 34 | P | Zahirul | [5 empty] | NFL2 |  |  | Cut Ok | 160 | 160 | 0 | 643 | 343 | [11 empty] | 39 | Sep'2 |  |  | 22.08.26
BS-ONS | 45964 13th | 22039968 | 6000 | 4116 | 2026-08-19 | 2026-08-21 | LS High nk Haalf Zipp Swt shirt | Swt Shirt |  |  | 2026-08-15 | 2026-08-25 | 2026-08-25 | 2026-09-12 |  |  | 2026-09-10 | 2026-09-07 |  | 2026-09-12 | 2026-09-15 | [6 empty] | 2026-09-15 | 2026-09-23 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-21 | 2026-09-23 | 40 | R | Shakel | [5 empty] | NFL2 |  |  | Cut Run | 4119 | 2268 | -1851 | 4065 | -1935 | [11 empty] | 39 | Sep'2 |  |  | 05.09.26
BS-ONS | 43629 5th | 22029227 | 7040 | 6200 | 2026-08-19 | 2026-08-21 | LS Hoody jacket w full zipper and kangro pkt | Hoody |  |  | 2026-08-23 | 2026-08-31 | 2026-08-30 | 2026-08-14 |  |  | 2026-09-10 | 2026-09-10 |  | 2026-09-14 | 2026-09-17 | [6 empty] | 2026-09-16 | 2026-09-24 |  |  | 2026-09-25 | 2026-09-26 | 2026-09-28 | 2026-09-28 | 2026-09-30 | 40 | X | Shakel | [5 empty] | NFL3 |  |  | Need Cut | 6200 | 1240 | -4960 | 0 | -7040 | [11 empty] | 40 | Sep'2 |  |  | 12.09.26
BS-ONS | 42483 7th | 22035827 | 7548 | 1771 | 2026-08-15 | 2026-08-18 | MENS SS R NK TS | TS |  |  | 2026-08-19 | 2026-08-24 | 2026-08-26 | 2026-09-03 |  |  | 2026-09-01 | 2026-08-28 |  | 2026-09-02 | 2026-09-04 | 2026-09-04 | 2026-09-08 |  |  |  |  | 2026-09-08 | 2026-09-11 |  |  | 2026-09-12 | 2026-09-12 | 2026-09-14 | 2026-09-19 | 2026-09-21 | 35 | D1 | Shovon | FR,BK |  | black hermony- 906 pcs frt back 1 clr rub ,,jet black hand eye- 1106 pcs frt back 1 clr rub print ,,jet black valencia- 806 pcs frt back photo print ,,jet black mount fuji -1106 pcs frt back 2 clr rub ,,white -906 pcs Frt back 1 clr rub print ,,dark navy-906 pcs frt 1 clr rub back 2 clr rub,,egret-906 pcs frt back 1 clr rub,,,black brocken-906 pcs frt 1 clr rub back 1 clr photo black white print |  | sub plan print as usual out | NFL1 |  |  | Cut Run | 1772 | 1657 | -115 | 6634 | -914 | [11 empty] | 39 | Sep'1 |  |  | 28.08.26
BS-ONL | 22040 27th | 152191323 | 3300 | 680 | 2026-08-17 | 2026-08-19 | LDS 2 PACK LEGGING | LEGGING |  |  | 2026-10-24: 2026-09-07; 2026-10-26: 2026-09-02; 2026-11-02: 2026-09-10; 2026-11-05: 2026-09-12 | [6 empty] | 2026-09-15 | 2026-09-18 |  |  | 2026-09-21 | 2026-09-23 | 2026-09-24 | 2026-09-28 | 2026-09-30 | 42 | M | Imran |  |  |  |  | Stock fab from 43465/3300 pcs need sewing | NFL2 |  |  | Cut Ok | 0 | 0 | 0 | 3348 | 48 | [11 empty] | 40 | Sep'1 |  |  | 02.09.26
BS-ONL | 26030 22th | 15308926 | 3816 | 896 | 2026-08-14 | 2026-08-20 | LDS SS TS W BK CUT & SEW & SIDE SLEET | TS |  |  | 2026-08-24 | 2026-08-29 | 2026-09-01 | 2026-09-07 |  |  | 2026-09-03 | 2026-09-02 |  | 2026-09-07 | 2026-09-08 | [6 empty] | 2026-09-08 | 2026-09-11 |  |  | 2026-09-12 | 2026-09-14 | 2026-09-14 | 2026-09-12 | 2026-09-14 | 29 | U | Dalim | [5 empty] | NFL3 |  |  | Cut Ok | 896 | 865 | -31 | 3906 | 90 | [11 empty] | 38 | Sep'1 |  |  | 02.09.26
BS-ONL | 43969 40th | 15270390 | 34943 | 5649 | 2026-08-15 | 2026-08-20 | SS o nk TS | TS |  |  | 2026-08-24 | 2026-09-05 | 2026-09-02 | 2026-09-14 |  |  | 2026-09-10 | 2026-09-07 |  | 2026-09-11 | 2026-09-16 | [6 empty] | 2026-09-14 | 2026-09-25 |  |  | 2026-09-25 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-28 | 42 | ZA2 | Dalim | [5 empty] | NFL3 |  |  | Need Cut | 5649 | 3307 | -2342 | 0 | -34943 | [11 empty] | 40 | Sep'2 |  |  | 02.09.26
BS-ONL | 27204 63th | 15323159 | 2070 | 544 | 2026-08-14 | 2026-08-20 | LS o nk TS | TS |  |  | 2026-09-24 | 2026-09-28 | 2026-09-01 | 2026-09-09 |  |  | 2026-09-08 | 2026-09-07 |  | 2026-09-11 | 2026-09-12 | [6 empty] | 2026-09-15 | 2026-09-16 |  |  | 2026-09-17 | 2026-09-19 | 2026-09-19 | 2026-09-19 | 2026-09-21 | 36 | G1 | Dalim | [5 empty] | NFL1 |  |  | Need Cut FB | 543 | 30 | -513 | 0 | -2070 | [11 empty] | 39 | Sep'2 |  |  | 07.09.26
UTG-AF | 48704 | BAD3299 | 500 | 95 | 2026-08-19 | 2026-08-20 | Tank Top w placket and flat knit tie band | Tank Top | 2026-08-24 | 2026-08-29 | 2026-08-29 | 2026-09-04 | 2026-09-04 | 2026-09-10 |  |  | 2026-09-04 | 2026-09-05 | 2026-09-09 | 2026-09-10 | 2026-09-11 | [6 empty] | 2026-09-12 | 2026-09-14 |  |  | 2026-09-15 | 2026-09-16 | 2026-09-18 | 2026-09-19 | 2026-09-21 | 31 | N/2 | Rana |  |  |  | YD |  | NCL |  |  | Need Test Cut | 95 | 0 | -95 | 0 | -500 | [11 empty] | 39 | Sep'1
UTG-AF | 48702 | BAD3297 | 500 | 265 | 2026-08-19 | 2026-08-20 | Strap dress w ring buckle | Dress |  |  | 2026-08-24 | 2026-08-28 | 2026-08-29 | 2026-09-07 |  |  | 2026-09-04 | 2026-09-05 | 2026-09-09 | 2026-09-10 | 2026-09-11 | [6 empty] | 2026-09-12 | 2026-09-14 |  |  | 2026-09-15 | 2026-09-16 | 2026-09-18 | 2026-09-19 | 2026-09-21 | 31 | N/2 | Rana | [5 empty] | NCL |  |  | Need Test Cut | 265 | 0 | -265 | 0 | -500 | [11 empty] | 39 | Sep'1
UTG-AF | 48703 | BAD3298 | 500 | 145 | 2026-08-19 | 2026-08-20 | LS Love Nk TS | TS |  |  | 2026-08-24 | 2026-08-28 | 2026-08-29 | 2026-09-07 |  |  | 2026-09-04 | 2026-09-05 | 2026-09-09 | 2026-09-10 | 2026-09-11 | [6 empty] | 2026-09-12 | 2026-09-14 |  |  | 2026-09-15 | 2026-09-16 | 2026-09-18 | 2026-09-19 | 2026-09-21 | 31 | N/3 | Rana | [5 empty] | NCL |  |  | Need Test Cut | 145 | 0 | -145 | 0 | -500 | [11 empty] | 39 | Sep'1
BS-ONS | 26828 80th | 22029226 | 1000 | 654 | 2026-08-19 | 2026-08-21 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-09-07 | 2026-09-12 | 2026-09-15 | 2026-09-30 |  |  | 2026-10-05 | 2026-10-05 |  | 2026-10-10 | 2026-10-12 | [6 empty] | 2026-10-14 | 2026-10-15 |  |  | 2026-10-16 | 2026-10-17 | 2026-10-20 | 2026-10-26 | 2026-10-28 | 68 | A | Shakel | [5 empty] | NFL1 |  |  | Need Cut FB | 654 | 0 | -654 | 0 | -1000 | [11 empty] | 44 | Oct'1 |  |  | 25.08.26
BS-ONL | 48615 | 15390900 | 32379 | 4508 | 2026-08-15 | 2026-08-18 | YD ,AOP & Solid SL V nk Tank Top | Tank Top | 2026-08-25 | 2026-08-30 | 2026-09-23 | 2026-09-07 | 2026-09-02 | 2026-09-15 | 2026-09-15 | 2026-09-21 | 2026-09-16 | 2026-09-16 | 2026-09-21 | 2026-09-22 | 2026-09-28 | 2026-09-25 | 2026-10-01 |  |  |  |  | 2026-10-01 | 2026-10-12 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 65 | ZA1 | Jannati | Nk |  | 12 combo nk Label Print | YD & AOP |  | NFL3 |  |  | Need Test Cut | 4508 | 0 | -4508 | 0 | -32379 | [11 empty] | 43 | Sep'3 |  |  | 07.09.26
BS-ONL | 48613 | 15391465 | 3706 | 1073 | 2026-08-15 | 2026-08-19 | LS o nk TS w front nk slit w woven frog closure btn | TS |  |  | 2026-09-01 | 2026-09-05 | 2026-09-10 | 2026-09-25 |  |  | 2026-09-28 | 2026-09-28 | 2026-10-03 | 2026-10-05 | 2026-10-06 | [6 empty] | 2026-10-08 | 2026-10-12 |  |  | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 65 | Q | Jannati | [5 empty] | NFL2 |  |  | File Due | 1073 | 0 | -1073 | 0 | -3706 | [11 empty] | 43 | Oct'1
BS-ONL | 48610 1st | 15391574 | 40257 | 5670 | 2026-08-15 | 2026-08-19 | SS o nk TS w btm Lace attach | TS |  |  | 2026-08-22 | 2026-09-04 | 2026-09-01 | 2026-09-21 |  |  | 2026-09-19 | 2026-09-19 | 2026-09-24 | 2026-09-26 | 2026-10-03 | [6 empty] | 2026-10-01 | 2026-10-15 |  |  | 2026-10-17 | 2026-10-17 | 2026-10-20 | 2026-10-24 | 2026-10-26 | 70 | V | Jannati |  |  |  |  | Lace | NFL3 |  |  | Size Set Run | 5670 | 3855 | -1815 | 0 | -40257 | [11 empty] | 44 | Sep'3 |  |  | 04.09.26
BS-ONL | 48612 | 15267224 | 9270 | 2339 | 2026-08-15 | 2026-08-19 | AOP SS O Nk Rib TS w slve btm letus | TS |  |  | 2026-08-25 | 2026-08-07 | 2026-09-07 | 2026-09-14 | 2026-09-17 | 2026-09-25 | 2026-09-25 | 2026-09-25 | 2026-10-01 | 2026-10-02 | 2026-10-05 | [6 empty] | 2026-10-05 | 2026-10-10 |  |  | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-19 | 2026-10-21 | 65 | N2 | Jannati |  |  |  | AOP |  | NFL2 |  |  | Need Cut | 2362 | 1351 | -1011 | 0 | -9270 | [11 empty] | 43 | Oct'1 |  |  | 04.09.26
BS-ONL | 48616 | 15390901 | 5196 | 903 | 2026-08-15 | 2026-08-20 | AOP & Solid SS V nk elastic Gathering TS | TS |  |  | 2026-08-28 | 2026-09-03 | 2026-09-06 | 2026-09-18 | 2026-09-18 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-29 | 2026-10-01 | 2026-10-03 | 2026-10-03 | 2026-10-07 |  |  |  |  | 2026-10-08 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-24 | 2026-10-16 | 70 | Z | Jannati | Nk |  | 6 combo nk label print | AOP |  | NFL3 |  |  | Need Test Cut | 903 | 0 | -903 | 0 | -5196 | [11 empty] | 42 | Oct'1 |  |  | 07.09.26
BS-ONL | 48532 2nd | 15391922 | 979 | 226 | 2026-08-18 | 2026-08-20 | YD SS O nk TS w Hand sewn beads | TS | 2026-08-25 | 2026-08-30 | 2026-09-05 | 2026-09-11 | 2026-09-14 | 2026-09-18 |  |  | 2026-09-25 | 2026-09-17 |  | 2026-09-21 | 2026-09-22 | 2026-09-24 | 2026-09-26 | 2026-09-28 | 2026-10-07 |  |  | 2026-10-10 | 2026-10-12 |  |  | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-24 | 2026-10-26 | 67 | F | Jannati | Fr,Bk |  | phanthom stripe -581 pcs frt 2 clr rub back photo print w 2 clr rub hand sewn beads,, Primrose pink-398 pcs frt photo print w 2 clr rub and hand sewn beads back no print |  | Hand sewn beads | NFL1 |  |  | Need Cut | 226 | 127 | -99 | 0 | -979 | [11 empty] | 44 | Sep'3 |  |  | 31.08.26
BS-ONL | 48660 | 15392243 | 1680 | 327 | 2026-08-13 | 2026-08-19 | SS o nk TS | TS |  |  | 2026-08-27 | 2026-08-31 | 2026-09-03 | 2026-09-16 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-22 | 2026-09-24 | 2026-09-25 | 2026-09-28 | 2026-09-30 |  |  | 2026-10-02 | 2026-10-08 | 2026-10-12 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-21 | 67 | N1 | Mainul | Chest | Chest | c.dan flowers-1044 pcs 7 clr pig print and 7 clr flat 4 clr terry emb ,,c.dan hearts-636 pcs no print 2 clr terry emb |  |  | NFL2 |  |  | File Due | 327 | 0 | -327 | 0 | -1680 | [11 empty] | 43 | Sep'3
BS-ONL | 48663 | 15393265 | 8352 | 1613 | 2026-08-13 | 2026-08-19 | SS o nk TS | TS |  |  | 2026-08-25 | 2026-08-31 | 2026-09-02 | 2026-09-15 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-21 | 2026-09-23 | 2026-09-26 |  |  |  |  | 2026-09-25 | 2026-10-06 | 2026-10-07 | 2026-10-10 |  |  | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-19 | 2026-10-21 | 67 | W2 | Mainul |  | Fr & Bk | c.dan-4176 pcs,,pink-4176 pcs both combo frt back 1 clr flat 6 clr terry emb |  |  | NFL3 |  |  | File Due | 1614 | 1572 | -42 | 0 | -8352 | [11 empty] | 43 | Sep'3
BS-ONL | 48661 | 15392580 | 627 | 104 | 2026-08-13 | 2026-08-19 | SS o nk TS | TS |  |  | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-18 |  |  | 2026-09-23 | 2026-09-23 | 2026-09-29 | 2026-10-01 | 2026-10-01 |  |  |  |  | 2026-10-03 | 2026-10-08 | 2026-10-12 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-21 | 67 | N1 | Mainul |  | AOE | white roses-627 pcs frt both slve 5 clr flat all over emb |  |  | NFL2 |  |  | File Due | 104 | 104 | 0 | 0 | -627 | [11 empty] | 43 | Oct'1
BS-ONL | 48656 | 15312683 | 1752 | 1128 | 2026-08-13 | 2026-08-19 | LS Swt hoody w rib | Hoody |  |  | 2026-08-25 | 2026-09-03 | 2026-09-04 | 2026-09-18 |  |  | 2026-09-21 | 2026-09-21 | 2026-09-26 | 2026-09-28 | 2026-09-29 | 2026-10-02 | 2026-10-05 |  |  |  |  | 2026-10-07 | 2026-10-09 |  |  | 2026-10-10 | 2026-10-12 | 2026-10-13 | 2026-10-19 | 2026-10-21 | 67 | R | Mainul | Fr & Bk & Slv |  | black-1752 pcs frt 3 clr rub one slve 3 clr rub back 7 clr rub |  |  | NFL2 |  |  | File Due | 1129 | 0 | -1129 | 0 | -1752 | [11 empty] | 43 | Sep'3
BS-ONL | 48657 | 15396541 | 5016 | 1659 | 2026-08-13 | 2026-08-19 | YD SS o nk TS | TS | 2026-08-28 | 2026-09-05 | 2026-09-05 | 2026-09-19 | 2026-09-18 | 2026-09-26 |  |  | 2026-09-29 | 2026-09-29 | 2026-10-03 | 2026-10-05 | 2026-10-09 | [6 empty] | 2026-10-09 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-21 | 67 | T1 | Imran |  |  |  | YD |  | NFL3 |  |  | File Due | 1660 | 0 | -1660 | 0 | -5016 | [11 empty] | 43 | Oct'1
BS-ONL | 48659 | 15372446 | 4608 | 1924 | 2026-08-13 | 2026-08-20 | LS Swt Shirt w cuff btm rib | Swt Shirt |  |  | 2026-08-27 | 2026-09-05 | 2026-09-08 | 2026-09-22 |  |  | 2026-09-23 | 2026-09-23 | 2026-09-28 | 2026-10-01 | 2026-10-03 | 2026-10-03 | 2026-10-08 |  |  |  |  | 2026-10-09 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 67 | Q | Mainul | Fr,Bk |  | c.dan-2304 pcs ,,,pink-2304 pcs frt 1 clr rub bacj 7 clr rub |  |  | NFL2 |  |  | File Due | 1924 | 633 | -1291 | 0 | -4608 | [11 empty] | 43 | Oct'1
BS-ONL | 48658 | 15367075 | 1272 | 252 | 2026-08-13 | 2026-08-21 | SS o Nk TS | TS |  |  | 2026-09-01 | 2026-09-05 | 2026-09-13 | 2026-09-22 |  |  | 2026-09-25 | 2026-09-25 | 2026-09-30 | 2026-10-02 | 2026-10-03 | 2026-10-05 | 2026-10-07 |  |  |  |  | 2026-10-09 | 2026-10-10 |  |  | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-19 | 2026-10-21 | 67 | N2 | Mainul | Bk |  | c.dan-1272 pcs 2 clr pig print |  |  | NFL2 |  |  | CAD | 252 | 0 | -252 | 0 | -1272 | [11 empty] | 43 | Oct'1 |  |  | 16.09.26
BS-ONL | 48667 | 15396740 | 3048 | 508 | 2026-08-13 | 2026-08-21 | SS V Nk TS w nk lurex emb and shlder btn hand sewing | TS |  |  | 2026-09-01 | 2026-09-05 | 2026-09-10 | 2026-09-23 |  |  | 2026-09-25 | 2026-09-25 | 2026-09-30 | 2026-10-02 | 2026-10-05 |  |  |  |  | 2026-10-05 | 2026-10-07 | 2026-10-08 | 2026-10-12 |  |  | 2026-10-13 | 2026-10-14 | 2026-10-16 | 2026-10-19 | 2026-10-21 | 67 | U | Mainul |  | Nk | c.dna-1524 pcs,,mermaid-1524 pcs both combo nk line 1 clr lurex emb |  | Hand sewn button | NFL3 |  |  | File Due | 516 | 258 | -258 | 0 | -3048 | [11 empty] | 43 | Oct'1
BS-ONL | 48665 | 15393971 | 3288 | 476 | 2026-08-13 | 2026-08-21 | SS o nk TS w slve fold tuck | TS |  |  | 2026-09-03 | 2026-09-08 | 2026-09-12 | 2026-09-22 |  |  | 2026-09-25 | 2026-09-25 | 2026-10-01 | 2026-10-02 | 2026-10-05 |  |  |  |  | 2026-10-05 | 2026-10-08 | 2026-10-09 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-21 | 67 | K | Mainul |  | Chest | c.dan blue-1644 pcs,,c.dan pink-1644 pcs both combo 1 clr flat emb |  |  | NFL2 |  |  | CAD | 476 | 0 | -476 | 0 | -3288 | [11 empty] | 43 | Oct'1 |  |  | 16.09.26
BS-ONL | 48662 | 15393258 | 5256 | 2105 | 2026-08-13 | 2026-08-21 | LS Swt Shirt w cuff btm rib | Swt Shirt |  |  | 2026-08-26 | 2026-09-07 | 2026-09-07 | 2026-09-22 |  |  | 2026-09-22 | 2026-09-22 | 2026-09-28 | 2026-09-29 | 2026-10-01 |  |  |  |  | 2026-10-01 | 2026-10-09 | 2026-10-09 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 67 | N2 | Mainul |  | Fr & Bk | c.daan-2628 pcs,,pink-2628 pcs both combo frt back 6 clr terry 1 clr flat emb |  |  | NFL2 |  |  | File Due | 2104 | 0 | -2104 | 0 | -5256 | [11 empty] | 43 | Sep'3
BS-ONL | 48664 | 15393404 | 8262 | 1766 | 2026-08-13 | 2026-08-21 | SS o nk TS | TS |  |  | 2026-08-27 | 2026-09-07 | 2026-09-08 | 2026-09-22 |  |  | 2026-09-22 | 2026-09-22 | 2026-09-28 | 2026-09-30 | 2026-10-02 |  |  |  |  | 2026-10-02 | 2026-10-08 | 2026-10-10 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 67 | G2 | Mainul |  | Chest | c.dan-4374 pcs,,pink-3888 pcs both combo 3 clr terry 1 clr flat emb |  |  | NFL1 |  |  | CAD | 1767 | 0 | -1767 | 0 | -8262 | [11 empty] | 43 | Sep'3 |  |  | 16.09.26
BS-ONL | 48666 | 15396715 | 7728 | 1110 | 2026-08-13 | 2026-08-21 | SS o nk TS | TS |  |  | 2026-08-28 | 2026-09-04 | 2026-09-08 | 2026-09-22 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-29 | 2026-10-01 | 2026-10-03 | 2026-10-03 | 2026-10-08 |  |  |  |  | 2026-10-09 | 2026-10-13 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 67 | G2 | Mainul | Fr,Bk |  | c.dan-3864 pcs frt 2 clr pig back 4 clr rpig,,pink-3864 pcs frt 1 clr pig back 7 clr photo print |  |  | NFL1 |  |  | CAD | 1110 | 520 | -590 | 0 | -7728 | [11 empty] | 43 | Oct'1 |  |  | 16.09.26
BS-ONL | 48607 | 15387396 | 3690 | 508 | 2026-08-15 | 2026-08-18 | SS o nk TS | TS |  |  | 2026-08-28 | 2026-09-04 | 2026-09-08 | 2026-09-22 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-29 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-06 |  |  |  |  | 2026-10-08 | 2026-10-12 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-21 | 65 | T1 | Imran | Chest,Nk |  | black-1845 pcs,,birch-1845 pcs both combo 3 clr pig |  | License order | NFL3 |  |  | File Due | 508 | 0 | -508 | 0 | -3690 | [11 empty] | 43 | Oct'1
BS-ONL | 48619 | 15291465 | 26646 | 4078 | 2026-08-15 | 2026-08-19 | SS o nk TS | TS |  |  | 2026-08-25 | 2026-09-04 | 2026-09-03 | 2026-09-19 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-19 | 2026-09-22 | 2026-09-26 | 2026-09-25 | 2026-10-07 |  |  |  |  | 2026-10-07 | 2026-10-17 |  |  | 2026-10-19 | 2026-10-20 | 2026-10-22 | 2026-10-24 | 2026-10-26 | 70 | V | Imran | Fr,Bk |  | corsage-10665 pcs frt 3 clr gltr back 2 clr pig photo print 5 clr gltr print ,,Ice water-5318 pcs frt back 5 clr pig 4 clr gltr ,,c.dancer-10673 pcs frt 4 clr pig 2 clr gltr back 5 clr pig 4 clr gltr w photo print |  |  | NFL3 |  |  | Need Cut | 4078 | 3304 | -774 | 0 | -26646 | [11 empty] | 44 | Sep'3 |  |  | 05.09.26
BS-ONL | 41880 26th | 15062199/15185296 | 2876 | 989 | 2026-08-14 | 2026-08-19 | HW legging Drawstring at leg opening | Legging |  |  | 2026-09-01 | 2026-09-10 | 2026-09-10 | 2026-09-23 |  |  | 2026-09-23 | 2026-09-23 |  | 2026-09-28 | 2026-09-29 | 2026-10-01 | 2026-10-03 |  |  |  |  | 2026-10-05 | 2026-10-08 |  |  | 2026-10-09 | 2026-10-10 | 2026-10-10 | 2026-10-12 | 2026-10-14 | 59 | E | Khalid | Waist |  | 3 combo waist lettering logo print |  |  | NFL1 |  |  | CAD | 989 | 0 | -989 | 0 | -2876 | [11 empty] | 42 | Sep'3 |  |  | 17.09.26
BS-ONL | 45320 7th | 15303954 | 1940 | 881 | 2026-08-14 | 2026-08-19 | Swt pant w side pkt drawstring | PANT |  |  | 2026-08-27 | 2026-09-04 | 2026-09-07 | 2026-09-21 |  |  | 2026-09-21 | 2026-09-19 |  | 2026-09-24 | 2026-09-25 |  |  |  |  | 2026-09-28 | 2026-09-29 | 2026-10-01 | 2026-10-03 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-12 | 2026-10-14 | 59 | P | Khalid |  | Thigh | black-1940 pcs 1 clr flat emb |  |  | NFL2 |  |  | Need Cut | 881 | 881 | 0 | 0 | -1940 | [11 empty] | 42 | Sep'3 |  |  | 12.09.26
BS-ONL | 41875 17th | 15303956 | 576 | 246 | 2026-08-14 | 2026-08-19 | PANT W PKT | PANT |  |  | 2026-09-01 | 2026-09-05 | 2026-09-10 | 2026-09-24 |  |  | 2026-09-25 | 2026-09-25 |  | 2026-09-29 | 2026-09-29 |  |  |  |  | 2026-10-01 | 2026-10-01 | 2026-10-05 | 2026-10-06 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-12 | 2026-10-14 | 59 | P | Khalid |  | LEG | BLACK 576 PCS 1 CLR LETTERING EMB AT ONE LEG |  |  | NFL2 |  |  | Need Cut | 247 | 247 | 0 | 0 | -576 | [11 empty] | 42 | Sep'3
BS-ONL | 47070 2nd | 15377771 | 1823 | 269 | 2026-08-14 | 2026-08-20 | SS o nk TS | TS |  |  | 2026-08-28 | 2026-09-03 | 2026-09-07 | 2026-09-18 |  |  | 2026-09-18 | 2026-09-18 |  | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-29 |  |  |  |  | 2026-10-01 | 2026-10-03 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-12 | 2026-10-14 | 59 | K | Khalid | Fr,Bk |  | black-944 pcs front 1 clr Rub 1 clr foil back 1 clr foil,,white-879 pcs front 1 clr pig 1 clr foil back 1 clr foil |  |  | NFL2 |  |  | Size Set Run PC | 269 | 0 | -269 | 0 | -1823 | [11 empty] | 42 | Sep'3 |  |  | 12.09.26
BS-ONL | 45317 6th | 15084518 | 2193 | 605 | 2026-08-14 | 2026-08-20 | LDS 3/4 FOLD LEGGING | Legging |  |  | 2026-08-28 | 2026-09-03 | 2026-09-07 | 2026-09-18 |  |  | 2026-09-21 | 2026-09-21 |  | 2026-09-26 | 2026-09-28 | 2026-10-01 | 2026-10-02 |  |  |  |  | 2026-10-05 | 2026-10-08 |  |  | 2026-10-09 | 2026-10-10 | 2026-10-12 | 2026-10-12 | 2026-10-14 | 59 | L2 | Khalid | WAIST |  | 1 combo waist print |  |  | NFL2 |  |  | CAD | 606 | 0 | -606 | 0 | -2193 | [11 empty] | 42 | Sep'3 |  |  | 12.09.26
BS-ONL | 45328 2nd | 15374386/15366541 | 7296 | 1738 | 2026-08-14 | 2026-08-21 | High waist Legging | Legging |  |  | 2026-08-27 | 2026-09-07 | 2026-09-10 | 2026-09-21 |  |  | 2026-09-19 | 2026-09-19 | 2026-09-23 | 2026-09-24 | 2026-09-26 | 2026-09-26 | 2026-09-30 |  |  |  |  | 2026-10-01 | 2026-10-05 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-12 | 2026-10-14 | 59 | O2 | Khalid | Leg |  | black-7296 pcs 3 clr rub print at one leg |  |  | NFL2 |  |  | CAD | 1738 | 0 | -1738 | 0 | -7296 | [11 empty] | 42 | Sep'3 |  |  | 17.09.26
BS-ONL | 45330 2nd | 15374392/15388414/15388415 | 14102 | 2408 | 2026-08-14 | 2026-08-22 | SS o nk TS | TS |  |  | 2026-08-26 | 2026-09-04 | 2026-09-07 | 2026-09-17 |  |  | 2026-09-17 | 2026-09-17 | 2026-09-21 | 2026-09-22 | 2026-09-25 | 2026-09-24 | 2026-09-30 |  |  |  |  | 2026-10-01 | 2026-10-06 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-10 | 2026-10-12 | 2026-10-14 | 59 | W2 | Khalid | Chest |  | black-5705+752 pcs,,white-6465+580+600 pcs both combo 3 clr rub 1 clr foil/mettalic print |  |  | NFL3 |  |  | CAD | 2408 | 659 | -1749 | 0 | -14102 | [11 empty] | 42 | Sep'3 |  |  | 12.09.26
BS-ONL | 45315 6th | 15206049/15388435 | 1416 | 156 | 2026-08-14 | 2026-08-22 | High waist shorts | Shorts |  |  | 2026-09-01 | 2026-09-05 | 2026-09-10 | 2026-09-22 |  |  | 2026-09-24 | 2026-09-24 |  | 2026-09-28 | 2026-09-29 | 2026-10-01 | 2026-10-02 |  |  |  |  | 2026-10-05 | 2026-10-07 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-12 | 2026-10-14 | 59 | O1 | Khalid | WAIST |  | 1 combo logo print |  |  | NFL2 |  |  | CAD | 156 | 0 | -156 | 0 | -1416 | [11 empty] | 42 | Sep'3 |  |  | 17.09.26
BS-ONL | 45313 11th | 15311584 | 2265 | 361 | 2026-08-14 | 2026-08-22 | High waist shorts | Shorts |  |  | 2026-09-01 | 2026-09-10 | 2026-09-10 | 2026-09-23 |  |  | 2026-09-23 | 2026-09-23 |  | 2026-09-28 | 2026-09-29 | 2026-10-01 | 2026-10-02 |  |  |  |  | 2026-10-05 | 2026-10-08 |  |  | 2026-10-09 | 2026-10-10 | 2026-10-10 | 2026-10-12 | 2026-10-14 | 59 | o1 | Khalid | WAIST |  | 1 combo logo print |  |  | NFL2 |  |  | Need Cut FB | 361 | 0 | -361 | 0 | -2265 | [11 empty] | 42 | Sep'3 |  |  | 12.09.26
BS-ONL | 45314 6th | 15200077 | 1305 | 310 | 2026-08-14 | 2026-08-22 | LEGGING W WAIST PRINT | Legging |  |  | 2026-09-01 | 2026-09-05 | 2026-09-10 | 2026-09-19 |  |  | 2026-09-19 | 2026-09-19 |  | 2026-09-24 | 2026-09-24 | 2026-09-28 | 2026-09-29 |  |  |  |  | 2026-10-01 | 2026-10-03 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-09 | 2026-10-12 | 2026-10-14 | 59 | M | Khalid | WAIST |  | 1 combo label print |  |  | NFL2 |  |  | Need Cut FB | 310 | 0 | -310 | 0 | -1305 | [11 empty] | 42 | Sep'3 |  |  | 12.09.26
BS-ONL | 41873 13th | 15303953 | 848 | 379 | 2026-08-14 | 2026-08-22 | HIGH NK SWT W FULL ZIPPER PKT, CUFF BOND PKT | Swt Shirt |  |  | 2026-09-02 | 2026-09-08 | 2026-09-12 | 2026-09-25 |  |  | 2026-09-24 | 2026-09-24 |  | 2026-09-28 | 2026-09-29 |  |  |  |  | 2026-10-01 | 2026-10-02 | 2026-10-05 | 2026-10-07 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-12 | 2026-10-14 | 59 | R | Khalid |  | CHEST | BLACK 848 PCS 1 CLR FLAT EMB |  |  | NFL2 |  |  | Need Cut FB | 380 | 0 | -380 | 0 | -848 | [11 empty] | 42 | Sep'3 |  |  | 12.09.26
BS-ONL | 48692 | 15388356 | 504 | 57 | 2026-08-14 | 2026-08-22 | SS o nk TS | TS |  |  | 2026-09-02 | 2026-09-05 | 2026-09-10 | 2026-09-18 |  |  | 2026-09-22 | 2026-09-22 | 2026-09-26 | 2026-09-28 | 2026-09-28 | 2026-10-01 | 2026-10-02 |  |  |  |  | 2026-10-05 | 2026-10-06 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-10 | 2026-10-12 | 2026-10-14 | 59 | L | Khalid | Chest |  | white-504 pcs 4 clr cmyk print |  |  | NFL2 |  |  | Size Set Run PC | 57 | 0 | -57 | 0 | -504 | [11 empty] | 42 | Sep'3 |  |  | 12.09.26
BS-ONL | 45876 2nd | 15318138 | 504 | 295 | 2026-08-12 | 2026-08-19 | LS o nk Swt Shirt w cuff btm rib | Swt Shirt |  |  | 2026-09-01 | 2026-09-04 | 2026-09-10 | 2026-09-21 |  |  | 2026-09-22 | 2026-09-22 | 2026-09-28 | 2026-10-01 | 2026-10-01 |  |  |  |  | 2026-10-03 | 2026-10-09 | 2026-10-12 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-16 | 2026-10-16 | 2026-10-26 | 2026-10-28 | 75 | N2 | Zahirul |  | Chest | Dusty blue-504 pcs denim applique emb |  |  | NFL2 |  |  | Need Test Cut | 295 | 0 | -295 | 0 | -504 | [11 empty] | 44 | Oct'1 |  |  | 15.09.26
BS-ONL | 30530 5th | 15326481 | 1716 | 257 | 2026-08-15 | 2026-08-19 | LS v nk TS | TS |  |  | 2026-09-01 | 2026-09-04 | 2026-09-10 | 2026-09-22 |  |  | 2026-09-25 | 2026-09-25 | 2026-09-30 | 2026-10-02 | 2026-10-03 | [6 empty] | 2026-10-06 | 2026-10-09 |  |  | 2026-10-10 | 2026-10-12 | 2026-10-14 | 2026-10-19 | 2026-10-21 | 65 | Z | Zahirul | [5 empty] | NFL3 |  |  | Size Set Run PC | 525 | 0 | -525 | 0 | -1716 | [11 empty] | 43 | Oct'1 |  |  | 12.09.26
BS-ONL | 44707 2nd | 15371058 | 2256 | 275 | 2026-08-15 | 2026-08-21 | SS o nk TS | TS |  |  | 2026-09-01 | 2026-09-05 | 2026-09-08 | 2026-09-21 |  |  | 2026-09-23 | 2026-09-23 | 2026-09-28 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-07 |  |  |  |  | 2026-10-09 | 2026-10-12 |  |  | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 65 | Z | Zahirul | Fr,Bk |  | sunlight-1644 pcs frt photo print back 7 clr rub photo print 3 clr puff print ,,c.dan amor-612 pcs |  | 1 combo print at work due | NFL3 |  |  | Po Sheet Due | 575 | 415 | -160 | 0 | -2256 | [11 empty] | 43 | Sep'3
BS-ONL | 46309 6th | 15188034 | 2000 | 520 | 2026-08-19 | 2026-08-22 | Legging w elatic waist belt | Legging |  |  | 2026-09-07 | 2026-09-12 | 2026-09-21 | 2026-09-30 |  |  | 2026-10-03 | 2026-10-03 |  | 2026-10-09 | 2026-10-10 | [6 empty] | 2026-10-13 | 2026-10-15 |  |  | 2026-10-17 | 2026-10-19 | 2026-10-21 | 2026-10-26 | 2026-10-28 | 68 | O1 | Zahirul | [5 empty] | NFL2 |  |  | PPM Due | 520 | 0 | -520 | 0 | -2000 | [11 empty] | 44 | Oct'1 |  |  | 12.09.26
BS-ONL | 45478 2nd | 15368742 | 1716 | 380 | 2026-08-12 | 2026-08-22 | SS O nk TS | TS |  |  | 2026-09-01 | 2026-09-05 | 2026-09-10 | 2026-09-21 |  |  | 2026-09-22 | 2026-09-22 | 2026-09-26 | 2026-09-28 | 2026-09-29 | 2026-10-01 | 2026-10-02 |  |  |  |  | 2026-10-05 | 2026-10-07 |  |  | 2026-10-09 | 2026-10-10 | 2026-10-13 | 2026-10-19 | 2026-10-21 | 68 | K | Zahirul | Chest,Nk |  | wild-1716 pcs 1 clr pig print |  |  | NFL2 |  |  | Po Sheet Due | 380 | 0 | -380 | 0 | -1716 | [11 empty] | 43 | Sep'3
BS-ONL | 26030 23th | 15308926 | 19678 | 4592 | 2026-08-14 | 2026-08-20 | LDS SS TS W BK CUT & SEW & SIDE SLEET | TS |  |  | 2026-08-25 | 2026-09-08 | 2026-09-05 | 2026-09-24 |  |  | 2026-09-22 | 2026-09-21 |  | 2026-09-25 | 2026-09-30 | [6 empty] | 2026-10-01 | 2026-10-10 |  |  | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 66 | U | Dalim | [5 empty] | NFL3 |  |  | Cut Run | 4591 | 2145 | -2446 | 10274 | -9404 | [11 empty] | 43 | Sep'3 |  |  | 02.09.26
BS-ONL | 27204 64th | 15323159 | 18160 | 4357 | 2026-08-14 | 2026-08-20 | LS o nk TS | TS |  |  | 2026-08-25 | 2026-09-05 | 2026-09-08 | 2026-09-22 |  |  | 2026-09-21 | 2026-09-21 |  | 2026-09-26 | 2026-09-30 | [6 empty] | 2026-10-01 | 2026-10-07 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-12 | 2026-10-14 | 59 | G1 | Dalim | [5 empty] | NFL1 |  |  | Need Cut | 4381 | 395 | -3986 | 0 | -18160 | [11 empty] | 42 | Sep'3 |  |  | 07.09.26
BS-ONL | 27204 65th | 15323159 | 19372 | 4818 | 2026-08-14 | 2026-08-20 | LS o nk TS | TS |  |  | 2026-09-01 | 2026-09-12 | 2026-09-15 | 2026-10-02 |  |  | 2026-09-30 | 2026-09-25 |  | 2026-10-03 | 2026-10-08 | [6 empty] | 2026-10-07 | 2026-10-15 |  |  | 2026-10-17 | 2026-10-19 | 2026-10-21 | 2026-10-26 | 2026-10-28 | 73 | G1 | Dalim | [5 empty] | NFL1 |  |  | Need Cut FB | 4818 | 285 | -4533 | 0 | -19372 | [11 empty] | 44 | Oct'1 |  |  | 07.09.26
BS-ONL | 48701 | 15399377 | 15000 | 6600 | 2026-08-18 | 2026-08-20 | 3/4 Reglan slve Swt shirt | Swt Shirt |  |  | 2026-08-26 | 2026-09-10 | 2026-09-08 | 2026-09-28 |  |  | 2026-09-25 | 2026-09-25 | 2026-10-02 | 2026-10-05 | 2026-10-08 | [6 empty] | 2026-10-07 | 2026-10-12 |  |  | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 62 | D1 | Dalim | [5 empty] | NFL1 |  |  | File Due | 6999 | 0 | -6999 | 0 | -15000 | [11 empty] | 43 | Oct'1
BS-ONL | 41836 9th | 15343893 | 10134 | 1749 | 2026-08-14 | 2026-08-20 | SS o nk TS | TS |  |  | 2026-08-25 | 2026-09-05 | 2026-09-05 | 2026-09-19 |  |  | 2026-09-17 | 2026-09-17 |  | 2026-09-22 | 2026-09-24 | [6 empty] | 2026-09-26 | 2026-09-30 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-06 | 51 | W2 | Dalim | [5 empty] | NFL3 |  |  | Cut Run | 1748 | 817 | -931 | 4806 | -5328 | [11 empty] | 41 | Sep'3 |  |  | 02.09.26
BS-ONL | 45448 2nd | 15370919 | 516 | 160 | 2026-08-18 | 2026-08-22 | LS v nk Wrap TS | TS |  |  | 2026-09-01 | 2026-09-05 | 2026-09-10 | 2026-09-21 |  |  | 2026-09-21 | 2026-09-21 | 2026-09-26 | 2026-09-29 | 2026-09-29 | [6 empty] | 2026-10-02 | 2026-10-03 |  |  | 2026-10-05 | 2026-10-07 | 2026-10-09 | 2026-10-12 | 2026-10-14 | 55 | K | Zahirul | [5 empty] | NFL2 |  |  | Po Sheet Due | 160 | 0 | -160 | 0 | -516 | [11 empty] | 42 | Sep'3
BS-ONL | 48694 | 15385910 | 1020 | 300 | 2026-08-14 | 2026-08-22 | SS o nk TS | TS |  |  | 2026-09-01 | 2026-09-04 | 2026-09-05 | 2026-09-19 |  |  | 2026-09-17 | 2026-09-17 | 2026-09-22 | 2026-09-24 | 2026-09-24 | 2026-09-26 | 2026-09-29 |  |  |  |  | 2026-10-01 | 2026-10-02 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-12 | 2026-10-14 | 59 | N2 | Khalid | Fr,Bk |  | white-514 pcs,,black-506 pcs both combo frt 1 clr rub back 2 clr rub |  | Seven Zone brand | NFL2 |  |  | File Due | 300 | 0 | -300 | 0 | -1020 | [11 empty] | 42 | Sep'3
BS-ONL | 48695 | 15385884 | 504 | 352 | 2026-08-14 | 2026-08-20 | LS Full Zipper Swt hoody w kangaro pkt and drawstring | Hoody |  |  | 2026-09-01 | 2026-09-05 | 2026-09-09 | 2026-09-19 |  |  | 2026-09-21 | 2026-09-21 | 2026-09-26 | 2026-09-29 | 2026-09-29 |  |  |  |  | 2026-10-01 | 2026-10-01 | 2026-10-03 | 2026-10-05 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-12 | 2026-10-14 | 59 | R | Khalid |  | Chest | LGM-504 pcs 1 clr flat emb logo emb |  | Seven Zone brand | NFL2 |  |  | File Due | 353 | 0 | -353 | 0 | -504 | [11 empty] | 42 | Sep'3
BS-ONL | 48696 | 15385912 | 1615 | 413 | 2026-08-14 | 2026-08-22 | SS o nk TS w side cut&sew half moon and eyehole | TS |  |  | 2026-08-28 | 2026-08-07 | 2026-08-08 | 2026-09-17 |  |  | 2026-09-17 | 2026-09-17 | 2026-09-23 | 2026-09-25 | 2026-09-26 |  |  |  |  | 2026-09-29 | 2026-09-30 | 2026-10-03 | 2026-10-06 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-10 | 2026-10-12 | 2026-10-14 | 59 | J | Khalid | Chest |  | white-532 pcs,,black-509 pcs,,dark-574 pcs all combo 1 clr flat logo emb |  | Seven Zone brand | NFL2 |  |  | File Due | 413 | 0 | -413 | 0 | -1615 | [11 empty] | 42 | Sep'3
BS-ONL | 48697 | 15385896 | 1230 | 375 | 2026-08-14 | 2026-08-20 | Waist belt shorts w side pkt drawstring | Shorts |  |  | 2026-08-26 | 2026-09-02 | 2026-09-03 | 2026-09-19 |  |  | 2026-09-17 | 2026-09-17 | 2026-09-23 | 2026-09-25 | 2026-09-26 |  |  |  |  | 2026-09-29 | 2026-09-30 | 2026-10-03 | 2026-10-06 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-12 | 2026-10-14 | 59 | P | Khalid |  | Thigh | LGM-615 pcs,,black-615 pcs both combo 1 clr flat logo emb |  | Seven Zone brand | NFL2 |  |  | File Due | 376 | 0 | -376 | 0 | -1230 | [11 empty] | 42 | Sep'3
OVS SPA | 47851 | 271POL050TL50-6198 | 3225 | 950 | 2026-07-23 | 2026-08-19 | LS Polo Shirt w popline collar mock bottom and golden button at side slit | Polo |  |  | 2026-09-01 | 2026-09-11 | 2026-09-12 | 2026-09-26 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-06 | 2026-10-07 | 2026-10-08 | [6 empty] | 2026-10-10 | 2026-10-16 |  |  | 2026-10-17 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-21 | 90 | J | Khairul | [5 empty] | NFL2 |  |  | File Due | 950 | 0 | -950 | 0 | -3225 | [11 empty] | 43 | Oct'1
GBX-New Look | 47424 5th | 9646803 | 996 | 1649 | 2026-08-18 | 2026-08-19 | YD legging w drawstring | Legging | 2026-09-01 | 2026-09-07 | 2026-09-08 | 2026-09-18 | 2026-09-18 | 2026-09-24 |  |  | 2026-09-23 | 2026-09-23 |  | 2026-09-28 | 2026-09-30 | [6 empty] | 2026-10-01 | 2026-10-05 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-10 | 2026-10-10 | 53 | N/1 | Sifat |  |  |  | YD |  | NCL |  |  | Po Sheet Due | 1649 | 0 | -1649 | 0 | -996 | [11 empty] | 41 | Sep'3
GBX-New Look | 47403 6th | 9603199 | 5052 | 628 | 2026-08-18 | 2026-08-19 | YD SL TS w full placket btn | TS | 2026-09-01 | 2026-09-05 | 2026-09-08 | 2026-09-15 | 2026-09-15 | 2026-09-21 |  |  | 2026-09-21 | 2026-09-21 |  | 2026-09-26 | 2026-09-29 | [6 empty] | 2026-09-29 | 2026-10-04 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-10 | 2026-10-10 | 53 | N/3 | Sifat |  |  |  | YD |  | NCL |  |  | Po Sheet Due | 628 | 0 | -628 | 0 | -5052 | [11 empty] | 41 | Sep'3
GBX-New Look | 46804 4th | 9602962 | 5778 | 751 | 2026-08-22 | 2026-08-20 | SL TS w btm boulson over seam | TS |  |  | 2026-09-01 | 2026-09-05 | 2026-09-10 | 2026-09-21 |  |  | 2026-09-21 | 2026-09-21 |  | 2026-09-26 | 2026-09-29 | [6 empty] | 2026-10-01 | 2026-10-05 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-10 | 2026-10-10 | 49 | N/1 | Sifat | [5 empty] | NCL |  |  | Po Sheet Due | 750 | 0 | -750 | 0 | -5778 | [11 empty] | 41 | Sep'3
GBX-New Look | 48552 2nd | 9686536 | 10603 | 1189 | 2026-08-20 | 2026-08-20 | AOP SS reglan contrast slve TS | TS |  |  | 2026-08-28 | 2026-09-05 | 2026-09-08 | 2026-09-21 | 2026-09-19 | 2026-09-28 | 2026-09-25 | 2026-09-24 |  | 2026-09-28 | 2026-10-02 | [6 empty] | 2026-10-01 | 2026-10-07 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-09 | 2026-10-10 | 2026-10-10 | 51 | N/1 | Sifat |  |  |  | AOP |  | NCL |  |  | Po Sheet Due | 1189 | 0 | -1189 | 0 | -10603 | [11 empty] | 41 | Oct'1
GBX-New Look | 48552 3rd | 9686536 | 11113 | 1196 | 2026-08-20 | 2026-08-20 | YD SS reglan contrast slve TS | TS | 2026-09-02 | 2026-09-10 | 2026-09-12 | 2026-09-23 | 2026-09-22 | 2026-09-28 |  |  | 2026-09-28 | 2026-09-28 | 2026-10-03 | 2026-10-05 | 2026-10-08 | [6 empty] | 2026-10-07 | 2026-10-15 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-17 | 2026-10-17 | 2026-10-18 | 58 | N/1 | Sifat |  |  |  | YD |  | NCL |  |  | Po Sheet Due | 1261 | 0 | -1261 | 0 | -11113 | [11 empty] | 43 | Oct'1
GBX-New Look | 47936 6th | 9657695 | 10045 | 1034 | 2026-08-22 | 2026-08-21 | SS reglan contrast slve TS | TS |  |  | 2026-08-25 | 2026-09-03 | 2026-09-05 | 2026-09-18 |  |  | 2026-09-15 | 2026-09-15 |  | 2026-09-20 | 2026-09-24 | [6 empty] | 2026-09-24 | 2026-09-30 |  |  | 2026-10-03 | 2026-10-05 | 2026-10-06 | 2026-10-10 | 2026-10-10 | 49 | N/2 | Sifat | [5 empty] | NCL |  |  | Po Sheet Due | 1080 | 0 | -1080 | 0 | -10045 | [11 empty] | 41 | Sep'2
GBX-New Look | 48751 | NYC09 | 4040 | 512 | 2026-08-20 | 2026-08-21 | SS reglan contrast slve TS | TS |  |  | 2026-09-01 | 2026-09-04 | 2026-09-07 | 2026-09-19 |  |  | 2026-09-18 | 2026-09-18 | 2026-09-21 | 2026-09-23 | 2026-09-25 | 2026-09-25 | 2026-09-29 |  |  |  |  | 2026-10-01 | 2026-10-04 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-10 | 2026-10-10 | 51 | N/1 | Sifat | Chest |  | white -4040 pcs 2 clr rub print |  |  | NCL |  |  | File Due | 550 | 0 | -550 | 0 | -4040 | [11 empty] | 41 | Sep'3
UTG-(Even & Odd) | 45963 14th | BAD0962BU | 900 | 220 | 2026-08-08 | 2026-08-21 | LDS LS R NK TS | TS |  |  | 2026-08-24 | 2026-08-31 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-12 | 2026-09-14 |  | 2026-09-17 | 2026-09-18 | [6 empty] | 2026-09-19 | 2026-09-21 |  |  | 2026-09-22 | 2026-09-24 | 2026-09-26 | 2026-10-03 | 2026-10-05 | 56 | N/1 | Rony | [5 empty] | NCL |  |  | Need Test Cut | 220 | 0 | -220 | 0 | -900 | [11 empty] | 41 | Sep'2
UTG-(Even & Odd) | 24241 17th | BAD0981Z | 1700 | 333 | 2026-08-08 | 2026-08-21 | LDS LS OFF SHOULDER TS | TS |  |  | 2026-08-24 | 2026-08-31 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-11 | 2026-09-12 |  | 2026-09-16 | 2026-09-17 | [6 empty] | 2026-09-18 | 2026-09-21 |  |  | 2026-09-22 | 2026-09-24 | 2026-09-26 | 2026-10-03 | 2026-10-05 | 56 | N/1 | Rony | [5 empty] | NCL |  |  | Need Test Cut | 333 | 0 | -333 | 0 | -1700 | [11 empty] | 41 | Sep'2
UTG-(Even & Odd) | 44596 7th | BAD2946G | 1600 | 423 | 2026-08-08 | 2026-08-21 | LS BODYSUIT | SUIT |  |  | 2026-08-24 | 2026-08-31 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-11 | 2026-09-12 |  | 2026-09-17 | 2026-09-18 | [6 empty] | 2026-09-19 | 2026-09-22 |  |  | 2026-09-23 | 2026-09-25 | 2026-09-28 | 2026-10-03 | 2026-10-05 | 56 | N/3 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 422 | 401 | -21 | 0 | -1600 | [11 empty] | 41 | Sep'2
UTG-(Even & Odd) | 41637 10th | BAD1502P | 1600 | 390 | 2026-08-08 | 2026-08-21 | LS ROLL NK TS | TS |  |  | 2026-08-24 | 2026-08-31 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-11 | 2026-09-12 |  | 2026-09-16 | 2026-09-17 | [6 empty] | 2026-09-18 | 2026-09-21 |  |  | 2026-09-22 | 2026-09-24 | 2026-09-26 | 2026-10-03 | 2026-10-05 | 56 | N/1 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 390 | 195 | -195 | 0 | -1600 | [11 empty] | 41 | Sep'2
UTG-(Even & Odd) | 23325 18th | BAD0960BG | 800 | 202 | 2026-08-08 | 2026-08-21 | LS HIGH NK TS | TS |  |  | 2026-08-25 | 2026-08-31 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-14 | 2026-09-15 |  | 2026-09-17 | 2026-09-18 | [6 empty] | 2026-09-19 | 2026-09-21 |  |  | 2026-09-22 | 2026-09-24 | 2026-09-26 | 2026-10-03 | 2026-10-05 | 56 | N/2 | Rony | [5 empty] | NCL |  |  | Need Test Cut | 202 | 0 | -202 | 0 | -800 | [11 empty] | 41 | Sep'2
UTG-(Even & Odd) | 46873 3rd | BAD3194B | 680 | 287 | 2026-08-08 | 2026-08-21 | LS boat nk TS | TS |  |  | 2026-08-24 | 2026-08-31 | 2026-09-01 | 2026-09-12 |  |  | 2026-09-12 | 2026-09-14 |  | 2026-09-16 | 2026-09-17 | [6 empty] | 2026-09-19 | 2026-09-21 |  |  | 2026-09-22 | 2026-09-24 | 2026-09-26 | 2026-10-03 | 2026-10-05 | 56 | N/2 | Rony | [5 empty] | NCL |  |  | Need Test Cut | 287 | 0 | -287 | 0 | -680 | [11 empty] | 41 | Sep'2
UTG-(Even & Odd) | 41645 12th | BAD2681K | 2000 | 468 | 2026-08-08 | 2026-08-21 | Cropped LS TS w placket | TS |  |  | 2026-08-24 | 2026-08-29 | 2026-08-31 | 2026-09-12 |  |  | 2026-09-11 | 2026-09-12 |  | 2026-09-16 | 2026-09-17 | [6 empty] | 2026-09-18 | 2026-09-22 |  |  | 2026-09-23 | 2026-09-25 | 2026-09-28 | 2026-10-03 | 2026-10-05 | 56 | N/3 | Rony | [5 empty] | NCL |  |  | Ready Test Cut | 468 | 234 | -234 | 0 | -2000 | [11 empty] | 41 | Sep'2
BS-ONL | 48610 2nd | 15391574 | 2560 | 368 | 2026-08-15 | 2026-08-19 | SS o nk TS w btm Lace attach | TS |  |  | 2026-09-05 | 2026-09-10 | 2026-09-20 | 2026-10-05 |  |  | 2026-10-07 | 2026-10-07 |  | 2026-10-13 | 2026-10-14 | [6 empty] | 2026-10-16 | 2026-10-17 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-27 | 2026-11-09 | 2026-11-11 | 86 | V | Jannati |  |  |  |  | Lace | NFL3 |  |  | Po Sheet Due | 368 | 0 | -368 | 0 | -2560 | [11 empty] | 46 | Oct'2
BS-ONL | 48668 | 15288478 | 6132 | 1007 | 2026-08-13 | 2026-08-20 | SS v nk TS | TS |  |  | 2026-09-04 | 2026-09-12 | 2026-09-15 | 2026-09-30 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-07 | 2026-10-09 | 2026-10-12 |  |  |  |  | 2026-10-12 | 2026-10-21 | 2026-10-23 | 2026-10-28 |  |  | 2026-10-30 | 2026-10-31 | 2026-11-02 | 2026-11-09 | 2026-11-11 | 88 | M | Mainul |  | AOE | c.dan-3066 pcs,,Mermaid-3066 pcs both combo frt both slve 1 clr lurex all over emb |  |  | NFL2 |  |  | File Due | 1008 | 0 | -1008 | 0 | -6132 | [11 empty] | 46 | Oct'1
BS-ONL | 48676 | 15257467 | 8463 | 1085 | 2026-08-13 | 2026-08-20 | AOP & Solid SS o nk TS w btm front knot | TS |  |  | 2026-09-06 | 2026-09-13 | 2026-09-20 | 2026-10-03 | 2026-10-06 | 2026-10-12 | 2026-10-14 | 2026-10-14 | 2026-10-19 | 2026-10-21 | 2026-10-24 | [6 empty] | 2026-10-24 | 2026-10-30 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-05 | 2026-11-09 | 2026-11-11 | 88 | U | Mainul |  |  |  | AOP |  | NFL3 |  |  | File Due | 1087 | 119 | -968 | 0 | -8463 | [11 empty] | 46 | Oct'3
BS-ONL | 48674 | 15393981 | 1080 | 418 | 2026-08-13 | 2026-08-22 | LS half zipper high nk Swt Shirt w cuff btm rib | Swt Shirt |  |  | 2026-09-07 | 2026-09-12 | 2026-09-16 | 2026-10-06 |  |  | 2026-10-08 | 2026-10-08 | 2026-10-14 | 2026-10-16 | 2026-10-17 | 2026-10-20 | 2026-10-22 |  |  |  |  | 2026-10-24 | 2026-10-27 |  |  | 2026-10-29 | 2026-10-31 | 2026-11-03 | 2026-11-09 | 2026-11-11 | 88 | R | Mainul | Chest |  | c.dan-540 pcs,,mermaid-540 pcs both combo 1 clr pig print |  |  | NFL2 |  |  | File Due | 426 | 0 | -426 | 0 | -1080 | [11 empty] | 46 | Oct'2
BS-ONL | 48671 | 15392570 | 1596 | 268 | 2026-08-13 | 2026-08-22 | SS o nk TS | TS |  |  | 2026-09-05 | 2026-09-10 | 2026-09-18 | 2026-09-30 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-09 | 2026-10-12 | 2026-10-13 |  |  | 2026-10-15 | 2026-10-17 |  |  | 2026-10-20 | 2026-10-22 |  |  | 2026-10-24 | 2026-10-27 | 2026-10-30 | 2026-11-09 | 2026-11-11 | 88 | M | Mainul | Heat Press/Heat Seal |  | black-798 pcs,,white-798 pcs both combo Stone sticker Heat press |  | Imp Stone sticker | NFL2 |  |  | File Due | 268 | 0 | -268 | 0 | -1596 | [11 empty] | 46 | Oct'2
BS-ONL | 48675 | 15397296 | 500 | 58 | 2026-08-13 | 2026-08-22 | Elasted Shorts | Shorts |  |  | 2026-09-10 | 2026-09-14 | 2026-09-22 | 2026-10-05 |  |  | 2026-10-10 | 2026-10-10 | 2026-10-15 | 2026-10-17 | 2026-10-17 | [6 empty] | 2026-10-20 | 2026-10-21 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-28 | 2026-11-09 | 2026-11-11 | 88 | O1 | Mainul | [5 empty] | NFL2 |  |  | File Due | 62 | 0 | -62 | 0 | -500 | [11 empty] | 46 | Oct'2
BS-ONL | 48672 | 15393024 | 6149 | 1509 | 2026-08-13 | 2026-08-22 | half slve boat nk TS w back pleat | TS |  |  | 2026-09-06 | 2026-09-13 | 2026-09-20 | 2026-10-03 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-10 | 2026-10-12 | 2026-10-14 | [6 empty] | 2026-10-14 | 2026-10-17 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-26 | 2026-11-09 | 2026-11-11 | 88 | ZA2 | Mainul | [5 empty] | NFL3 |  |  | File Due | 1509 | 0 | -1509 | 0 | -6149 | [11 empty] | 46 | Oct'2
BS-ONL | 48670 | 15397289 | 3264 | 336 | 2026-08-13 | 2026-08-22 | Square nk Tank top | Tank Top |  |  | 2026-09-08 | 2026-09-15 | 2026-09-24 | 2026-10-07 |  |  | 2026-10-10 | 2026-10-10 | 2026-10-15 | 2026-10-17 | 2026-10-19 | [6 empty] | 2026-10-21 | 2026-10-24 |  |  | 2026-10-27 | 2026-10-29 | 2026-10-30 | 2026-11-09 | 2026-11-11 | 88 | G1 | Mainul | [5 empty] | NFL1 |  |  | File Due | 336 | 0 | -336 | 0 | -3264 | [11 empty] | 46 | Oct'2
BS-ONL | 48673 | 15393974 | 4598 | 871 | 2026-08-13 | 2026-08-22 | SS o nk TS | TS |  |  | 2026-09-10 | 2026-09-15 | 2026-09-22 | 2026-10-03 |  |  | 2026-10-07 | 2026-10-07 | 2026-10-12 | 2026-10-14 | 2026-10-16 | 2026-10-17 | 2026-10-20 |  |  |  |  | 2026-10-23 | 2026-10-27 |  |  | 2026-10-29 | 2026-10-30 | 2026-11-02 | 2026-11-07 | 2026-11-09 | 86 | F | Mainul | Chest |  | c.dan out-1914 pcs 3 clr pig ,,c.dan la dolce-2684 pcs 8 clr pig print |  |  | NFL1 |  |  | File Due | 871 | 766 | -105 | 0 | -4598 | [11 empty] | 46 | Oct'2
BS-ONL | 48606 | 15391993 | 5370 | 997 | 2026-08-15 | 2026-08-18 | SS o nk TS | TS |  |  | 2026-09-06 | 2026-09-12 | 2026-09-20 | 2026-10-04 |  |  | 2026-10-08 | 2026-10-08 | 2026-10-14 | 2026-10-16 | 2026-10-19 | 2026-10-19 | 2026-10-23 |  |  |  |  | 2026-10-26 | 2026-10-29 |  |  | 2026-10-31 | 2026-11-02 | 2026-11-03 | 2026-11-07 | 2026-11-09 | 84 | L1 | Imran | Chest,Nk |  | phanthom-2202 pcs 3 clr rub print ,,birch-2328 pcs 1 clr photo print ,,corsage-840 pcs 2 clr pig |  | License order | NFL2 |  |  | File Due | 997 | 146 | -851 | 0 | -5370 | [11 empty] | 46 | Oct'2
BS-ONL | 45327 2nd | 15366549 | 14532 | 3185 | 2026-08-14 | 2026-08-20 | Shorts w side pkt and drawstring | Shorts |  |  | 2026-09-01 | 2026-09-10 | 2026-09-12 | 2026-10-01 |  |  | 2026-10-01 | 2026-10-01 | 2026-10-08 | 2026-10-10 | 2026-10-14 |  |  |  |  | 2026-10-13 | 2026-10-19 | 2026-10-19 | 2026-10-31 |  |  | 2026-11-03 | 2026-11-04 | 2026-11-10 | 2026-11-23 | 2026-11-25 | 101 | P | Khalid |  | Thigh | skyway -5084 pcs,,night sky-5612 pcs,,coral-3836 pcs all combo 1 clr flat emb |  |  | NFL2 |  |  | Po Sheet Due | 3185 | 0 | -3185 | 0 | -14532 | [11 empty] | 48 | Oct'1
BS-ONL | 48693 | 15387728 | 1224 | 258 | 2026-08-14 | 2026-08-20 | 3/4 High waist Legging | Legging |  |  | 2026-09-15 | 2026-09-20 | 2026-10-01 | 2026-10-10 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-19 | 2026-10-22 | 2026-10-23 | 2026-10-26 | 2026-10-27 |  |  |  |  | 2026-11-02 | 2026-11-03 |  |  | 2026-11-05 | 2026-11-07 | 2026-11-12 | 2026-11-23 | 2026-11-25 | 101 | L2 | Khalid | leg |  | black-1224 pcs 1 clr rub print at one leg |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -1224 | [11 empty] | 48 | Oct'3
BS-ONL | 45337 2nd | 15366482 | 2772 | 1144 | 2026-08-14 | 2026-08-22 | Swt pant w leg cuff side pkt and waist drawstring | PANT |  |  | 2026-09-18 | 2026-09-26 | 2026-10-02 | 2026-10-17 |  |  | 2026-10-20 | 2026-10-20 | 2026-10-26 | 2026-10-29 | 2026-10-30 |  |  |  |  | 2026-11-03 | 2026-11-06 | 2026-11-09 | 2026-11-12 |  |  | 2026-11-14 | 2026-11-16 | 2026-11-18 | 2026-11-23 | 2026-11-25 | 101 | P | Khalid |  | Thigh | skyway-612 pcs...N.sky-2160 pcs all combo 1 clr flat emb at one thigh |  |  | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -2772 | [11 empty] | 48 | Oct'3
BS-ONL | 46106 2nd | 15370241 | 636 | 384 | 2026-08-14 | 2026-08-22 | Swt pant w side pkt cuff drawstring and side contrast piping | Pant |  |  | 2026-09-10 | 2026-09-17 | 2026-09-25 | 2026-10-09 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-21 | 2026-10-23 | 2026-10-24 | 2026-10-27 | 2026-10-28 |  |  |  |  | 2026-11-02 | 2026-11-04 |  |  | 2026-11-06 | 2026-11-07 | 2026-11-10 | 2026-11-23 | 2026-11-25 | 101 | P | Khalid | Thigh |  | pumic stone-636 pcs 1 clr rub logo |  |  | NFL2 |  |  | Po Sheet Due | 385 | 0 | -385 | 0 | -636 | [11 empty] | 48 | Oct'3
BS-ONL | 45335 2nd | 15366480 | 16716 | 2995 | 2026-08-14 | 2026-08-22 | LDS TS W TURN UP AT SLV | TS |  |  | 2026-09-12 | 2026-09-22 | 2026-09-22 | 2026-10-12 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-20 | 2026-10-22 | 2026-10-27 |  |  |  |  | 2026-10-26 | 2026-11-02 | 2026-11-02 | 2026-11-09 |  |  | 2026-11-11 | 2026-11-13 | 2026-11-16 | 2026-11-23 | 2026-11-25 | 101 | D | Khalid |  | CHEST | skyway-5648 pcs,,NIGHT SKY 6716 PCS,, coral-4352 pcs ALL COMBO 1 CLR FLAT EMB |  |  | NFL1 |  |  | Po Sheet Due | 2995 | 0 | -2995 | 0 | -16716 | [11 empty] | 48 | Oct'3
BS-ONL | 46105 2nd | 15370293 | 756 | 433 | 2026-08-14 | 2026-08-22 | LS reglan Swt jacket w full zipper side pkt and contrast piping | Jacket |  |  | 2026-09-15 | 2026-09-23 | 2026-10-01 | 2026-10-15 |  |  | 2026-10-17 | 2026-10-17 | 2026-10-24 | 2026-10-27 | 2026-10-28 | 2026-10-30 | 2026-10-31 |  |  |  |  | 2026-11-05 | 2026-11-07 |  |  | 2026-11-10 | 2026-11-12 | 2026-11-13 | 2026-11-23 | 2026-11-25 | 101 | R | Khalid | Chest |  | p.stone-756 pcs 1 clr rub logo |  |  | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -756 | [11 empty] | 48 | Oct'3
BS-ONL | 45336 2nd | 15366481 | 4212 | 1541 | 2026-08-14 | 2026-08-22 | LS high nk jacket w full zipper and btm drawstring | Jacket |  |  | 2026-09-10 | 2026-09-21 | 2026-09-22 | 2026-09-10 |  |  | 2026-10-13 | 2026-10-13 | 2026-10-19 | 2026-10-21 | 2026-10-24 |  |  |  |  | 2026-10-26 | 2026-10-29 | 2026-11-02 | 2026-11-07 |  |  | 2026-11-10 | 2026-11-12 | 2026-11-18 | 2026-11-23 | 2026-11-25 | 101 | R | Khalid |  | CHEST | skyway-1356 pcss,,night sky-2856 pcs all combo 1 clr flat emb |  |  | NFL2 |  |  | Po Sheet Due | 1542 | 0 | -1542 | 0 | -4212 | [11 empty] | 48 | Oct'3
BS-ONL | 48691 | 15387655 | 870 | 225 | 2026-08-14 | 2026-08-22 | SL o nk TS | TS |  |  | 2026-09-18 | 2026-09-23 | 2026-10-01 | 2026-10-13 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-23 | 2026-10-26 | 2026-10-27 | 2026-10-29 | 2026-10-31 |  |  |  |  | 2026-11-05 | 2026-11-06 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-23 | 2026-11-25 | 101 | L | Khalid | Chest |  | white-870 pcs 1 clr rub print |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -870 | [11 empty] | 48 | Oct'3
BS-ONL | 48643 | 15187962 | 600 | 250 | 2026-08-12 | 2026-08-19 | Tank Top | Tank Top |  |  | 2026-09-07 | 2026-09-10 | 2026-09-18 | 2026-09-30 |  |  | 2026-10-07 | 2026-10-07 | 2026-10-13 | 2026-10-16 | 2026-10-16 | [6 empty] | 2026-10-20 | 2026-10-21 |  |  | 2026-10-23 | 2026-10-27 | 2026-10-30 | 2026-11-16 | 2026-11-18 | 96 | T1 | Zahirul | [5 empty] | NFL3 |  |  | File Due | 250 | 0 | -250 | 0 | -600 | [11 empty] | 47 | Oct'2
BS-ONL | 45970 2nd | 15371984 | 960 | 628 | 2026-08-12 | 2026-08-22 | LS Swt shirt dress w nk cuff rib | DRESS |  |  | 2026-09-10 | 2026-09-15 | 2026-09-25 | 2026-10-10 |  |  | 2026-10-12 | 2026-10-12 | 2026-10-17 | 2026-10-19 | 2026-10-20 | 2026-10-22 | 2026-10-28 |  |  |  |  | 2026-11-02 | 2026-11-03 |  |  | 2026-11-05 | 2026-11-07 | 2026-11-10 | 2026-11-16 | 2026-11-18 | 96 | J | Zahirul | Sleeve |  | black-960 pcs both slv 2 clr rub 4 clr puff print |  |  | NFL2 |  |  | Po Sheet Due | 628 | 0 | -628 | 0 | -960 | [11 empty] | 47 | Oct'2
BS-ONL | 43969 41th | 15270390 | 20464 | 3325 | 2026-08-15 | 2026-08-20 | SS o nk TS | TS |  |  | 2026-09-03 | 2026-09-11 | 2026-09-12 | 2026-09-30 |  |  | 2026-09-26 | 2026-09-25 |  | 2026-10-01 | 2026-10-06 | [6 empty] | 2026-10-06 | 2026-10-13 |  |  | 2026-10-15 | 2026-10-19 | 2026-10-22 | 2026-11-08 | 2026-11-10 | 85 | ZA2 | Dalim | [5 empty] | NFL3 |  |  | Cut Run | 3326 | 2287 | -1039 | 5878 | -14586 | [11 empty] | 46 | Oct'1 |  |  | 02.09.26
BS-ONL | 26030 24th | 15308926 | 7332 | 1722 | 2026-08-14 | 2026-08-20 | LDS SS TS W BK CUT & SEW & SIDE SLEET | TS |  |  | 2026-09-10 | 2026-09-17 | 2026-09-20 | 2026-10-03 |  |  | 2026-09-28 | 2026-09-28 |  | 2026-10-05 | 2026-10-08 | [6 empty] | 2026-10-09 | 2026-10-14 |  |  | 2026-10-17 | 2026-10-20 | 2026-10-25 | 2026-11-16 | 2026-11-18 | 94 | U | Dalim | [5 empty] | NFL3 |  |  | Need Cut FB | 1714 | 0 | -1714 | 0 | -7332 | [11 empty] | 47 | Oct'1 |  |  | 02.09.26
BS-ONL | 27204 66th | 15323159 | 9690 | 2366 | 2026-08-14 | 2026-08-20 | LS o nk TS | TS |  |  | 2026-09-12 | 2026-09-20 | 2026-09-25 | 2026-10-10 |  |  | 2026-10-10 | 2026-10-10 |  | 2026-10-17 | 2026-10-20 | [6 empty] | 2026-10-23 | 2026-10-28 |  |  | 2026-10-30 | 2026-11-03 | 2026-11-05 | 2026-11-16 | 2026-11-18 | 94 | D1 | Dalim | [5 empty] | NFL1 |  |  | Need Cut FB | 2365 | 0 | -2365 | 0 | -9690 | [11 empty] | 47 | Oct'2 |  |  | 07.09.26
BS-ONL | 41836 10th | 15343893 | 53656 | 9256 | 2026-08-14 | 2026-08-20 | SS o nk TS | TS |  |  | 2026-09-01 | 2026-09-14 | 2026-09-14 | 2026-10-03 |  |  | 2026-10-25 | 2026-10-25 |  | 2026-10-30 | 2026-10-07 | [6 empty] | 2026-10-05 | 2026-10-24 |  |  | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-11-16 | 2026-11-18 | 94 | W2 | Dalim | [5 empty] | NFL3 |  |  | Need Cut | 9255 | 2282 | -6973 | 0 | -53656 | [11 empty] | 47 | Oct'3 |  |  | 02.09.26
BS-ONL | 29254 16th | 15247221 | 648 | 130 | 2026-08-18 | 2026-08-22 | SS o nk TS | TS |  |  | 2026-09-08 | 2026-09-12 | 2026-09-17 | 2026-09-30 |  |  | 2026-10-03 | 2026-10-03 |  | 2026-10-09 | 2026-10-09 | [6 empty] | 2026-10-12 | 2026-10-13 |  |  | 2026-10-15 | 2026-10-20 | 2026-10-26 | 2026-11-16 | 2026-11-18 | 90 | T2 | Zahirul | [5 empty] | NFL3 |  |  | Po Sheet Due | 130 | 0 | -130 | 0 | -648 | [11 empty] | 47 | Oct'1
OVS SPA | 47844 | 271TSH015TS15-6198 | 13200 | 1915 | 2026-08-07 | 2026-08-21 | SL O nk TS | TS |  |  | 2026-09-10 | 2026-09-25 | 2026-10-01 | 2026-10-15 |  |  | 2026-10-27 | 2026-10-26 | 2026-10-31 | 2026-11-02 | 2026-11-06 | [6 empty] | 2026-11-06 | 2026-11-12 |  |  | 2026-11-13 | 2026-11-16 | 2026-11-18 | 2026-11-23 | 2026-11-23 | 108 | G1 | Khairul | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -13200 | [11 empty] | 48 | Nov'1
OVS SPA | 47846 | 271TSH015TS15P-6198 | 8483 | 1370 | 2026-08-15 | 2026-08-21 | AOP SL O nk TS | TS |  |  | 2026-09-10 | 2026-09-22 | 2026-09-25 | 2026-10-08 | 2026-10-10 | 2026-10-20 | 2026-10-27 | 2026-10-26 | 2026-10-31 | 2026-11-02 | 2026-11-05 | [6 empty] | 2026-11-05 | 2026-11-11 |  |  | 2026-11-12 | 2026-11-14 | 2026-11-16 | 2026-11-23 | 2026-11-23 | 100 | G2 | Khairul |  |  |  | AOP |  | NFL1 |  |  | File Due | 1370 | 0 | -1370 | 0 | -8483 | [11 empty] | 48 | Nov'1
OVS SPA | 47845 | 271TSH015TS15F-6198 | 8483 | 1275 | 2026-08-15 | 2026-08-21 | AOP SL O nk TS | TS |  |  | 2026-09-10 | 2026-09-22 | 2026-09-25 | 2026-10-08 | 2026-10-10 | 2026-10-20 | 2026-10-27 | 2026-10-26 | 2026-10-31 | 2026-11-02 | 2026-11-05 | [6 empty] | 2026-11-05 | 2026-11-11 |  |  | 2026-11-12 | 2026-11-14 | 2026-11-16 | 2026-11-23 | 2026-11-23 | 100 | G2 | Khairul |  |  |  | AOP |  | NFL1 |  |  | File Due | 1275 | 0 | -1275 | 0 | -8483 | [11 empty] | 48 | Nov'1
GBX-New Look | 48709 | ID915-W35D | 710 | 182 | 2026-08-20 | 2026-08-20 | Ladies Halter nk Dress | Dress |  |  | 2026-09-17 | 2026-09-21 | 2026-10-03 | 2026-10-14 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-21 | 2026-10-23 | 2026-10-24 | [6 empty] | 2026-10-27 | 2026-10-29 |  |  | 2026-10-31 | 2026-11-02 | 2026-11-03 | 2026-11-07 | 2026-11-08 | 79 | N/3 | Sifat | [5 empty] | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -710 | [11 empty] | 46 | Oct'3
GBX-New Look | 48707 | INDOJ915-35466 | 710 | 285 | 2026-08-20 | 2026-08-20 | Ladies Halter nk Dress popline | Dress |  |  | 2026-09-10 | 2026-09-15 | 2026-10-01 | 2026-10-10 |  |  | 2026-10-13 | 2026-10-13 | 2026-10-19 | 2026-10-21 | 2026-10-22 | [6 empty] | 2026-10-24 | 2026-10-27 |  |  | 2026-10-29 | 2026-10-30 | 2026-11-02 | 2026-11-07 | 2026-11-08 | 79 | N/3 | Sifat | [5 empty] | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -710 | [11 empty] | 46 | Oct'3
GBX-New Look | 48708 | INDOJ915-35388 | 710 | 300 | 2026-08-20 | 2026-08-20 | Sholder less Bandeau flippy mini dresss | Dress |  |  | 2026-09-13 | 2026-09-16 | 2026-10-01 | 2026-10-10 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-20 | 2026-10-23 | 2026-10-24 | [6 empty] | 2026-10-26 | 2026-10-29 |  |  | 2026-10-31 | 2026-11-02 | 2026-11-03 | 2026-11-07 | 2026-11-08 | 79 | N/2 | Sifat | [5 empty] | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -710 | [11 empty] | 46 | Oct'3
GBX-New Look | 48723 | 9696982 | 708 | 206 | 2026-08-20 | 2026-08-21 | YD Strap Flipi Dress | Dress | 2026-09-15 | 2026-09-20 | 2026-09-22 | 2026-09-28 | 2026-10-04 | 2026-10-10 |  |  | 2026-10-13 | 2026-10-13 | 2026-10-20 | 2026-10-22 | 2026-10-23 | [6 empty] | 2026-10-26 | 2026-10-29 |  |  | 2026-10-30 | 2026-10-31 | 2026-11-02 | 2026-11-07 | 2026-11-08 | 79 | N/3 | Sifat |  |  |  | YD |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -708 | [11 empty] | 46 | Oct'3
GBX-New Look | 48711 | 9693020 | 6569 | 1611 | 2026-08-20 | 2026-08-22 | AOP Three layer skirt | Skirt |  |  | 2026-09-03 | 2026-09-10 | 2026-09-16 | 2026-09-30 | 2026-10-03 | 2026-10-12 | 2026-10-12 | 2026-10-12 | 2026-10-17 | 2026-10-19 | 2026-10-22 | [6 empty] | 2026-10-22 | 2026-10-31 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-07 | 2026-11-08 | 79 | N/3 | Sifat |  |  |  | AOP |  | NCL |  |  | File Due | 1593 | 0 | -1593 | 0 | -6569 | [11 empty] | 46 | Oct'2
GBX-New Look | 48710 | 9693023 | 6463 | 1866 | 2026-08-20 | 2026-08-22 | YD Double layer Skirt | Skirt | 2026-09-10 | 2026-09-21 | 2026-09-19 | 2026-10-03 | 2026-10-02 | 2026-10-10 |  |  | 2026-10-10 | 2026-10-10 | 2026-10-15 | 2026-10-17 | 2026-10-22 | [6 empty] | 2026-10-22 | 2026-10-29 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-07 | 2026-11-08 | 79 | N/3 | Sifat |  |  |  | YD |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -6463 | [11 empty] | 46 | Oct'2
GBX-TM Lewin | 48561 | Ottoman SS zip polo | 1590 | 714 | 2026-08-17 | 2026-08-20 | SS Half zipper Polo Shirt | Polo |  |  | 2026-09-10 | 2026-09-22 | 2026-09-22 | 2026-10-06 |  |  | 2026-10-09 | 2026-10-09 | 2026-10-15 | 2026-10-17 | 2026-10-19 | [6 empty] | 2026-10-21 | 2026-10-24 |  |  | 2026-10-27 | 2026-10-28 | 2026-10-30 | 2026-11-05 | 2026-11-05 | 80 | N/1 | Shofi | [5 empty] | NCL |  |  | File Due | 714 | 0 | -714 | 0 | -1590 | [11 empty] | 45 | Oct'2
GBX-TM Lewin | 48558 | Pique SS Polo | 1578 | 540 | 2026-08-17 | 2026-08-20 | SS Polo Shirt w collar pplacket btn and side slit | Polo |  |  | 2026-09-02 | 2026-09-12 | 2026-09-16 | 2026-09-30 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-09 | 2026-10-12 | 2026-10-14 | [6 empty] | 2026-10-15 | 2026-10-19 |  |  | 2026-10-21 | 2026-10-23 | 2026-10-27 | 2026-11-05 | 2026-11-05 | 80 | N/1 | Shofi | [5 empty] | NCL |  |  | File Due | 540 | 0 | -540 | 0 | -1578 | [11 empty] | 45 | Oct'2
UTG-(Even & Odd) | 46615 10th | BAD2287G | 600 | 174 | 2026-08-08 | 2026-08-21 | SKIRT W SIDE SLIT | Skirt |  |  | 2026-09-23 | 2026-09-30 | 2026-10-01 | 2026-10-10 |  |  | 2026-10-21 | 2026-10-22 |  | 2026-10-26 | 2026-10-27 | [6 empty] | 2026-10-28 | 2026-10-30 |  |  | 2026-10-31 | 2026-11-02 | 2026-11-04 | 2026-11-21 | 2026-11-23 | 105 | N/1 | Rony | [5 empty] | NCL |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -600 | [11 empty] | 48 | Oct'3
UTG-(Even & Odd) | 48713 | BAD3286 | 800 | 319 | 2026-08-08 | 2026-08-21 | YD LS boat nk TS | TS | 2026-09-01 | 2026-09-10 | 2026-09-11 | 2026-09-19 | 2026-09-21 | 2026-09-28 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-12 | 2026-10-13 | 2026-10-14 | [6 empty] | 2026-10-15 | 2026-10-17 |  |  | 2026-10-19 | 2026-10-21 | 2026-10-23 | 2026-11-07 | 2026-11-09 | 91 | N/1 | Rony |  |  |  | YD |  | NCL |  |  | File Due | 319 | 0 | -319 | 0 | -800 | [11 empty] | 46 | Oct'2
UTG-(Even & Odd) | 48712 | BAD3285 | 1600 | 610 | 2026-08-08 | 2026-08-21 | LS o nk YD TS | TS | 2026-09-01 | 2026-09-10 | 2026-09-11 | 2026-09-19 | 2026-09-21 | 2026-09-28 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-12 | 2026-10-13 | 2026-10-14 | [6 empty] | 2026-10-15 | 2026-10-17 |  |  | 2026-10-19 | 2026-10-21 | 2026-10-23 | 2026-11-07 | 2026-11-09 | 91 | N/1 | Rony |  |  |  | YD |  | NCL |  |  | File Due | 610 | 0 | -610 | 0 | -1600 | [11 empty] | 46 | Oct'2
UTG-(Even & Odd) | 48714 | BAD3284 | 500 | 267 | 2026-08-08 | 2026-08-21 | LS Mini Dress w waist gathering | Dress |  |  | 2026-09-01 | 2026-09-08 | 2026-09-10 | 2026-09-18 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-12 | 2026-10-13 | 2026-10-14 | [6 empty] | 2026-10-15 | 2026-10-17 |  |  | 2026-10-19 | 2026-10-21 | 2026-10-23 | 2026-11-07 | 2026-11-09 | 91 | N/2 | Rony | [5 empty] | NCL |  |  | File Due | 267 | 0 | -267 | 0 | -500 | [11 empty] | 46 | Oct'2
BS-ONL | 46219 2nd | 15375848 | 2445 | 382 | 2026-08-15 | 2026-08-19 | SS o nk TS w critical hand sewn beads | TS |  |  | 2026-09-08 | 2026-09-14 | 2026-09-21 | 2026-10-09 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-23 | 2026-10-26 | 2026-10-27 | 2026-10-29 | 2026-10-31 | 2026-11-10 | 2026-11-25 |  |  | 2026-11-04 | 2026-11-07 |  |  | 2026-11-27 | 2026-11-28 | 2026-11-30 | 2026-12-14 | 2026-12-16 | 121 | M | Jannati | Chest |  | sunlight-990 pcs 3 clr pig alloover print at chest and 1 clr all overhandsewn beads attach at chest,,white-1455 pcs 7 clr pig 1 clr gltr print and 1 clr handsewn beads |  | Hand sewn beads | NFL2 |  |  | Po Sheet Due | 382 | 227 | -155 | 0 | -2445 | [11 empty] | 51 | Oct'3
BS-ONL | 48669 | 15328355 | 2640 | 374 | 2026-08-13 | 2026-08-19 | Rib Tank top w front fake placket w snap btn | Tank Top |  |  | 2026-09-12 | 2026-09-22 | 2026-09-28 | 2026-10-12 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-21 | 2026-10-23 | 2026-10-24 | [6 empty] | 2026-10-27 | 2026-10-30 |  |  | 2026-10-31 | 2026-11-02 | 2026-11-03 | 2026-11-09 | 2026-11-11 | 88 | N2 | Mainul | [5 empty] | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -2640 | [11 empty] | 46 | Nov'1
BS-ONL | 48686 | 15393982 | 2504 | 1033 | 2026-08-13 | 2026-08-21 | LS o nk Swt Shirt w cuff btm rib | Swt Shirt |  |  | 2026-09-15 | 2026-09-22 | 2026-10-02 | 2026-10-17 |  |  | 2026-10-21 | 2026-10-21 | 2026-10-27 | 2026-10-29 | 2026-10-30 | 2026-11-04 | 2026-11-09 |  |  |  |  | 2026-11-12 | 2026-11-14 |  |  | 2026-11-17 | 2026-11-19 | 2026-11-23 | 2026-12-14 | 2026-12-16 | 123 | N2 | Mainul | Bk |  | pink -1652 pcs 11 clr rub print ,,butter -852 pcs 8 clr rub print |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -2504 | [11 empty] | 51 | Oct'3
BS-ONL | 48681 | 15391747 | 2016 | 428 | 2026-08-13 | 2026-08-21 | SS o nk TS | TS |  |  | 2026-09-15 | 2026-09-21 | 2026-10-01 | 2026-10-15 |  |  | 2026-10-17 | 2026-10-17 | 2026-10-24 | 2026-10-27 | 2026-10-28 | 2026-11-02 | 2026-11-04 |  |  | 2026-11-05 | 2026-11-13 | 2026-11-16 | 2026-11-19 |  |  | 2026-11-23 | 2026-11-25 | 2026-11-30 | 2026-12-14 | 2026-12-16 | 123 | O1 | Mainul | Chest | Chest | c.dan-1008 pcs,,corsage-1008 pcs both combo 1 clr pig and twill fabric applique emb |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -2016 | [11 empty] | 51 | Oct'3
BS-ONL | 48685 | 15393973 | 1872 | 263 | 2026-08-13 | 2026-08-21 | SS o nk TS | TS |  |  | 2026-09-17 | 2026-09-22 | 2026-10-06 | 2026-10-20 |  |  | 2026-10-25 | 2026-10-25 | 2026-11-02 | 2026-11-04 | 2026-11-05 | 2026-11-07 | 2026-11-12 |  |  |  |  | 2026-11-16 | 2026-11-18 |  |  | 2026-11-20 | 2026-11-24 | 2026-11-28 | 2026-12-14 | 2026-12-16 | 123 | O1 | Mainul | Chest |  | chocolate-936 pcs,,butter-936 pcs both combo 2 clr rub print |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -1872 | [11 empty] | 51 | Nov'1
BS-ONL | 48682 | 15392104 | 6258 | 1025 | 2026-08-13 | 2026-08-21 | SS o nk TS | TS |  |  | 2026-09-16 | 2026-09-22 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-17 | 2026-10-17 | 2026-10-24 | 2026-10-27 | 2026-10-30 |  |  |  |  | 2026-11-01 | 2026-11-12 | 2026-11-16 | 2026-11-20 |  |  | 2026-11-23 | 2026-11-25 | 2026-11-30 | 2026-12-14 | 2026-12-16 | 123 | O1 | Mainul |  | AOE | c.dan nk line fruit-3033 pcs frt nk line fruit patch attach applique emb ,,c.dan all over fruit-3225 pcs frt both slve all over fruit patch attach applique emb |  | Imp Fruit patch | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -6258 | [11 empty] | 51 | Oct'3
BS-ONL | 48683 | 15393395 | 4944 | 775 | 2026-08-13 | 2026-08-21 | SS V nk TS w slve fold tuck | TS |  |  | 2026-09-15 | 2026-09-21 | 2026-10-01 | 2026-10-15 |  |  | 2026-10-20 | 2026-10-20 | 2026-10-26 | 2026-10-28 | 2026-10-31 | 2026-11-04 | 2026-11-10 |  |  |  |  | 2026-11-13 | 2026-11-18 |  |  | 2026-11-20 | 2026-11-23 | 2026-11-27 | 2026-12-14 | 2026-12-16 | 123 | K | Mainul | Chest |  | c.dan-1648 pcs,,pink-1648 pcss,mermaid-1648 pcs all combo 1 clr gltr print |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -4944 | [11 empty] | 51 | Oct'3
BS-ONL | 48684 | 15393462 | 4800 | 801 | 2026-08-13 | 2026-08-21 | SS U nk TS | TS |  |  | 2026-09-11 | 2026-09-18 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-21 | 2026-10-23 | 2026-10-24 | 2026-10-27 | 2026-11-02 |  |  |  |  | 2026-11-05 | 2026-11-09 |  |  | 2026-11-12 | 2026-11-14 | 2026-11-20 | 2026-12-14 | 2026-12-16 | 123 | O1 | Mainul | Chest |  | c.dan-2400 pcs, pink-2400 pcs both combo 3 clr flock print |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -4800 | [11 empty] | 51 | Oct'3
BS-ONL | 48679 | 15377499 | 1400 | 359 | 2026-08-13 | 2026-08-21 | Full smock Tank top | Tank Top |  |  | 2026-09-15 | 2026-09-21 | 2026-10-02 | 2026-10-15 |  |  | 2026-10-21 | 2026-10-21 | 2026-10-27 | 2026-11-06 | 2026-11-07 | 2026-10-30 | 2026-11-04 |  |  |  |  | 2026-11-12 | 2026-11-14 |  |  | 2026-11-17 | 2026-11-20 | 2026-11-25 | 2026-12-14 | 2026-12-16 | 123 | M | Mainul |  |  |  |  | Smock at full body | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -1400 | [11 empty] | 51 | Nov'1
BS-ONL | 48678 | 15344142 | 1600 | 185 | 2026-08-13 | 2026-08-21 | AOP elasted shorts | Shorts |  |  | 2026-09-14 | 2026-09-18 | 2026-10-01 | 2026-10-10 | 2026-10-14 | 2026-10-20 | 2026-10-22 | 2026-10-22 | 2026-10-27 | 2026-10-29 | 2026-10-30 | [6 empty] | 2026-11-04 | 2026-11-06 |  |  | 2026-11-09 | 2026-11-12 | 2026-11-18 | 2026-12-14 | 2026-12-16 | 123 | L2 | Mainul |  |  |  | AOP |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -1600 | [11 empty] | 51 | Oct'3
BS-ONL | 48680 | 15380291 | 2232 | 264 | 2026-08-13 | 2026-08-21 | Contrast Strap Tank top | Tank Top |  |  | 2026-09-15 | 2026-09-22 | 2026-10-05 | 2026-10-25 |  |  | 2026-11-03 | 2026-11-03 | 2026-11-09 | 2026-11-12 | 2026-11-13 | [6 empty] | 2026-11-16 | 2026-11-17 |  |  | 2026-11-19 | 2026-11-21 | 2026-11-25 | 2026-12-14 | 2026-12-16 | 123 | M | Mainul | [5 empty] | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -2232 | [11 empty] | 51 | Nov'2
BS-ONL | 48677 | 15315193 | 1185 | 176 | 2026-08-13 | 2026-08-21 | SS o nk TS | TS |  |  | 2026-09-17 | 2026-09-23 | 2026-10-05 | 2026-10-18 |  |  | 2026-10-25 | 2026-10-25 | 2026-11-03 | 2026-11-05 | 2026-11-06 | 2026-11-09 | 2026-11-13 |  |  |  |  | 2026-11-16 | 2026-11-18 |  |  | 2026-11-20 | 2026-11-23 | 2026-11-28 | 2026-12-14 | 2026-12-16 | 123 | O1 | Mainul | Chest |  | c.dan-1185 pcs 2 clr pig 1 clr foil |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -1185 | [11 empty] | 51 | Nov'1
BS-ONL | 46748 14th | 15244714 | 5640 | 871 | 2026-08-15 | 2026-08-18 | SS o nk TS | TS |  |  | 2026-09-18 | 2026-09-25 | 2026-10-05 | 2026-10-20 |  |  | 2026-10-27 | 2026-10-27 |  | 2026-11-03 | 2026-11-06 | 2026-11-07 | 2026-11-10 |  |  |  |  | 2026-11-13 | 2026-11-17 |  |  | 2026-11-19 | 2026-11-20 | 2026-11-24 | 2026-12-14 | 2026-12-16 | 121 | F | Imran | Chest |  | beetroot-2820 pcs,,mermaid-2820 pcs all combo 1 clr gltr print |  |  | NFL1 |  |  | Need Cut FB | 0 | 0 | 0 | 0 | -5640 | [11 empty] | 51 | Nov'1 |  |  | 05.09.26
BS-ONL | 48642 | 15392656 | 6996 | 1581 | 2026-08-12 | 2026-08-19 | SS o nk TS | TS |  |  | 2026-09-20 | 2026-09-27 | 2026-10-05 | 2026-10-25 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-09 | 2026-11-12 | 2026-11-14 | [6 empty] | 2026-11-17 | 2026-11-21 |  |  | 2026-11-23 | 2026-11-25 | 2026-11-30 | 2026-12-21 | 2026-12-23 | 131 | T1 | Zahirul | [5 empty] | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -6996 | [11 empty] | 52 | Nov'2
BS-ONL | 43591 3rd | 15346092 | 2700 | 575 | 2026-08-12 | 2026-08-22 | SS o nk TS | TS |  |  | 2026-09-21 | 2026-09-25 | 2026-10-06 | 2026-10-18 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-30 | 2026-11-02 | 2026-11-03 | 2026-11-05 | 2026-11-06 |  |  | 2026-11-09 | 2026-11-12 | 2026-11-16 | 2026-11-19 |  |  | 2026-11-21 | 2026-11-24 | 2026-11-30 | 2026-12-21 | 2026-12-23 | 131 | T1 | Zahirul | Chest | Chest | Black-2700 pcs 1 clr rub 1 clr foil print and 1 clr flat emb |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -2700 | [11 empty] | 52 | Nov'1
BS-ONL | 27950 4th | 15315311 | 1908 | 475 | 2026-08-12 | 2026-08-22 | SS o nk TS | TS |  |  | 2026-09-23 | 2026-09-28 | 2026-10-01 | 2026-10-13 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-21 | 2026-10-23 | 2026-10-24 | 2026-10-27 | 2026-10-30 |  |  | 2026-11-02 | 2026-11-06 | 2026-11-09 | 2026-11-12 |  |  | 2026-11-14 | 2026-11-17 | 2026-11-19 | 2026-12-21 | 2026-12-23 | 131 | M | Zahirul | CHEST | CHEST | BLACK 1908 PCS 2 CLR RUB 1 CLR SEQ |  |  | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1908 | [11 empty] | 52 | Oct'3
BS-ONL | 27958 4th | 15176215 | 504 | 72 | 2026-08-12 | 2026-08-22 | Shorts w btm lace attach | Shorts |  |  | 2026-09-21 | 2026-09-23 | 2026-10-04 | 2026-10-14 |  |  | 2026-10-17 | 2026-10-17 | 2026-10-24 | 2026-10-28 | 2026-10-28 | [6 empty] | 2026-11-02 | 2026-11-03 |  |  | 2026-11-05 | 2026-11-07 | 2026-11-15 | 2026-12-21 | 2026-12-23 | 131 | A | Zahirul |  |  |  |  | Imp Lace | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -504 | [11 empty] | 52 | Oct'3
BS-ONL | 27954 4th | 15206763 | 516 | 110 | 2026-08-12 | 2026-08-22 | LDS 3/4 LEGGING W LACE AT LEG | LEGGING |  |  | 2026-09-21 | 2026-09-24 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-17 | 2026-10-17 | 2026-10-24 | 2026-10-28 | 2026-10-29 | [6 empty] | 2026-11-03 | 2026-11-04 |  |  | 2026-11-06 | 2026-11-10 | 2026-11-14 | 2026-12-21 | 2026-12-23 | 131 | A | Zahirul |  |  |  |  | Imp Lace | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -516 | [11 empty] | 52 | Oct'3
BS-ONL | 42450 4th | 15346157 | 4404 | 820 | 2026-08-12 | 2026-08-22 | SS o nk TS w slve woven emb lace | TS |  |  | 2026-10-03 | 2026-10-10 | 2026-10-20 | 2026-11-05 |  |  | 2026-11-10 | 2026-11-10 | 2026-11-16 | 2026-11-18 | 2026-11-21 | [6 empty] | 2026-11-23 | 2026-11-28 |  |  | 2026-12-02 | 2026-12-05 | 2026-12-10 | 2026-12-21 | 2026-12-23 | 131 | A | Zahirul |  |  |  |  | Imp woven Lace | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -4404 | [11 empty] | 52 | Nov'2
BS-ONL | 41836 11th | 15343893 | 7366 | 1271 | 2026-08-14 | 2026-08-20 | SS o nk TS | TS |  |  | 2026-09-15 | 2026-09-22 | 2026-09-25 | 2026-10-10 |  |  | 2026-10-12 | 2026-10-12 |  | 2026-10-19 | 2026-10-20 | [6 empty] | 2026-10-23 | 2026-10-28 |  |  | 2026-10-30 | 2026-11-05 | 2026-11-12 | 2026-12-21 | 2026-12-23 | 129 | W2 | Dalim | [5 empty] | NFL3 |  |  | Need Cut FB | 1273 | 0 | -1273 | 0 | -7366 | [11 empty] | 52 | Oct'2 |  |  | 02.09.26
BS-ONL | 42460 3rd | 15356881 | 1512 | 350 | 2026-08-18 | 2026-08-22 | SS O NK TS | TS |  |  | 2026-09-17 | 2026-09-22 | 2026-10-05 | 2026-10-18 |  |  | 2026-10-26 | 2026-10-26 | 2026-11-01 | 2026-11-04 | 2026-11-05 | 2026-11-07 | 2026-11-11 |  |  |  |  | 2026-11-14 | 2026-11-17 |  |  | 2026-11-19 | 2026-11-20 | 2026-11-25 | 2026-12-10 | 2026-12-12 | 114 | T1 | Zahirul | Fr,Bk |  | fuchisa-1104 pcs frt back 1 clr rub ,,c.dan-408 pcs frt back 4 clr rub print |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1512 | [11 empty] | 50 | Nov'1
BS-ONL | 48699 | 15355052 | 1128 | 220 | 2026-08-18 | 2026-08-22 | Belly part Elasted Legging | Legging |  |  | 2026-10-01 | 2026-10-05 | 2026-10-13 | 2026-10-25 |  |  | 2026-11-04 | 2026-11-04 | 2026-11-09 | 2026-11-12 | 2026-11-13 | [6 empty] | 2026-11-16 | 2026-11-18 |  |  | 2026-11-20 | 2026-11-23 | 2026-11-25 | 2026-12-14 | 2026-12-16 | 118 | P | Zahirul | [5 empty] | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -1128 | [11 empty] | 51 | Nov'2
BS-ONL | 45307 2nd | 15253458 | 528 | 180 | 2026-08-18 | 2026-08-22 | SS wrap maternity dress | Dress |  |  | 2026-10-01 | 2026-10-04 | 2026-10-10 | 2026-10-24 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-09 | 2026-11-12 | 2026-11-13 | [6 empty] | 2026-11-16 | 2026-11-18 |  |  | 2026-11-20 | 2026-11-23 | 2026-11-28 | 2026-12-14 | 2026-12-16 | 118 | J | Zahirul | [5 empty] | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -528 | [11 empty] | 51 | Nov'2
OVS SPA | 48487 | 271NDG021LDY14-6111 | 3734 | 1182 | 2026-08-15 | 2026-08-21 | AOP SL Dress w lace and frt self fabric string | Dress |  |  | 2026-10-01 | 2026-10-13 | 2026-10-14 | 2026-10-28 | 2026-11-02 | 2026-11-12 | 2026-11-28 | 2026-11-27 | 2026-12-02 | 2026-12-03 | 2026-12-05 | [6 empty] | 2026-12-07 | 2026-12-12 |  |  | 2026-12-14 | 2026-12-16 | 2026-12-18 | 2026-12-21 | 2026-12-21 | 128 | N/3 | Basir |  |  |  | AOP | Lace | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -3734 | [11 empty] | 52 | Dec'1
OVS SPA | 48599 | 271NDG007SB3-6111 | 7239 | 1689 | 2026-08-15 | 2026-08-21 | SS Full placket btn long dress w frt lace | Dress |  |  | 2026-10-01 | 2026-10-14 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-24 | 2026-11-25 | 2026-11-30 | 2026-12-01 | 2026-12-04 | [6 empty] | 2026-12-04 | 2026-12-14 |  |  | 2026-12-15 | 2026-12-17 | 2026-12-19 | 2026-12-21 | 2026-12-21 | 128 | B | Basir |  |  |  |  | Lace | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -7239 | [11 empty] | 52 | Dec'1
OVS SPA | 48600 | 271NDG014APW1-6111 | 8339 | 2001 | 2026-08-15 | 2026-08-21 | AOP SS frill slve gathered dress w front pleat | Dress |  |  | 2026-10-01 | 2026-10-13 | 2026-10-14 | 2026-10-28 | 2026-11-02 | 2026-11-12 | 2026-11-27 | 2026-11-25 | 2026-11-30 | 2026-12-01 | 2026-12-04 | [6 empty] | 2026-12-04 | 2026-12-14 |  |  | 2026-12-15 | 2026-12-17 | 2026-12-19 | 2026-12-21 | 2026-12-21 | 128 | N/3 | Basir |  |  |  | AOP |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -8339 | [11 empty] | 52 | Dec'1
OVS SPA | 48601 | 271NDG016PRLR2-6111 | 8067 | 1963 | 2026-08-15 | 2026-08-21 | AOP SS half placket btn dress w frt pkt and lower cut&sew | Dress |  |  | 2026-10-01 | 2026-10-13 | 2026-10-14 | 2026-10-28 | 2026-11-02 | 2026-11-12 | 2026-11-27 | 2026-11-25 | 2026-11-30 | 2026-12-01 | 2026-12-04 | [6 empty] | 2026-12-04 | 2026-12-14 |  |  | 2026-12-15 | 2026-12-17 | 2026-12-19 | 2026-12-21 | 2026-12-21 | 128 | C | Basir |  |  |  | AOP |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -8067 | [11 empty] | 52 | Dec'1
OVS SPA | 48602 | 271NDG0117SBA4-6111 | 6039 | 1480 | 2026-08-15 | 2026-08-21 | AOP SS half placket btn dress | Dress |  |  | 2026-10-01 | 2026-10-14 | 2026-10-15 | 2026-10-30 | 2026-11-02 | 2026-11-13 | 2026-11-24 | 2026-11-25 | 2026-11-30 | 2026-12-01 | 2026-12-04 | [6 empty] | 2026-12-04 | 2026-12-12 |  |  | 2026-12-14 | 2026-12-16 | 2026-12-18 | 2026-12-21 | 2026-12-21 | 128 | A | Basir |  |  |  | AOP |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -6039 | [11 empty] | 52 | Dec'1
OVS SPA | 48604 | 271PJA039PYJ10-6111 | 11012 | 1622 | 2026-08-15 | 2026-08-21 | AOP SS Frill slve TS Shorts w wiast bow sring | Top & BTM |  |  | 2026-10-01 | 2026-10-13 | 2026-10-14 | 2026-10-28 | 2026-11-02 | 2026-11-12 | 2026-11-24 | 2026-11-25 | 2026-11-30 | 2026-12-01 | 2026-12-05 | [6 empty] | 2026-12-04 | 2026-12-12 |  |  | 2026-12-14 | 2026-12-16 | 2026-12-18 | 2026-12-21 | 2026-12-21 | 128 | Q+P | Basir |  |  |  | AOP |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -11012 | [11 empty] | 52 | Dec'1
BS-ONL | 48687 | 15382416 | 3360 | 325 | 2026-08-13 | 2026-08-21 | AOP Tank top w strap nk Lace | Tank Top |  |  | 2026-10-01 | 2026-10-06 | 2026-10-10 | 2026-10-25 | 2026-11-02 | 2026-11-07 | 2026-11-14 | 2026-11-14 | 2026-11-23 | 2026-11-26 | 2026-11-27 | [6 empty] | 2026-12-01 | 2026-12-04 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-15 | 2027-01-11 | 2027-01-13 | 151 | M | Mainul |  |  |  | AOP | Lace | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -3360 | [11 empty] | 3 | Nov'3
BS-ONL | 48688 | 15357056 | 2600 | 840 | 2026-08-13 | 2026-08-21 | SL Frill long cut& sew dress | Dress |  |  | 2026-11-01 | 2026-11-05 | 2026-11-10 | 2026-11-25 |  |  | 2026-12-04 | 2026-12-04 | 2026-12-11 | 2026-12-14 | 2026-12-17 | [6 empty] | 2026-12-21 | 2026-12-24 |  |  | 2026-12-28 | 2026-12-30 | 2027-01-10 | 2027-02-08 | 2027-02-10 | 179 | J | Mainul | [5 empty] | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -2600 | [11 empty] | 7 | Dec'2
BS-ONL | 48698 | 15397439 | 680 | 135 | 2026-08-18 | 2026-08-22 | Belly part Elasted Legging | Legging |  |  | 2026-10-10 | 2026-10-14 | 2026-10-20 | 2026-10-30 |  |  | 2026-11-16 | 2026-11-16 | 2026-11-23 | 2026-11-26 | 2026-11-26 | [6 empty] | 2026-12-01 | 2026-12-02 |  |  | 2026-12-05 | 2026-12-08 | 2026-12-12 | 2027-01-11 | 2027-01-13 | 146 | L2 | Zahirul | [5 empty] | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -680 | [11 empty] | 3 | Nov'3
BS-ONS | 45964 14th | 22039968 | 5000 | 3638 | 2026-08-25 | 2026-08-26 | LS High nk Haalf Zipp Swt shirt | Swt Shirt |  |  | 2026-08-28 | 2026-09-03 | 2026-09-03 | 2026-09-14 |  |  | 2026-09-10 | 2026-09-10 |  | 2026-09-14 | 2026-09-18 | [6 empty] | 2026-09-18 | 2026-09-24 |  |  | 2026-09-25 | 2026-09-26 | 2026-09-26 | 2026-09-28 | 2026-09-30 | 34 | R | Shakel | [5 empty] | NFL2 |  |  | Cut Run | 3637 | 2603 | -1034 | 2268 | -2732 | [11 empty] | 40 | Sep'2 |  |  | 05.09.26
BS-ONS | 26828 76th | 22029226 | 11016 | 6883 | 2026-08-27 | 2026-08-28 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-08-17 | 2026-08-31 | 2026-08-25 | 2026-09-10 |  |  | 2026-09-05 | 2026-09-05 |  | 2026-09-10 | 2026-09-13 | [6 empty] | 2026-09-12 | 2026-09-18 |  |  | 2026-09-19 | 2026-09-19 | 2026-09-21 | 2026-09-21 | 2026-09-23 | 25 | E | Shakel | [5 empty] | NFL1 |  |  | Cut Run | 7141 | 2824 | -4317 | 4638 | -6378 | [11 empty] | 39 | Sep'1 |  |  | 07.09.26
BS-ONL | 22034 55th | 15060061 | 18358 | 3051 | 2026-08-20 | 2026-08-24 | Tank Top | Tank Top |  |  | 2026-11-24: 2026-09-10; 2026-11-25: 2026-09-10; 2026-12-01: 2026-09-14; 2026-12-05: 2026-09-18 | [6 empty] | 2026-09-18 | 2026-09-24 |  |  | 2026-09-25 | 2026-09-26 | 2026-09-28 | 2026-09-28 | 2026-09-30 | 39 | G1 | Imran |  |  |  |  | Stock fab from 43465/VMI | NFL1 |  |  | Cut Run | 0 | 0 | 0 | 4550 | -13808 | [11 empty] | 40 | Sep'2 |  |  | 02.09.26
BS-ONL | 22035 74th | 15095808 | 22048 | 3148 | 2026-08-20 | 2026-08-24 | Tank Top | Tank Top |  |  | 2026-11-24: 2026-09-10; 2026-11-25: 2026-09-07; 2026-12-01: 2026-09-12; 2026-12-05: 2026-09-17 | [6 empty] | 2026-09-16 | 2026-09-25 |  |  | 2026-09-26 | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2026-09-30 | 39 | ZA2 | Imran |  |  |  |  | Stock fab from 43465/VMI | NFL3 |  |  | Need Cut FB | 0 | 0 | 0 | 0 | -22048 | [11 empty] | 40 | Sep'2 |  |  | 02.09.26
UTG-AF | 41711 5th | BAD1529mamaAJ | 4000 | 915 | 2026-08-25 | 2026-08-26 | Legging | Legging |  |  | 2026-08-27 | 2026-09-02 | 2026-09-02 | 2026-09-11 |  |  | 2026-09-11 | 2026-09-12 |  | 2026-09-14 | 2026-09-15 | [6 empty] | 2026-09-16 | 2026-09-19 |  |  | 2026-09-21 | 2026-09-23 | 2026-09-25 | 2026-09-26 | 2026-09-28 | 32 | N/3 | Rana | [5 empty] | NCL |  |  | Ready Test Cut | 915 | 455 | -460 | 0 | -4000 | [11 empty] | 40 | Sep'2
UTG-AF | 41712 16th | BAD2323mamaAB | 3600 | 930 | 2026-08-25 | 2026-08-26 | LDS LONG LEGGINGS | LEGGING |  |  | 2026-08-27 | 2026-09-02 | 2026-09-02 | 2026-09-11 |  |  | 2026-09-11 | 2026-09-12 |  | 2026-09-14 | 2026-09-15 | [6 empty] | 2026-09-16 | 2026-09-19 |  |  | 2026-09-21 | 2026-09-23 | 2026-09-25 | 2026-09-26 | 2026-09-28 | 32 | O1 | Rana | [5 empty] | NFL2 |  |  | Need Cut | 930 | 310 | -620 | 0 | -3600 | [11 empty] | 40 | Sep'2 |  |  | 02.09.26
BS-ONL | 48690 | 15393464 | 1008 | 150 | 2026-08-26 | 2026-08-28 | SS o nk TS | TS |  |  | 2026-09-05 | 2026-09-10 | 2026-09-12 | 2026-09-26 |  |  | 2026-09-28 | 2026-09-28 | 2026-10-03 | 2026-10-06 | 2026-10-07 | 2026-10-09 | 2026-10-13 |  |  |  |  | 2026-10-15 | 2026-10-16 |  |  | 2026-10-17 | 2026-10-19 | 2026-10-21 | 2026-10-26 | 2026-10-28 | 61 | L1 | Mainul | Chest |  | c.dan-504 pcs,,cayenne-504 pcs both combo 1 clr flock print |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -1008 | [11 empty] | 44 | Oct'1
BS-ONL | 48952 | 15400304 | 5972 | 2664 | 2026-08-26 | 2026-08-28 | LS TS w nk Rib and front placket button | TS |  |  | 2026-09-03 | 2026-09-12 | 2026-09-12 | 2026-09-25 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-29 | 2026-10-01 | 2026-10-03 | [6 empty] | 2026-10-03 | 2026-10-08 |  |  | 2026-10-09 | 2026-10-10 | 2026-10-12 | 2026-10-12 | 2026-10-14 | 47 | S | Mainul | [5 empty] | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -5972 | [11 empty] | 42 | Oct'1
BS-ONL | 22040 28th | 152191323 | 10000 | 1984 | 2026-08-25 | 2026-08-26 | LDS 2 PACK LEGGING | LEGGING |  |  | 2026-11-24: 2026-09-15; 2026-11-25: 2026-09-11; 2026-12-01: 2026-09-15; 2026-12-05: 2026-09-18 | [6 empty] | 2026-09-21 | 2026-09-28 |  |  | 2026-09-30 | 2026-10-02 | 2026-10-05 | 2026-10-19 | 2026-10-21 | 55 | O1 | Imran |  |  |  |  | Stock fab from 43465 | NFL2 |  |  | Need Cut FB | 0 | 0 | 0 | 0 | -10000 | [11 empty] | 43 | Sep'2 |  |  | 02.09.26
BS-ONL | 48640 | 15397791 | 2004 | 395 | 2026-08-12 | 2026-08-26 | Solid Tank Top | Tank Top |  |  | 2026-09-02 | 2026-09-07 | 2026-09-12 | 2026-09-24 |  |  | 2026-09-26 | 2026-09-26 | 2026-10-03 | 2026-10-05 | 2026-10-06 | 2026-10-08 | 2026-10-09 |  |  |  |  | 2026-10-12 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-21 | 68 | T1 | Zahirul | Nk |  | 4 combo nk label print |  |  | NFL3 |  |  | File Due | 395 | 0 | -395 | 0 | -2004 | [11 empty] | 43 | Oct'1
BS-ONL | 48634 | 15392911 | 747 | 255 | 2026-08-12 | 2026-08-28 | LS o nk Swt shirt w both slve woven lace and side slit | Swt Shirt |  |  | 2026-09-07 | 2026-09-13 | 2026-09-22 | 2026-10-02 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-08 | 2026-10-10 | 2026-10-10 | [6 empty] | 2026-10-13 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 68 | R | Zahirul |  |  |  |  | Woven Lace | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -747 | [11 empty] | 43 | Oct'1
BS-ONL | 48637 | 15392804 | 2418 | 1275 | 2026-08-12 | 2026-08-28 | LS O nk Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-09-03 | 2026-09-09 | 2026-09-11 | 2026-09-26 |  |  | 2026-09-26 | 2026-09-26 | 2026-10-02 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-10 |  |  |  |  | 2026-10-13 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 68 | T2 | Zahirul | Chest |  | cayene-762 pcs 2 clr rub ,,black trddy-756 pcs ,,black-900 pcs |  | 2 combo print artwork due | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2418 | [11 empty] | 43 | Oct'1
BS-ONL | 48636 | 15392912 | 504 | 265 | 2026-08-12 | 2026-08-28 | LS Swt shirt dress w slve woven lace | Dress |  |  | 2026-09-08 | 2026-09-13 | 2026-09-22 | 2026-10-03 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-10 | 2026-10-12 | 2026-10-12 | [6 empty] | 2026-10-14 | 2026-10-15 |  |  | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-19 | 2026-10-21 | 68 | R | Zahirul |  |  |  |  | Woven Lace | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -504 | [11 empty] | 43 | Oct'2
BS-ONL | 48638 | 15338080 | 1800 | 560 | 2026-08-12 | 2026-08-28 | High waist Legging w cut & sew mesh and leg opening lace attach | Legging |  |  | 2026-09-08 | 2026-09-13 | 2026-09-21 | 2026-09-30 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-06 | 2026-10-08 | 2026-10-09 | [6 empty] | 2026-10-12 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-21 | 68 | P | Zahirul |  |  |  |  | Mesh & lace | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -1800 | [11 empty] | 43 | Oct'1
BS-ONL | 48632 | 15395966 | 1364 | 345 | 2026-08-12 | 2026-08-29 | SS O nk TS | TS |  |  | 2026-09-07 | 2026-09-12 | 2026-09-15 | 2026-09-28 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-08 | 2026-10-10 | 2026-10-10 | [6 empty] | 2026-10-13 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 68 | F | Zahirul | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -1364 | [11 empty] | 43 | Oct'1
BS-ONL | 48831 | 15398778 | 1650 | 605 | 2026-08-21 | 2026-08-26 | LS Swt Shirt w cuff btm rib | Swt Shirt |  |  | 2026-08-28 | 2026-09-10 | 2026-09-05 | 2026-09-18 |  |  | 2026-09-14 | 2026-09-18 | 2026-09-19 | 2026-09-22 | 2026-09-23 |  |  |  |  | 2026-09-24 | 2026-09-29 | 2026-10-01 | 2026-10-02 |  |  | 2026-10-03 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-07 | 45 | N1 | Abid | Chest | Chest | Zephyr-825 pcs,,bracken-825 pcs both combo 1 clr rub 1 clr terry emb |  |  | NFL2 |  |  | File Due | 606 | 0 | -606 | 0 | -1650 | [11 empty] | 41 | Sep'3
GBX-New Look | 48724 | RW915-2587 | 14010 | 2061 | 2026-08-24 | 2026-08-24 | Front double layer Tank top | Tank Top |  |  | 2026-08-27 | 2026-09-08 | 2026-09-07 | 2026-09-23 |  |  | 2026-09-21 | 2026-09-21 | 2026-09-25 | 2026-09-28 | 2026-10-03 | [6 empty] | 2026-10-01 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 54 | N/3 | Sifat | [5 empty] | NCL |  |  | File Due | 2212 | 0 | -2212 | 0 | -14010 | [11 empty] | 43 | Sep'3
GBX-New Look | 48726 | CNOFJTSS38016 | 2470 | 325 | 2026-08-27 | 2026-08-25 | V nk Tank Top | Tank Top |  |  | 2026-09-12 | 2026-09-17 | 2026-09-21 | 2026-10-05 |  |  | 2026-10-07 | 2026-10-07 | 2026-10-12 | 2026-10-14 | 2026-10-15 | [6 empty] | 2026-10-13 | 2026-10-16 |  |  | 2026-10-17 | 2026-10-19 | 2026-10-20 | 2026-10-24 | 2026-10-25 | 58 | N/1 | Sifat | [5 empty] | NCL |  |  | File Due | 325 | 0 | -325 | 0 | -2470 | [11 empty] | 44 | Oct'2
GBX-New Look | 48543 3rd | 9148519 | 6560 | 1515 | 2026-08-27 | 2026-08-25 | Skirt w three layer frill | Skirt |  |  | 2026-09-01 | 2026-09-09 | 2026-09-14 | 2026-09-26 |  |  | 2026-09-30 | 2026-09-26 |  | 2026-10-01 | 2026-10-05 | [6 empty] | 2026-10-05 | 2026-10-12 |  |  | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 50 | N/2 | Sifat | [5 empty] | NCL |  |  | Po Sheet Due | 1515 | 0 | -1515 | 0 | -6560 | [11 empty] | 42 | Oct'1
GBX-New Look | 48543 4th | 9148519 | 20200 | 4652 | 2026-08-27 | 2026-08-25 | Skirt w three layer frill | Skirt |  |  | 2026-09-01 | 2026-09-12 | 2026-09-12 | 2026-09-26 |  |  | 2026-09-25 | 2026-09-22 |  | 2026-09-26 | 2026-10-04 | [6 empty] | 2026-10-01 | 2026-10-20 |  |  | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-24 | 2026-10-25 | 58 | N/1 | Sifat | [5 empty] | NCL |  |  | Po Sheet Due | 4652 | 0 | -4652 | 0 | -20200 | [11 empty] | 44 | Sep'3
GBX-New Look | 48728 | CNOFJTSS37412 V2 | 18600 | 1960 | 2026-08-27 | 2026-08-25 | Wrap fitted Cami Tank top | Tank Top |  |  | 2026-09-01 | 2026-09-13 | 2026-09-12 | 2026-09-28 |  |  | 2026-09-28 | 2026-09-28 | 2026-10-03 | 2026-10-05 | 2026-10-09 | [6 empty] | 2026-10-08 | 2026-10-19 |  |  | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-24 | 2026-10-25 | 58 | N/3 | Sifat | [5 empty] | NCL |  |  | File Due | 1960 | 0 | -1960 | 0 | -18600 | [11 empty] | 44 | Oct'1
GBX-New Look | 48727 | RW915-2586 | 1020 | 25 | 2026-08-29 | 2026-08-27 | AOP Cut & Sew Strap cami Tank top | Tank Top |  |  | 2026-09-10 | 2026-09-14 | 2026-09-21 | 2026-09-30 | 2026-10-02 | 2026-10-08 | 2026-10-08 | 2026-10-08 | 2026-10-14 | 2026-10-16 | 2026-10-17 | [6 empty] | 2026-10-20 | 2026-10-22 |  |  | 2026-10-24 | 2026-10-26 | 2026-10-27 | 2026-10-31 | 2026-10-31 | 63 | N/2 | Sifat |  |  |  | AOP |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -1020 | [11 empty] | 44 | Oct'2
GBX-New Look | 48730 | CNOFJTKL37381 | 820 | 116 | 2026-08-22 | 2026-08-27 | SL V nk Strap Cami dress w lace | Dress |  |  | 2026-09-10 | 2026-09-05 | 2026-09-24 | 2026-10-05 |  |  | 2026-10-07 | 2026-10-07 | 2026-10-14 | 2026-10-16 | 2026-10-17 | [6 empty] | 2026-10-20 | 2026-10-22 |  |  | 2026-10-22 | 2026-10-24 | 2026-10-26 | 2026-10-31 | 2026-10-31 | 70 | N/3 | Sifat |  |  |  |  | Lace | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -820 | [11 empty] | 44 | Oct'2
GBX-New Look | 48944 | 9602962 | 5597 | 896 | 2026-08-28 | 2026-08-27 | YD Cinched waist slash nk TS | TS | 2026-09-14 | 2026-09-19 | 2026-09-21 | 2026-09-30 | 2026-10-02 | 2026-10-08 |  |  | 2026-10-09 | 2026-10-09 | 2026-10-14 | 2026-10-16 | 2026-10-19 | [6 empty] | 2026-10-19 | 2026-10-23 |  |  | 2026-10-26 | 2026-10-27 | 2026-10-30 | 2026-10-31 | 2026-10-31 | 64 | N/1 | Sifat |  |  |  | YD |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -5597 | [11 empty] | 44 | Oct'2
GBX-New Look | 47424 6th | 9646803 | 6551 | 2144 | 2026-08-25 | 2026-08-27 | YD legging w drawstring | Legging | 2026-09-15 | 2026-09-22 | 2026-09-22 | 2026-10-03 | 2026-10-03 | 2026-10-10 |  |  | 2026-10-10 | 2026-10-10 |  | 2026-10-25 | 2026-10-19 | [6 empty] | 2026-10-19 | 2026-10-24 |  |  | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-31 | 2026-10-31 | 67 | N/1 | Sifat |  |  |  | YD |  | NCL |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -6551 | [11 empty] | 44 | Oct'3
GBX-New Look | 48729 | CNOFJTSS38024 | 1020 | 188 | 2026-08-28 | 2026-08-28 | YD front double halter nk Cami w side slit | Tank Top | 2026-09-15 | 2026-09-21 | 2026-09-25 | 2026-09-30 | 2026-10-03 | 2026-10-08 |  |  | 2026-10-10 | 2026-10-10 | 2026-10-15 | 2026-10-17 | 2026-10-19 | [6 empty] | 2026-10-21 | 2026-10-23 |  |  | 2026-10-24 | 2026-10-26 | 2026-10-27 | 2026-10-31 | 2026-10-31 | 64 | N/1 | Sifat |  |  |  | YD |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -1020 | [11 empty] | 44 | Oct'2
GBX-New Look | 48725 | CNOFJTSS37566 | 17591 | 2187 | 2026-08-25 | 2026-08-28 | YD SS o nk TS | TS | 2026-09-12 | 2026-09-21 | 2026-09-19 | 2026-09-30 | 2026-09-28 | 2026-10-05 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-08 | 2026-10-10 | 2026-10-15 | [6 empty] | 2026-10-13 | 2026-10-27 |  |  | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-10-31 | 67 | Y | Sifat |  |  |  | YD |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -17591 | [11 empty] | 44 | Oct'1
GBX-New Look | 48731 | RW915-2576 | 820 | 152 | 2026-08-28 | 2026-08-28 | YD henley Tank top w frt placket btn | Tank Top | 2026-09-17 | 2026-09-22 | 2026-09-25 | 2026-09-30 | 2026-10-05 | 2026-10-10 |  |  | 2026-10-12 | 2026-10-12 | 2026-10-17 | 2026-10-19 | 2026-10-19 | [6 empty] | 2026-10-21 | 2026-10-23 |  |  | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-31 | 2026-10-31 | 64 | N/1 | Sifat |  |  |  | YD |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -820 | [11 empty] | 44 | Oct'2
GBX-Maurices | 48715 | 2596383/4706383 | 11498 | 2411 | 2026-08-25 | 2026-08-26 | YD SS o nk TS | TS | 2026-09-05 | 2026-09-14 | 2026-09-12 | 2026-09-22 | 2026-09-18 | 2026-09-25 |  |  | 2026-09-23 | 2026-09-23 | 2026-09-28 | 2026-10-01 | 2026-10-05 | 2026-10-03 | 2026-10-09 |  |  |  |  | 2026-10-08 | 2026-10-16 |  |  | 2026-10-19 | 2026-10-20 | 2026-10-22 | 2026-10-24 | 2026-10-24 | 60 | N/3 | Mannan | Chest,HP |  | br. White-11498 pcs 1 clr pig /Rub print and nk HP sticker | YD |  | NCL |  |  | File Due | 2411 | 0 | -2411 | 0 | -11498 | [11 empty] | 43 | Oct'1
GBX-Maurices | 48716 | 2590899/4257899 | 17776 | 3698 | 2026-08-26 | 2026-08-28 | SS crew nk TS w frt pkt | TS |  |  | 2026-09-05 | 2026-09-15 | 2026-09-14 | 2026-09-30 |  |  | 2026-10-01 | 2026-09-29 | 2026-10-04 | 2026-10-05 | 2026-10-12 | 2026-10-12 | 2026-10-22 |  |  | 2026-10-06 | 2026-10-13 | 2026-10-09 | 2026-10-20 |  |  | 2026-10-22 | 2026-10-23 | 2026-10-23 | 2026-10-24 | 2026-10-24 | 59 | N/3 | Mannan | Heat Press/Heat Seal | Chest | Cinder-17776 pcs 6 clr flat emb and nk Heat seal |  |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -17776 | [11 empty] | 43 | Oct'1
UTG-AF | 43306 19th | BAD1368AL | 5000 | 890 | 2026-08-27 | 2026-08-29 | LDS V NK TS | TS |  |  | 2026-09-05 | 2026-09-12 | 2026-09-14 | 2026-09-26 |  |  | 2026-10-01 | 2026-10-02 |  | 2026-10-05 | 2026-10-06 | [6 empty] | 2026-10-07 | 2026-10-10 |  |  | 2026-10-12 | 2026-10-14 | 2026-10-16 | 2026-10-24 | 2026-10-26 | 58 | G2 | Rana | [5 empty] | NFL1 |  |  | CAD | 0 | 0 | 0 | 0 | -5000 | [11 empty] | 44 | Oct'1 |  |  | 15.09.26
BS-NMT | 48754 | 13241567 | 9310 | 1047 | 2026-08-20 | 2026-08-28 | SS o nk TS w nk rib | TS |  |  | 2026-09-07 | 2026-09-15 | 2026-09-25 | 2026-10-10 |  |  | 2026-10-10 | 2026-10-10 | 2026-10-15 | 2026-10-17 | 2026-10-21 | 2026-10-20 | 2026-10-26 |  |  |  |  | 2026-10-26 | 2026-10-31 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-07 | 2026-11-14 | 2026-11-16 | 86 | ZA2 | Kamruzzaman | Chest,Nk |  | crockery-3356 pcs 5 clr rub,,basil shark-448 pcs 6 clr rub ,,basil space-1452 pcs 5 clr rub ,,blue-1540 pcs 4 clr rub..spellbound-2514 pcs 6 clr rub |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -9310 | [11 empty] | 47 | Oct'2
BS-NMT | 48756 | 13231015 | 4044 | 549 | 2026-08-20 | 2026-08-28 | AOP SS o nk Dress w btm cut&sew slve frill | Dress |  |  | 2026-09-08 | 2026-09-15 | 2026-09-23 | 2026-10-08 | 2026-10-09 | 2026-10-16 | 2026-10-17 | 2026-10-17 | 2026-10-22 | 2026-10-24 | 2026-10-27 | 2026-10-28 | 2026-10-30 |  |  |  |  | 2026-11-02 | 2026-11-05 |  |  | 2026-11-07 | 2026-11-10 | 2026-11-12 | 2026-11-14 | 2026-11-16 | 86 | V | Kamruzzaman | Nk |  | 3 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -4044 | [11 empty] | 47 | Oct'3
BS-NMT | 48757 | 13230153 | 6516 | 842 | 2026-08-20 | 2026-08-28 | AOP SL Tank top dress | Dress |  |  | 2026-09-10 | 2026-09-15 | 2026-09-22 | 2026-10-05 | 2026-10-06 | 2026-10-12 | 2026-10-12 | 2026-10-12 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 2026-10-21 | 2026-10-24 |  |  |  |  | 2026-10-26 | 2026-10-30 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-10 | 2026-11-16 | 2026-11-18 | 88 | T1 | Kamruzzaman | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -6516 | [11 empty] | 47 | Oct'2
BS-NMT | 48759 | 13227472/13231673 | 5437 | 820 | 2026-08-20 | 2026-08-28 | SS o nk TS w nk rib | TS |  |  | 2026-09-12 | 2026-09-18 | 2026-10-01 | 2026-10-15 |  |  | 2026-10-17 | 2026-10-17 | 2026-10-22 | 2026-10-24 | 2026-10-26 | 2026-10-28 | 2026-11-03 |  |  |  |  | 2026-11-05 | 2026-11-09 |  |  | 2026-11-12 | 2026-11-14 | 2026-11-17 | 2026-11-21 | 2026-11-23 | 93 | ZA2 | Kamruzzaman | Chest,Nk |  | crockery-376 pcs 3 clr rub ,,popcorn-766 pcs 3 clr rub,,blue-851 pcs 1 clr rub ,,c.dan-1572 pcs 3 clr pig ,,mosstone-1872 pcs 5 clr rub |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -5437 | [11 empty] | 48 | Oct'3
BS-NMT | 48760 | 13266439 | 3789 | 669 | 2026-08-20 | 2026-08-28 | SS o nk TS w nk rib | TS |  |  | 2026-09-10 | 2026-09-16 | 2026-10-01 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-20 | 2026-10-22 | 2026-10-26 | 2026-10-26 | 2026-10-31 |  |  |  |  | 2026-11-05 | 2026-11-09 |  |  | 2026-11-11 | 2026-11-13 | 2026-11-16 | 2026-11-21 | 2026-11-23 | 93 | ZA2 | Kamruzzaman | Chest,Nk |  | blue-1530 pcs 4 clr rub ,,c.dan-1371 pcs 2 clr pig ,,pink-888 pcs 2 clr pig |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3789 | [11 empty] | 48 | Oct'3
BS-NMT | 48761 | 13259697/13257632 | 6782 | 1170 | 2026-08-20 | 2026-08-28 | SS o nk TS w nk rib | TS |  |  | 2026-09-04 | 2026-09-15 | 2026-09-25 | 2026-10-13 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-21 | 2026-10-23 | 2026-10-26 | 2026-10-28 | 2026-11-02 |  |  |  |  | 2026-11-04 | 2026-11-07 |  |  | 2026-11-10 | 2026-11-12 | 2026-11-16 | 2026-11-23 | 2026-11-25 | 95 | ZA2 | Kamruzzaman | Chest,Nk |  | green-2011 pcs 1 clr rub ,,crockery-1304 pcs 2 clr rub ,,blue-1731 pcs 3 clr rub ,,spellbound-1736 pcs 5 clr rub |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -6782 | [11 empty] | 48 | Oct'3
BS-NMT | 48763 | 13267490 | 4294 | 780 | 2026-08-20 | 2026-08-28 | SS o nk TS w nk rib | TS |  |  | 2026-09-09 | 2026-09-15 | 2026-09-27 | 2026-10-13 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-20 | 2026-10-22 | 2026-10-24 | 2026-10-26 | 2026-10-30 |  |  |  |  | 2026-11-03 | 2026-11-06 |  |  | 2026-11-09 | 2026-11-12 | 2026-11-14 | 2026-11-21 | 2026-11-23 | 93 | ZA2 | Kamruzzaman | Chest,Nk |  | c.dan-1184 pcs 5 clr pig ,,green-1555 pcs 3 clr rub ,,blue-1555 pcs 4 clr rub |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -4294 | [11 empty] | 48 | Oct'3
BS-NMT | 48764 | 13231684 | 2160 | 265 | 2026-08-20 | 2026-08-28 | SL o nk TS w nk rib | TS |  |  | 2026-09-10 | 2026-09-15 | 2026-10-01 | 2026-10-13 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-21 | 2026-10-23 | 2026-10-24 | 2026-10-27 | 2026-10-30 |  |  |  |  | 2026-11-02 | 2026-11-04 |  |  | 2026-11-06 | 2026-11-09 | 2026-11-12 | 2026-11-23 | 2026-11-25 | 95 | T1 | Kamruzzaman | Chest,Nk |  | c.dan-1080 pcs,,Navy-1080 pcs |  | Print art work due | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2160 | [11 empty] | 48 | Oct'3
BS-NMT | 48765 | 13214406/13231661 | 4916 | 914 | 2026-08-20 | 2026-08-28 | AOP SS o nk Dress w btm cut&sew slve frill | Dress |  |  | 2026-09-05 | 2026-09-13 | 2026-09-21 | 2026-10-05 | 2026-10-06 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-19 | 2026-10-21 | 2026-10-23 | 2026-10-23 | 2026-10-26 |  |  |  |  | 2026-10-27 | 2026-10-30 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-07 | 2026-11-17 | 2026-11-19 | 89 | V | Kamruzzaman | Nk |  | 3 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -4916 | [11 empty] | 47 | Oct'3
BS-NMT | 48766 | 13227481 | 2429 | 658 | 2026-08-20 | 2026-08-28 | Waist belt pant w side pkt | Pant |  |  | 2026-09-17 | 2026-09-22 | 2026-10-01 | 2026-10-13 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-21 | 2026-10-23 | 2026-10-24 | 2026-10-27 | 2026-10-28 |  |  |  |  | 2026-11-02 | 2026-11-05 |  |  | 2026-11-07 | 2026-11-10 | 2026-11-13 | 2026-11-23 | 2026-11-25 | 95 | X | Kamruzzaman | Waist |  | 2 combo label print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2429 | [11 empty] | 48 | Oct'3
BS-NMT | 48752 | 13224958 | 1396 | 120 | 2026-08-20 | 2026-08-29 | LS O nk TS w nk Rib | TS |  |  | 2026-09-10 | 2026-09-14 | 2026-09-25 | 2026-10-10 |  |  | 2026-10-10 | 2026-10-10 | 2026-10-15 | 2026-10-17 | 2026-10-19 | 2026-10-20 | 2026-10-23 |  |  |  |  | 2026-10-26 | 2026-10-27 |  |  | 2026-10-28 | 2026-10-30 | 2026-11-05 | 2026-11-16 | 2026-11-18 | 88 | ZA1 | Kamruzzaman | Chest,Nk |  | blue-532 pcs,,c.dan-432 pcs,,vanilla-432 pcs all combo 5 clr pig print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1396 | [11 empty] | 47 | Oct'2
BS-NMT | 48755 | 13234339 | 2747 | 339 | 2026-08-20 | 2026-08-29 | LS O nk TS w nk Rib | TS |  |  | 2026-09-08 | 2026-09-14 | 2026-09-22 | 2026-10-10 |  |  | 2026-10-12 | 2026-10-12 | 2026-10-17 | 2026-10-19 | 2026-10-20 | 2026-10-20 | 2026-10-23 |  |  |  |  | 2026-10-26 | 2026-10-28 |  |  | 2026-10-30 | 2026-11-03 | 2026-11-05 | 2026-11-16 | 2026-11-18 | 88 | ZA1 | Kamruzzaman | Chest,Nk |  | c.dan-891 pcs,,crockery-147 pcs,,basil-756 pcs,,blue-953 pcs all combo 6 clr pig /rub print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2747 | [11 empty] | 47 | Oct'2
BS-NMT | 48753 | 13228145 | 3400 | 349 | 2026-08-20 | 2026-08-29 | SS TS w roll slve fold tuck | TS |  |  | 2026-09-08 | 2026-09-14 | 2026-09-23 | 2026-10-09 |  |  | 2026-10-10 | 2026-10-10 | 2026-10-15 | 2026-10-17 | 2026-10-20 | 2026-10-20 | 2026-10-24 |  |  |  |  | 2026-10-27 | 2026-10-30 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-06 | 2026-11-16 | 2026-11-18 | 88 | Z | Kamruzzaman | Chest,Nk |  | blue-1164 pcs 5 clr rub ,,pink-1200 pcs 4 clr pig ,,orchid-1036 pcs 4 clr pig |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3400 | [11 empty] | 47 | Oct'2
BS-NMT | 48758 | 13227467 | 815 | 114 | 2026-08-20 | 2026-08-29 | SS TS w roll slve fold tuck | TS |  |  | 2026-09-10 | 2026-09-14 | 2026-10-01 | 2026-10-13 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-21 | 2026-10-23 | 2026-10-23 | 2026-10-26 | 2026-10-28 |  |  |  |  | 2026-10-30 | 2026-10-31 |  |  | 2026-11-04 | 2026-11-07 | 2026-11-10 | 2026-11-23 | 2026-11-25 | 95 | Z | Kamruzzaman | Chest,Nk |  | blue-280 pcs 2 clr rub ,,pink-280 pcs 1 clr pig ,,orchid-255 pcs 5 clr pig |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -815 | [11 empty] | 48 | Oct'3
BS-NMT | 48747 | 13266169 | 2239 | 1054 | 2026-08-19 | 2026-08-29 | LS Swt hoodie w cuff btm rib and kangaro pkt | Hoody |  |  | 2026-09-10 | 2026-09-17 | 2026-10-01 | 2026-10-15 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-20 | 2026-10-22 | 2026-10-24 | 2026-10-26 | 2026-10-30 |  |  |  |  | 2026-11-02 | 2026-11-05 |  |  | 2026-11-07 | 2026-11-10 | 2026-11-14 | 2026-11-22 | 2026-11-24 | 95 | S | Shamoly | Fr,Bk |  | oceana-1157 pcsfrt 1 clr rub 1 clr puff back 5 clr rub 1 clr puff,,pink-1082 pcs frt 2 clr rub 1 clr puff back 4 clr rub 2 clr puff |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2239 | [11 empty] | 48 | Oct'3
BS-NMT | 48792 | 13246830 | 2933 | 256 | 2026-08-19 | 2026-08-28 | LS body w collar placket wood btn front bow and btm snap btn | Body |  |  | 2026-09-08 | 2026-09-15 | 2026-09-24 | 2026-10-07 |  |  | 2026-10-09 | 2026-10-09 | 2026-10-15 | 2026-10-17 | 2026-10-20 | 2026-10-20 | 2026-10-23 |  |  |  |  | 2026-10-24 | 2026-10-31 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-09 | 2026-11-16 | 2026-11-18 | 89 | S+T | Mosaddik | Nk |  | 2 combo nk label print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2933 | [11 empty] | 47 | Oct'2
BS-NMT | 48798 | 13265575 | 3681 | 526 | 2026-08-19 | 2026-08-28 | AOP LS swt shirt w cuff btm rib & shlder snap btn | Swt Shirt |  |  | 2026-09-15 | 2026-09-21 | 2026-10-01 | 2026-10-12 | 2026-10-12 | 2026-10-19 | 2026-10-20 | 2026-10-20 | 2026-10-26 | 2026-10-28 | 2026-10-30 | [6 empty] | 2026-11-02 | 2026-11-06 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 89 | T2 | Mosaddik |  |  |  | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3681 | [11 empty] | 47 | Oct'3
BS-NMT | 48795 | 13265536 | 1691 | 140 | 2026-08-19 | 2026-08-28 | SS o nk TS w nk rib w snap btn | TS |  |  | 2026-09-10 | 2026-09-15 | 2026-09-23 | 2026-10-05 |  |  | 2026-10-07 | 2026-10-07 | 2026-10-13 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-22 |  |  |  |  | 2026-10-24 | 2026-10-27 |  |  | 2026-10-29 | 2026-10-31 | 2026-11-05 | 2026-11-16 | 2026-11-18 | 89 | Y | Mosaddik | Chest,Nk |  | c.dan -808 pcs 4 clr rub 4 clr puff ,,sepia-883 pcs 4 clr rub 2 clr puff |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1691 | [11 empty] | 47 | Oct'2
BS-NMT | 48797 | 13265547 | 3751 | 382 | 2026-08-19 | 2026-08-28 | Sw pant w printed herringbone tape drawstring | Pant |  |  | 2026-09-08 | 2026-09-16 | 2026-09-22 | 2026-10-05 |  |  | 2026-10-07 | 2026-10-07 | 2026-10-14 | 2026-10-16 | 2026-10-17 | 2026-10-10 | 2026-10-14 |  |  |  |  | 2026-10-20 | 2026-10-23 |  |  | 2026-10-26 | 2026-10-28 | 2026-10-31 | 2026-11-16 | 2026-11-18 | 89 | U | Mosaddik | Panel Print |  | 3 combo 1900 yds herringbone tape 1 clr rub print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3751 | [11 empty] | 47 | Oct'2
BS-NMT | 48799 | 13265576 | 2285 | 259 | 2026-08-19 | 2026-08-28 | AOP waist fold swt pant w rib | Pant |  |  | 2026-09-18 | 2026-09-24 | 2026-10-01 | 2026-10-10 | 2026-10-12 | 2026-10-17 | 2026-10-19 | 2026-10-19 | 2026-10-24 | 2026-10-27 | 2026-10-28 | [6 empty] | 2026-11-02 | 2026-11-03 |  |  | 2026-11-05 | 2026-11-07 | 2026-11-10 | 2026-11-16 | 2026-11-18 | 89 | W1 | Mosaddik |  |  |  | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2285 | [11 empty] | 47 | Oct'3
BS-NMT | 48941 | 13266174 | 15692 | 2524 | 2026-08-19 | 2026-08-28 | SS o nk TS | TS |  |  | 2026-09-10 | 2026-09-22 | 2026-09-27 | 2026-10-12 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-19 | 2026-10-21 | 2026-10-24 | 2026-10-24 | 2026-10-31 |  |  |  |  | 2026-11-02 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-15 | 2026-11-17 | 88 | ZA2 | Jafar | Fr & Bk & Nk |  | Oceana-7896 pcs frt 1 clr rub back 5 clr rub 1 clr puff,,pink-7796 pcs frt 1 clr rub 1 clr puff back 4 clr rub 2 clr puff |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -15692 | [11 empty] | 47 | Oct'3
BS-ONS | 48283 3rd | 22042341 | 4860 | 3333 | 2026-08-23 | 2026-08-26 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-09-15 | 2026-09-23 | 2026-10-02 | 2026-10-18 |  |  | 2026-10-21 | 2026-10-21 |  | 2026-10-28 | 2026-10-29 | 2026-10-27 | 2026-10-30 |  |  |  |  | 2026-11-03 | 2026-11-06 |  |  | 2026-11-10 | 2026-11-12 | 2026-11-13 | 2026-11-16 | 2026-11-18 | 85 | E | Shakel | Fr,Bk |  | black parks-2438 pcs,,vintage khaki-2438 pcs both combo frt 1 clr rub back 1 clr rub 1 clr puff |  |  | NFL1 |  |  | Need Cut FB | 0 | 0 | 0 | 0 | -4860 | [11 empty] | 47 | Oct'3 |  |  | 12.09.26
BS-ONS | 46616 5th | 22039183 | 1530 | 1403 | 2026-08-23 | 2026-08-26 | LS Swt Hoody | Hoody |  |  | 2026-09-15 | 2026-09-21 | 2026-09-25 | 2026-10-12 |  |  | 2026-10-16 | 2026-10-16 |  | 2026-10-22 | 2026-10-23 | 2026-10-26 | 2026-10-29 |  |  |  |  | 2026-11-02 | 2026-11-04 |  |  | 2026-11-06 | 2026-11-06 | 2026-11-10 | 2026-11-16 | 2026-11-18 | 85 | B | Shakel | Fr,Bk |  | crown blue-1538 pcs frt back 1 clr HD 1 clr puff print |  |  | NFL1 |  |  | Po Sheet Due | 1402 | 0 | -1402 | 0 | -1530 | [11 empty] | 47 | Oct'3
BS-ONL | 48611 | 15391332 | 4401 | 980 | 2026-08-15 | 2026-08-28 | SS o nk TS w front chrochet emb patch attach | TS | [8 empty] | 2026-10-14 | 2026-10-14 | 2026-10-20 | 2026-10-22 | 2026-10-24 |  |  |  |  | 2026-10-22 | 2026-10-26 | 2026-10-26 | 2026-10-30 |  |  | 2026-11-02 | 2026-11-05 | 2026-11-07 | 2026-11-09 | 2026-11-11 | 86 | M | Jannati |  | Patch | c.dan pkt -1551 pcs,,coffe bean square-942 pcs,,coffe bean pkt-636 pcs,,c.dan square-1272 pcs all combo patch emb at chest (develop at Slama Emb) |  | Imp Fab on 10/10 | NFL2 |  |  | CAD | 0 | 0 | 0 | 0 | -4401 | [11 empty] | 46 | Oct'3 |  |  | 15.09.26
BS-ONL | 48689 | 15399655 | 816 | 553 | 2026-08-20 | 2026-08-26 | LS Swt hoody w cuff btm rib | Hoody |  |  | 2026-09-10 | 2026-09-16 | 2026-09-22 | 2026-10-06 |  |  | 2026-10-08 | 2026-10-08 | 2026-10-16 | 2026-10-16 | 2026-10-19 | 2026-10-23 | [5 empty] | 2026-10-26 | 2026-10-28 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-09 | 2026-11-11 | 81 | R | Mainul | slv,Chest |  | p.stone-816 pcs back both slve 9 clr rub print |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -816 | [11 empty] | 46 | Oct'2
BS-ONL | 48649 | 15394332 | 7293 | 1685 | 2026-08-20 | 2026-08-24 | SS O nk TS w btm Lace attach | TS |  |  | 2026-09-15 | 2026-09-24 | 2026-10-02 | 2026-10-17 |  |  | 2026-10-20 | 2026-10-20 | 2026-10-26 | 2026-10-28 | 2026-10-31 | [6 empty] | 2026-11-02 | 2026-11-10 |  |  | 2026-11-14 | 2026-11-12 | 2026-11-14 | 2026-11-16 | 2026-11-18 | 88 | A | Zahirul |  |  |  |  | Imp Lace | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -7293 | [11 empty] | 47 | Oct'3
BS-ONL | 27945 4th | 15317993 | 1068 | 300 | 2026-08-12 | 2026-08-26 | SS o nk TS | TS |  |  | 2026-09-15 | 2026-09-22 | 2026-10-01 | 2026-10-10 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-20 | 2026-10-22 | 2026-10-23 | 2026-10-26 | 2026-10-29 |  |  |  |  | 2026-11-02 | 2026-11-04 |  |  | 2026-11-06 | 2026-11-09 | 2026-11-11 | 2026-11-16 | 2026-11-18 | 96 | N1 | Zahirul | Chest,Nk |  | Phntom-1068 Pcs 4 clr rub print |  | License order | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1068 | [11 empty] | 47 | Oct'3
BS-ONL | 48646 | 15396061 | 2064 | 490 | 2026-08-12 | 2026-08-28 | SS o nk TS | TS |  |  | 2026-09-17 | 2026-09-22 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-20 | 2026-10-23 | 2026-10-24 | [6 empty] | 2026-10-27 | 2026-10-29 |  |  | 2026-10-31 | 2026-11-03 | 2026-11-05 | 2026-11-16 | 2026-11-18 | 96 | Z | Zahirul | [5 empty] | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2064 | [11 empty] | 47 | Oct'3
OVS SPA | 47855 | 271TSH061TS61-6198 | 5870 | 910 | 2026-08-14 | 2026-08-27 | SS boat nk TS w flat knit rib | TS | 2026-09-21 | 2026-09-30 | 2026-10-01 | 2026-10-10 | 2026-10-12 | 2026-10-23 |  |  | 2026-10-19 | 2026-10-28 | 2026-11-03 | 2026-11-04 | 2026-11-06 | [6 empty] | 2026-11-07 | 2026-11-12 |  |  | 2026-11-13 | 2026-11-16 | 2026-11-18 | 2026-11-19 | 2026-11-19 | 97 | G2 | Khairul | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -5870 | [11 empty] | 47 | Nov'1
OVS SPA | 47842 | 271TNK006V6-6198 | 13250 | 1850 | 2026-08-15 | 2026-08-27 | V nk Tank top w shlder Loop | Tank Top |  |  | 2026-10-01 | 2026-10-12 | 2026-10-13 | 2026-10-24 |  |  | 2026-10-27 | 2026-10-26 | 2026-10-31 | 2026-11-02 | 2026-11-06 | [6 empty] | 2026-11-05 | 2026-11-11 |  |  | 2026-11-12 | 2026-11-14 | 2026-11-17 | 2026-11-23 | 2026-11-23 | 100 | ZA1 | Khairul | [5 empty] | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -13250 | [11 empty] | 48 | Nov'1
OVS SPA | 48565 | 271JOG569-282 | 17712 | 1230 | 2026-08-17 | 2026-08-27 | SS TS and Swt shorts w drawstring | Top & BTM |  |  | 2026-09-17 | 2026-09-28 | 2026-10-01 | 2026-10-13 |  |  | 2026-10-17 | 2026-10-10 | 2026-10-17 | 2026-10-19 | 2026-10-24 | 2026-10-23 | 2026-10-28 |  |  |  |  | 2026-10-26 | 2026-11-05 |  |  | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-09 | 2026-11-09 | 84 | P+Q | Khairul | Chest |  | white top-8856 pcs 4 clr rub print ,,blue btm -8856 pcs no print |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -17712 | [11 empty] | 46 | Oct'2
OVS SPA | 48566 | 271JOG570-282 | 20130 | 1835 | 2026-08-17 | 2026-08-27 | SS TS and Swt shorts w side pkt drawstring | Top & BTM |  |  | 2026-09-17 | 2026-09-28 | 2026-10-01 | 2026-10-13 |  |  | 2026-10-17 | 2026-10-10 | 2026-10-17 | 2026-10-19 | 2026-10-24 | 2026-10-23 | 2026-10-28 |  |  |  |  | 2026-10-27 | 2026-11-05 |  |  | 2026-11-06 | 2026-11-07 | 2026-11-07 | 2026-11-09 | 2026-11-09 | 84 | A+C | Khairul | Chest & Leg |  | Aurora top-10065 pcs chest 4 clr rub print ,,Ebony btm-10065 pcs one leg 3 clr rub |  |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -20130 | [11 empty] | 46 | Oct'2
OVS SPA | 47852 | 271TSH060TS60-6198 | 5870 | 910 | 2026-08-17 | 2026-08-27 | SS v nk TS w flat knit rib nk | TS | 2026-09-21 | 2026-09-30 | 2026-10-01 | 2026-10-10 | 2026-10-12 | 2026-10-23 |  |  | 2026-10-29 | 2026-10-28 | 2026-11-03 | 2026-11-04 | 2026-11-06 | [6 empty] | 2026-11-07 | 2026-11-12 |  |  | 2026-11-13 | 2026-11-16 | 2026-11-18 | 2026-11-19 | 2026-11-19 | 94 | G2 | Khairul | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -5870 | [11 empty] | 47 | Nov'1
GBX-TM Lewin | 47783 2nd | 68911 | 530 | 393 | 2026-08-26 | 2026-08-27 | LS Cut & Sew Polo Shirt | Polo |  |  | 2026-09-12 | 2026-09-21 | 2026-09-25 | 2026-10-10 |  |  | 2026-10-10 | 2026-10-10 |  | 2026-10-16 | 2026-10-17 | [6 empty] | 2026-10-20 | 2026-10-23 |  |  | 2026-10-24 | 2026-10-26 | 2026-10-28 | 2026-11-05 | 2026-11-05 | 71 | N/3 | Shofi | [5 empty] | NCL |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -530 | [11 empty] | 45 | Oct'2
UTG-AF | 48596 | BAD3296nurs | 600 | 175 | 2026-08-12 | 2026-08-25 | SS TS w side seam gathering | TS |  |  | 2026-09-18 | 2026-09-28 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-23 | 2026-10-24 | 2026-10-28 | 2026-10-29 | 2026-10-30 | [6 empty] | 2026-11-02 | 2026-11-04 |  |  | 2026-11-05 | 2026-11-07 | 2026-11-09 | 2026-11-21 | 2026-11-23 | 101 | G1 | Rana | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -600 | [11 empty] | 48 | Oct'3
UTG-AF | 48598 | BAD3294nurs | 1200 | 201 | 2026-08-12 | 2026-08-25 | Wrap Tank Top | Tank Top |  |  | 2026-09-18 | 2026-09-28 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-23 | 2026-10-24 | 2026-10-28 | 2026-10-29 | 2026-10-30 | [6 empty] | 2026-11-02 | 2026-11-04 |  |  | 2026-11-05 | 2026-11-07 | 2026-11-09 | 2026-11-21 | 2026-11-23 | 101 | G1 | Rana | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -1200 | [11 empty] | 48 | Oct'3
UTG-AF | 48591 | BAD3293 | 2000 | 425 | 2026-08-12 | 2026-08-25 | Cap Slve TS | TS |  |  | 2026-09-18 | 2026-09-28 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-23 | 2026-10-24 | 2026-10-28 | 2026-10-29 | 2026-10-30 | [6 empty] | 2026-11-02 | 2026-11-04 |  |  | 2026-11-05 | 2026-11-07 | 2026-11-09 | 2026-11-21 | 2026-11-23 | 101 | G1 | Rana | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -2000 | [11 empty] | 48 | Oct'3
UTG-AF | 48594 | BAD3288 | 2000 | 368 | 2026-08-12 | 2026-08-25 | Wide Nk Tank Top | Tank Top |  |  | 2026-09-18 | 2026-09-28 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-23 | 2026-10-24 | 2026-10-28 | 2026-10-29 | 2026-10-30 | [6 empty] | 2026-11-02 | 2026-11-04 |  |  | 2026-11-05 | 2026-11-07 | 2026-11-09 | 2026-11-21 | 2026-11-23 | 101 | G1 | Rana | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -2000 | [11 empty] | 48 | Oct'3
UTG-AF | 45148 2nd | BAD2972A | 2400 | 425 | 2026-08-12 | 2026-08-25 | SS TS w puff slve | TS |  |  | 2026-10-01 | 2026-10-13 | 2026-10-14 | 2026-10-26 |  |  | 2026-10-23 | 2026-10-24 |  | 2026-10-28 | 2026-10-30 | [6 empty] | 2026-11-02 | 2026-11-05 |  |  | 2026-11-06 | 2026-11-09 | 2026-11-11 | 2026-11-21 | 2026-11-23 | 101 | N/2 | Rana | [5 empty] | NCL |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -2400 | [11 empty] | 48 | Oct'3
UTG-AF | 46291 2nd | BAD3135nursA | 700 | 240 | 2026-08-12 | 2026-08-25 | Nursing dress w slve frill | DRESS |  |  | 2026-10-01 | 2026-10-07 | 2026-10-08 | 2026-10-20 |  |  | 2026-10-24 | 2026-10-26 |  | 2026-10-29 | 2026-10-30 | [6 empty] | 2026-11-02 | 2026-11-04 |  |  | 2026-11-05 | 2026-11-07 | 2026-11-09 | 2026-11-21 | 2026-11-23 | 101 | N/2 | Rana | [5 empty] | NCL |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -700 | [11 empty] | 48 | Oct'3
UTG-AF | 42566 10th | BAD2784J | 1900 | 505 | 2026-08-12 | 2026-08-25 | SS POLO SHIRT W LACE | POLO |  |  | 2026-10-01 | 2026-10-13 | 2026-10-14 | 2026-10-26 |  |  | 2026-10-23 | 2026-10-24 |  | 2026-10-28 | 2026-10-30 | [6 empty] | 2026-11-02 | 2026-11-05 |  |  | 2026-11-06 | 2026-11-09 | 2026-11-11 | 2026-11-21 | 2026-11-23 | 101 | N/2 | Rana |  |  |  |  | Lace | NCL |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1900 | [11 empty] | 48 | Oct'3
UTG-AF | 42567 6th | BAD2785F | 2000 | 542 | 2026-08-12 | 2026-08-25 | LDS SS TS | TS |  |  | 2026-09-21 | 2026-09-30 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-23 | 2026-10-24 |  | 2026-10-28 | 2026-10-29 | [6 empty] | 2026-11-02 | 2026-11-04 |  |  | 2026-11-05 | 2026-11-07 | 2026-11-09 | 2026-11-21 | 2026-11-23 | 101 | D1 | Rana | [5 empty] | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -2000 | [11 empty] | 48 | Oct'3
UTG-AF | 45798 3rd | BAD3016B | 6000 | 1129 | 2026-08-12 | 2026-08-25 | YD wide nk Cap slve TS | TS | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-09-25 | 2026-09-26 | 2026-10-07 |  |  | 2026-10-22 | 2026-10-23 |  | 2026-10-29 | 2026-10-30 | [6 empty] | 2026-11-02 | 2026-11-06 |  |  | 2026-11-07 | 2026-11-09 | 2026-11-11 | 2026-11-21 | 2026-11-23 | 101 | D1 | Rana |  |  |  | YD |  | NFL1 |  |  | Po Sheet Due | 1130 | 0 | -1130 | 0 | -6000 | [11 empty] | 48 | Oct'3
UTG-AF | 48589 | BAD3287 | 3600 | 733 | 2026-08-12 | 2026-08-25 | YD & Solid Square nk Cap slve TS | TS | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-09-25 | 2026-09-26 | 2026-10-07 |  |  | 2026-10-22 | 2026-10-23 | 2026-10-28 | 2026-10-29 | 2026-10-30 | [6 empty] | 2026-11-02 | 2026-11-06 |  |  | 2026-11-07 | 2026-11-09 | 2026-11-11 | 2026-11-21 | 2026-11-23 | 101 | F | Rana |  |  |  | YD |  | NFL1 |  |  | File Due | 732 | 0 | -732 | 0 | -3600 | [11 empty] | 48 | Oct'3
UTG-AF | 43071 2nd | BAD1299mamaH | 1200 | 269 | 2026-08-12 | 2026-08-25 | Solid & YD SS o nk TS | TS | 2026-09-01 | 2026-09-12 | 2026-09-14 | 2026-09-25 | 2026-09-28 | 2026-10-08 |  |  | 2026-10-23 | 2026-10-24 |  | 2026-10-29 | 2026-10-30 | [6 empty] | 2026-11-02 | 2026-11-04 |  |  | 2026-11-05 | 2026-11-07 | 2026-11-10 | 2026-11-21 | 2026-11-23 | 101 | N/1 | Rana |  |  |  | YD |  | NCL |  |  | Po Sheet Due | 270 | 0 | -270 | 0 | -1200 | [11 empty] | 48 | Oct'3
UTG-AF | 46294 2nd | BAD3137mamaA | 3600 | 795 | 2026-08-12 | 2026-08-25 | SS o nk TS and Skirt | Top & BTM |  |  | 2026-09-18 | 2026-09-30 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-23 | 2026-10-24 |  | 2026-10-28 | 2026-10-30 | [6 empty] | 2026-11-02 | 2026-11-05 |  |  | 2026-11-06 | 2026-11-09 | 2026-11-11 | 2026-11-21 | 2026-11-23 | 101 | N/1 | Rana | [5 empty] | NCL |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -3600 | [11 empty] | 48 | Oct'3
UTG-AF | 48590 | BAD3292 | 700 | 208 | 2026-08-12 | 2026-08-25 | SS waterfall top w waist belt knot | TS |  |  | 2026-09-21 | 2026-09-30 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-22 | 2026-10-23 | 2026-10-28 | 2026-10-29 | 2026-10-30 | [6 empty] | 2026-11-02 | 2026-11-04 |  |  | 2026-11-05 | 2026-11-07 | 2026-11-09 | 2026-11-21 | 2026-11-23 | 101 | N/1 | Rana | [5 empty] | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -700 | [11 empty] | 48 | Oct'3
UTG-AF | 48592 | BAD3290 | 700 | 110 | 2026-08-12 | 2026-08-25 | SS wrap TS | TS |  |  | 2026-09-21 | 2026-09-30 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-22 | 2026-10-23 | 2026-10-28 | 2026-10-29 | 2026-10-30 | [6 empty] | 2026-11-02 | 2026-11-04 |  |  | 2026-11-05 | 2026-11-07 | 2026-11-09 | 2026-11-21 | 2026-11-23 | 101 | N/1 | Rana | [5 empty] | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -700 | [11 empty] | 48 | Oct'3
UTG-AF | 48595 | BAD3291 | 700 | 160 | 2026-08-12 | 2026-08-25 | SS O nk TS w btm frill | TS |  |  | 2026-09-18 | 2026-09-28 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-23 | 2026-10-24 | 2026-10-29 | 2026-10-30 | 2026-10-31 | [6 empty] | 2026-11-02 | 2026-11-04 |  |  | 2026-11-05 | 2026-11-07 | 2026-11-10 | 2026-11-21 | 2026-11-23 | 101 | N/1 | Rana | [5 empty] | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -700 | [11 empty] | 48 | Oct'3
UTG-AF | 48597 | BAD3295nurs | 1600 | 270 | 2026-08-12 | 2026-08-25 | Tank top w slhder placket button | Tank Top |  |  | 2026-09-18 | 2026-09-28 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-23 | 2026-10-24 | 2026-10-29 | 2026-10-30 | 2026-10-31 | [6 empty] | 2026-11-02 | 2026-11-04 |  |  | 2026-11-05 | 2026-11-07 | 2026-11-10 | 2026-11-21 | 2026-11-23 | 101 | N/1 | Rana | [5 empty] | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -1600 | [11 empty] | 48 | Oct'3
UTG-AF | 48593 | BAD3289 | 800 | 165 | 2026-08-12 | 2026-08-25 | SS high nk TS w slhder placket press button | TS |  |  | 2026-09-18 | 2026-09-28 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-23 | 2026-10-24 | 2026-10-29 | 2026-10-30 | 2026-10-31 | [6 empty] | 2026-11-02 | 2026-11-04 |  |  | 2026-11-05 | 2026-11-07 | 2026-11-10 | 2026-11-21 | 2026-11-23 | 101 | N/1 | Rana | [5 empty] | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -800 | [11 empty] | 48 | Oct'3
BS-NMT | 48740 | 13266226 | 1824 | 252 | 2026-08-19 | 2026-08-25 | SS o nk TS | TS |  |  | 2026-09-25 | 2026-09-30 | 2026-10-10 | 2026-10-25 |  |  | 2026-11-03 | 2026-11-03 | 2026-11-09 | 2026-11-12 | 2026-11-13 | 2026-11-16 | 2026-11-20 |  |  |  |  | 2026-11-23 | 2026-11-25 |  |  | 2026-11-27 | 2026-11-30 | 2026-12-08 | 2026-12-26 | 2026-12-28 | 129 | T1 | Shamoly | Chest,Nk |  | c.dan-912 pcs,,black-912 pcs both combo 2 clr rub 1 clr gltr |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1824 | [11 empty] | 53 | Nov'2
BS-NMT | 48739 | 13266210 | 5960 | 844 | 2026-08-19 | 2026-08-25 | SS o nk TS | TS |  |  | 2026-09-23 | 2026-09-30 | 2026-10-07 | 2026-10-23 |  |  | 2026-10-28 | 2026-10-28 | 2026-11-05 | 2026-11-08 | 2026-11-10 | 2026-11-12 | 2026-11-17 |  |  |  |  | 2026-11-20 | 2026-11-24 |  |  | 2026-11-27 | 2026-11-30 | 2026-12-07 | 2026-12-28 | 2026-12-30 | 131 | ZA1 | Shamoly | Fr & Bk & Nk |  | coral-2930 pcs frt back 8 clr rub 1 clr gltr print ,,c.dan-3030 pcs frt 1 clr puff print back 7 clr pig 1 clr puff |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -5960 | [11 empty] | 53 | Nov'1
BS-NMT | 48738 | 13266189 | 6396 | 943 | 2026-08-19 | 2026-08-25 | SS o nk TS | TS |  |  | 2026-09-25 | 2026-09-30 | 2026-10-10 | 2026-10-22 |  |  | 2026-10-28 | 2026-10-28 | 2026-11-05 | 2026-11-07 | 2026-11-10 | 2026-11-12 | 2026-11-17 |  |  |  |  | 2026-11-20 | 2026-11-24 |  |  | 2026-11-26 | 2026-11-28 | 2026-12-08 | 2026-12-26 | 2026-12-28 | 129 | ZA1 | Shamoly | Fr & Bk & Nk |  | green-3173 pcs frt back 6 clr rub 3 clr puff ,,black-3223 pcs frt 2 clr rub 2 clr puff back 4 clr rub 2 clr puff |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -6396 | [11 empty] | 53 | Nov'1
BS-NMT | 48737 | 13266183 | 2531 | 382 | 2026-08-19 | 2026-08-25 | SS o nk TS | TS |  |  | 2026-09-25 | 2026-09-30 | 2026-10-05 | 2026-10-20 |  |  | 2026-10-26 | 2026-10-26 | 2026-11-03 | 2026-11-06 | 2026-11-07 | 2026-11-10 | 2026-11-14 |  |  |  |  | 2026-11-18 | 2026-11-21 |  |  | 2026-11-24 | 2026-11-27 | 2026-12-05 | 2026-12-26 | 2026-12-28 | 129 | T1 | Shamoly | Fr & Bk & Nk |  | green-2531 pcs frt 1 clr rub 1 clr puff back 2 clr rub 3 clr puff |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2531 | [11 empty] | 53 | Nov'1
BS-NMT | 48736 | 13266177 | 725 | 113 | 2026-08-19 | 2026-08-25 | SS o nk TS | TS |  |  | 2026-10-01 | 2026-10-04 | 2026-10-10 | 2026-10-25 |  |  | 2026-11-05 | 2026-11-05 | 2026-11-11 | 2026-11-14 | 2026-11-14 | 2026-11-17 | 2026-11-19 |  |  |  |  | 2026-11-23 | 2026-11-25 |  |  | 2026-11-28 | 2026-11-30 | 2026-12-05 | 2026-12-26 | 2026-12-28 | 129 | T1 | Shamoly | Chest,Nk |  | bluee-725 pcs 2 clr rub 2 clr puff |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -725 | [11 empty] | 53 | Nov'2
BS-NMT | 48741 | 13266227 | 2533 | 388 | 2026-08-19 | 2026-08-25 | SS o nk TS | TS |  |  | 2026-10-01 | 2026-10-05 | 2026-10-12 | 2026-10-30 |  |  | 2026-11-04 | 2026-11-04 | 2026-11-10 | 2026-11-12 | 2026-11-13 | 2026-11-16 | 2026-11-19 |  |  |  |  | 2026-11-23 | 2026-11-26 |  |  | 2026-11-28 | 2026-12-03 | 2026-12-10 | 2026-12-26 | 2026-12-28 | 129 | T1 | Shamoly | Fr & Bk & Nk |  | c.dancer-1549 pcs,,Turquise-984 pcs both combo frt back 3 clr rub 1 clr gltr |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2533 | [11 empty] | 53 | Nov'2
BS-NMT | 48742 | 13266228 | 1026 | 170 | 2026-08-19 | 2026-08-29 | Swt Shorts w side pkt drawstring | Shorts |  |  | 2026-10-01 | 2026-10-05 | 2026-10-13 | 2026-10-30 |  |  | 2026-11-09 | 2026-11-09 | 2026-11-14 | 2026-11-17 | 2026-11-18 |  |  |  |  | 2026-11-20 | 2026-11-23 | 2026-11-26 | 2026-11-28 |  |  | 2026-12-02 | 2026-12-05 | 2026-12-10 | 2026-12-21 | 2026-12-23 | 124 | X | Shamoly |  | Thigh | black-1026 pcs 3 clr flat emb |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1026 | [11 empty] | 52 | Nov'2
BS-NMT | 48940 | 13265711 | 11934 | 865 | 2026-08-19 | 2026-08-28 | Ealstic waist shorts w herringbone drawstring | Shorts |  |  | 2026-09-17 | 2026-09-27 | 2026-10-05 | 2026-10-23 |  |  | 2026-10-28 | 2026-10-28 | 2026-11-04 | 2026-11-06 | 2026-11-10 | 2026-11-12 | 2026-11-16 |  |  | 2026-11-10 | 2026-11-20 | 2026-11-23 | 2026-11-28 |  |  | 2026-12-03 | 2026-12-07 | 2026-12-10 | 2026-12-21 | 2026-12-23 | 124 | U | Jafar | Waist | AOE | blue-5106 pcs,,fairy-6828 pcs both combo frt 2 part 2 clr flat all over emb |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -11934 | [11 empty] | 52 | Nov'1
BS-NMT | 45586 3rd | 13240424 | 12002 | 2110 | 2026-08-19 | 2026-08-28 | Long Tank Top | Tank Top |  |  | 2026-09-22 | 2026-10-03 | 2026-10-12 | 2026-10-30 |  |  | 2026-11-07 | 2026-11-07 | 2026-11-14 | 2026-11-17 | 2026-11-21 | 2026-11-21 | 2026-11-26 |  |  |  |  | 2026-12-01 | 2026-12-07 |  |  | 2026-12-09 | 2026-12-11 | 2026-12-15 | 2026-12-28 | 2026-12-30 | 131 | ZA1 | Jafar | Nk |  | 3 combo label print |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -12002 | [11 empty] | 53 | Nov'2
BS-NMT | 45589 3rd | 13241233 | 11324 | 1651 | 2026-08-19 | 2026-08-28 | SS o nk TS w nk Rib Gmts dye acid wash | TS |  |  | 2026-09-22 | 2026-09-28 | 2026-10-12 | 2026-10-22 |  |  | 2026-10-27 | 2026-10-27 | 2026-11-07 | 2026-11-12 | 2026-11-16 | 2026-12-05 | 2026-12-09 |  |  |  |  | 2026-11-18 | 2026-11-24 | 2026-11-24 | 2026-12-05 | 2026-12-12 | 2026-12-14 | 2026-12-17 | 2026-12-28 | 2026-12-30 | 131 | ZA2 | Jafar | Chest |  | blue-3913 pcs,,black-1757 pcs,,green-5654 pcs all combo 2 clr HD print |  | Gmts dye acid wash | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -11324 | [11 empty] | 53 | Nov'2
BS-NMT | 45574 4th | 13201014 | 13649 | 1412 | 2026-08-19 | 2026-08-28 | Solid legging w waist elastic | Legging |  |  | 2026-09-15 | 2026-09-22 | 2026-10-05 | 2026-10-20 |  |  | 2026-10-24 | 2026-10-24 | 2026-10-28 | 2026-10-30 | 2026-11-03 | 2026-11-03 | 2026-11-07 |  |  |  |  | 2026-11-10 | 2026-11-14 |  |  | 2026-11-18 | 2026-11-20 | 2026-11-27 | 2026-12-28 | 2026-12-30 | 131 | W2 | Jafar | Waist |  | 5 combo label print |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -13649 | [11 empty] | 53 | Oct'3
BS-NMT | 45578 4th | 13215793 | 15375 | 1636 | 2026-08-19 | 2026-08-28 | SS o nk TS | TS |  |  | 2026-09-21 | 2026-09-30 | 2026-10-07 | 2026-10-25 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-07 | 2026-11-10 | 2026-11-14 | 2026-11-13 | 2026-11-20 |  |  |  |  | 2026-11-23 | 2026-11-30 |  |  | 2026-12-03 | 2026-12-05 | 2026-12-10 | 2026-12-28 | 2026-12-30 | 131 | ZA1 | Jafar | Chest,Nk |  | c.an -4940 pcs 4 clr pig ,,hibicus-5241 pcs 4 clr rub,,pink-5194 pcs 3 clr pig |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -15375 | [11 empty] | 53 | Nov'1
BS-NMT | 44843 5th | 13251915 | 14436 | 1432 | 2026-08-19 | 2026-08-28 | GIRLS SS TS | TS |  |  | 2026-09-18 | 2026-09-30 | 2026-10-08 | 2026-10-23 |  |  | 2026-10-25 | 2026-10-25 | 2026-11-02 | 2026-11-04 | 2026-11-08 | 2026-11-10 | 2026-11-15 |  |  | 2026-11-07 | 2026-11-20 | 2026-11-23 | 2026-11-28 |  |  | 2026-12-03 | 2026-12-05 | 2026-12-10 | 2026-12-21 | 2026-12-23 | 124 | ZA2 | Jafar | Nk | Chest | blue-6003 pcs,,fairy-8433 pcs both combo chest 2 clr flat all over emb |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -14436 | [11 empty] | 52 | Nov'1
BS-NMT | 45573 5th | 13191810 | 25618 | 1864 | 2026-08-19 | 2026-08-28 | Short Leggings w waist elatic | Legging |  |  | 2026-09-18 | 2026-09-27 | 2026-10-05 | 2026-10-24 |  |  | 2026-10-25 | 2026-10-25 | 2026-10-30 | 2026-11-03 | 2026-11-07 | 2026-11-06 | 2026-11-12 |  |  |  |  | 2026-11-12 | 2026-11-19 |  |  | 2026-11-23 | 2026-11-26 | 2026-11-30 | 2026-12-28 | 2026-12-30 | 131 | W2 | Jafar | Waist |  | 9 combo label print |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -25618 | [11 empty] | 53 | Nov'1
BS-NMT | 45581 5th | 13228199 | 38123 | 2516 | 2026-08-19 | 2026-08-28 | Short Leggings | Legging |  |  | 2026-09-22 | 2026-09-30 | 2026-10-05 | 2026-10-25 |  |  | 2026-10-28 | 2026-10-28 | 2026-11-04 | 2026-11-06 | 2026-01-12 | 2026-11-11 | 2026-11-18 |  |  |  |  | 2026-11-18 | 2026-11-28 |  |  | 2026-12-04 | 2026-12-05 | 2026-12-08 | 2026-12-28 | 2026-12-30 | 131 | W2 | Jafar | Waist |  | 6 combo label print |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -38123 | [11 empty] | 53 | Nov'1
BS-NMT | 45583 4th | 13230078 | 16880 | 2546 | 2026-08-19 | 2026-08-28 | SS TS w btm knot | TS |  |  | 2026-09-23 | 2026-09-30 | 2026-10-10 | 2026-10-30 |  |  | 2026-11-05 | 2026-11-05 | 2026-11-12 | 2026-11-16 | 2026-11-21 | 2026-11-20 | 2026-11-26 |  |  |  |  | 2026-12-01 | 2026-12-08 |  |  | 2026-12-10 | 2026-12-12 | 2026-12-17 | 2026-12-28 | 2026-12-30 | 131 | V | Jafar | Nk |  | 3 combo label print |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -16880 | [11 empty] | 53 | Nov'2
BS-NMT | 45584 5th | 13236672 | 41722 | 4331 | 2026-08-19 | 2026-08-28 | Tank Top | Tank Top |  |  | 2026-09-15 | 2026-09-30 | 2026-10-05 | 2026-10-24 |  |  | 2026-10-25 | 2026-10-25 | 2026-11-02 | 2026-11-04 | 2026-11-12 | 2026-11-09 | 2026-11-16 |  |  |  |  | 2026-11-16 | 2026-11-30 |  |  | 2026-12-05 | 2026-12-07 | 2026-12-10 | 2026-12-28 | 2026-12-30 | 131 | G1 | Jafar | NK |  | 7 combo label print |  |  | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -41722 | [11 empty] | 53 | Nov'1
BS-NMT | 45576 5th | 13215107 | 30752 | 3956 | 2026-08-19 | 2026-08-28 | SS AOP capsl dress | Dress |  |  | 2026-09-12 | 2026-09-25 | 2026-09-27 | 2026-10-18 | 2026-10-15 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-11-06 | 2026-11-08 | 2026-11-14 | 2026-11-12 | 2026-11-20 |  |  |  |  | 2026-11-19 | 2026-11-30 |  |  | 2026-12-04 | 2026-12-07 | 2026-12-10 | 2026-12-21 | 2026-12-23 | 124 | V | Jafar | Nk |  | 4 combo label print | AOP |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -30752 | [11 empty] | 52 | Nov'1
BS-ONL | 48619 2nd | 15291465 | 10080 | 1543 | 2026-08-20 | 2026-08-24 | SS o nk TS | TS |  |  | 2026-09-17 | 2026-09-24 | 2026-10-03 | 2026-10-17 |  |  | 2026-10-22 | 2026-10-22 |  | 2026-10-28 | 2026-10-31 | 2026-11-03 | 2026-11-07 |  |  |  |  | 2026-11-10 | 2026-11-14 |  |  | 2026-11-17 | 2026-11-19 | 2026-11-25 | 2026-12-14 | 2026-12-16 | 116 | V | Imran | Fr,Bk |  | corsage-5040 pcs frt 3 clr gltr back 2 clr pig photo print 5 clr gltr print ,,c.dancer-5040 pcs frt 4 clr pig 2 clr gltr back 5 clr pig 4 clr gltr w photo print |  |  | NFL3 |  |  | Need Cut FB | 0 | 0 | 0 | 0 | -10080 | [11 empty] | 51 | Oct'3 |  |  | 05.09.26
BS-ONL | 48644 | 15392706 | 1488 | 370 | 2026-08-12 | 2026-08-28 | Rib Tank Top | Tank Top |  |  | 2026-10-03 | 2026-10-06 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-11 | 2026-11-11 | 2026-11-17 | 2026-11-20 | 2026-11-21 |  |  |  |  | 2026-11-24 | 2026-11-25 | 2026-12-01 | 2026-12-02 |  |  | 2026-12-04 | 2026-12-07 | 2026-12-10 | 2026-12-21 | 2026-12-23 | 131 | G1 | Zahirul |  | Chest | black-846 pcs,,white-642 pcs both combo 1 clr flat emb |  |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -1488 | [11 empty] | 52 | Nov'2
BS-ONL | 42573 3rd | 15356922 | 1068 | 310 | 2026-08-20 | 2026-08-24 | SS O NK TS | TS |  |  | 2026-10-01 | 2026-10-05 | 2026-10-10 | 2026-10-23 |  |  | 2026-10-28 | 2026-10-28 | 2026-11-06 | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-16 |  |  |  |  | 2026-11-18 | 2026-11-20 |  |  | 2026-11-23 | 2026-11-25 | 2026-11-30 | 2026-12-14 | 2026-12-16 | 116 | T1 | Zahirul | Fr,Bk |  | c.dan-1068 pcs fr 3 clr pig back 10 clr pig print |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1068 | [11 empty] | 51 | Nov'1
BS-NMT | 48745 | 13266165 | 3220 | 899 | 2026-08-19 | 2026-08-29 | SS Full placket btn Shirt w self fab collar | Shirt |  |  | 2026-10-01 | 2026-10-07 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-10 | 2026-11-10 | 2026-11-17 | 2026-11-19 | 2026-11-21 | 2026-11-24 | 2026-11-27 |  |  |  |  | 2026-12-01 | 2026-12-05 |  |  | 2026-12-08 | 2026-12-10 | 2026-12-15 | 2027-01-23 | 2027-01-25 | 157 | S | Shamoly | Nk |  | 1 combo label print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3220 | [11 empty] | 5 | Nov'2
BS-NMT | 48746 | 13266175 | 5923 | 874 | 2026-08-19 | 2026-08-29 | SL O nk TS | TS |  |  | 2026-10-03 | 2026-10-10 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-13 | 2026-11-13 | 2026-11-20 | 2026-11-23 | 2026-11-26 | 2026-11-27 | 2026-12-03 |  |  |  |  | 2026-12-07 | 2026-12-10 |  |  | 2026-12-12 | 2026-12-17 | 2026-12-22 | 2027-01-22 | 2027-01-24 | 156 | ZA1 | Shamoly | Fr & Bk & Nk |  | oceana-3072 pcs frt back 4 clr rub 2 clr puff ,,white-2851 pcs frt 2 clr pig 1 clr puff back 5 clr pig 2 clr puff |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -5923 | [11 empty] | 5 | Nov'3
BS-NMT | 48744 | 13266161 | 3825 | 832 | 2026-08-19 | 2026-08-29 | Swt Shors w side back pkt and herringbone drawstring | Shorts |  |  | 2026-10-03 | 2026-10-09 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-11 | 2026-11-11 | 2026-11-17 | 2026-11-20 | 2026-11-23 | 2026-11-25 | 2026-11-27 |  |  |  |  | 2026-12-01 | 2026-12-04 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-14 | 2027-01-24 | 2027-01-26 | 158 | X | Shamoly | Waist |  | 1 combo label print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3825 | [11 empty] | 5 | Nov'2
BS-NMT | 48743 | 13266207 | 610 | 265 | 2026-08-19 | 2026-08-29 | LS Swt hoodie w cuff btm rib | Hoody |  |  | 2026-10-01 | 2026-10-06 | 2026-10-13 | 2026-10-30 |  |  | 2026-11-07 | 2026-11-07 | 2026-11-14 | 2026-11-18 | 2026-11-18 | 2026-11-20 | 2026-11-26 |  |  |  |  | 2026-12-01 | 2026-12-02 |  |  | 2026-12-04 | 2026-12-08 | 2026-12-12 | 2026-12-28 | 2026-12-30 | 131 | T2 | Shamoly | Fr,Bk |  | c.dan -610 pcs frt 1 clr puff back 7 clr pig 1 clr puff |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -610 | [11 empty] | 53 | Nov'2
BS-NMT | 48651 | 13227161 | 3753 | 751 | 2026-08-12 | 2026-08-24 | LS Swt Shirt w cuff btm rib | Swt Shirt |  |  | 2026-09-25 | 2026-09-30 | 2026-10-10 | 2026-10-28 |  |  | 2026-11-04 | 2026-11-04 | 2026-11-10 | 2026-11-13 | 2026-11-17 | 2026-11-18 | 2026-11-23 |  |  | 2026-11-24 | 2026-11-28 | 2026-12-02 | 2026-12-07 |  |  | 2026-12-09 | 2026-12-12 | 2026-12-18 | 2027-01-04 | 2027-01-06 | 145 | Z | Sanaul | Chest | Chest | lake-3753 pcs 3 clr rub print and 3D woven flap attach applique emb |  |  | NFL3 |  |  | CAD | 0 | 0 | 0 | 0 | -3753 | [11 empty] | 2 | Nov'2 |  |  | 14.09.26
BS-NMT | 48654 | 13231142 | 3753 | 772 | 2026-08-12 | 2026-08-24 | Swt pant w side pkt drawstring | Pant |  |  | 2026-10-01 | 2026-10-05 | 2026-10-12 | 2026-10-30 |  |  | 2026-11-10 | 2026-11-10 | 2026-11-16 | 2026-11-19 | 2026-11-21 | 2026-11-24 | 2026-11-27 |  |  |  |  | 2026-12-03 | 2026-12-07 |  |  | 2026-12-09 | 2026-12-11 | 2026-12-17 | 2027-01-04 | 2027-01-06 | 145 | U | Sanaul | Thigh |  | lake-3753 pcs 3 clr rub print |  |  | NFL3 |  |  | CAD | 0 | 0 | 0 | 0 | -3753 | [11 empty] | 2 | Nov'2 |  |  | 14.09.26
BS-NMT | 48653 | 13231140 | 3753 | 644 | 2026-08-12 | 2026-08-24 | Swt pant w drawstring | Pant |  |  | 2026-10-01 | 2026-10-05 | 2026-10-12 | 2026-10-30 |  |  | 2026-11-12 | 2026-11-12 | 2026-11-19 | 2026-11-22 | 2026-11-24 | 2026-11-25 | 2026-11-29 |  |  |  |  | 2026-12-01 | 2026-12-04 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-14 | 2027-01-04 | 2027-01-06 | 145 | U | Sanaul | Thigh |  | orchid-3753 pcs 4 clr rub print |  |  | NFL3 |  |  | CAD | 0 | 0 | 0 | 0 | -3753 | [11 empty] | 2 | Nov'3 |  |  | 14.09.26
BS-NMT | 48652 | 13231139 | 3753 | 792 | 2026-08-12 | 2026-08-24 | LS Swt Shirt w cuff btm rib | Swt Shirt |  |  | 2026-09-25 | 2026-09-30 | 2026-10-08 | 2026-10-24 |  |  | 2026-10-29 | 2026-10-29 | 2026-11-05 | 2026-11-07 | 2026-11-10 | 2026-11-11 | 2026-11-14 |  |  | 2026-11-17 | 2026-11-27 | 2026-12-01 | 2026-12-04 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-14 | 2027-01-04 | 2027-01-06 | 145 | Z | Sanaul | Chest | Chest | orchid-3753 pcs 1 clr rub print and 1 clr tapping emb |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3753 | [11 empty] | 2 | Nov'1
BS-ONL | 46748 15th | 15244714 | 7128 | 1101 | 2026-08-20 | 2026-08-24 | SS o nk TS | TS |  |  | 2026-10-05 | 2026-10-15 | 2026-11-01 | 2026-11-15 |  |  | 2026-11-20 | 2026-11-20 |  | 2026-11-25 | 2026-11-28 | 2026-12-02 | 2026-12-05 |  |  |  |  | 2026-12-09 | 2026-12-14 |  |  | 2026-12-17 | 2026-12-19 | 2026-12-23 | 2027-01-11 | 2027-01-13 | 144 | F | Imran | Chest |  | beetroot-3564 pcs,,mermaid-3564 pcs all combo 1 clr gltr print |  |  | NFL1 |  |  | Need Cut FB | 0 | 0 | 0 | 0 | -7128 | [11 empty] | 3 | Nov'3 |  |  | 05.09.26
BS-ONL | 42574 3rd | 15356928 | 696 | 155 | 2026-08-15 | 2026-08-24 | SS o nk TS | TS |  |  | 2026-10-12 | 2026-10-15 | 2026-10-20 | 2026-10-30 |  |  | 2026-11-14 | 2026-11-14 | 2026-11-21 | 2026-11-24 | 2026-11-24 | 2026-11-27 | 2026-11-30 |  |  |  |  | 2026-12-05 | 2026-12-05 |  |  | 2026-12-08 | 2026-12-10 | 2026-12-14 | 2027-01-11 | 2027-01-13 | 149 | ZA2 | Zahirul | Fr,Bk |  | pink-696 pcs frt back 7 clr pig print |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -696 | [11 empty] | 3 | Nov'3
OVS SPA | 48569 | 271JOG652-282 | 23758 | 1950 | 2026-08-17 | 2026-08-27 | SS contast slve nk TS and Swt shorts w side bk pkt drawstring | Top & BTM |  |  | 2026-10-26 | 2026-11-07 | 2026-11-10 | 2026-11-23 |  |  | 2026-12-10 | 2026-12-01 | 2026-12-07 | 2026-12-08 | 2026-12-12 | 2026-12-12 | 2026-12-18 |  |  |  |  | 2026-12-18 | 2026-12-24 |  |  | 2026-12-25 | 2026-12-28 | 2026-12-30 | 2027-01-04 | 2027-01-04 | 140 | N/2 | Khairul | Chest |  | white top-11879 pcs 3 clr rub print ,,mist btm-11879 pcs no print |  |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -23758 | [11 empty] | 2 | Dec'1
BS-ONS | 26828 81th | 22029226 | 4000 | 2670 | 2026-08-29 | 2026-09-04 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-09-10 | 2026-09-14 | 2026-09-16 | 2026-09-30 |  |  | 2026-09-29 | 2026-09-29 |  | 2026-10-03 | 2026-10-05 | [6 empty] | 2026-10-06 | 2026-10-08 |  |  | 2026-10-09 | 2026-10-10 | 2026-10-12 | 2026-10-12 | 2026-10-14 | 44 | E | Shakel | [5 empty] | NFL1 |  |  | Need Cut FB | 0 | 0 | 0 | 0 | -4000 | [11 empty] | 42 | Oct'1 |  |  | 07.09.26
BS-ONS | 26828 82th | 22029226 | 11000 | 7233 | 2026-08-29 | 2026-09-04 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-09-10 | 2026-09-20 | 2026-09-18 | 2026-10-05 |  |  | 2026-10-02 | 2026-10-02 |  | 2026-10-07 | 2026-10-10 | [6 empty] | 2026-10-09 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-21 | 51 | E | Shakel | [5 empty] | NFL1 |  |  | Need Cut FB | 0 | 0 | 0 | 0 | -11000 | [11 empty] | 43 | Oct'1 |  |  | 07.09.26
BS-ONS | 45964 15th | 22039968 | 6000 | 4100 | 2026-08-27 | 2026-09-04 | LS High nk Haalf Zipp Swt shirt | Swt Shirt |  |  | 2026-09-12 | 2026-09-18 | 2026-09-18 | 2026-10-04 |  |  | 2026-10-01 | 2026-10-01 |  | 2026-10-06 | 2026-10-10 | [6 empty] | 2026-10-10 | 2026-10-15 |  |  | 2026-10-16 | 2026-10-17 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 53 | R | Shakel | [5 empty] | NFL2 |  |  | Need Cut FB | 0 | 0 | 0 | 0 | -6000 | [11 empty] | 43 | Oct'1 |  |  | 05.09.26
BS-ONS | 45964 16th | 22039968 | 4000 | 2758 | 2026-08-27 | 2026-09-04 | LS High nk Haalf Zipp Swt shirt | Swt Shirt |  |  | 2026-09-10 | 2026-09-15 | 2026-09-18 | 2026-10-01 |  |  | 2026-09-26 | 2026-09-26 |  | 2026-10-02 | 2026-10-05 | [6 empty] | 2026-10-05 | 2026-10-10 |  |  | 2026-10-10 | 2026-10-12 | 2026-10-12 | 2026-10-12 | 2026-10-14 | 46 | R | Shakel | [5 empty] | NFL2 |  |  | Need Cut FB | 0 | 0 | 0 | 0 | -4000 | [11 empty] | 42 | Oct'1 |  |  | 05.09.26
BS-ONS | 26827 58th | 22029225 | 6000 | 5388 | 2026-08-27 | 2026-09-04 | LS Swt hoodie w kangaro pkt and drawstring and cuff btm rib | HOODY |  |  | 2026-09-14 | 2026-09-21 | 2026-09-18 | 2026-10-05 |  |  | 2026-10-01 | 2026-10-01 |  | 2026-10-05 | 2026-10-08 | [6 empty] | 2026-10-08 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 53 | B | Shakel | [5 empty] | NFL1 |  |  | Need Cut FB | 0 | 0 | 0 | 0 | -6000 | [11 empty] | 43 | Oct'1 |  |  | 07.09.26
BS-ONS | 48957 | 22041367 | 10604 | 3172 | 2026-08-28 | 2026-09-04 | SS o nk TS | TS |  |  | 2026-09-07 | 2026-09-12 | 2026-09-14 | 2026-09-25 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-28 | 2026-10-01 | 2026-10-05 | 2026-10-03 | 2026-10-08 |  |  | 2026-10-06 | 2026-10-10 | 2026-10-10 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-17 | 2026-10-19 | 50 | F | Shakel | Fr & Bk & Nk | BK | black-5674 pcs,,c.dan-4978 pcs both combo frt 1 clr pig back photo print and 1 clr flat emb at border of the photo print artwork |  | License order | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -10604 | [11 empty] | 43 | Oct'1
BS-ONS | 48947 | 22042630 | 1092 | 334 | 2026-08-26 | 2026-08-31 | SS o nk TS | TS |  |  | 2026-09-05 | 2026-09-08 | 2026-09-10 | 2026-09-19 |  |  | 2026-09-19 | 2026-09-19 | 2026-09-24 | 2026-09-26 | 2026-09-26 | 2026-09-28 | 2026-09-30 |  |  |  |  | 2026-10-01 | 2026-10-02 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-05 | 2026-10-05 | 2026-10-07 | 40 | D1 | Shovon | Chest |  | c.dan-496 pcs,,white-596 pcs both combo 1 clr rub 1 clr flock print |  |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -1092 | [11 empty] | 41 | Sep'3
BS-ONS | 48946 | 22041273 | 3163 | 1055 | 2026-08-26 | 2026-08-31 | LS TS w half self fabric nk placket button | TS |  |  | 2026-09-03 | 2026-09-10 | 2026-09-10 | 2026-09-21 |  |  | 2026-09-18 | 2026-09-18 | 2026-09-25 | 2026-09-28 | 2026-09-30 | [6 empty] | 2026-10-01 | 2026-10-03 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-07 | 40 | C | Shovon | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -3163 | [11 empty] | 41 | Sep'3
BS-ONS | 48959 | 22042689 | 5262 | 2928 | 2026-08-31 | 2026-09-03 | LS Swt polo shirt w cuff btm rib and contrast woven collar placket w button | Polo |  |  | 2026-09-05 | 2026-09-10 | 2026-09-10 | 2026-09-22 |  |  | 2026-09-17 | 2026-09-17 | 2026-09-22 | 2026-09-24 | 2026-09-28 |  |  |  |  | 2026-09-26 | 2026-10-02 | 2026-10-02 | 2026-10-09 |  |  | 2026-10-10 | 2026-10-10 | 2026-10-12 | 2026-10-12 | 2026-10-14 | 42 | X | Shovon |  | Chest | demitasse-2646 pcs ,,pine grove-2616 pcs both combo 1 clr flat and woven applique lettering emb |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -5262 | [11 empty] | 42 | Sep'3
BS-ONS | 30588 21th | 22031724 | 10000 | 4117 | 2026-09-03 | 2026-09-03 | SS o nk TS | TS |  |  | 2026-09-10 | 2026-09-25 | 2026-09-24 | 2026-10-08 |  |  | 2026-10-07 | 2026-10-07 |  | 2026-10-12 | 2026-10-15 | [6 empty] | 2026-10-15 | 2026-10-20 |  |  | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-26 | 2026-10-28 | 53 | G2 | Dalim | [5 empty] | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -10000 | [11 empty] | 44 | Oct'2
BS-ONL | 30708 18th | 15201465 | 4410 | 728 | 2026-08-31 | 2026-09-01 | Long Tank Top | Tank top |  |  | 2026-09-10 | 2026-09-15 | 2026-09-21 | 2026-10-05 |  |  | 2026-10-08 | 2026-10-08 |  | 2026-10-12 | 2026-10-13 | [6 empty] | 2026-10-15 | 2026-10-19 |  |  | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-26 | 2026-10-28 | 56 | G1 | Mainul | [5 empty] | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -4410 | [11 empty] | 44 | Oct'2
BS-ONL | 30711 9th | 15209156 | 4410 | 1076 | 2026-08-31 | 2026-09-01 | LS o nk TS | TS |  |  | 2026-09-07 | 2026-09-12 | 2026-09-13 | 2026-09-25 |  |  | 2026-09-23 | 2026-09-23 |  | 2026-09-28 | 2026-09-29 | [6 empty] | 2026-10-01 | 2026-10-03 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-12 | 2026-10-14 | 42 | W2 | Mainul | [5 empty] | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -4410 | [11 empty] | 42 | Sep'3
BS-ONL | 46748 16th | 15244714 | 3024 | 467 | 2026-08-27 | 2026-08-31 | SS o nk TS | TS |  |  | 2026-09-10 | 2026-09-13 | 2026-09-18 | 2026-09-28 |  |  | 2026-09-25 | 2026-09-25 |  | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 |  |  |  |  | 2026-10-06 | 2026-10-08 |  |  | 2026-10-09 | 2026-10-10 | 2026-10-12 | 2026-10-12 | 2026-10-14 | 46 | F | Imran | Chest |  | black-3024 1 clr gltr print |  | Stock fab from 24508 92th | NFL1 |  |  | Need Cut FB | 0 | 0 | 0 | 0 | -3024 | [11 empty] | 42 | Oct'1 |  |  | 05.09.26
BS-ONL | 48633 | 15396849 | 588 | 170 | 2026-08-12 | 2026-08-31 | SS O nk TS | TS |  |  | 2026-09-07 | 2026-09-10 | 2026-09-16 | 2026-09-26 |  |  | 2026-09-28 | 2026-09-28 | 2026-10-05 | 2026-10-06 | 2026-10-06 |  |  |  |  | 2026-10-08 | 2026-10-12 | 2026-10-14 | 2026-10-15 |  |  | 2026-10-16 | 2026-10-17 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 68 | T1 | Zahirul |  | Chest | c.dan-588 pcs 3 clr flat 1 clr terry emb |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -588 | [11 empty] | 43 | Oct'1
BS-ONL | 48635 | 15396488 | 831 | 175 | 2026-08-12 | 2026-08-31 | Elasted Legging | Legging |  |  | 2026-09-12 | 2026-09-15 | 2026-09-21 | 2026-09-30 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-07 | 2026-10-09 | 2026-10-09 | [6 empty] | 2026-10-12 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 68 | O1 | Zahirul | [5 empty] | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -831 | [11 empty] | 43 | Oct'1
BS-ONL | 48639 | 15395986 | 2568 | 655 | 2026-08-12 | 2026-08-31 | SS o nk TS | TS |  |  | 2026-09-07 | 2026-09-11 | 2026-09-14 | 2026-09-26 |  |  | 2026-09-28 | 2026-09-28 | 2026-10-03 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-10 |  |  |  |  | 2026-10-13 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 68 | F | Zahirul | Fr,Bk |  | white universe-528 pcs,,white self love-456 pcs,,denim-504 pcs,,corsage-612 pcs,,white pasry-468 pcs |  | Print artwork due (need sub plan) | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -2568 | [11 empty] | 43 | Oct'1
BS-ONL | 48189 2nd | 15370026 | 1000 | 730 | 2026-09-03 | 2026-09-04 | LS Swt hoody w cuff btm rib and drawstring | Hoody |  |  | 2026-09-13 | 2026-09-17 | 2026-09-21 | 2026-10-05 |  |  | 2026-10-02 | 2026-10-02 |  | 2026-10-07 | 2026-10-08 |  |  |  |  | 2026-10-09 | 2026-10-10 | 2026-10-13 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 46 | B | Zahirul |  | Chest | black-1000 pcs 1 clr lurex heart emb |  |  | NFL1 |  |  | Size Set Run PC | 0 | 0 | 0 | 0 | -1000 | [11 empty] | 43 | Oct'1 |  |  | 12.09.26
BS-ONL | 27204 67th | 15323159 | 11040 | 2669 | 2026-09-01 | 2026-09-03 | LS o nk TS | TS |  |  | 2026-09-05 | 2026-09-12 | 2026-09-12 | 2026-09-22 |  |  | 2026-09-18 | 2026-09-18 |  | 2026-09-23 | 2026-09-26 | [6 empty] | 2026-09-26 | 2026-09-30 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-05 | 2026-10-05 | 2026-10-07 | 34 | G1 | Dalim | [5 empty] | NFL1 |  |  | Need Cut FB | 0 | 0 | 0 | 0 | -11040 | [11 empty] | 41 | Sep'3 |  |  | 07.09.26
BS-ONL | 46236 2nd | 15381948 | 1480 | 270 | 2026-09-01 | 2026-09-01 | Tank Top | Tank Top |  |  | 2026-09-07 | 2026-09-10 | 2026-09-13 | 2026-09-25 |  |  | 2026-09-25 | 2026-09-25 | 2026-10-01 | 2026-10-02 | 2026-10-02 | [6 empty] | 2026-10-05 | 2026-10-06 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-10 | 2026-10-12 | 2026-10-14 | 41 | T1 | Zahirul | [5 empty] | NFL3 |  |  | Need Test Cut | 0 | 0 | 0 | 0 | -1480 | [11 empty] | 42 | Oct'1 |  |  | 12.09.26
BS-ONL | 46322 2nd | 15384474 | 840 | 187 | 2026-09-01 | 2026-09-01 | Tank Top | Tank Top |  |  | 2026-09-07 | 2026-09-10 | 2026-09-14 | 2026-09-25 |  |  | 2026-09-26 | 2026-09-26 | 2026-10-02 | 2026-10-03 | 2026-10-03 | [6 empty] | 2026-10-05 | 2026-10-07 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-12 | 2026-10-14 | 41 | K | Zahirul | [5 empty] | NFL2 |  |  | Need Test Cut | 0 | 0 | 0 | 0 | -840 | [11 empty] | 42 | Oct'1 |  |  | 12.09.26
BS-ONL | 48958 | 15400894 | 2000 | 400 | 2026-09-01 | 2026-09-02 | Tank Top | Tank Top |  |  | 2026-09-10 | 2026-09-14 | 2026-09-21 | 2026-10-02 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-07 | 2026-10-09 | 2026-10-10 | [6 empty] | 2026-10-12 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-21 | 48 | G1 | Zahirul | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -2000 | [11 empty] | 43 | Oct'1
BS-ONL | 47709 3rd | 15299770 | 6210 | 841 | 2026-08-25 | 2026-09-01 | LS o nk TS w blind hem | TS |  |  | 2026-09-08 | 2026-09-14 | 2026-09-21 | 2026-10-03 |  |  | 2026-10-03 | 2026-10-03 |  | 2026-10-07 | 2026-10-10 | [6 empty] | 2026-10-12 | 2026-10-17 |  |  | 2026-10-19 | 2026-10-20 | 2026-10-22 | 2026-10-26 | 2026-10-28 | 62 | N1 | Abid | [5 empty] | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -6210 | [11 empty] | 44 | Oct'1
BS-ONL | 48836 | 15390711 | 732 | 110 | 2026-08-24 | 2026-09-03 | SS o nk TS w gmts dyeing normal wash | TS |  |  | 2026-09-12 | 2026-09-15 | 2026-09-21 | 2026-09-26 |  |  | 2026-09-26 | 2026-09-26 | 2026-10-03 | 2026-10-06 | 2026-10-06 | 2026-10-14 | 2026-10-15 |  |  |  |  | 2026-10-18 | 2026-10-09 | 2026-10-12 | 2026-10-13 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-19 | 2026-10-21 | 56 | N1 | Abid | Chest |  | sweet dream-732 pcs 1 clr rub 1 clr puff print |  | Gmts dye normal wash | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -732 | [11 empty] | 43 | Oct'1
BS-ONL | 48837 | 15390713/15398343 | 640 | 219 | 2026-08-24 | 2026-09-03 | LS swt shirt w nk cuff bm rib | Swt Shirt |  |  | 2026-09-10 | 2026-09-13 | 2026-09-21 | 2026-10-02 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-06 | 2026-10-08 | 2026-10-08 | 2026-10-10 | 2026-10-12 |  |  |  |  | 2026-10-13 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 56 | N2 | Abid | slv,Chest |  | tofu-640 pcs frt both slve 4 clr rub print |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -640 | [11 empty] | 43 | Oct'1
BS-ONL | 47705 2nd | 15393197 | 735 | 253 | 2026-08-24 | 2026-09-03 | Elasted Pant | Pant |  |  | 2026-09-12 | 2026-09-20 | 2026-09-24 | 2026-10-03 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-07 | 2026-10-10 | 2026-10-10 | [6 empty] | 2026-10-13 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-20 | 55 | P | Abid | [5 empty] | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -735 | [11 empty] | 43 | Oct'1
BS-ONL | 48835 | 15390115 | 1068 | 225 | 2026-08-24 | 2026-09-03 | LS swt shirt w nk cuff bm rib | Swt Shirt |  |  | 2026-09-09 | 2026-09-13 | 2026-09-15 | 2026-09-27 |  |  | 2026-09-26 | 2026-09-26 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-05 | 2026-10-08 |  |  | 2026-10-07 | 2026-10-10 | 2026-10-13 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 56 | N2 | Abid | Chest | Chest | sweet dream-492 pcs chest 6 clr rub and 2 clr terry emb back no print ,,tofu-576 pcs frt back 1 clr pig 1 clr flock print no emb |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -1068 | [11 empty] | 43 | Oct'1
BS-ONL | 48832 | 15390672 | 1344 | 196 | 2026-08-24 | 2026-09-03 | SS o nk TS | TS |  |  | 2026-09-10 | 2026-09-13 | 2026-09-15 | 2026-09-26 |  |  | 2026-09-25 | 2026-09-25 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-03 | 2026-10-05 |  |  | 2026-10-07 | 2026-10-10 | 2026-10-13 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 56 | M | Abid | Chest | Chest | c.dan-1344 pcs 1 clr pig print and denim fab applique emb |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -1344 | [11 empty] | 43 | Oct'1
GBX-New Look | 48301 3rd | 9672271 | 11115 | 2457 | 2026-09-02 | 2026-09-01 | SS reglan contrast slve TS | TS |  |  | 2026-09-08 | 2026-09-16 | 2026-09-21 | 2026-10-09 |  |  | 2026-10-08 | 2026-10-08 |  | 2026-10-13 | 2026-10-17 | [6 empty] | 2026-10-16 | 2026-10-24 |  |  | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-31 | 2026-10-31 | 59 | N/3 | Sifat | [5 empty] | NCL |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -11115 | [11 empty] | 44 | Oct'2
GBX-New Look | 48954 | LS Ragan Tee | 9090 | 1516 | 2026-09-02 | 2026-09-01 | LS reglan contrast slve TS | TS |  |  | 2026-09-10 | 2026-09-17 | 2026-09-22 | 2026-10-09 |  |  | 2026-10-09 | 2026-10-09 | 2026-10-14 | 2026-10-16 | 2026-10-19 | [6 empty] | 2026-10-19 | 2026-10-26 |  |  | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-31 | 2026-10-31 | 59 | N/1 | Sifat | [5 empty] | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -9090 | [11 empty] | 44 | Oct'2
BS-NMT | 48902 | 13257457 | 1845 | 308 | 2026-08-19 | 2026-08-31 | SS o nk TS | TS |  |  | 2026-09-18 | 2026-09-25 | 2026-10-09 | 2026-10-23 |  |  | 2026-10-28 | 2026-10-28 | 2026-11-04 | 2026-11-06 | 2026-11-07 | [6 empty] | 2026-11-10 | 2026-11-13 |  |  | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-23 | 2026-11-25 | 96 | Z | Tomal | [5 empty] | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1845 | [11 empty] | 48 | Nov'1
BS-NMT | 48796 | 13265546 | 1330 | 197 | 2026-08-19 | 2026-09-01 | LS SWt full zipper cardigan w nk cuff YD tipping rib | Cardigan | 2026-09-15 | 2026-09-20 | 2026-09-18 | 2026-09-26 | 2026-10-01 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-20 | 2026-10-22 | 2026-10-23 |  |  |  |  | 2026-10-26 | 2026-10-30 | 2026-11-03 | 2026-11-05 |  |  | 2026-11-07 | 2026-11-10 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 89 | R | Mosaddik |  | Chest | spellbound-1330 pcs 1 clr flat 1 clr terry emb | YD |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -1330 | [11 empty] | 47 | Oct'3
BS-NMT | 48793 | 13257098 | 2642 | 173 | 2026-08-19 | 2026-09-01 | AOP Elasted Legging | Legging |  |  | 2026-09-16 | 2026-09-25 | 2026-10-01 | 2026-10-12 | 2026-10-15 | 2026-10-20 | 2026-10-23 | 2026-10-23 | 2026-10-29 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 |  |  |  |  | 2026-11-09 | 2026-11-10 |  |  | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-16 | 2026-11-18 | 89 | W2 | Mosaddik | Waist |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2642 | [11 empty] | 47 | Nov'1
BS-NMT | 48794 | 13257099 | 2588 | 270 | 2026-08-19 | 2026-09-01 | AOP LS body w shlder btm snap btn | Body |  |  | 2026-09-15 | 2026-09-22 | 2026-10-01 | 2026-10-10 | 2026-10-12 | 2026-10-19 | 2026-10-20 | 2026-10-20 | 2026-10-24 | 2026-10-27 | 2026-10-28 | 2026-10-30 | 2026-10-31 |  |  |  |  | 2026-11-04 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 89 | Y | Mosaddik | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2588 | [11 empty] | 47 | Oct'3
BS-NMT | 48816 | 13229233 | 2496 | 188 | 2026-08-20 | 2026-08-31 | AOP SS o nk TS w shlder snap btn | TS |  |  | 2026-09-10 | 2026-09-15 | 2026-09-24 | 2026-10-07 | 2026-10-09 | 2026-10-15 | 2026-10-16 | 2026-10-16 | 2026-10-22 | 2026-10-24 | 2026-10-26 | 2026-10-27 | 2026-10-29 |  |  |  |  | 2026-11-02 | 2026-11-04 |  |  | 2026-11-06 | 2026-11-07 | 2026-11-10 | 2026-11-16 | 2026-11-18 | 88 | T1 | Sabikun | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2496 | [11 empty] | 47 | Oct'3
BS-NMT | 48826 | 13269013 | 1920 | 100 | 2026-08-20 | 2026-08-31 | AOP SS o nk TS w shlder snap btn | TS |  |  | 2026-09-10 | 2026-09-14 | 2026-09-25 | 2026-10-06 | 2026-10-08 | 2026-10-14 | 2026-10-15 | 2026-10-15 | 2026-10-21 | 2026-10-23 | 2026-10-24 | 2026-10-27 | 2026-10-30 |  |  |  |  | 2026-11-03 | 2026-11-05 |  |  | 2026-11-07 | 2026-11-10 | 2026-11-11 | 2026-11-16 | 2026-11-18 | 88 | T1 | Sabikun | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1920 | [11 empty] | 47 | Oct'3
BS-NMT | 48813 | 132226053 | 2208 | 184 | 2026-08-20 | 2026-08-31 | LS o nk TS w shlder snap btn | TS |  |  | 2026-09-12 | 2026-09-16 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-20 | 2026-10-22 | 2026-10-23 | 2026-10-26 | 2026-10-29 |  |  |  |  | 2026-11-02 | 2026-11-05 |  |  | 2026-11-06 | 2026-11-07 | 2026-11-09 | 2026-11-16 | 2026-11-18 | 88 | T1 | Sabikun | Chest,Nk |  | c.dan-1104 pcs 2 clr rub 1 clr puff 1 clr gltr ,,orchid-1104 pcs 1 clr rub 1 clr puff 1 clr gltr |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2208 | [11 empty] | 47 | Oct'3
BS-NMT | 48830 | 13267910 | 6171 | 410 | 2026-08-20 | 2026-08-31 | AOP SS TS w shlder snap btn ,Shorts and Hat | Top,bottom & Hat |  |  | 2026-09-10 | 2026-09-15 | 2026-09-24 | 2026-10-07 | 2026-10-09 | 2026-10-15 | 2026-10-16 | 2026-10-16 | 2026-10-22 | 2026-10-24 | 2026-10-27 | 2026-10-28 | 2026-10-31 |  |  |  |  | 2026-11-04 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-10 | 2026-01-12 | 2026-11-15 | 2026-11-17 | 87 | S+T+Z | Sabikun | Waist & Nk |  | 6 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -6171 | [11 empty] | 47 | Oct'3
BS-NMT | 48823 | 13267901 | 7140 | 459 | 2026-08-20 | 2026-08-31 | AOP SS TS w shlder snap btn ,Shorts and Hat | Top,bottom & Hat |  |  | 2026-09-10 | 2026-09-16 | 2026-09-25 | 2026-10-10 | 2026-10-12 | 2026-10-17 | 2026-10-19 | 2026-10-19 | 2026-10-24 | 2026-10-26 | 2026-10-29 | 2026-10-29 | 2026-10-31 |  |  |  |  | 2026-11-03 | 2026-11-06 |  |  | 2026-11-07 | 2026-11-09 | 2026-11-10 | 2026-11-15 | 2026-11-17 | 87 | S+T+W2 | Sabikun | Waist & Nk |  | 6 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -7140 | [11 empty] | 47 | Oct'3
BS-NMT | 48828 | 13269019 | 1200 | 60 | 2026-08-20 | 2026-08-31 | Elasted shorts | Shorts |  |  | 2026-09-13 | 2026-09-18 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-19 | 2026-10-21 | 2026-10-22 | 2026-10-24 | 2026-10-26 |  |  |  |  | 2026-10-28 | 2026-10-30 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-10 | 2026-11-16 | 2026-11-18 | 88 | T2 | Sabikun | Waist |  | 2 combo label print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1200 | [11 empty] | 47 | Oct'3
BS-NMT | 48829 | 13269020 | 1174 | 96 | 2026-08-20 | 2026-08-31 | AOP & solid Swt Pant w waist rib and herringbone string | Pant |  |  | 2026-09-13 | 2026-09-18 | 2026-10-01 | 2026-10-15 | 2026-10-15 | 2026-10-20 | 2026-10-22 | 2026-10-22 | 2026-10-27 | 2026-10-29 | 2026-10-30 | 2026-11-02 | 2026-11-02 |  |  |  |  | 2026-11-04 | 2026-11-06 |  |  | 2026-11-07 | 2026-11-09 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 88 | W2 | Sabikun | Waist |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1174 | [11 empty] | 47 | Oct'3
BS-NMT | 48827 | 13269015 | 2736 | 215 | 2026-08-20 | 2026-08-31 | AOP & solid Swt Pant w waist rib and herringbone string | Pant |  |  | 2026-09-10 | 2026-09-15 | 2026-09-25 | 2026-10-10 | 2026-10-12 | 2026-10-17 | 2026-10-20 | 2026-10-20 | 2026-10-24 | 2026-10-27 | 2026-10-28 | 2026-10-30 | 2026-10-31 |  |  |  |  | 2026-11-04 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 88 | W2 | Sabikun | Waist |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2736 | [11 empty] | 47 | Oct'3
BS-NMT | 48814 | 13226056 | 1704 | 90 | 2026-08-20 | 2026-08-31 | Elasted Legging | Legging |  |  | 2026-09-07 | 2026-09-10 | 2026-09-18 | 2026-09-30 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-08 | 2026-10-10 | 2026-10-10 | 2026-10-13 | 2026-10-13 |  |  |  |  | 2026-10-15 | 2026-10-16 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-28 | 2026-11-16 | 2026-11-18 | 88 | W2 | Sabikun | Waist |  | 2 combo label print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1704 | [11 empty] | 47 | Oct'1
BS-NMT | 48824 | 13267906 | 1608 | 127 | 2026-08-20 | 2026-08-31 | AOP & solid Swt Pant w waist rib and herringbone string | Pant |  |  | 2026-09-10 | 2026-09-15 | 2026-09-27 | 2026-10-10 | 2026-10-12 | 2026-10-18 | 2026-10-19 | 2026-10-19 | 2026-10-24 | 2026-10-27 | 2026-10-28 | 2026-10-30 | 2026-10-31 |  |  |  |  | 2026-11-03 | 2026-11-04 |  |  | 2026-11-06 | 2026-11-09 | 2026-11-10 | 2026-11-16 | 2026-11-18 | 88 | W2 | Sabikun | Waist |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1608 | [11 empty] | 47 | Oct'3
BS-NMT | 48819 | 13229243 | 310 | 22 | 2026-08-20 | 2026-08-31 | Hat | Hat |  |  | 2026-09-17 | 2026-09-21 | 2026-10-05 | 2026-10-17 |  |  | 2026-10-21 | 2026-10-21 | 2026-10-27 | 2026-10-30 | 2026-10-30 | 2026-11-02 | 2026-11-02 |  |  |  |  | 2026-11-04 | 2026-11-05 |  |  | 2026-11-07 | 2026-11-10 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 88 | S | Sabikun | Nk |  | 1 combo label print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -310 | [11 empty] | 47 | Oct'3
BS-NMT | 48815 | 13229232 | 585 | 41 | 2026-08-20 | 2026-08-31 | Hat | Hat |  |  | 2026-09-15 | 2026-09-18 | 2026-10-05 | 2026-10-17 |  |  | 2026-10-22 | 2026-10-22 | 2026-10-27 | 2026-10-31 | 2026-10-31 | 2026-11-04 | 2026-11-04 |  |  |  |  | 2026-11-06 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-16 | 2026-11-18 | 88 | S | Sabikun | Nk |  | 1 combo label print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -585 | [11 empty] | 47 | Oct'3
BS-NMT | 48825 | 13267909 | 1806 | 156 | 2026-08-20 | 2026-08-31 | AOP body suit w snap btn and Hat | Suit,Hat |  |  | 2026-09-10 | 2026-09-14 | 2026-09-25 | 2026-10-08 | 2026-10-10 | 2026-10-17 | 2026-10-19 | 2026-10-19 | 2026-10-24 | 2026-10-27 | 2026-10-28 | 2026-10-30 | 2026-10-31 |  |  |  |  | 2026-11-04 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 88 | S+T2 | Sabikun | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1806 | [11 empty] | 47 | Oct'3
BS-NMT | 48822 | 13267896 | 4086 | 359 | 2026-08-20 | 2026-08-31 | AOP body suit w snap btn and Hat | Suit,Hat |  |  | 2026-09-08 | 2026-09-15 | 2026-09-22 | 2026-10-10 | 2026-10-12 | 2026-10-20 | 2026-10-21 | 2026-10-21 | 2026-10-26 | 2026-10-28 | 2026-10-31 | 2026-10-30 | 2026-11-02 |  |  |  |  | 2026-11-04 | 2026-11-09 |  |  | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 88 | S+T2 | Sabikun | Nk |  | 3 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -4086 | [11 empty] | 47 | Oct'3
BS-NMT | 48820 | 13230776 | 1683 | 166 | 2026-08-20 | 2026-08-31 | SS Over all body w wrap body snap btn | Body |  |  | 2026-09-10 | 2026-09-15 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-23 | 2026-10-24 |  |  |  |  | 2026-10-27 | 2026-10-29 |  |  | 2026-10-31 | 2026-11-03 | 2026-11-06 | 2026-11-16 | 2026-11-18 | 88 | Y | Sabikun | Chest,Nk |  | c.dan-879 pcs,,wreath-804 pcs both combo 2 clr rub 1 clr puff |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1683 | [11 empty] | 47 | Oct'2
BS-NMT | 48821 | 13230813 | 1622 | 162 | 2026-08-20 | 2026-08-31 | SS Wrap body suit w snap btn | Body |  |  | 2026-09-10 | 2026-09-15 | 2026-09-27 | 2026-10-10 |  |  | 2026-10-12 | 2026-10-12 | 2026-10-17 | 2026-10-19 | 2026-10-20 | 2026-10-22 | 2026-10-28 |  |  |  |  | 2026-10-26 | 2026-10-28 |  |  | 2026-10-30 | 2026-10-31 | 2026-11-05 | 2026-11-16 | 2026-11-18 | 88 | Y | Sabikun | Chest,Nk |  | orchid-811 pcs,,pink-811 pcs both combo 1 clr rub 1 clr gltr |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1622 | [11 empty] | 47 | Oct'2
BS-NMT | 48818 | 13229241 | 4908 | 390 | 2026-08-20 | 2026-08-31 | AOP SS body suit w btm shlder snap btn | Body |  |  | 2026-09-09 | 2026-09-15 | 2026-09-23 | 2026-10-07 | 2026-10-09 | 2026-10-16 | 2026-10-17 | 2026-10-17 | 2026-10-22 | 2026-10-24 | 2026-10-27 | 2026-10-27 | 2026-10-30 |  |  |  |  | 2026-11-02 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 88 | Y | Sabikun | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -4908 | [11 empty] | 47 | Oct'3
BS-NMT | 48817 | 13229234 | 4626 | 390 | 2026-08-20 | 2026-08-31 | AOP SS body suit w btm shlder snap btn | Body |  |  | 2026-09-10 | 2026-09-15 | 2026-09-22 | 2026-10-05 | 2026-10-07 | 2026-10-15 | 2026-10-16 | 2026-10-16 | 2026-10-22 | 2026-10-24 | 2026-10-27 | 2026-10-27 | 2026-10-30 |  |  |  |  | 2026-11-02 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 88 | S | Sabikun | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -4626 | [11 empty] | 47 | Oct'3
BS-NMT | 48939 | 13265710 | 13762 | 1881 | 2026-08-19 | 2026-09-01 | SS O nk Dress w btm mesh | Dress |  |  | 2026-09-10 | 2026-09-22 | 2026-09-25 | 2026-10-13 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-20 | 2026-10-23 | 2026-10-29 | [6 empty] | 2026-10-28 | 2026-11-12 |  |  | 2026-11-13 | 2026-11-14 | 2026-11-16 | 2026-11-16 | 2026-11-18 | 89 | S | Jafar | [5 empty] | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -13762 | [11 empty] | 47 | Oct'3
BS-NMT | 48935 | 13257824 | 7470 | 660 | 2026-08-19 | 2026-09-01 | AOP & Solid SS o Nk TS | TS |  |  | 2026-09-10 | 2026-09-16 | 2026-10-01 | 2026-10-15 | 2026-10-10 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-22 | 2026-10-24 | 2026-10-27 | 2026-10-27 | 2026-10-31 |  |  |  |  | 2026-11-02 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-11 | 2026-11-13 | 2026-11-16 | 2026-11-18 | 89 | ZA1 | Jafar | Chest,Nk |  | silver AOP -2490 pcs no print ,,ink-2490 pcs 3 clr rub print at chest,,green-2490 pcs 3 clr rub print at chest |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -7470 | [11 empty] | 47 | Oct'3
BS-NMT | 48934 | 13245914 | 5376 | 582 | 2026-08-19 | 2026-09-01 | Tank top | Tank Top |  |  | 2026-09-12 | 2026-09-21 | 2026-10-05 | 2026-10-17 |  |  | 2026-10-21 | 2026-10-21 | 2026-10-27 | 2026-10-30 | 2026-11-02 | 2026-11-03 | 2026-11-06 |  |  |  |  | 2026-11-09 | 2026-11-13 |  |  | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-23 | 2026-11-25 | 96 | T1 | Jafar | Nk |  | 4 combo label print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -5376 | [11 empty] | 48 | Oct'3
BS-NMT | 44847 3rd | 13244670 | 6282 | 838 | 2026-08-19 | 2026-09-01 | SS o nk TS | TS |  |  | 2026-09-10 | 2026-09-16 | 2026-09-27 | 2026-10-14 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-21 | 2026-10-24 | 2026-10-27 | 2026-10-27 | 2026-10-31 |  |  |  |  | 2026-11-04 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 89 | ZA2 | Jafar | Chest,Nk |  | c.dan-2094 pcs 6 clr pig ,,blue-2094 pcs 5 clr rub ,,pink-2094 pcs 5 clr pig |  | Artwork due | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -6282 | [11 empty] | 47 | Oct'3
BS-NMT | 48906 | 13265347 | 1070 | 494 | 2026-08-19 | 2026-08-31 | LS Swt hoody w cuff btm rib | Hoody |  |  | 2026-09-18 | 2026-09-24 | 2026-10-06 | 2026-10-20 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-29 | 2026-11-02 | 2026-11-02 | 2026-11-04 | 2026-11-07 |  |  |  |  | 2026-11-10 | 2026-11-12 |  |  | 2026-11-14 | 2026-11-16 | 2026-11-17 | 2026-11-23 | 2026-11-25 | 96 | S | Tomal | Fr,Bk |  | crockery-1070 pcs frt back 5 clr rub w photo print back |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1070 | [11 empty] | 48 | Nov'1
BS-NMT | 48909 | 13265440 | 6402 | 1030 | 2026-08-19 | 2026-08-31 | AOP SS o nk TS | TS |  |  | 2026-09-15 | 2026-09-22 | 2026-09-26 | 2026-10-12 | 2026-10-13 | 2026-10-20 | 2026-10-21 | 2026-10-21 | 2026-10-26 | 2026-10-28 | 2026-10-31 | 2026-11-02 | 2026-11-04 |  |  |  |  | 2026-11-05 | 2026-11-09 |  |  | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 89 | ZA1 | Tomal | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -6402 | [11 empty] | 47 | Oct'3
BS-NMT | 48901 | 13241058 | 6518 | 695 | 2026-08-19 | 2026-08-31 | SS Polo shirt w YD tipping collar ans placket btn | Polo | 2026-09-12 | 2026-09-18 | 2026-09-18 | 2026-09-28 | 2026-10-02 | 2026-10-15 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-22 | 2026-10-24 | 2026-10-27 | 2026-10-27 | 2026-10-30 |  |  | 2026-10-02 | 2026-10-31 | 2026-11-02 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 89 | S | Tomal | Nk | Chest | c.dan-3365 pcs,,spellbound-3153 pcs both combo 1 clr flat emb | YD |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -6518 | [11 empty] | 47 | Oct'3
BS-NMT | 48904 | 13265337 | 815 | 327 | 2026-08-19 | 2026-08-31 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-09-12 | 2026-09-17 | 2026-10-01 | 2026-10-14 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-24 | 2026-10-26 | 2026-10-27 | 2026-10-29 | 2026-10-31 |  |  |  |  | 2026-11-04 | 2026-11-05 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-13 | 2026-11-23 | 2026-11-25 | 96 | Z | Tomal | Fr,Bk |  | black-815 pcs frt back photo print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -815 | [11 empty] | 48 | Oct'3
BS-NMT | 48912 | 13265484 | 3463 | 1071 | 2026-08-19 | 2026-08-31 | LS Full ziper cut&sew swt shirt cardigan w cuff btm rib | Cardigan |  |  | 2026-09-13 | 2026-09-23 | 2026-10-01 | 2026-10-16 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-24 | 2026-10-27 | 2026-10-31 | [6 empty] | 2026-11-02 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 89 | R | Tomal | [5 empty] | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -3463 | [11 empty] | 47 | Oct'3
BS-NMT | 48903 | 13265328 | 2913 | 573 | 2026-08-19 | 2026-08-31 | SS o nk TS nk Rib | TS |  |  | 2026-09-12 | 2026-09-17 | 2026-10-05 | 2026-10-17 |  |  | 2026-10-22 | 2026-10-22 | 2026-10-27 | 2026-10-30 | 2026-10-31 | 2026-10-04 | 2026-10-07 |  |  |  |  | 2026-11-10 | 2026-11-13 |  |  | 2026-11-14 | 2026-11-17 | 2026-11-18 | 2026-11-23 | 2026-11-25 | 96 | Z | Tomal | Chest,Nk |  | crockery-1404 pcs,,c.dan-1509 pcs both combo photo print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2913 | [11 empty] | 48 | Oct'3
BS-NMT | 48905 | 13265346 | 1766 | 327 | 2026-08-19 | 2026-08-31 | SS o nk TS nk Rib | TS |  |  | 2026-09-15 | 2026-09-21 | 2026-10-01 | 2026-10-15 |  |  | 2026-10-17 | 2026-10-17 | 2026-10-23 | 2026-10-26 | 2026-10-27 | 2026-10-29 | 2026-10-31 |  |  |  |  | 2026-11-04 | 2026-11-06 |  |  | 2026-11-07 | 2026-11-09 | 2026-11-12 | 2026-11-23 | 2026-11-25 | 96 | Z | Tomal | Fr & Bk & Nk |  | mosstone-823 pcs,,black-943 pcs both combo frt back photo print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1766 | [11 empty] | 48 | Oct'3
BS-NMT | 48911 | 13265473 | 6061 | 625 | 2026-08-19 | 2026-08-31 | SS o nk TS nk Rib w one combo design zipper | TS |  |  | 2026-09-10 | 2026-09-16 | 2026-09-21 | 2026-10-03 |  |  | 2026-10-01 | 2026-10-01 | 2026-10-09 | 2026-10-12 | 2026-10-16 | 2026-10-15 | 2026-10-31 |  |  | 2026-10-24 | 2026-10-30 | 2026-11-04 | 2026-11-09 |  |  | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 89 | ZA1 | Tomal | Chest,Nk | Chest | mosstone-3176 pcs 6 clr rub w inside woven padding print and printed woven applique attach emb ,,blue-992 pcs 3 clr rub at chest and 2 clr rub at inside tunk wovenfabric print no emb ,,spellbound-1893 pcs 3 clr HD holographic critical print no emb |  | one combo Outside print plan mn print | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -6061 | [11 empty] | 47 | Oct'2
BS-NMT | 48907 | 13265351 | 958 | 251 | 2026-08-19 | 2026-08-31 | YD SS o nk TS | TS | 2026-09-20 | 2026-09-27 | 2026-10-01 | 2026-10-10 | 2026-10-14 | 2026-10-20 |  |  | 2026-10-24 | 2026-10-24 | 2026-10-31 | 2026-11-03 | 2026-11-04 | 2026-11-06 | 2026-11-10 |  |  |  |  | 2026-11-12 | 2026-11-13 |  |  | 2026-11-14 | 2026-11-16 | 2026-11-17 | 2026-11-23 | 2026-11-25 | 96 | Z | Tomal | Chest,Nk |  | mosstone-958 pcs 1 clr rub print | YD |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -958 | [11 empty] | 48 | Nov'1
BS-NMT | 48913 | 13268958 | 2157 | 473 | 2026-08-19 | 2026-08-31 | Swt pant w drawstring | Pant |  |  | 2026-09-14 | 2026-09-22 | 2026-10-01 | 2026-10-15 |  |  | 2026-10-20 | 2026-10-20 | 2026-10-26 | 2026-10-29 | 2026-10-30 | [6 empty] | 2026-11-03 | 2026-11-06 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 89 | X | Tomal | [5 empty] | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2157 | [11 empty] | 47 | Oct'3
BS-NMT | 48908 | 13265439 | 3207 | 436 | 2026-08-19 | 2026-08-31 | LS O nk TS | TS |  |  | 2026-09-12 | 2026-09-17 | 2026-10-01 | 2026-10-15 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-22 | 2026-10-24 | 2026-10-26 | 2026-10-28 | 2026-10-31 |  |  |  |  | 2026-11-04 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 89 | ZA2 | Tomal | Fr & Bk & Nk |  | c.dan-1641 pcs frt back 8 clr pig ,,spellbound-1566 pcs frt 14 clr pig print back no print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3207 | [11 empty] | 47 | Oct'3
BS-NMT | 48910 | 13265457 | 3708 | 955 | 2026-08-19 | 2026-08-31 | Swt cut&sew pant w side pkt drawstring | Pant |  |  | 2026-09-10 | 2026-09-22 | 2026-10-02 | 2026-10-17 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-24 | 2026-10-27 | 2026-10-31 | [6 empty] | 2026-11-02 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 89 | X | Tomal | [5 empty] | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3708 | [11 empty] | 47 | Oct'3
BS-NMT | 48876 | 13228342 | 2088 | 211 | 2026-08-19 | 2026-09-01 | SS o nk TS | TS |  |  | 2026-09-10 | 2026-09-15 | 2026-10-02 | 2026-10-15 |  |  | 2026-10-17 | 2026-10-17 | 2026-10-22 | 2026-10-24 | 2026-10-26 | 2026-10-28 | 2026-10-29 |  |  | 2026-10-28 | 2026-10-30 | 2026-11-02 | 2026-11-04 |  |  | 2026-11-06 | 2026-11-09 | 2026-11-11 | 2026-11-16 | 2026-11-18 | 89 | T1 | Haider | Nk | Chest | orchid-944 pcs,,violet-1144 pcs both combo woven lace laser cutting patch make and attach emb |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2088 | [11 empty] | 47 | Oct'3
BS-NMT | 48877 | 13265516 | 850 | 199 | 2026-08-19 | 2026-08-31 | YD lurex LS Swt shirt w nk cuff rib | Swt Shirt | 2026-09-21 | 2026-09-26 | 2026-10-01 | 2026-10-06 | 2026-10-14 | 2026-10-20 |  |  | 2026-10-22 | 2026-10-22 | 2026-10-27 | 2026-10-29 | 2026-10-29 | [6 empty] | 2026-11-02 | 2026-11-03 |  |  | 2026-11-05 | 2026-11-07 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 89 | Z | Haider |  |  |  | YD |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -850 | [11 empty] | 47 | Oct'3
BS-NMT | 48878 | 13254144 | 2150 | 271 | 2026-08-19 | 2026-08-31 | YD lurex Swt elasted skirt | Skirt | 2026-09-21 | 2026-09-26 | 2026-10-01 | 2026-10-07 | 2026-10-13 | 2026-10-20 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-28 | 2026-10-30 | 2026-10-31 | [6 empty] | 2026-11-03 | 2026-11-05 |  |  | 2026-11-07 | 2026-11-09 | 2026-11-10 | 2026-11-16 | 2026-11-18 | 89 | Z | Haider |  |  |  | YD |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2150 | [11 empty] | 47 | Oct'3
BS-NMT | 48879 | 13265824 | 1824 | 481 | 2026-08-19 | 2026-08-31 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-09-10 | 2026-09-15 | 2026-10-01 | 2026-10-10 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-20 | 2026-10-22 | 2026-10-23 | 2026-10-30 | 2026-11-02 |  |  | 2026-10-26 | 2026-10-28 | 2026-11-04 | 2026-11-06 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 89 | T2 | Haider | Chest | Chest | violet tulle-1824 pcs 1 clr flat emb and print on emb thread after emb 4 clr pig sublimation print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1824 | [11 empty] | 47 | Oct'3
BS-NMT | 48880 | 13265825 | 1050 | 259 | 2026-08-19 | 2026-08-31 | Waist belt swt pant w side back pkt | Pant |  |  | 2026-09-10 | 2026-09-15 | 2026-10-01 | 2026-10-10 |  |  | 2026-10-13 | 2026-10-13 | 2026-10-19 | 2026-10-21 | 2026-10-22 | 2026-10-29 | 2026-10-31 |  |  | 2026-10-24 | 2026-10-27 | 2026-11-02 | 2026-11-04 |  |  | 2026-11-06 | 2026-11-10 | 2026-11-11 | 2026-11-16 | 2026-11-18 | 89 | X | Haider | Thigh | Thigh | violet tulle-1050 pcs 1 clr flat emb and print on emb thread after emb 3 clr pig sublimation print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1050 | [11 empty] | 47 | Oct'3
BS-NMT | 48881 | 13257100 | 2125 | 296 | 2026-08-19 | 2026-08-31 | AOP LS on TS | TS |  |  | 2026-09-15 | 2026-09-21 | 2026-10-01 | 2026-10-10 | 2026-10-12 | 2026-10-17 | 2026-10-19 | 2026-10-19 | 2026-10-24 | 2026-10-27 | 2026-10-28 | 2026-10-30 | 2026-10-31 |  |  |  |  | 2026-11-03 | 2026-11-05 |  |  | 2026-11-07 | 2026-11-09 | 2026-11-10 | 2026-11-16 | 2026-11-18 | 89 | Z | Haider | Nk |  | 2 combo nk label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2125 | [11 empty] | 47 | Oct'3
BS-NMT | 48882 | 13257101 | 2125 | 232 | 2026-08-19 | 2026-08-31 | AOP Elasted Legging | Legging |  |  | 2026-09-15 | 2026-09-21 | 2026-10-01 | 2026-10-10 | 2026-10-12 | 2026-10-17 | 2026-10-20 | 2026-10-20 | 2026-10-24 | 2026-10-26 | 2026-10-27 | 2026-10-29 | 2026-10-30 |  |  |  |  | 2026-11-03 | 2026-11-05 |  |  | 2026-11-07 | 2026-11-10 | 2026-11-13 | 2026-11-16 | 2026-11-18 | 89 | W1 | Haider | Waist |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2125 | [11 empty] | 47 | Oct'3
BS-NMT | 48883 | 13265423 | 1138 | 171 | 2026-08-19 | 2026-08-31 | LS o nk Dress w btm mesh attach | Dress |  |  | 2026-09-12 | 2026-09-16 | 2026-10-05 | 2026-10-15 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-24 | 2026-10-27 | 2026-10-28 | 2026-10-30 | 2026-10-31 |  |  |  |  | 2026-11-04 | 2026-11-06 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 89 | S | Haider | Nk |  | 1 combo label print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1138 | [11 empty] | 47 | Oct'3
BS-NMT | 48884 | 13265424 | 2027 | 106 | 2026-08-19 | 2026-08-31 | Elasted Skirt w mesh | Skirt |  |  | 2026-09-14 | 2026-09-18 | 2026-10-05 | 2026-10-15 |  |  | 2026-10-20 | 2026-10-20 | 2026-10-26 | 2026-10-28 | 2026-10-28 | 2026-10-30 | 2026-10-31 |  |  |  |  | 2026-11-03 | 2026-11-05 |  |  | 2026-11-07 | 2026-11-09 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 89 | Y | Haider | Waist |  | 1 combo label print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2027 | [11 empty] | 47 | Oct'3
BS-ONS | 47818 5th | 22041282 | 11742 | 3987 | 2026-08-26 | 2026-08-31 | SS TS w nk and arm hole contrast piping | TS |  |  | 2026-09-10 | 2026-09-23 | 2026-09-25 | 2026-10-13 |  |  | 2026-10-12 | 2026-10-12 |  | 2026-10-17 | 2026-10-21 | [6 empty] | 2026-10-22 | 2026-10-27 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-07 | 2026-11-09 | 73 | ZA1 | Shovon | [5 empty] | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -11742 | [11 empty] | 46 | Oct'2
BS-ONS | 44077 10th | 22012786 | 30075 | 6251 | 2026-08-26 | 2026-09-02 | MENS R NK SS TS W SELF FABRIC NK BINDING | TS |  |  | 2026-09-08 | 2026-09-20 | 2026-09-22 | 2026-10-12 |  |  | 2026-10-10 | 2026-10-10 |  | 2026-10-16 | 2026-10-21 | [6 empty] | 2026-10-20 | 2026-10-29 |  |  | 2026-10-31 | 2026-11-02 | 2026-11-04 | 2026-11-09 | 2026-11-11 | 75 | F | Shovon | [5 empty] | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -30075 | [11 empty] | 46 | Oct'2
BS-ONS | 44078 5th | 22012787 | 30646 | 6400 | 2026-08-26 | 2026-09-02 | MENS R NK SS TS W SELF FABRIC NK BINDING | TS |  |  | 2026-09-08 | 2026-09-18 | 2026-09-22 | 2026-10-12 |  |  | 2026-10-10 | 2026-10-10 |  | 2026-10-16 | 2026-10-21 | [6 empty] | 2026-10-20 | 2026-10-30 |  |  | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-09 | 2026-11-11 | 75 | ZA2 | Shovon | [5 empty] | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -30646 | [11 empty] | 46 | Oct'2
BS-ONL | 48299 3rd | 15390922 | 2681 | 627 | 2026-09-02 | 2026-09-03 | SS o nk TS | TS |  |  | 2026-09-10 | 2026-09-15 | 2026-09-28 | 2026-10-09 |  |  | 2026-10-07 | 2026-10-07 |  | 2026-10-12 | 2026-10-13 | 2026-10-15 | 2026-10-20 |  |  |  |  | 2026-10-23 | 2026-10-26 |  |  | 2026-10-28 | 2026-10-30 | 2026-10-31 | 2026-11-09 | 2026-11-11 | 68 | L1 | Jannati | Fr,Bk |  | air blue-710 pcs frt 1 clr pig back photo print w 2 clr pig ,,lollipop-1119 pcs frt photo print w 2 clr pig back no print ,,corage-301 pcs frt 2 clr pig back no print ,,white pastry-551 pcs frt back photo print |  |  | NFL2 |  |  | Need Cut FB | 0 | 0 | 0 | 0 | -2681 | [11 empty] | 46 | Oct'2 |  |  | 07.09.26
BS-ONL | 48614 2nd | 15391466 | 1050 | 218 | 2026-09-02 | 2026-09-03 | SS U nk TS w front woven frog closure button | TS |  |  | 2026-09-10 | 2026-09-14 | 2026-10-01 | 2026-10-10 |  |  | 2026-10-10 | 2026-10-10 |  | 2026-10-15 | 2026-10-16 | [6 empty] | 2026-10-20 | 2026-10-22 |  |  | 2026-10-24 | 2026-10-27 | 2026-10-30 | 2026-11-09 | 2026-11-11 | 68 | M | Jannati | [5 empty] | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1050 | [11 empty] | 46 | Oct'2
BS-ONL | 48615 2nd | 15390900 | 1000 | 142 | 2026-09-02 | 2026-09-03 | YD ,AOP & Solid SL V nk Tank Top | Tank Top | 2026-09-08 | 2026-09-12 | 2026-09-10 | 2026-09-15 | 2026-09-15 | 2026-09-23 | 2026-09-22 | 2026-09-27 | 2026-10-01 | 2026-10-01 |  | 2026-10-05 | 2026-10-05 | 2026-10-08 | 2026-10-08 |  |  |  |  | 2026-10-12 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-16 | 2026-10-20 | 2026-11-09 | 2026-11-11 | 68 | ZA1 | Jannati | Nk |  | 4 combo nk Label Print | YD & AOP |  | NFL3 |  |  | Need Test Cut | 0 | 0 | 0 | 0 | -1000 | [11 empty] | 46 | Oct'1 |  |  | 07.09.26
BS-ONL | 48610 3rd | 15391574 | 1432 | 206 | 2026-09-02 | 2026-09-04 | SS o nk TS w btm Lace attach | TS |  |  | 2026-09-13 | 2026-09-18 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-10 | 2026-10-10 |  | 2026-10-15 | 2026-10-16 | [6 empty] | 2026-10-20 | 2026-10-22 |  |  | 2026-10-24 | 2026-10-26 | 2026-10-28 | 2026-11-09 | 2026-11-11 | 68 | V | Jannati |  |  |  |  | Lace | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1432 | [11 empty] | 46 | Oct'2
BS-ONL | 48620 2nd | 15391460 | 799 | 128 | 2026-09-02 | 2026-09-04 | SS V nk TS w nk Lace and slve btm letus stich | TS |  |  | 2026-09-13 | 2026-09-18 | 2026-10-01 | 2026-10-10 |  |  | 2026-10-12 | 2026-10-12 |  | 2026-10-19 | 2026-10-19 | [6 empty] | 2026-10-24 | 2026-10-26 |  |  | 2026-10-27 | 2026-10-28 | 2026-10-30 | 2026-11-09 | 2026-11-11 | 68 | K | Jannati | [5 empty] | NFL2 |  |  | Need Test Cut | 0 | 0 | 0 | 0 | -799 | [11 empty] | 46 | Oct'2 |  |  | 07.09.26
BS-ONL | 48648 | 15397799 | 1096 | 365 | 2026-08-12 | 2026-08-31 | SS o nk TS w back cut&sew pleat | TS |  |  | 1900-08-26 | 2026-09-26 | 2026-10-08 | 2026-10-20 |  |  | 2026-10-25 | 2026-10-25 | 2026-11-03 | 2026-11-05 | 2026-11-05 | [6 empty] | 2026-11-09 | 2026-11-10 |  |  | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-16 | 2026-11-18 | 96 | Z | Zahirul | [5 empty] | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1096 | [11 empty] | 47 | Nov'1
BS-ONL | 48650 | 15396136 | 3168 | 760 | 2026-08-12 | 2026-08-31 | SS o nk TS | TS |  |  | 2026-09-15 | 2026-09-22 | 2026-10-02 | 2026-10-15 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-24 | 2026-10-27 | 2026-10-28 | 2026-10-30 | 2026-11-04 |  |  |  |  | 2026-11-06 | 2026-11-09 |  |  | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 96 | F | Zahirul | Chest,Nk |  | phanthom-1440 pcs 3 clr rub print ,,birtch-1128 pcs,,corsage-600 pcs |  | print art work due | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -3168 | [11 empty] | 47 | Oct'3
BS-ONL | 48647 | 15396839 | 1248 | 290 | 2026-08-12 | 2026-08-31 | SS o nk TS w slve fold tuck | TS |  |  | 2026-09-13 | 2026-09-18 | 2026-10-05 | 2026-10-17 |  |  | 2026-10-21 | 2026-10-21 | 2026-10-27 | 2026-10-29 | 2026-10-30 | 2026-11-02 | 2026-11-05 |  |  |  |  | 2026-11-07 | 2026-11-09 |  |  | 2026-11-11 | 2026-11-13 | 2026-11-14 | 2026-11-16 | 2026-11-18 | 96 | F | Zahirul | Chest |  | ice water-648 pcs 7 clr rub 3 clr gltr print ,,c.dan-600 pcs |  | print art work due | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -1248 | [11 empty] | 47 | Oct'3
BS-ONL | 43969 42th | 15270390 | 3040 | 494 | 2026-09-01 | 2026-09-03 | SS o nk TS | TS |  |  | 2026-09-14 | 2026-09-18 | 2026-10-01 | 2026-10-10 |  |  | 2026-10-10 | 2026-10-10 |  | 2026-10-15 | 2026-10-17 | [6 empty] | 2026-10-20 | 2026-10-23 |  |  | 2026-10-24 | 2026-10-27 | 2026-10-28 | 2026-11-02 | 2026-11-04 | 62 | Z | Dalim | [5 empty] | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -3040 | [11 empty] | 45 | Oct'2
BS-ONL | 27204 68th | 15323159 | 3040 | 737 | 2026-09-01 | 2026-09-03 | LS o nk TS | TS |  |  | 2026-09-18 | 2026-09-22 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-12 | 2026-10-12 |  | 2026-10-17 | 2026-10-19 | [6 empty] | 2026-10-21 | 2026-10-23 |  |  | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-11-02 | 2026-11-04 | 62 | D1 | Dalim | [5 empty] | NFL1 |  |  | Need Cut FB | 0 | 0 | 0 | 0 | -3040 | [11 empty] | 45 | Oct'2 |  |  | 07.09.26
BS-ONL | 48838 | 15390875 | 3264 | 427 | 2026-08-24 | 2026-09-03 | Imp Fabric SS o nk TS | TS | [8 empty] | 2026-11-02 | 2026-11-02 | 2026-11-07 | 2026-11-10 | 2026-11-13 | [6 empty] | 2026-11-13 | 2026-11-17 |  |  | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-23 | 2026-11-25 | 91 | L1 | Abid |  |  |  |  | Imp fabric on 06/11 | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -3264 | [11 empty] | 48 | Nov'1
BS-ONL | 48841 | 15390683 | 1218 | 428 | 2026-08-24 | 2026-09-03 | LS Swt shirt w cufff btm rib | Swt Shirt |  |  | 2026-09-22 | 2026-09-26 | 2026-10-06 | 2026-10-22 |  |  | 2026-10-24 | 2026-10-24 | 2026-10-30 | 2026-11-02 | 2026-11-02 | 2026-11-04 | 2026-11-06 |  |  |  |  | 2026-11-09 | 2026-11-10 |  |  | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-23 | 2026-11-25 | 91 | N2 | Abid | Fr,Bk |  | tofu-698 pcs frt 1 clr pig 3 clr HD back 1 clr pig 4 clr HD ,,pear-520 pcs frt 2 clr rub back 3 clr rub 1 clr mettalic |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -1218 | [11 empty] | 48 | Nov'1
BS-ONL | 48839 | 15368338 | 1272 | 121 | 2026-08-24 | 2026-09-03 | SS o nk Frill slve TS w blind hem | TS |  |  | 2026-09-22 | 2026-09-25 | 2026-10-05 | 2026-10-20 |  |  | 2026-10-24 | 2026-10-24 | 2026-10-31 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-07 |  |  | 2026-11-07 | 2026-11-11 | 2026-11-13 | 2026-11-16 |  |  | 2026-11-17 | 2026-11-18 | 2026-11-20 | 2026-11-23 | 2026-11-25 | 91 | Q | Abid | Chest | Chest | c.dan-756 pcs 11 clr rub 1 clr puff print no emb ,,bloom-516 pcs 6 clr rub 3 flower applique emb |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -1272 | [11 empty] | 48 | Nov'1
BS-ONL | 48842 | 15394083 | 4476 | 787 | 2026-08-24 | 2026-09-03 | SS o nk TS w blind hem | TS |  |  | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-17 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-24 | 2026-10-27 | 2026-10-30 | 2026-11-02 | 2026-11-06 |  |  |  |  | 2026-11-09 | 2026-11-12 |  |  | 2026-11-14 | 2026-11-16 | 2026-11-17 | 2026-11-23 | 2026-11-25 | 91 | L1 | Abid | Fr,Bk |  | black-1992 pcs frt back 3 clr rub 1 clr gltr ,,tapioca-2484 pcs frt 2 clr rub 2 clr gltr back 4 clr rub 3 clr gltr |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -4476 | [11 empty] | 48 | Oct'3
BS-ONL | 48840 | 15390372 | 552 | 65 | 2026-08-24 | 2026-09-03 | LS o nk TS w blind hem | TS |  |  | 2026-09-23 | 2026-09-26 | 2026-10-07 | 2026-10-20 |  |  | 2026-10-24 | 2026-10-24 | 2026-10-29 | 2026-10-31 | 2026-10-31 | 2026-11-03 | 2026-11-04 |  |  |  |  | 2026-11-06 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-23 | 2026-11-25 | 91 | L1 | Abid | Chest |  | c.dan-552 pcs 1 clr rub 4 clr puff print |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -552 | [11 empty] | 48 | Oct'3
BS-ONL | 48216 2nd | 15381667 | 5484 | 1014 | 2026-08-24 | 2026-09-04 | SS o nk TS w back cut&sew pleat | TS |  |  | 2026-09-16 | 2026-09-25 | 2026-10-01 | 2026-10-15 |  |  | 2026-10-13 | 2026-10-13 |  | 2026-10-19 | 2026-10-22 | [6 empty] | 2026-10-22 | 2026-10-28 |  |  | 2026-10-30 | 2026-11-03 | 2026-11-06 | 2026-11-23 | 2026-11-25 | 91 | Q | Abid | [5 empty] | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -5484 | [11 empty] | 48 | Oct'2
OVS SPA | 48493 | 271TNK036V36-6198 | 12000 | 1830 | 2026-08-28 | 2026-09-02 | SL O nk TS w arm hole imp Lace attach | TS |  |  | 2026-09-25 | 2026-10-10 | 2026-10-12 | 2026-10-24 |  |  | 2026-11-07 | 2026-11-06 | 2026-11-11 | 2026-11-12 | 2026-11-16 | [6 empty] | 2026-11-16 | 2026-11-25 |  |  | 2026-11-25 | 2026-11-26 | 2026-11-28 | 2026-11-30 | 2026-11-30 | 94 | A | Khairul |  |  |  |  | Imp Lace | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -12000 | [11 empty] | 49 | Nov'2
OVS SPA | 48319 | 271PJA412SPFISS-6111 | 7878 | 1628 | 2026-09-28 | 2026-09-03 | SS TS and AOP Legging w self fab bow string | Top & BTM |  |  | 2026-09-19 | 2026-09-30 | 2026-10-01 | 2026-10-12 | 2026-10-13 | 2026-10-21 | 2026-10-29 | 2026-10-30 | 2026-11-03 | 2026-11-04 | 2026-11-06 | [6 empty] | 2026-11-07 | 2026-11-12 |  |  | 2026-11-13 | 2026-11-14 | 2026-11-16 | 2026-11-18 | 2026-11-20 | 51 | E+H | Basir |  |  |  | AOP |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -7878 | [11 empty] | 47 | Nov'1
GBX-Maurices | 48735 | 2524615/4704615 | 12718 | 5224 | 2026-09-02 | 2026-09-03 | AOP SS crew nk TS w slve fold tuck and full body smock | TS |  |  | 2026-09-12 | 2026-09-25 | 2026-09-24 | 2026-10-06 | 2026-10-04 | 2026-10-19 | 2026-10-14 | 2026-10-14 | 2026-10-20 | 2026-10-30 | 2026-11-06 |  |  | 2026-10-23 | 2026-11-02 |  |  | 2026-11-04 | 2026-11-14 |  |  | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-20 | 2026-11-20 | 79 | N/1 | Mannan |  |  | smock T&A 23/10 to 02/11 | AOP |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -12718 | [11 empty] | 47 | Oct'3
GBX-Maurices | 48720 | 2598286/4258286 | 7619 | 1686 | 2026-09-02 | 2026-09-03 | SS O nk TS w btm moon hem w gmts dye acid wash | TS |  |  | 2026-09-15 | 2026-09-22 | 2026-10-01 | 2026-10-08 |  |  | 2026-10-12 | 2026-10-12 | 2026-10-21 | 2026-10-24 | 2026-10-28 | 2026-11-12 | 2026-11-16 |  |  | 2026-10-27 | 2026-11-02 | 2026-11-02 | 2026-11-09 | 2026-11-07 | 2026-11-14 | 2026-11-18 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-20 | 79 | N/1 | Mannan | Heat Press/Heat Seal | Chest | night shadow blue-7619 pcs self fab lazer cut border 1 clr satin stitch emb and nk HP label |  | Gmts dye acid wash | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -7619 | [11 empty] | 47 | Oct'3
GBX-Maurices | 48733 | 2522489 | 6915 | 1364 | 2026-09-02 | 2026-09-03 | AOP & solid SS one off shlder nk TS | TS |  |  | 2026-09-15 | 2026-09-22 | 2026-10-01 | 2026-10-14 | 2026-10-10 | 2026-10-17 | 2026-10-19 | 2026-10-19 | 2026-10-24 | 2026-10-27 | 2026-10-31 | 2026-10-29 | 2026-11-03 |  |  |  |  | 2026-11-02 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-09 | 2026-11-10 | 2026-11-10 | 2026-11-10 | 69 | N/1 | Mannan | Heat Press/Heat Seal |  | 1 combo nk HP label | AOP |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -6915 | [11 empty] | 46 | Oct'3
GBX-Maurices | 48719 | 2523162/4703162 | 19508 | 4167 | 2026-09-02 | 2026-09-04 | SS V nk TS w nk rawedge | TS |  |  | 2026-09-14 | 2026-09-24 | 2026-09-24 | 2026-10-08 |  |  | 2026-10-09 | 2026-10-09 | 2026-10-14 | 2026-10-16 | 2026-10-21 | 2026-10-19 | 2026-10-29 |  |  |  |  | 2026-10-24 | 2026-11-06 |  |  | 2026-11-07 | 2026-11-07 | 2026-11-09 | 2026-11-10 | 2026-11-10 | 69 | N/1 | Mannan | Chest,HP |  | Gardenia-core-12118 pcs,,plus-7390 pcs both 6 clr rub print and nk HP sticker |  |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -19508 | [11 empty] | 46 | Oct'2
GBX-Maurices | 48721 | 2523162/4703162 | 16806 | 3486 | 2026-09-02 | 2026-09-04 | SS V nk TS w slve fold tuck and side slit | TS |  |  | 2026-09-12 | 2026-09-22 | 2026-09-24 | 2026-10-10 |  |  | 2026-10-10 | 2026-10-10 | 2026-10-15 | 2026-10-17 | 2026-10-22 | 2026-10-21 | 2026-10-28 |  |  |  |  | 2026-10-26 | 2026-11-06 |  |  | 2026-11-07 | 2026-11-09 | 2026-11-10 | 2026-11-10 | 2026-11-10 | 69 | N/3 | Mannan | Chest,HP |  | moonscape- core-11996 pcs,,plus-4810 pcs both 1 clr pig 1 clr foil print and nk HP sticker |  |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -16806 | [11 empty] | 46 | Oct'2
GBX-Maurices | 48717 | 2592600/4259600 | 29416 | 6852 | 2026-09-02 | 2026-09-04 | SS o nk TS w gmts dye acid wash | TS |  |  | 2026-09-12 | 2026-09-25 | 2026-09-24 | 2026-10-06 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-10 | 2026-10-13 | 2026-10-19 | 2026-10-27 | 2026-11-06 |  |  |  |  | 2026-10-16 | 2026-10-29 | 2026-10-22 | 2026-11-03 | 2026-11-09 | 2026-11-09 | 2026-11-10 | 2026-11-10 | 2026-11-10 | 69 | N/3 | Mannan | Chest,HP |  | fushion coral core-19698 pcs,,plus-9718 pcs both 1 clr puff 1 clr rub print and nk HP sticker |  | Gmts dye pigment wash | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -29416 | [11 empty] | 46 | Oct'2
GBX -Sainsbury's | 48956 | 149048504 | 6595 | 2236 | 2026-08-25 | 2026-09-03 | SS o nk TS w gmts dye acid wash | TS |  |  | 2026-09-08 | 2026-09-17 | 2026-09-21 | 2026-09-28 |  |  | 2026-09-28 | 2026-09-26 | 2026-10-05 | 2026-10-08 | 2026-10-12 | 2026-10-23 | 2026-10-28 | 2026-10-26 | 2026-10-30 |  |  | 2026-10-12 | 2026-10-16 | 2026-10-16 | 2026-10-26 | 2026-11-03 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-05 | 72 | Z | Morad | Chest,Nk & stone |  | gri light wash-6775 pcs 5 clr rub 1 clr stone heat press attach |  | Gmts dye acid wash | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -6595 | [11 empty] | 45 | Oct'1
GBX -Sainsbury's | 48955 | 149048985 | 5835 | 1926 | 2026-08-25 | 2026-09-03 | SS o nk TS w gmts dye acid wash | TS |  |  | 2026-09-10 | 2026-09-18 | 2026-09-24 | 2026-09-30 |  |  | 2026-10-01 | 2026-09-28 | 2026-10-06 | 2026-10-09 | 2026-10-13 | 2026-10-26 | 2026-10-31 |  |  |  |  | 2026-10-13 | 2026-10-19 | 2026-10-19 | 2026-10-28 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-05 | 72 | T2 | Morad | Chest,Nk |  | Pink light wash-5835 pcs 7 clr rub 1 clr puff print |  | Gmts dye acid wash | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -5835 | [11 empty] | 45 | Oct'1
UTG-AF | 42481 13th | BAD1547mamaAB | 9000 | 1686 | 2026-09-01 | 2026-09-03 | NUIRSING TANK TOP | Tank Top |  |  | 2026-09-21 | 2026-09-30 | 2026-10-01 | 2026-10-13 |  |  | 2026-10-24 | 2026-10-26 |  | 2026-10-27 | 2026-10-30 | [6 empty] | 2026-11-02 | 2026-11-09 |  |  | 2026-11-10 | 2026-11-11 | 2026-11-13 | 2026-11-14 | 2026-11-16 | 74 | K1 | Rana | [5 empty] | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -9000 | [11 empty] | 47 | Oct'3
UTG-AF | 41948 6th | BAD0984mamaBM | 4500 | 855 | 2026-09-01 | 2026-09-03 | SS o nk TS | TS |  |  | 2026-09-21 | 2026-09-30 | 2026-10-01 | 2026-10-13 |  |  | 2026-10-24 | 2026-10-26 |  | 2026-10-28 | 2026-10-29 | [6 empty] | 2026-11-02 | 2026-11-06 |  |  | 2026-11-07 | 2026-11-09 | 2026-11-11 | 2026-11-14 | 2026-11-16 | 74 | N1 | Rana | [5 empty] | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -4500 | [11 empty] | 47 | Oct'3
UTG-AF | 41833 6th | BAD1056nursAK | 4400 | 880 | 2026-09-01 | 2026-09-03 | O NK SS TS | TS |  |  | 2026-09-21 | 2026-09-30 | 2026-10-01 | 2026-10-13 |  |  | 2026-10-24 | 2026-10-26 |  | 2026-10-28 | 2026-10-29 | [6 empty] | 2026-11-02 | 2026-11-09 |  |  | 2026-11-10 | 2026-11-11 | 2026-11-13 | 2026-11-14 | 2026-11-16 | 74 | G2 | Rana | [5 empty] | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -4400 | [11 empty] | 47 | Oct'3
UTG-AF | 29756 11th | BAD2344mamaN | 7000 | 1463 | 2026-09-01 | 2026-09-03 | LDS O NK SS TOP & SKIRT | Top & BTM |  |  | 2026-09-18 | 2026-09-30 | 2026-10-01 | 2026-10-14 |  |  | 2026-10-23 | 2026-10-24 |  | 2026-10-26 | 2026-10-28 | [6 empty] | 2026-11-02 | 2026-11-09 |  |  | 2026-11-10 | 2026-11-11 | 2026-11-13 | 2026-11-14 | 2026-11-16 | 74 | D1 | Rana | [5 empty] | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -7000 | [11 empty] | 47 | Oct'3
UTG-AF | 41952 5th | BAD1666mamaR | 4500 | 938 | 2026-09-01 | 2026-09-03 | YD SS v Nk TS | TS | 2026-09-15 | 2026-09-25 | 2026-09-26 | 2026-10-06 | 2026-10-07 | 2026-10-17 |  |  | 2026-10-24 | 2026-10-26 |  | 2026-10-29 | 2026-10-30 | [6 empty] | 2026-11-02 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-14 | 2026-11-16 | 74 | G2 | Rana | [5 empty] | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -4500 | [11 empty] | 47 | Oct'3
BS-NMT | 48769 | 13228228/13231736 | 4187 | 359 | 2026-08-19 | 2026-09-02 | SL o nk TS | TS |  |  | 2026-09-25 | 2026-09-30 | 2026-10-10 | 2026-10-28 |  |  | 2026-11-05 | 2026-11-05 | 2026-11-11 | 2026-11-14 | 2026-11-18 | 2026-11-18 | 2026-11-24 |  |  |  |  | 2026-11-26 | 2026-11-30 |  |  | 2026-12-03 | 2026-12-08 | 2026-12-10 | 2026-12-20 | 2026-12-22 | 123 | T1 | Kamruzzaman | Chest,Nk |  | atomizer-1141 pcs 5 clr rub ,,green-1523 pcs 6 clr rub /pig,,crockery-1523 pcs 6 clr rub |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -4187 | [11 empty] | 52 | Nov'2
BS-NMT | 48774 | 13228154 | 2091 | 166 | 2026-08-19 | 2026-09-02 | AOP Elasted Legging | Legging |  |  | 2026-09-23 | 2026-09-27 | 2026-10-08 | 2026-10-20 | 2026-10-25 | 2026-10-30 | 2026-11-10 | 2026-11-10 | 2026-11-16 | 2026-11-18 | 2026-11-19 | 2026-11-21 | 2026-11-23 |  |  |  |  | 2026-11-26 | 2026-11-28 |  |  | 2026-12-02 | 2026-12-05 | 2026-12-10 | 2026-12-21 | 2026-12-23 | 124 | W2 | Kamruzzaman | Waist |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2091 | [11 empty] | 52 | Nov'2
BS-NMT | 48775 | 13254890/13258463 | 3005 | 288 | 2026-08-19 | 2026-09-02 | LS Shirt w full placket one button | Shirt |  |  | 2026-09-15 | 2026-09-25 | 2026-10-05 | 2026-10-20 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-29 | 2026-11-02 | 2026-11-03 | 2026-11-05 | 2026-11-07 |  |  |  |  | 2026-11-10 | 2026-11-14 |  |  | 2026-11-17 | 2026-11-20 | 2026-11-30 | 2026-12-21 | 2026-12-23 | 124 | V | Kamruzzaman | Nk |  | 3 combo label print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3005 | [11 empty] | 52 | Nov'1
BS-NMT | 48776 | 13245831 | 1920 | 304 | 2026-08-19 | 2026-09-02 | SS AOP capsl dress | Dress |  |  | 2026-09-25 | 2026-09-30 | 2026-10-10 | 2026-10-23 | 2026-11-02 | 2026-11-10 | 2026-11-13 | 2026-11-13 | 2026-11-20 | 2026-11-24 | 2026-11-25 | 2026-11-27 | 2026-11-28 |  |  |  |  | 2026-12-02 | 2026-12-04 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-14 | 2026-12-21 | 2026-12-23 | 124 | T2 | Kamruzzaman | Nk |  | 3 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1920 | [11 empty] | 52 | Nov'3
BS-NMT | 48778 | 13228171 | 5029 | 578 | 2026-08-19 | 2026-09-02 | AOP Strap shlder body suit w btm snap btn | Suit |  |  | 2026-09-22 | 2026-09-28 | 2026-10-05 | 2026-10-23 | 2026-10-28 | 2026-11-08 | 2026-11-12 | 2026-11-12 | 2026-11-18 | 2026-11-21 | 2026-11-24 | 2026-11-25 | 2026-11-28 |  |  |  |  | 2026-12-04 | 2026-12-11 |  |  | 2026-12-12 | 2026-12-15 | 2026-12-17 | 2026-12-21 | 2026-12-23 | 124 | S | Kamruzzaman | Nk |  | 4 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -5029 | [11 empty] | 52 | Nov'3
BS-NMT | 48779 | 13215112 | 9056 | 641 | 2026-08-19 | 2026-09-02 | AOP Shorts w side pkt drawstring | Shorts |  |  | 2026-09-18 | 2026-09-24 | 2026-10-03 | 2026-10-18 | 2026-10-20 | 2026-10-27 | 2026-10-29 | 2026-10-29 | 2026-11-05 | 2026-11-07 | 2026-11-11 | 2026-11-10 | 2026-11-14 |  |  |  |  | 2026-11-14 | 2026-11-19 |  |  | 2026-11-23 | 2026-11-25 | 2026-11-30 | 2026-12-20 | 2026-12-22 | 123 | U | Kamruzzaman | Waist |  | 4 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -9056 | [11 empty] | 52 | Nov'1
BS-NMT | 48783 | 13241654 | 4990 | 578 | 2026-08-19 | 2026-09-02 | Tank Top w waist knot | Tank Top |  |  | 2026-09-17 | 2026-09-22 | 2026-10-01 | 2026-10-14 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-22 | 2026-10-24 | 2026-10-27 | 2026-10-28 | 2026-11-04 |  |  |  |  | 2026-11-06 | 2026-11-10 |  |  | 2026-11-12 | 2026-11-14 | 2026-11-20 | 2026-12-28 | 2026-12-30 | 131 | V | Kamruzzaman | Chest,Nk |  | c.dan-2055 pcs 1 clr pig ,,blue-2130 pcs 4 clr rub,,melon-805 pcs 4 clr rub |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -4990 | [11 empty] | 53 | Oct'3
BS-NMT | 48791 | 13254886 | 1431 | 191 | 2026-08-19 | 2026-09-02 | Waist belt shorts w drawstring | Shorts |  |  | 2026-10-05 | 2026-10-10 | 2026-10-22 | 2026-11-08 |  |  | 2026-11-14 | 2026-11-14 | 2026-11-23 | 2026-11-26 | 2026-11-27 | 2026-12-01 | 2026-12-03 |  |  |  |  | 2026-12-07 | 2026-12-09 |  |  | 2026-12-11 | 2026-12-14 | 2026-12-17 | 2026-12-28 | 2026-12-30 | 131 | X | Kamruzzaman | Thigh |  | pink-753 pcs,,,vanilla-678 pcs all combo 1 clr rub print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1431 | [11 empty] | 53 | Nov'3
BS-NMT | 48790 | 13254886 | 2099 | 680 | 2026-08-19 | 2026-09-02 | LS swt shirt w bk btm rib | Swt Shirt |  |  | 2026-10-10 | 2026-10-15 | 2026-10-25 | 2026-11-10 |  |  | 2026-11-17 | 2026-11-17 | 2026-11-23 | 2026-11-26 | 2026-11-28 | 2026-12-03 | 2026-12-07 |  |  |  |  | 2026-12-10 | 2026-12-12 |  |  | 2026-12-15 | 2026-12-18 | 2026-12-22 | 2026-12-28 | 2026-12-30 | 131 | Z | Kamruzzaman | Chest |  | pink-787 pcs,,,vanilla-1312 pcs all combo 1 clr rub print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2099 | [11 empty] | 53 | Nov'3
BS-NMT | 48788 | 13228208 | 8266 | 2039 | 2026-08-19 | 2026-09-02 | SL AOP cut sew o nk Dress | Dress |  |  | 2026-09-22 | 2026-09-30 | 2026-10-05 | 2026-10-17 | 2026-10-20 | 2026-10-29 | 2026-11-02 | 2026-11-02 | 2026-11-07 | 2026-11-10 | 2026-11-13 | 2026-11-12 | 2026-11-16 |  |  |  |  | 2026-11-18 | 2026-11-23 |  |  | 2026-11-25 | 2026-11-28 | 2026-12-06 | 2026-12-26 | 2026-12-28 | 129 | V | Kamruzzaman | Nk |  | 4 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -8266 | [11 empty] | 53 | Nov'1
BS-NMT | 48787 | 13215236 | 6031 | 980 | 2026-08-19 | 2026-09-02 | AOP Strap shlder body suit w btm snap btn | Suit |  |  | 2026-09-23 | 2026-09-30 | 2026-10-05 | 2026-10-20 | 2026-10-25 | 2026-11-07 | 2026-11-12 | 2026-11-12 | 2026-11-17 | 2026-11-21 | 2026-11-24 | 2026-11-25 | 2026-11-28 |  |  |  |  | 2026-12-02 | 2026-12-08 |  |  | 2026-12-10 | 2026-12-14 | 2026-12-17 | 2026-12-28 | 2026-12-30 | 131 | S | Kamruzzaman | Nk |  | 4 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -6031 | [11 empty] | 53 | Nov'3
BS-NMT | 48786 | 13228209/13232113 | 7426 | 1572 | 2026-08-19 | 2026-09-02 | SS AOP capsl dress | Dress |  |  | 2026-09-22 | 2026-10-02 | 2026-10-08 | 2026-10-24 | 2026-10-28 | 2026-11-08 | 2026-11-13 | 2026-11-13 | 2026-11-20 | 2026-11-23 | 2026-11-26 | 2026-11-26 | 2026-11-30 |  |  |  |  | 2026-12-01 | 2026-12-05 |  |  | 2026-12-08 | 2026-12-10 | 2026-12-14 | 2026-12-27 | 2026-12-29 | 130 | T2 | Kamruzzaman | Nk |  | 4 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -7426 | [11 empty] | 53 | Nov'3
BS-NMT | 48777 | 13228172/13232106 | 13132 | 2134 | 2026-08-19 | 2026-09-02 | AOP SL o nk Cut&sew dress | Dress |  |  | 2026-09-22 | 2026-09-30 | 2026-10-05 | 2026-10-24 | 2026-10-27 | 2026-11-08 | 2026-11-13 | 2026-11-13 | 2026-11-19 | 2026-11-21 | 2026-11-26 | 2026-11-26 | 2026-11-30 |  |  |  |  | 2026-12-01 | 2026-12-07 |  |  | 2026-12-09 | 2026-12-11 | 2026-12-14 | 2026-12-19 | 2026-12-21 | 122 | V | Kamruzzaman | Nk |  | 4 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -13132 | [11 empty] | 52 | Nov'3
BS-NMT | 48771 | 13228175 | 9859 | 844 | 2026-08-19 | 2026-09-02 | AOP & solid SS o nk TS | TS |  |  | 2026-09-22 | 2026-09-27 | 2026-10-04 | 2026-10-20 | 2026-10-17 | 2026-10-23 | 2026-10-25 | 2026-10-25 | 2026-10-30 | 2026-11-02 | 2026-11-05 | 2026-11-06 | 2026-11-11 |  |  |  |  | 2026-11-14 | 2026-11-18 |  |  | 2026-11-20 | 2026-11-23 | 2026-11-30 | 2026-12-21 | 2026-12-23 | 124 | ZA2 | Kamruzzaman | Chest,Nk |  | pink-3053 pcs 3 clr rub ,,blue-1630 pcs 3 clr rub ,,navy-1160 pcs 4 clr rub ,,Aqua-2843 pcs 5 clr rub ,,chambray AOP -1173 pcs no print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -9859 | [11 empty] | 52 | Nov'1
BS-NMT | 48782 | 13228179/13233823 | 5212 | 704 | 2026-08-19 | 2026-09-02 | SS O nk TS | TS |  |  | 2026-10-01 | 2026-10-05 | 2026-10-20 | 2026-11-05 |  |  | 2026-11-12 | 2026-11-12 | 2026-11-17 | 2026-11-19 | 2026-11-21 | 2026-11-24 | 2026-11-27 |  |  |  |  | 2026-12-03 | 2026-12-05 |  |  | 2026-12-08 | 2026-12-10 | 2026-12-15 | 2026-12-27 | 2026-12-29 | 130 | W2 | Kamruzzaman | Chest,Nk |  | Blue-1478 pcs 5 clr rub,,c.dan-756 pcs 4 clr pig ,,vanilla-1950 pcs 2 clr pig ,,pink-1028 pcs 4 clr pig |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -5212 | [11 empty] | 53 | Nov'2
BS-NMT | 48784 | 13233830 | 3160 | 345 | 2026-08-19 | 2026-09-02 | SS O nk TS | TS |  |  | 2026-10-01 | 2026-10-06 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-14 | 2026-11-14 | 2026-11-20 | 2026-11-23 | 2026-11-24 | 2026-11-26 | 2026-11-30 |  |  |  |  | 2026-12-05 | 2026-12-07 |  |  | 2026-12-09 | 2026-12-12 | 2026-12-15 | 2026-12-28 | 2026-12-30 | 131 | W2 | Kamruzzaman | Chest,Nk |  | pink-1580 pcs 3 clr pig ,,c.dan-1580 pcs 4 clr pig |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3160 | [11 empty] | 53 | Nov'3
BS-NMT | 48781 | 13224966 | 1363 | 199 | 2026-08-19 | 2026-09-03 | SS O nk TS | TS |  |  | 2026-10-08 | 2026-10-12 | 2026-10-27 | 2026-11-10 |  |  | 2026-11-17 | 2026-11-17 | 2026-11-23 | 2026-11-26 | 2026-11-27 | 2026-12-01 | 2026-12-03 |  |  |  |  | 2026-12-10 | 2026-12-11 |  |  | 2026-12-14 | 2026-12-17 | 2026-12-22 | 2026-12-28 | 2026-12-30 | 131 | Z | Kamruzzaman | Chest,Nk |  | green-744 pcs 5 clr rub,,blue-619 pcs 1 clr rub |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1363 | [11 empty] | 53 | Nov'3
BS-NMT | 48767 | 13227488/13231752 | 4438 | 473 | 2026-08-19 | 2026-09-03 | SS o nk roll slve TS | TS |  |  | 2026-10-01 | 2026-10-05 | 2026-10-13 | 2026-10-30 |  |  | 2026-11-10 | 2026-11-10 | 2026-11-16 | 2026-11-19 | 2026-11-21 | 2026-11-24 | 2026-11-27 |  |  |  |  | 2026-12-01 | 2026-12-04 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-12 | 2026-12-20 | 2026-12-22 | 123 | Y | Kamruzzaman | Chest,Nk |  | green-1708 pcs 5 clr rub ,,crockery-1130 pcs 7 clr rub ,,blue-1600 pcs 5 clr rub |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -4438 | [11 empty] | 52 | Nov'2
BS-NMT | 48770 | 13228144 | 3454 | 311 | 2026-08-19 | 2026-09-03 | SS O nk TS | TS |  |  | 2026-10-01 | 2026-10-05 | 2026-10-13 | 2026-10-30 |  |  | 2026-11-06 | 2026-11-06 | 2026-11-13 | 2026-11-16 | 2026-11-17 | 2026-11-19 | 2026-11-23 |  |  |  |  | 2026-11-26 | 2026-11-30 |  |  | 2026-12-03 | 2026-12-07 | 2026-12-12 | 2026-12-21 | 2026-12-23 | 124 | Z | Kamruzzaman | Chest,Nk |  | blue-1332 pcs 1 clr rub 3 clr gltr ,,c.dan-320 pcs 3 clr pig 2 clr gltr ,,vanilla-1332 pcs 4 clr rub 1 clr gltr ,,pink-470 pcs 4 clr rub 1 clr gltr |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3454 | [11 empty] | 52 | Nov'2
BS-NMT | 48773 | 13228148 | 1464 | 101 | 2026-08-19 | 2026-09-03 | SS O nk TS | TS |  |  | 2026-10-01 | 2026-10-05 | 2026-10-13 | 2026-10-30 |  |  | 2026-11-07 | 2026-11-07 | 2026-11-14 | 2026-11-17 | 2026-11-18 | 2026-11-21 | 2026-11-24 |  |  |  |  | 2026-11-27 | 2026-11-28 |  |  | 2026-12-03 | 2026-12-06 | 2026-12-12 | 2026-12-21 | 2026-12-23 | 124 | Z | Kamruzzaman | Chest,Nk |  | pink-488 pcs,,vanilla-488 pcs ,,hibicus-488 pcs all combo 5 clr rub |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1464 | [11 empty] | 52 | Nov'2
BS-NMT | 48772 | 13228169 | 1918 | 744 | 2026-08-19 | 2026-09-03 | AOP SL o nk TS | TS |  |  | 2026-10-01 | 2026-10-05 | 2026-10-10 | 2026-10-24 | 2026-10-28 | 2026-11-05 | 2026-11-13 | 2026-11-13 | 2026-11-19 | 2026-11-21 | 2026-11-23 | 2026-11-25 | 2026-11-27 |  |  |  |  | 2026-12-01 | 2026-12-02 |  |  | 2026-12-05 | 2026-12-08 | 2026-12-12 | 2026-12-21 | 2026-12-23 | 124 | Y | Kamruzzaman | Nk |  | 4 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1918 | [11 empty] | 52 | Nov'3
BS-NMT | 48768 | 13228225 | 2155 | 217 | 2026-08-19 | 2026-09-03 | SS O nk TS | TS |  |  | 2026-10-01 | 2026-10-06 | 2026-10-13 | 2026-10-30 |  |  | 2026-11-12 | 2026-11-12 | 2026-11-17 | 2026-11-20 | 2026-11-21 | 2026-11-24 | 2026-11-27 |  |  |  |  | 2026-12-02 | 2026-12-04 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-12 | 2026-12-21 | 2026-12-23 | 124 | Y | Kamruzzaman | Chest,Nk |  | Atomizer-732 pcs 5 clr rub ,,green-755 pcs 6 clr rub ,,crockery-668 pcs 6 clr rub |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2155 | [11 empty] | 52 | Nov'2
BS-NMT | 48785 | 13228210 | 4618 | 627 | 2026-08-19 | 2026-09-03 | SS O nk TS | TS |  |  | 2026-10-05 | 2026-10-10 | 2026-10-20 | 2026-11-05 |  |  | 2026-11-14 | 2026-11-14 | 2026-11-19 | 2026-11-21 | 2026-11-23 | 2026-11-25 | 2026-11-30 |  |  |  |  | 2026-12-04 | 2026-12-07 |  |  | 2026-12-09 | 2026-12-12 | 2026-12-17 | 2026-12-26 | 2026-12-28 | 129 | W2 | Kamruzzaman | Chest,Nk |  | pink-1116 pcs 2 clr pig ,,blue-1214 pcs 5 clr rub ,,c.dan-1414 pcs 6 clr pig ,,navy-874 pcs 1 clr rub |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -4618 | [11 empty] | 53 | Nov'3
BS-NMT | 48780 | 13228173 | 7672 | 633 | 2026-08-19 | 2026-09-03 | SS TS and AOP shorts w side pkt herringbone string | Top & BTM |  |  | 2026-09-22 | 2026-09-28 | 2026-10-05 | 2026-10-20 | 2026-10-23 | 2026-10-30 | 2026-11-07 | 2026-11-07 | 2026-11-14 | 2026-11-17 | 2026-11-20 | 2026-11-23 | 2026-11-27 |  |  |  |  | 2026-12-01 | 2026-12-04 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-12 | 2026-12-19 | 2026-12-21 | 122 | U+W2 | Kamruzzaman | Chest,Nk,Waist |  | pink top-1461 pcs 3 clr rub ,,pink btm aop-1461 pcs no print ,,blue top-703 pcs 3 clr rub ,,blue btm AOP-703 pcs no print ,,navy top-468 pcs 4 clr rub ,,navy btm AOP-468 pcs no print ,,aqua top-1204 pcs 5 clr rub ,,aqua btm aop-1204 pcs no print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -7672 | [11 empty] | 52 | Nov'2
BS-NMT | 48789 | 13228212 | 3892 | 219 | 2026-08-19 | 2026-09-03 | SS TS and AOP shorts w side pkt herringbone string | Top & BTM |  |  | 2026-10-01 | 2026-10-05 | 2026-10-10 | 2026-10-24 | 2026-10-29 | 2026-11-05 | 2026-11-10 | 2026-11-10 | 2026-11-16 | 2026-11-19 | 2026-11-20 | 2026-11-24 | 2026-11-27 |  |  |  |  | 2026-12-01 | 2026-12-03 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-14 | 2026-12-28 | 2026-12-30 | 131 | X+W2 | Kamruzzaman | Chest,Nk,Waist |  | blue top-973 pcs 5 clr rub ,,blue aop btm-973 pcs no print ,,navy top-973 pcss 1 clr rub ,,navy aop bttm-973 pcs | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3892 | [11 empty] | 53 | Nov'2
BS-NMT | 48925 | 13266880 | 2175 | 500 | 2026-08-19 | 2026-09-01 | SS TS w contrast nk slve piping | TS |  |  | 2026-10-01 | 2026-10-07 | 2026-10-20 | 2026-11-05 |  |  | 2026-11-14 | 2026-11-14 | 2026-11-20 | 2026-11-23 | 2026-11-24 | [6 empty] | 2026-11-27 | 2026-11-30 |  |  | 2026-12-03 | 2026-12-07 | 2026-12-15 | 2026-12-28 | 2026-12-30 | 131 | ZA1 | Tomal | [5 empty] | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2175 | [11 empty] | 53 | Nov'3
BS-NMT | 48916 | 13254997 | 5223 | 1361 | 2026-08-19 | 2026-09-01 | Swt short pant w side pkt drawsring | Shorts |  |  | 2026-10-01 | 2026-10-08 | 2026-10-13 | 2026-10-30 |  |  | 2026-11-14 | 2026-11-14 | 2026-11-21 | 2026-11-24 | 2026-11-27 | [6 empty] | 2026-12-01 | 2026-12-05 |  |  | 2026-12-08 | 2026-12-10 | 2026-12-15 | 2026-12-28 | 2026-12-30 | 131 | X | Tomal | [5 empty] | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -5223 | [11 empty] | 53 | Nov'3
BS-NMT | 48924 | 13266839 | 3810 | 632 | 2026-08-19 | 2026-09-01 | SS Shirt and Swt shorts w contrast piping | Top & BTM |  |  | 2026-10-01 | 2026-10-07 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-14 | 2026-11-14 | 2026-11-21 | 2026-11-24 | 2026-11-27 | [6 empty] | 2026-12-01 | 2026-12-04 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-14 | 2026-12-28 | 2026-12-30 | 131 | S+U | Tomal | [5 empty] | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3810 | [11 empty] | 53 | Nov'3
BS-NMT | 48915 | 13261974 | 5040 | 685 | 2026-08-19 | 2026-09-01 | SS o nk TS w nk rib | TS |  |  | 2026-09-25 | 2026-09-30 | 2026-10-13 | 2026-10-30 |  |  | 2026-11-07 | 2026-11-07 | 2026-11-14 | 2026-11-17 | 2026-11-20 | 2026-11-21 | 2026-11-27 |  |  |  |  | 2026-12-01 | 2026-12-04 |  |  | 2026-12-07 | 2026-12-10 | 2026-12-14 | 2026-12-28 | 2026-12-30 | 131 | W2 | Tomal | Chest |  | turtle-1215 pcs,,pink-1290 pcs,,white-1590 pcs,,navy-945 pcs all combo 3 clr photo print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -5040 | [11 empty] | 53 | Nov'2
BS-NMT | 48807 | 13266190 | 3975 | 384 | 2026-08-19 | 2026-09-02 | LS body w bk nk btn and btm snap btn | Body |  |  | 2026-09-22 | 2026-09-30 | 2026-10-08 | 2026-10-24 |  |  | 2026-10-28 | 2026-10-28 | 2026-11-05 | 2026-11-07 | 2026-11-12 | 2026-11-11 | 2026-11-14 |  |  |  |  | 2026-11-17 | 2026-11-21 |  |  | 2026-11-24 | 2026-11-26 | 2026-11-30 | 2026-12-21 | 2026-12-23 | 124 | T2 | Mosaddik | Nk |  | 3 combo label print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3975 | [11 empty] | 52 | Nov'1
BS-NMT | 48810 | 13266195 | 6103 | 563 | 2026-08-19 | 2026-09-02 | AOP SS cut&sew dress | Dress |  |  | 2026-09-15 | 2026-09-21 | 2026-10-03 | 2026-10-17 | 2026-10-20 | 2026-10-29 | 2026-11-03 | 2026-11-03 | 2026-11-09 | 2026-11-11 | 2026-11-14 | 2026-11-14 | 2026-11-18 |  |  |  |  | 2026-11-20 | 2026-11-26 |  |  | 2026-11-28 | 2026-11-30 | 2026-12-05 | 2026-12-19 | 2026-12-21 | 122 | T2 | Mosaddik | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -6103 | [11 empty] | 52 | Nov'2
BS-NMT | 48809 | 13266194 | 3094 | 311 | 2026-08-19 | 2026-09-02 | Swt pant w waist hem rib | Pant |  |  | 2026-10-01 | 2026-10-05 | 2026-10-12 | 2026-10-30 |  |  | 2026-11-05 | 2026-11-05 | 2026-11-11 | 2026-11-14 | 2026-11-17 |  |  |  |  | 2026-11-18 | 2026-11-23 | 2026-11-26 | 2026-11-30 |  |  | 2026-12-03 | 2026-12-05 | 2026-12-10 | 2026-12-21 | 2026-12-23 | 124 | Z | Mosaddik |  | Leg | pink-2262 pcs,,peyote-832 pcs both combo both leg 2 clr chian stich and 1 clr crochet flower attach emb |  | emb sub plan | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3094 | [11 empty] | 52 | Nov'2
BS-NMT | 48800 | 13215724 | 3916 | 361 | 2026-08-19 | 2026-09-02 | Swt shorts w side pkt drawstring | Shorts |  |  | 2026-10-01 | 2026-10-05 | 2026-10-12 | 2026-10-30 |  |  | 2026-11-06 | 2026-11-06 | 2026-11-13 | 2026-11-16 | 2026-11-18 | [6 empty] | 2026-11-20 | 2026-11-25 |  |  | 2026-11-27 | 2026-11-30 | 2026-12-06 | 2026-12-19 | 2026-12-21 | 122 | U | Mosaddik | [5 empty] | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3916 | [11 empty] | 52 | Nov'2
BS-NMT | 48803 | 13266119 | 4334 | 228 | 2026-08-19 | 2026-09-02 | AOP Swt shorts w drawstring | Shorts |  |  | 2026-10-01 | 2026-10-05 | 2026-10-08 | 2026-10-21 | 2026-10-23 | 2026-10-30 | 2026-11-06 | 2026-11-06 | 2026-11-12 | 2026-11-14 | 2026-11-16 | 2026-11-18 | 2026-11-20 |  |  |  |  | 2026-11-23 | 2026-11-28 |  |  | 2026-12-03 | 2026-12-06 | 2026-12-18 | 2026-12-19 | 2026-12-21 | 122 | U | Mosaddik | Waist |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -4334 | [11 empty] | 52 | Nov'2
BS-NMT | 48811 | 13266196 | 4753 | 246 | 2026-08-19 | 2026-09-02 | AOP Swt shorts w drawstring w btm letus | Shorts |  |  | 2026-09-18 | 2026-09-25 | 2026-10-01 | 2026-10-14 | 2026-10-17 | 2026-10-24 | 2026-10-28 | 2026-10-28 | 2026-11-04 | 2026-11-06 | 2026-11-09 | 2026-11-09 | 2026-11-12 |  |  |  |  | 2026-11-14 | 2026-11-20 |  |  | 2026-11-23 | 2026-11-25 | 2026-11-30 | 2026-12-19 | 2026-12-21 | 122 | X | Mosaddik | Waist |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -4753 | [11 empty] | 52 | Nov'1
BS-NMT | 48801 | 13254689 | 1146 | 136 | 2026-08-19 | 2026-09-02 | Swt pant w waist hem rib and cargo pkt and drawstring | Pant |  |  | 2026-10-01 | 2026-10-06 | 2026-10-13 | 2026-10-30 |  |  | 2026-11-07 | 2026-11-07 | 2026-11-14 | 2026-11-18 | 2026-11-20 | [6 empty] | 2026-11-24 | 2026-11-26 |  |  | 2026-11-28 | 2026-11-30 | 2026-12-06 | 2026-12-21 | 2026-12-23 | 124 | X | Mosaddik | [5 empty] | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1146 | [11 empty] | 52 | Nov'2
BS-NMT | 48806 | 13266178 | 2296 | 180 | 2026-08-19 | 2026-09-02 | SS o nk TS w shlder snap btn | TS |  |  | 2026-09-22 | 2026-09-28 | 2026-10-08 | 2026-10-25 |  |  | 2026-10-28 | 2026-10-28 | 2026-11-07 | 2026-11-10 | 2026-11-13 | 2026-11-14 | 2026-11-17 |  |  | 2026-11-13 | 2026-11-20 | 2026-11-23 | 2026-11-26 |  |  | 2026-11-28 | 2026-11-30 | 2026-12-06 | 2026-12-21 | 2026-12-23 | 124 | T1 | Mosaddik | Nk | Chest | c.dan-1028 pcs,,pink-1268 pcs both combo 1 clr chiffon fab applique emb |  | emb sub plan | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2296 | [11 empty] | 52 | Nov'1
BS-NMT | 48804 | 13266120 | 2200 | 171 | 2026-08-19 | 2026-09-02 | AOP SS o nk TS w shlder snap btn | TS |  |  | 2026-10-04 | 2026-10-08 | 2026-10-12 | 2026-10-26 | 2026-11-02 | 2026-11-07 | 2026-11-09 | 2026-11-09 | 2026-11-14 | 2026-11-17 | 2026-11-18 | 2026-11-20 | 2026-11-23 |  |  |  |  | 2026-11-26 | 2026-11-30 |  |  | 2026-12-03 | 2026-12-07 | 2026-12-10 | 2026-12-21 | 2026-12-23 | 124 | T1 | Mosaddik | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2200 | [11 empty] | 52 | Nov'2
BS-NMT | 48802 | 13266099 | 812 | 108 | 2026-08-19 | 2026-09-02 | LS SWt shirt w cuff btm rib slder snap btn | Swt Shirt |  |  | 2026-10-05 | 2026-10-10 | 2026-10-17 | 2026-10-30 |  |  | 2026-11-07 | 2026-11-07 | 2026-11-14 | 2026-11-17 | 2026-11-18 |  |  |  |  | 2026-11-20 | 2026-11-27 | 2026-12-01 | 2026-12-02 |  |  | 2026-12-04 | 2026-12-07 | 2026-12-10 | 2026-12-21 | 2026-12-23 | 124 | T2 | Mosaddik |  | Front,Slv | peyote-812 pcs chest both slve 1 clr flat 2 clr terry all over emb |  | emb sub plan | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -812 | [11 empty] | 52 | Nov'2
BS-NMT | 48808 | 13266193 | 4119 | 688 | 2026-08-19 | 2026-09-02 | LS SWt shirt w cuff btm rib slder snap btn | Swt Shirt |  |  | 2026-10-01 | 2026-10-05 | 2026-10-13 | 2026-10-28 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-09 | 2026-11-12 | 2026-11-16 |  |  |  |  | 2026-11-16 | 2026-11-27 | 2026-12-01 | 2026-12-04 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-12 | 2026-12-21 | 2026-12-23 | 124 | T2 | Mosaddik |  | Front,Slv | pink-2842 pcs,,peyote-1277 pcs both combo frt both slve 2 clr chian stich and 1 clr crochet flower attach all over emb |  | emb sub plan | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -4119 | [11 empty] | 52 | Nov'2
BS-NMT | 48805 | 13266121 | 3086 | 334 | 2026-08-19 | 2026-09-02 | Aop overall w wood btn and btm snap btn | Overall |  |  | 2026-09-26 | 2026-09-30 | 2026-10-07 | 2026-10-20 | 2026-10-23 | 2026-10-31 | 2026-11-04 | 2026-11-04 | 2026-11-09 | 2026-11-12 | 2026-11-14 | 2026-11-16 | 2026-11-18 |  |  |  |  | 2026-11-20 | 2026-11-26 |  |  | 2026-11-28 | 2026-11-30 | 2026-12-05 | 2026-12-19 | 2026-12-21 | 122 | S | Mosaddik | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3086 | [11 empty] | 52 | Nov'2
BS-NMT | 48812 | 13266197 | 1966 | 98 | 2026-08-19 | 2026-09-02 | AOP Legging | Legging |  |  | 2026-09-24 | 2026-09-27 | 2026-10-05 | 2026-10-18 | 2026-10-22 | 2026-10-27 | 2026-10-30 | 2026-10-30 | 2026-11-05 | 2026-11-07 | 2026-11-07 | 2026-11-11 | 2026-11-12 |  |  |  |  | 2026-11-14 | 2026-11-16 |  |  | 2026-11-18 | 2026-11-21 | 2026-11-25 | 2026-12-21 | 2026-12-23 | 124 | W2 | Mosaddik | Waist |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1966 | [11 empty] | 52 | Nov'1
BS-NMT | 48942 | 13267469 | 2966 | 433 | 2026-08-19 | 2026-09-01 | SS o nk TS w nk rib | TS |  |  | 2026-10-01 | 2026-10-05 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-07 | 2026-11-07 | 2026-11-14 | 2026-11-17 | 2026-11-19 | 2026-11-21 | 2026-11-27 |  |  |  |  | 2026-12-01 | 2026-12-03 |  |  | 2026-12-07 | 2026-12-10 | 2026-12-15 | 2026-12-28 | 2026-12-30 | 131 | Z | Jafar | Chest,Nk |  | Navy-2966 pcs 8 clr rub 1 clr gltr |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2966 | [11 empty] | 53 | Nov'2
BS-NMT | 45590 3rd | 13241260 | 12771 | 3366 | 2026-08-19 | 2026-09-01 | Shorts pant w adj waist belt pocket drawstring gmts dye acid wash | Shorts |  |  | 2026-09-18 | 2026-09-30 | 2026-10-10 | 2026-10-25 |  |  | 2026-10-25 | 2026-10-25 | 2026-11-07 | 2026-11-12 | 2026-11-17 | 2026-12-02 | 2026-12-08 |  |  |  |  | 2026-11-16 | 2026-11-26 | 2026-11-24 | 2026-12-05 | 2026-12-11 | 2026-12-15 | 2026-12-18 | 2026-12-28 | 2026-12-30 | 131 | X | Jafar | Thigh |  | blue-3498 pcs,,black-3514 pcs,,green-5759 pcs all combo 2 clr HD print |  | Gmts dye acid wash | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -12771 | [11 empty] | 53 | Nov'2
BS-NMT | 45579 5th | 13218694 | 12350 | 2717 | 2026-08-19 | 2026-09-01 | SS YD Dress w waist elastic | Dress | 2026-09-17 | 2026-09-27 | 2026-10-01 | 2026-10-18 | 2026-10-23 | 2026-11-05 |  |  | 2026-11-10 | 2026-11-10 | 2026-11-17 | 2026-11-20 | 2026-11-26 | 2026-11-25 | 2026-11-30 |  |  |  |  | 2026-12-01 | 2026-12-09 |  |  | 2026-12-11 | 2026-12-14 | 2026-12-22 | 2026-12-26 | 2026-12-28 | 129 | V | Jafar | Nk |  | 3 combo label print | YD |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -12350 | [11 empty] | 53 | Nov'2
BS-NMT | 48936 | 13259417 | 6952 | 927 | 2026-08-19 | 2026-09-01 | SS boat nk wrap shlder TS w side seam gathering | TS |  |  | 2026-10-01 | 2026-10-06 | 2026-10-13 | 2026-10-30 |  |  | 2026-11-12 | 2026-11-12 | 2026-11-17 | 2026-11-20 | 2026-11-24 | 2026-11-25 | 2026-11-28 |  |  |  |  | 2026-12-03 | 2026-12-08 |  |  | 2026-12-10 | 2026-12-14 | 2026-12-18 | 2026-12-28 | 2026-12-30 | 131 | Z | Jafar | Nk |  | 3 combo label print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -6952 | [11 empty] | 53 | Nov'2
BS-NMT | 42039 2nd | 13219340 | 1266 | 160 | 2026-08-19 | 2026-09-01 | Elasted Legging | Legging |  |  | 2026-10-02 | 2026-10-06 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-07 | 2026-11-07 | 2026-11-14 | 2026-11-18 | 2026-01-18 | 2026-11-23 | 2026-11-23 |  |  |  |  | 2026-11-26 | 2026-11-27 |  |  | 2026-11-30 | 2026-12-04 | 2026-12-12 | 2026-12-28 | 2026-12-30 | 131 | W2 | Jafar | Waist |  | 2 combo label print |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1266 | [11 empty] | 53 | Nov'2
BS-NMT | 48933 | 13233848 | 4390 | 662 | 2026-08-19 | 2026-09-01 | SS TS w btm knot | TS |  |  | 2026-10-01 | 2026-10-06 | 2026-10-13 | 2026-10-30 |  |  | 2026-11-10 | 2026-11-10 | 2026-11-16 | 2026-11-19 | 2026-11-21 | 2026-11-24 | 2026-11-28 |  |  |  |  | 2026-12-04 | 2026-12-09 |  |  | 2026-12-11 | 2026-12-15 | 2026-12-18 | 2026-12-28 | 2026-12-30 | 131 | Z | Jafar | Nk |  | 2 combo label print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -4390 | [11 empty] | 53 | Nov'2
BS-NMT | 48937 | 13265705 | 3994 | 310 | 2026-08-19 | 2026-09-01 | SS O nk Body w btm snap btn | Body |  |  | 2026-09-20 | 2026-09-25 | 2026-10-08 | 2026-10-20 |  |  | 2026-10-27 | 2026-10-27 | 2026-11-04 | 2026-11-06 | 2026-11-10 | 2026-11-12 | 2026-11-16 |  |  | 2026-11-10 | 2026-11-21 | 2026-11-24 | 2026-11-28 |  |  | 2026-12-03 | 2026-12-05 | 2026-12-10 | 2026-12-20 | 2026-12-22 | 123 | Y | Jafar | Nk | Chest | fairy-3994 pcs 1 clr flat all over emb at chest |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3994 | [11 empty] | 52 | Nov'1
BS-NMT | 48938 | 13265708 | 3813 | 318 | 2026-08-19 | 2026-09-01 | SS O nk Body w btm snap btn | Body |  |  | 2026-09-25 | 2026-09-30 | 2026-10-10 | 2026-10-24 |  |  | 2026-10-27 | 2026-10-27 | 2026-11-07 | 2026-11-10 | 2026-11-13 | 2026-11-16 | 2026-11-19 |  |  | 2026-11-13 | 2026-11-24 | 2026-11-26 | 2026-11-30 |  |  | 2026-12-03 | 2026-12-05 | 2026-12-10 | 2026-12-21 | 2026-12-23 | 124 | Y | Jafar | Nk | Chest | blue-2718 pcs,,crockery-1095 pcs both combo 1 clr flat all over emb at chest |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3813 | [11 empty] | 52 | Nov'1
BS-NMT | 48943 | 13268448 | 8078 | 1289 | 2026-08-19 | 2026-09-01 | YD and Solid SS o nk TS | TS | 2026-09-23 | 2026-10-02 | 2026-10-05 | 2026-10-20 | 2026-10-25 | 2026-11-05 |  |  | 2026-11-12 | 2026-11-12 | 2026-11-18 | 2026-11-21 | 2026-11-26 | 2026-11-26 | 2026-12-04 |  |  |  |  | 2026-12-07 | 2026-12-12 |  |  | 2026-12-14 | 2026-12-17 | 2026-12-19 | 2026-12-28 | 2026-12-30 | 131 | Z | Jafar | Nk |  | 4 combo label print | YD |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -8078 | [11 empty] | 53 | Nov'3
BS-NMT | 45587 2nd | 13240425 | 2256 | 274 | 2026-08-19 | 2026-09-01 | SS o nk TS | TS |  |  | 2026-10-03 | 2026-10-09 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-13 | 2026-11-13 | 2026-11-19 | 2026-11-23 | 2026-11-24 | 2026-11-26 | 2026-11-28 |  |  |  |  | 2026-12-04 | 2026-12-05 |  |  | 2026-12-08 | 2026-12-10 | 2026-12-13 | 2026-12-28 | 2026-12-30 | 131 | W2 | Jafar | Nk |  | 2 combo label print |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -2256 | [11 empty] | 53 | Nov'3
BS-NMT | 45596 2nd | 13258062 | 6440 | 1461 | 2026-08-19 | 2026-09-01 | Long Tank top dress w side slit | Dress |  |  | 2026-10-01 | 2026-10-08 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-12 | 2026-11-12 | 2026-11-17 | 2026-11-20 | 2026-11-24 | 2026-11-26 | 2026-11-30 |  |  |  |  | 2026-12-04 | 2026-12-08 |  |  | 2026-12-10 | 2026-12-12 | 2026-12-15 | 2026-12-28 | 2026-12-30 | 131 | V | Jafar | Nk |  | 2 combo label print |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -6440 | [11 empty] | 53 | Nov'2
BS-NMT | 48918 | 13266070 | 3594 | 1003 | 2026-08-19 | 2026-09-01 | SS o nk TS w nk Rib | TS |  |  | 2026-09-25 | 2026-10-08 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-11 | 2026-11-11 | 2026-11-17 | 2026-11-20 | 2026-11-23 | 2026-11-25 | 2026-11-28 |  |  |  |  | 2026-12-02 | 2026-12-04 |  |  | 2026-12-08 | 2026-12-10 | 2026-12-15 | 2026-12-28 | 2026-12-30 | 131 | W2 | Tomal | Chest,Nk |  | blue-2122 pcs,,green-1472 pcs both combo 1 clr molding HD print |  | Need Sub plan | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3594 | [11 empty] | 53 | Nov'2
BS-NMT | 48917 | 13266055 | 2713 | 430 | 2026-08-19 | 2026-09-01 | SS o nk TS w nk Rib | TS |  |  | 2026-10-01 | 2026-10-05 | 2026-10-13 | 2026-10-30 |  |  | 2026-11-05 | 2026-11-05 | 2026-01-11 | 2026-11-13 | 2026-11-14 | 2026-11-17 | 2026-11-21 |  |  |  |  | 2026-11-25 | 2026-11-27 |  |  | 2026-11-30 | 2026-12-03 | 2026-12-10 | 2026-12-28 | 2026-12-30 | 131 | ZA1 | Tomal | Chest,Nk |  | c.dan-1369 pcs,,popcorn-1344 pcs both combo chest photo print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2713 | [11 empty] | 53 | Nov'2
BS-NMT | 48922 | 13266240 | 938 | 223 | 2026-08-19 | 2026-09-01 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-10-01 | 2026-10-05 | 2026-10-13 | 2026-10-28 |  |  | 2026-11-04 | 2026-11-04 | 2026-11-10 | 2026-11-12 | 2026-11-13 | 2026-11-16 | 2026-11-24 |  |  |  |  | 2026-11-27 | 2026-11-28 |  |  | 2026-12-03 | 2026-12-07 | 2026-12-12 | 2026-12-21 | 2026-12-23 | 124 | T2 | Tomal | Fr & Bk & Slv |  | green-938 pcs frt back both slve 3 clr rub 1 clr puff all over placement print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -938 | [11 empty] | 52 | Nov'2
BS-NMT | 48921 | 13266088 | 3999 | 400 | 2026-08-19 | 2026-09-01 | SS o nk TS w nk Rib | TS |  |  | 2026-09-15 | 2026-09-20 | 2026-10-05 | 2026-10-20 |  |  | 2026-10-22 | 2026-10-22 | 2026-10-28 | 2026-10-30 | 2026-10-31 | 2026-11-02 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-12 | 2026-11-14 | 2026-11-18 |  |  | 2026-11-20 | 2026-11-23 | 2026-11-30 | 2026-12-21 | 2026-12-23 | 124 | ZA1 | Tomal | Chest,Nk | Chest | green-1852 pcs plastisol photo print w 1 clr flock 1 clr tooth brush print no emb ,,popcorn-2147 pcs photo print and woven plap patch attach emb |  | need sub plan | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3999 | [11 empty] | 52 | Oct'3
BS-NMT | 48920 | 13266072 | 5409 | 1316 | 2026-08-19 | 2026-09-01 | Waist belt swt shorts w side pkt | Shorts |  |  | 2026-09-25 | 2026-10-04 | 2026-10-10 | 2026-10-30 |  |  | 2026-11-06 | 2026-11-06 | 2026-11-11 | 2026-11-14 | 2026-11-17 | 2026-11-17 | 2026-11-23 |  |  |  |  | 2026-11-25 | 2026-12-02 |  |  | 2026-12-04 | 2026-12-05 | 2026-12-13 | 2026-12-28 | 2026-12-30 | 131 | X | Tomal | Thigh |  | blue-3377 pcs,,green-2032 pcs both combo 1 clr molding HD print |  | need sub plan | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -5409 | [11 empty] | 53 | Nov'2
BS-NMT | 48919 | 13266071 | 3937 | 1429 | 2026-08-19 | 2026-09-01 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-09-22 | 2026-09-30 | 2026-10-10 | 2026-10-30 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-09 | 2026-11-12 | 2026-11-16 | 2026-11-16 | 2026-11-21 |  |  |  |  | 2026-11-24 | 2026-11-30 |  |  | 2026-12-04 | 2026-12-08 | 2026-12-14 | 2026-12-28 | 2026-12-30 | 131 | T2 | Tomal | Chest |  | blue-2581 pcs,,green-1356 pcs both combo 1 clr molding HD print |  | need sub plan | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3937 | [11 empty] | 53 | Nov'2
BS-NMT | 48923 | 13266243 | 810 | 157 | 2026-08-19 | 2026-09-01 | Swt Pant w waist belt and leg elastic | Pant |  |  | 2026-10-01 | 2026-10-05 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-06 | 2026-11-06 | 2026-11-13 | 2026-11-16 | 2026-11-17 | 2026-11-19 | 2026-11-24 |  |  |  |  | 2026-11-27 | 2026-11-30 |  |  | 2026-12-03 | 2026-12-05 | 2026-12-12 | 2026-12-21 | 2026-12-23 | 124 | X | Tomal | leg |  | green-810 pcs both leg 4 part 3 clr rub 1 clr puff all over print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -810 | [11 empty] | 52 | Nov'2
BS-NMT | 48885 | 13266251 | 10857 | 1097 | 2026-08-19 | 2026-09-02 | SS Puff slve o nk TS | TS |  |  | 2026-09-23 | 2026-09-29 | 2026-10-07 | 2026-10-24 |  |  | 2026-10-27 | 2026-10-27 | 2026-11-05 | 2026-11-07 | 2026-11-10 | 2026-11-12 | 2026-11-16 |  |  | 2026-11-10 | 2026-11-18 | 2026-11-19 | 2026-11-27 |  |  | 2026-11-29 | 2026-11-30 | 2026-12-05 | 2026-12-21 | 2026-12-23 | 124 | Z | Haider | Chest,Nk | Chest | c.dan-6430 pcs 1 clr flat 2 clr chian stitch emb no print ,,hibiscus-4427 pcs1 clr rub print 1 clr crochret flower attach emb |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -10857 | [11 empty] | 52 | Nov'1
BS-NMT | 48886 | 13266639 | 1564 | 147 | 2026-08-19 | 2026-09-02 | SS o nk TS | TS |  |  | 2026-10-01 | 2026-10-04 | 2026-10-10 | 2026-10-27 |  |  | 2026-11-04 | 2026-11-04 | 2026-11-11 | 2026-11-14 | 2026-11-16 | 2026-11-18 | 2026-11-20 |  |  | 2026-11-18 | 2026-11-25 | 2026-12-01 | 2026-12-02 |  |  | 2026-12-04 | 2026-12-07 | 2026-12-10 | 2026-12-21 | 2026-12-23 | 124 | T1 | Haider | Chest,Nk | Chest | c.dan-782 pcs 2 clr pig and 1 clr tapping emb ,,pink-782 pcs 2 clr pig print andd 2 clr tapping emb |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1564 | [11 empty] | 52 | Nov'2
BS-NMT | 48887 | 13266259 | 2452 | 228 | 2026-08-19 | 2026-09-02 | SS o nk TS | TS |  |  | 2026-10-01 | 2026-10-04 | 2026-10-12 | 2026-10-28 |  |  | 2026-11-04 | 2026-11-04 | 2026-11-10 | 2026-11-12 | 2026-11-14 | 2026-11-16 | 2026-11-21 |  |  | 2026-11-24 | 2026-11-27 | 2026-12-01 | 2026-12-03 |  |  | 2026-12-05 | 2026-12-08 | 2026-12-12 | 2026-12-19 | 2026-12-21 | 122 | T1 | Haider | Chest,Nk | Chest | pink-814 pcs 5 clr pig and 3 clr crochet patch attach emb ,,icy pink-824 pcs 4 clr rub 1 clr puff and silver lurex patch attach,,iris-814 pcs 4 clr rub and 2 clr flat 4 clr sequin emb |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -2452 | [11 empty] | 52 | Nov'2
BS-NMT | 48888 | 13266264 | 3004 | 233 | 2026-08-19 | 2026-09-02 | AOP Shorts w side pkt dawstring | Shorts |  |  | 2026-09-23 | 2026-09-28 | 2026-10-08 | 2026-10-24 | 2026-10-27 | 2026-11-05 | 2026-11-13 | 2026-11-13 | 2026-11-19 | 2026-11-21 | 2026-11-24 | 2026-11-25 | 2026-11-27 |  |  |  |  | 2026-12-01 | 2026-12-03 |  |  | 2026-12-05 | 2026-12-08 | 2026-12-11 | 2026-12-19 | 2026-12-21 | 122 | U | Haider | Waist |  | 2 combo label print | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3004 | [11 empty] | 52 | Nov'3
BS-NMT | 48889 | 13266262 | 6463 | 1179 | 2026-08-19 | 2026-09-02 | AOP Srap dress w cut&sew smock | Dress |  |  | 2026-09-24 | 2026-09-30 | 2026-10-10 | 2026-10-24 | 2026-10-27 | 2026-11-06 | 2026-11-11 | 2026-11-11 | 2026-11-17 | 2026-11-26 | 2026-11-30 | 2026-11-19 | 2026-11-25 |  |  |  |  | 2026-12-01 | 2026-12-04 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-12 | 2026-12-21 | 2026-12-23 | 124 | V | Haider |  |  | Smock | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -6463 | [11 empty] | 52 | Nov'3
BS-NMT | 48890 | 13266261 | 840 | 105 | 2026-08-19 | 2026-09-02 | AOP Srap dress w cut&sew smock | Dress |  |  | 2026-10-01 | 2026-10-05 | 2026-10-13 | 2026-10-25 | 2026-11-02 | 2026-11-07 | 2026-11-12 | 2026-11-12 | 2026-11-19 | 2026-11-26 | 2026-11-28 | 2026-11-21 | 2026-11-23 |  |  |  |  | 2026-12-01 | 2026-12-02 |  |  | 2026-12-04 | 2026-12-07 | 2026-12-10 | 2026-12-21 | 2026-12-23 | 124 | V | Haider |  |  | Smock | AOP |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -840 | [11 empty] | 52 | Nov'3
BS-NMT | 48891 | 13268941 | 1606 | 161 | 2026-08-19 | 2026-09-02 | SS Puff slve o nk TS | TS |  |  | 2026-10-01 | 2026-10-06 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-05 | 2026-11-05 | 2026-11-11 | 2026-11-13 | 2026-11-14 | 2026-11-17 | 2026-11-21 |  |  |  |  | 2026-11-25 | 2026-11-27 |  |  | 2026-11-30 | 2026-12-03 | 2026-12-07 | 2026-12-21 | 2026-12-23 | 124 | Z | Haider | Chest,Nk |  | white-803 pcs 3 clr rub digital print ,,pink-803 pcs 5 clr rub digital print |  | Print sub plan | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1606 | [11 empty] | 52 | Nov'2
BS-NMT | 48892 | 13266257 | 3635 | 335 | 2026-08-19 | 2026-09-02 | SS Puff slve o nk TS | TS |  |  | 2026-10-01 | 2026-10-05 | 2026-10-10 | 2026-10-27 |  |  | 2026-11-04 | 2026-11-04 | 2026-11-09 | 2026-11-12 | 2026-11-14 | 2026-11-16 | 2026-11-20 |  |  |  |  | 2026-11-23 | 2026-11-26 |  |  | 2026-11-28 | 2026-12-02 | 2026-12-06 | 2026-12-21 | 2026-12-23 | 124 | Z | Haider | Chest,Nk |  | white-1490 pcs 3 clr rub digital print ,,pink-2145 pcs 5 clr rub digital print |  | Print sub plan | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3635 | [11 empty] | 52 | Nov'2
BS-NMT | 48893 | 13266260 | 5695 | 603 | 2026-08-19 | 2026-09-02 | Tank Top | Tank Top |  |  | 2026-10-01 | 2026-10-05 | 2026-10-10 | 2026-10-24 |  |  | 2026-10-28 | 2026-10-28 | 2026-11-05 | 2026-11-07 | 2026-11-10 | 2026-11-11 | 2026-11-13 |  |  | 2026-11-11 | 2026-11-14 | 2026-11-18 | 2026-11-21 |  |  | 2026-11-24 | 2026-11-27 | 2026-12-05 | 2026-12-19 | 2026-12-21 | 122 | ZA2 | Haider | Nk | Chest | pink-1966 pvcs 3 clr flat emb ,,iris-1766 pcs 4 clr flat emb ,,violet-1963 pcs 1 clr flat emb |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -5695 | [11 empty] | 52 | Nov'1
BS-NMT | 48894 | 13266701 | 1853 | 382 | 2026-08-19 | 2026-09-02 | LS Cardigan w fill placket btn and Lace Attach at nk placket | Cardigan |  |  | 2026-10-02 | 2026-10-10 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-13 | 2026-11-13 | 2026-11-20 | 2026-11-24 | 2026-11-27 | 2026-11-27 | 2026-11-30 |  |  |  |  | 2026-12-04 | 2026-12-07 |  |  | 2026-12-09 | 2026-12-12 | 2026-12-15 | 2026-12-28 | 2026-12-30 | 131 | S | Haider | Nk |  | 2 combo label print |  | Lace | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1853 | [11 empty] | 53 | Nov'3
BS-NMT | 48895 | 13266698 | 810 | 99 | 2026-08-19 | 2026-09-02 | SS o nk TS | TS |  |  | 2026-10-04 | 2026-10-07 | 2026-10-18 | 2026-10-30 |  |  | 2026-11-10 | 2026-11-10 | 2026-11-17 | 2026-11-19 | 2026-11-19 | 2026-11-23 | 2026-11-23 |  |  | 2026-11-23 | 2026-11-27 | 2026-12-02 | 2026-12-03 |  |  | 2026-12-04 | 2026-12-08 | 2026-12-14 | 2026-12-26 | 2026-12-28 | 129 | T1 | Haider | Nk | Chest | blue-810 pcs 1 clr seq emb |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -810 | [11 empty] | 53 | Nov'2
BS-NMT | 48896 | 13265889 | 3472 | 517 | 2026-08-19 | 2026-09-02 | SS o nk TS | TS |  |  | 2026-10-01 | 2026-10-05 | 2026-10-12 | 2026-10-28 |  |  | 2026-11-05 | 2026-11-05 | 2026-11-10 | 2026-11-12 | 2026-11-14 | 2026-11-17 | 2026-11-23 |  |  |  |  | 2026-11-26 | 2026-11-30 |  |  | 2026-12-03 | 2026-12-05 | 2026-12-09 | 2026-12-28 | 2026-12-30 | 131 | ZA2 | Haider | Fr & Bk & Nk |  | white leo-1950 pcs,,white cherry-1522 pcs bot combo frt back digital photo print |  | print sub plan | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3472 | [11 empty] | 53 | Nov'2
BS-ONS | 45691 3rd | 22028147 | 7920 | 2063 | 2026-08-26 | 2026-09-02 | SS o nk TS w nk rib | TS |  |  | 2026-09-21 | 2026-09-27 | 2026-10-05 | 2026-10-20 |  |  | 2026-10-26 | 2026-10-26 |  | 2026-11-02 | 2026-11-05 | 2026-11-04 | 2026-11-09 |  |  |  |  | 2026-11-12 | 2026-11-16 |  |  | 2026-11-18 | 2026-11-20 | 2026-11-24 | 2026-12-07 | 2026-12-09 | 103 | F | Shovon | Heat Press/Heat Seal |  | green-1584 pcs,,white-1584 pcs,,LGM-1584 pcs,,coffee-1584 pcs,,black-1584 pcs all combo logo print heat press |  |  | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -7920 | [11 empty] | 50 | Nov'1
BS-ONS | 45957 2nd | 22029454 | 2099 | 457 | 2026-08-26 | 2026-09-03 | SS o nk TS | TS |  |  | 2026-10-01 | 2026-10-05 | 2026-10-10 | 2026-10-24 |  |  | 2026-10-27 | 2026-10-27 | 2026-11-03 | 2026-11-05 | 2026-11-06 | 2026-11-09 | 2026-11-12 |  |  |  |  | 2026-11-14 | 2026-11-16 |  |  | 2026-11-18 | 2026-11-20 | 2026-11-23 | 2026-12-07 | 2026-12-09 | 103 | F | Shovon | Chest |  | c.dan-1110 pcs,,white-989 pcs pcs all combo photo print |  |  | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -2099 | [11 empty] | 50 | Nov'1
BS-ONS | 48948 | 22042370 | 5624 | 1151 | 2026-08-26 | 2026-09-03 | SS o nk TS | TS |  |  | 2026-09-22 | 2026-09-30 | 2026-10-06 | 2026-10-23 |  |  | 2026-10-26 | 2026-10-26 | 2026-11-02 | 2026-11-05 | 2026-11-09 | 2026-11-09 | 2026-11-12 |  |  |  |  | 2026-11-16 | 2026-11-19 |  |  | 2026-11-21 | 2026-11-23 | 2026-11-25 | 2026-12-07 | 2026-12-09 | 103 | F | Shovon | Chest |  | coral-1331 pcs,,yellow-1331 pcs..green-1631 pcs,,mint-1331 pcs all combo 1 clr rub print |  |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -5624 | [11 empty] | 50 | Nov'1
BS-ONS | 48945 | 22042339 | 1020 | 261 | 2026-08-25 | 2026-08-31 | SS o nk TS w nk and slve contrast binding | TS |  |  | 2026-10-01 | 2026-10-05 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-07 | 2026-11-07 | 2026-11-14 | 2026-11-18 | 2026-11-19 | [6 empty] | 2026-11-23 | 2026-11-24 |  |  | 2026-11-26 | 2026-11-28 | 2026-12-03 | 2026-12-21 | 2026-12-23 | 118 | F | Shovon | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -1020 | [11 empty] | 52 | Nov'2
BS-ONL | 45983 2nd | 15381855 | 10080 | 1891 | 2026-08-27 | 2026-08-31 | Tank Top | TANK TOP | 2026-10-07: 2026-10-05; 2026-10-17: 2026-10-25 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-09 | 2026-11-12 | 2026-11-16 | [6 empty] | 2026-11-16 | 2026-11-28 |  |  | 2026-11-30 | 2026-12-03 | 2026-12-05 | 2026-12-14 | 2026-12-16 | 109 | R | Imran |  |  |  |  | stock fab from 42888 14th | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -10080 | [11 empty] | 51 | Nov'2
BS-ONL | 48700 | 15396196 | 372 | 90 | 2026-08-12 | 2026-08-31 | YD SS V nk TS w frt nk elastic gathering | TS | 2026-10-01 | 2026-10-05 | 2026-10-10 | 2026-10-14 | 2026-10-17 | 2026-10-22 |  |  | 2026-10-28 | 2026-10-28 | 2026-11-06 | 2026-11-09 | 2026-11-09 | [6 empty] | 2026-11-12 | 2026-11-12 |  |  | 2026-11-14 | 2026-11-17 | 2026-11-20 | 2026-12-14 | 2026-12-16 | 124 | M | Zahirul |  |  |  | YD |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -372 | [11 empty] | 51 | Nov'1
BS-ONL | 48645 | 15396142 | 2232 | 496 | 2026-08-12 | 2026-09-01 | SS o nk TS w stone hand sew metal buckle and bow attach at front | TS |  |  | 2026-10-01 | 2026-10-05 | 2026-10-12 | 2026-10-28 |  |  | 2026-11-03 | 2026-11-03 | 2026-11-09 | 2026-11-11 | 2026-11-12 | 2026-11-14 | 2026-11-16 | 2026-11-18 | 2026-11-21 | 2026-12-01 | 2026-12-05 | 2026-11-25 | 2026-11-28 |  |  | 2026-12-08 | 2026-12-10 | 2026-12-14 | 2026-12-21 | 2026-12-23 | 131 | M | Zahirul | Chest,Stone |  | c.dan-851 pcs 1 clr pig print and 1 size HP Stone and 2 metal buckle Hand sewing ,,LGM-848 pcs photo print w 2 clr gltr no stone,,pink-533 pcs photo print w 2 clr gltr and 1 mesh bow attach at sewing |  | 1 combo Hand sewing ring buckle | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -2232 | [11 empty] | 52 | Nov'2
BS-ONL | 48844 | 15389943 | 600 | 77 | 2026-08-24 | 2026-09-04 | SS o nk TS w blind hem w frt all over 5 woven bow attach | TS |  |  | 2026-10-10 | 2026-10-12 | 2026-10-23 | 2026-11-05 |  |  | 2026-11-14 | 2026-11-14 | 2026-11-21 | 2026-11-24 | 2026-11-25 | [6 empty] | 2026-11-27 | 2026-11-28 |  |  | 2026-12-02 | 2026-12-04 | 2026-12-08 | 2026-12-21 | 2026-12-23 | 119 | Q | Abid | [5 empty] | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -600 | [11 empty] | 52 | Nov'3
BS-ONL | 48854 | 15390394 | 1284 | 161 | 2026-08-24 | 2026-09-04 | Waist belt shorts w side pkt drawstring | Shorts |  |  | 2026-10-01 | 2026-10-05 | 2026-10-13 | 2026-10-30 |  |  | 2026-11-04 | 2026-11-04 | 2026-11-11 | 2026-11-14 | 2026-11-16 | 2026-11-18 | 2026-11-21 |  |  |  |  | 2026-11-24 | 2026-11-26 |  |  | 2026-11-28 | 2026-12-03 | 2026-12-08 | 2026-12-21 | 2026-12-23 | 119 | P | Abid | Thigh |  | pink-1284 pcs 3 clr pig print |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -1284 | [11 empty] | 52 | Nov'2
BS-ONL | 48858 | 15394093 | 15660 | 1984 | 2026-08-24 | 2026-09-04 | SS o nk TS w blind hem | TS |  |  | 2026-09-22 | 2026-09-30 | 2026-10-05 | 2026-10-22 |  |  | 2026-10-25 | 2026-10-25 | 2026-11-02 | 2026-11-04 | 2026-11-09 | 2026-11-07 | 2026-11-18 |  |  |  |  | 2026-11-18 | 2026-11-28 |  |  | 2026-12-03 | 2026-12-07 | 2026-12-10 | 2026-12-21 | 2026-12-23 | 119 | N2 | Abid | Fr,Bk |  | c.dan sunny-2556 pcs frt 2 clr rub 1 clr gltr back 7 clr rub 3 clr gltr ,,orchid-5064 pcs frt 2 cl rub 1 clr gltr back 4 clr rub 3 clr gltr ,,c.dan vacay- 5676 pcs frt 3 clr rub 1 clr gltr back 7 clr rub 3 clr gltr,,moonlight-2364 pcs frt 1 clr rub 1 clr gltr back 5 clr rub 3 clr gltr |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -15660 | [11 empty] | 52 | Nov'1
BS-ONL | 48852 | 15390375 | 2016 | 185 | 2026-08-24 | 2026-09-04 | AOP & solid SS o nk TS w blind hem | TS |  |  | 2026-10-01 | 2026-10-04 | 2026-10-10 | 2026-10-24 | 2026-11-02 | 2026-11-07 | 2026-11-11 | 2026-11-11 | 2026-11-17 | 2026-11-19 | 2026-11-20 | 2026-11-23 | 2026-11-27 |  |  |  |  | 2026-12-01 | 2026-12-03 |  |  | 2026-12-05 | 2026-12-08 | 2026-12-10 | 2026-12-21 | 2026-12-23 | 119 | N1 | Abid | Chest |  | c.dan-1296 pcs 4 clr rub ,,pink AOP-720 pcs no print | AOP |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -2016 | [11 empty] | 52 | Nov'2
BS-ONL | 48851 | 15390374 | 300 | 42 | 2026-08-24 | 2026-09-04 | SS o nk TS w blind hem | TS |  |  | 2026-10-07 | 2026-10-10 | 2026-10-18 | 2026-10-30 |  |  | 2026-11-11 | 2026-11-11 | 2026-11-17 | 2026-11-20 | 2026-11-20 | 2026-11-24 | 2026-11-26 |  |  |  |  | 2026-12-01 | 2026-12-02 |  |  | 2026-12-04 | 2026-12-07 | 2026-12-10 | 2026-12-21 | 2026-12-23 | 119 | N1 | Abid | Fr,Bk |  | puple-300 pcs frt 4 clr rub back 6 clr rub 1 clr HD print |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -300 | [11 empty] | 52 | Nov'2
BS-ONL | 48855 | 15390461 | 3960 | 469 | 2026-08-24 | 2026-09-04 | SL o nk TS | TS |  |  | 2026-09-25 | 2026-09-30 | 2026-10-10 | 2026-10-25 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-07 | 2026-11-10 | 2026-11-13 | 2026-11-13 | 2026-11-17 | 2026-11-17 | 2026-11-23 | 2026-11-17 | 2026-11-23 | 2026-11-25 | 2026-11-28 |  |  | 2026-11-30 | 2026-12-03 | 2026-12-08 | 2026-12-21 | 2026-12-23 | 119 | O1 | Abid | Chest,Stone | Chest | pink-1460 pcs 1 clr pig and 1 size heat press pearl attach no emb ,,c.dan-968 pcs 1 clr gltr gel and 1 clr seq emb ,,bracken-1532 pcs 1 clr foil and Heat press rinestone no emb |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -3960 | [11 empty] | 52 | Nov'1
BS-ONL | 48859 | 15394094 | 3360 | 504 | 2026-08-24 | 2026-09-04 | SS o nk TS w blind hem | TS |  |  | 2026-10-01 | 2026-10-05 | 2026-10-13 | 2026-10-30 |  |  | 2026-11-07 | 2026-11-07 | 2026-11-14 | 2026-11-17 | 2026-11-20 | 2026-11-20 | 2026-11-26 |  |  |  |  | 2026-12-01 | 2026-12-03 |  |  | 2026-12-05 | 2026-12-08 | 2026-12-10 | 2026-12-21 | 2026-12-23 | 119 | N1 | Abid | Fr,Bk |  | c.dan-1692 pcs frt 1 clr pig back 9 clr pig,,indigo-1668 pcs frt 1 clr rub back 8 clr rub |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -3360 | [11 empty] | 52 | Nov'2
BS-ONL | 48843 | 15370262 | 6564 | 886 | 2026-08-24 | 2026-09-04 | one shlder strap Tank top | Tank Top |  |  | 2026-10-07 | 2026-10-13 | 2026-10-20 | 2026-11-05 |  |  | 2026-11-12 | 2026-11-12 | 2026-11-19 | 2026-11-22 | 2026-11-25 | [6 empty] | 2026-11-26 | 31/11 |  |  | 2026-12-03 | 2026-12-05 | 2026-12-10 | 2026-12-19 | 2026-12-21 | 117 | M | Abid | [5 empty] | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -6564 | [11 empty] | 52 | Nov'3
BS-ONL | 48857 | 15390701 | 708 | 112 | 2026-08-24 | 2026-09-04 | SS o nk TS | TS |  |  | 2026-10-02 | 2026-10-05 | 2026-10-15 | 2026-10-27 |  |  | 2026-11-06 | 2026-11-06 | 2026-11-12 | 2026-11-14 | 2026-11-14 | 2026-11-18 | 2026-11-20 |  |  | 2026-11-23 | 2026-11-24 | 2026-11-27 | 2026-11-28 |  |  | 2026-11-30 | 2026-12-02 | 2026-12-08 | 2026-12-21 | 2026-12-23 | 119 | O1 | Abid | Fr,Bk | Chest | c.dancer-708 pcs frt 1 clr pig 1 clr puff back 1 clr pig 1 clr puff and 1 clr flat emb |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -708 | [11 empty] | 52 | Nov'2
BS-ONL | 48231 2nd | 15324397 | 4560 | 840 | 2026-08-24 | 2026-09-04 | SL Rib long Dress w side slit | Dress |  |  | 2026-10-01 | 2026-10-10 | 2026-10-16 | 2026-10-30 |  |  | 2026-11-05 | 2026-11-05 |  | 2026-11-10 | 2026-11-13 | [6 empty] | 2026-11-13 | 2026-11-18 |  |  | 2026-11-20 | 2026-11-24 | 2026-11-30 | 2026-12-20 | 2026-12-22 | 118 | M | Abid | [5 empty] | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -4560 | [11 empty] | 52 | Nov'1
BS-ONL | 48853 | 15390391 | 528 | 92 | 2026-08-24 | 2026-09-04 | SS o nk TS w nk rib | TS |  |  | 2026-10-02 | 2026-10-06 | 2026-10-13 | 2026-10-28 |  |  | 2026-11-04 | 2026-11-04 | 2026-11-09 | 2026-11-11 | 2026-11-11 | 2026-11-14 | 2026-11-14 |  |  | 2026-11-17 | 2026-11-20 | 2026-11-23 | 2026-11-24 |  |  | 2026-11-26 | 2026-11-28 | 2026-11-30 | 2026-12-21 | 2026-12-23 | 119 | N2 | Abid | Chest | Chest | pink-528 pcs 2 clr pig and 2 clr flat 2 clr terry emb |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -528 | [11 empty] | 52 | Nov'2
BS-ONL | 48849 | 15368509 | 1068 | 214 | 2026-08-24 | 2026-09-04 | chese cloth SS reglan slve dress w nk elastic w letus | Dress |  |  | 2026-10-05 | 2026-10-10 | 2026-10-15 | 2026-10-27 |  |  | 2026-11-11 | 2026-11-11 | 2026-11-17 | 2026-11-19 | 2026-11-20 | [6 empty] | 2026-11-23 | 2026-11-24 |  |  | 2026-11-26 | 2026-11-28 | 2026-12-03 | 2026-12-21 | 2026-12-23 | 119 | M | Abid | [5 empty] | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -1068 | [11 empty] | 52 | Nov'2
BS-ONL | 48846 | 15368505 | 4079 | 510 | 2026-08-24 | 2026-09-04 | chese cloth SS reglan slve TS w nk elastic w letus | TS |  |  | 2026-10-01 | 2026-10-08 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-09 | 2026-11-09 | 2026-11-14 | 2026-11-18 | 2026-11-21 | [6 empty] | 2026-11-24 | 2026-11-28 |  |  | 2026-12-02 | 2026-12-04 | 2026-12-07 | 2026-12-21 | 2026-12-23 | 119 | M | Abid | [5 empty] | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -4079 | [11 empty] | 52 | Nov'2
BS-ONL | 48845 | 15389960 | 6585 | 1756 | 2026-08-24 | 2026-09-04 | SS double layer TS w ballon slve and hem | TS |  |  | 2026-10-01 | 2026-10-08 | 2026-10-13 | 2026-10-30 |  |  | 2026-11-07 | 2026-11-07 | 2026-11-14 | 2026-11-17 | 2026-11-20 | [6 empty] | 2026-11-23 | 2026-11-28 |  |  | 2026-12-03 | 2026-12-05 | 2026-12-09 | 2026-12-20 | 2026-12-20 | 118 | J | Abid | [5 empty] | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -6585 | [11 empty] | 52 | Nov'2
BS-ONL | 48856 | 15390699 | 12344 | 1646 | 2026-08-24 | 2026-09-04 | SS o nk TS | TS |  |  | 2026-10-01 | 2026-10-07 | 2026-10-13 | 2026-10-28 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-09 | 2026-11-11 | 2026-11-14 | 2026-11-14 | 2026-11-20 |  |  |  |  | 2026-11-21 | 2026-11-28 |  |  | 2026-12-03 | 2026-12-05 | 2026-12-08 | 2026-12-21 | 2026-12-23 | 119 | L1 | Abid | Fr,Bk |  | c.dan-7512 pcs frt 1 clr puff back 1 clr puff 3 clr pig ,,blue-4832 pcs frt 1 clr puff 3 clr rub back no print |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -12344 | [11 empty] | 52 | Nov'2
BS-ONL | 48206 3rd | 15346421 | 4500 | 563 | 2026-08-24 | 2026-09-04 | AOP SS o nk TS | TS |  |  | 2026-09-22 | 2026-10-02 | 2026-10-05 | 2026-10-20 | 2026-10-27 | 2026-11-05 | 2026-11-10 | 2026-11-10 |  | 2026-11-17 | 2026-11-20 | [6 empty] | 2026-11-23 | 2026-11-27 |  |  | 2026-11-30 | 2026-12-03 | 2026-12-07 | 2026-12-14 | 2026-12-16 | 112 | O1 | Abid |  |  |  | AOP |  | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -4500 | [11 empty] | 51 | Nov'2
OVS SPA | 48525 | 271TSHFTT211-6172 | 5445 | 1066 | 2026-08-25 | 2026-09-01 | SS o nk TS w letus stitch | TS |  |  | 2026-10-20 | 2026-10-30 | 2026-11-02 | 2026-11-14 |  |  | 2026-11-24 | 2026-11-25 | 2026-12-01 | 2026-12-02 | 2026-12-03 | [6 empty] | 2026-12-04 | 2026-12-07 |  |  | 2026-12-08 | 2026-12-10 | 2026-12-12 | 2026-12-14 | 2026-12-14 | 111 | G2 | Shaker | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -5445 | [11 empty] | 51 | Dec'1
OVS SPA | 48529 | 271SHRFTB205-6172 | 1615 | 655 | 2026-08-25 | 2026-09-01 | AOP elasted Shorts w drawstring | Shorts |  |  | 2026-10-01 | 2026-10-10 | 2026-10-12 | 2026-10-24 | 2026-11-02 | 2026-11-12 | 2026-11-19 | 2026-11-20 | 2026-11-25 | 2026-11-26 | 2026-11-27 | [6 empty] | 2026-12-01 | 2026-12-03 |  |  | 2026-12-04 | 2026-12-07 | 2026-12-09 | 2026-12-14 | 2026-12-14 | 111 | N/3 | Shaker |  |  |  | AOP |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -1615 | [11 empty] | 51 | Nov'3
OVS SPA | 48530 | 271TSHFTT542-6172 | 1615 | 460 | 2026-08-25 | 2026-09-01 | AOP SS boat nk TS | TS |  |  | 2026-10-01 | 2026-10-10 | 2026-10-12 | 2026-10-22 | 2026-11-02 | 2026-11-12 | 2026-11-23 | 2026-11-25 | 2026-11-30 | 2026-12-01 | 2026-12-02 | [6 empty] | 2026-12-04 | 2026-12-05 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-11 | 2026-12-14 | 2026-12-14 | 111 | G1 | Shaker |  |  |  | AOP |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -1615 | [11 empty] | 51 | Dec'1
OVS SPA | 48544 | 271BDY230-256 | 3615 | 247 | 2026-08-20 | 2026-09-01 | SS body suit w bk nk and btm snap btn | Body |  |  | 2026-10-20 | 2026-10-31 | 2026-11-02 | 2026-11-13 |  |  | 2026-11-30 | 2026-11-24 | 2026-12-01 | 2026-12-02 | 2026-12-04 |  |  |  |  | 2026-12-05 | 2026-12-09 | 2026-12-09 | 2026-12-14 |  |  | 2026-12-15 | 2026-12-17 | 2026-12-19 | 2026-12-21 | 2026-12-21 | 123 | C | Shaker |  | Chest | blue-3615 pcs 2 clr flat emb |  |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -3615 | [11 empty] | 52 | Dec'1
OVS SPA | 48545 | 271RMP241-256 | 4846 | 363 | 2026-08-20 | 2026-09-01 | SL body w frt placket btn and btm snap btn | Romper |  |  | 2026-10-21 | 2026-10-30 | 2026-11-02 | 2026-11-14 |  |  | 2026-11-20 | 2026-11-14 | 2026-11-21 | 2026-11-23 | 2026-11-25 |  |  |  |  | 2026-11-26 | 2026-11-30 | 2026-12-01 | 2026-12-12 |  |  | 2026-12-14 | 2026-12-15 | 2026-12-17 | 2026-12-21 | 2026-12-21 | 123 | N/2 | Shaker |  | Chest | cement-4846 pcs 4 clr flat emb |  |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -4846 | [11 empty] | 52 | Nov'3
OVS SPA | 48546 | 271RMP242-256 | 2700 | 271 | 2026-08-20 | 2026-09-01 | SL body w slve frill frt placket btn and btm snap btn | Romper |  |  | 2026-10-20 | 2026-10-31 | 2026-11-02 | 2026-11-14 |  |  | 2026-11-28 | 2026-11-25 | 2026-12-01 | 2026-12-02 | 2026-12-04 |  |  |  |  | 2026-12-04 | 2026-12-07 | 2026-12-08 | 2026-12-12 |  |  | 2026-12-14 | 2026-12-16 | 2026-12-18 | 2026-12-21 | 2026-12-21 | 123 | B | Shaker |  | Chest | white-2700 pcs 2 clr flat emb |  |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -2700 | [11 empty] | 52 | Dec'1
OVS SPA | 48547 | 271SET236-256 | 7122 | 406 | 2026-08-20 | 2026-09-01 | SS TS w bk nk placket btn and shorts w fly btn | Top & BTM |  |  | 2026-10-20 | 2026-10-28 | 2026-11-02 | 2026-11-14 |  |  | 2026-11-25 | 2026-11-20 | 2026-11-26 | 2026-11-27 | 2026-11-30 |  |  |  |  | 2026-12-01 | 2026-12-05 | 2026-12-05 | 2026-12-12 |  |  | 2026-12-14 | 2026-12-15 | 2026-12-17 | 2026-12-21 | 2026-12-21 | 123 | N/3 | Shaker |  | Chest | white top-3561 pcs 3 clr flat emb ,,cement btm-3561 pcs no emb |  |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -7122 | [11 empty] | 52 | Nov'3
OVS SPA | 48548 | 271SET237-256 | 7530 | 751 | 2026-08-20 | 2026-09-01 | SL frill dress w nk placket btn and elasted shorts | Top & BTM |  |  | 2026-10-20 | 2026-10-30 | 2026-11-02 | 2026-11-13 |  |  | 2026-11-25 | 2026-11-20 | 2026-11-26 | 2026-11-27 | 2026-11-30 |  |  |  |  | 2026-12-01 | 2026-12-05 | 2026-12-05 | 2026-12-12 |  |  | 2026-12-14 | 2026-12-15 | 2026-12-17 | 2026-12-21 | 2026-12-21 | 123 | N/3 | Shaker |  | Chest | white top-3765 pcss 3 clr flat emb ,,papya btm-3765 pcs no emb |  |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -7530 | [11 empty] | 52 | Nov'3
OVS SPA | 47747 | 271TSHFTT131-6172 | 15780 | 2551 | 2026-08-25 | 2026-09-01 | SS o nk TS | TS |  |  | 2026-10-19 | 2026-10-31 | 2026-11-02 | 2026-11-16 |  |  | 2026-11-18 | 2026-11-19 | 2026-11-24 | 2026-11-25 | 2026-11-28 | [6 empty] | 2026-12-01 | 2026-12-07 |  |  | 2026-12-08 | 2026-12-09 | 2026-12-11 | 2026-12-14 | 2026-12-14 | 111 | G2 | Shaker | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -15780 | [11 empty] | 51 | Nov'3
OVS SPA | 47748 | 271TSHFTT131S-6172 | 6039 | 1097 | 2026-08-25 | 2026-09-01 | YD SS o nk TS | TS | 2026-10-01 | 2026-10-10 | 2026-10-12 | 2026-10-22 | 2026-11-02 | 2026-11-10 |  |  | 2026-11-24 | 2026-11-25 | 2026-11-30 | 2026-12-01 | 2026-12-03 | [6 empty] | 2026-12-03 | 2026-12-07 |  |  | 2026-12-08 | 2026-12-10 | 2026-12-12 | 2026-12-14 | 2026-12-14 | 111 | G1 | Shaker |  |  |  | YD |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -6039 | [11 empty] | 51 | Dec'1
OVS SPA | 47750 | 271TSHFTT522-6172 | 6838 | 1294 | 2026-08-25 | 2026-09-01 | SS U nk TS w lace at nk and btm frill | TS |  |  | 2026-10-17 | 2026-10-30 | 2026-11-02 | 2026-11-14 |  |  | 2026-11-21 | 2026-11-19 | 2026-11-24 | 2026-11-25 | 2026-11-27 | [6 empty] | 2026-12-01 | 2026-12-07 |  |  | 2026-12-08 | 2026-12-10 | 2026-12-12 | 2026-12-14 | 2026-12-14 | 111 | N/2 | Shaker |  |  |  |  | Lace | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -6838 | [11 empty] | 51 | Nov'3
OVS SPA | 47751 | 271TSHFTT529-6172 | 2828 | 467 | 2026-08-25 | 2026-09-01 | YD SS V nk TS w frt nk gathering | TS | 2026-10-01 | 2026-10-10 | 2026-10-12 | 2026-10-24 | 2026-11-02 | 2026-11-10 |  |  | 2026-11-20 | 2026-11-21 | 2026-11-26 | 2026-11-27 | 2026-11-28 | [6 empty] | 2026-12-01 | 2026-12-04 |  |  | 2026-12-05 | 2026-12-07 | 2026-12-09 | 2026-12-14 | 2026-12-14 | 111 | N/2 | Shaker |  |  |  | YD |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -2828 | [11 empty] | 51 | Nov'3
OVS SPA | 48603 | 271PJA036APW3-6111 | 17206 | 2466 | 2026-08-29 | 2026-09-03 | SS TS and AOP shorts w self fab bow string | Top & BTM |  |  | 2026-09-25 | 2026-10-10 | 2026-10-12 | 2026-10-26 | 2026-10-27 | 2026-11-07 | 2026-11-28 | 2026-11-18 | 2026-11-25 | 2026-11-26 | 2026-12-01 | 2026-12-01 | 2026-12-07 |  |  |  |  | 2026-12-07 | 2026-12-15 |  |  | 2026-12-15 | 2026-12-17 | 2026-12-29 | 2026-12-21 | 2026-12-21 | 114 | Q+P | Basir | Chest |  | white stripe blue top-3177 pcs 3 clr pig ,,pink top-3013 pcs 5 clr pig print ,,white stripe green top-2413 pcs no print ,, all btm -8603 pcs no print | AOP |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -17206 | [11 empty] | 52 | Nov'3
BS-NMT | 48748 | 13266269 | 805 | 166 | 2026-08-19 | 2026-09-01 | Strap Swt play suit w waist elastic and lurex tape binding and string | Suit | 2026-10-01 | 2026-10-05 | 2026-10-15 | 2026-10-20 | 2026-10-28 | 2026-11-10 |  |  | 2026-11-16 | 2026-11-16 | 2026-11-23 | 2026-11-26 | 2026-11-27 |  |  |  |  | 2026-12-01 | 2026-12-03 | 2026-12-07 | 2026-12-09 |  |  | 2026-12-11 | 2026-12-14 | 2026-12-21 | 2027-01-22 | 2027-01-24 | 156 | S | Shamoly |  | Chest | black-805 pcs 3 clr flat emb | YD |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -805 | [11 empty] | 5 | Nov'3
BS-ONL | 48230 3rd | 15325767 | 1000 | 110 | 2026-08-24 | 2026-09-04 | SS TS w slve woven emb lace | TS |  |  | 2026-10-20 | 2026-10-24 | 2026-10-05 | 2026-11-20 |  |  | 2026-11-27 | 2026-11-27 |  | 2026-12-04 | 2026-12-05 | [6 empty] | 2026-12-09 | 2026-12-10 |  |  | 2026-12-14 | 2026-12-17 | 2026-12-22 | 2027-01-11 | 2027-01-13 | 140 | M | Abid |  |  |  |  | Lace | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1000 | [11 empty] | 3 | Dec'1
OVS SPA | 48531 | 271TSHFTT327-6172 | 3626 | 586 | 2026-08-25 | 2026-09-01 | SS o nk TS w side gathering w string | TS |  |  | 2026-11-02 | 2026-11-10 | 2026-11-12 | 2026-11-25 |  |  | 2026-12-15 | 2026-12-17 | 2026-12-22 | 2026-12-23 | 2026-12-24 | [6 empty] | 2026-12-26 | 2026-12-31 |  |  | 2027-01-04 | 2027-01-04 | 2027-01-06 | 2027-01-12 | 2027-01-12 | 140 | N/2 | Shaker | [5 empty] | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -3626 | [11 empty] | 3 | Dec'3
OVS SPA | 48897 | 271SHR028-222 | 3016 | 917 | 2026-08-26 | 2026-09-04 | Waist belt shorts w side pkt and drawstring | Shorts |  |  | 2026-11-10 | 2026-11-21 | 2026-11-23 | 2026-12-05 |  |  | 2027-01-05 | 2026-12-18 | 2026-12-28 | 2026-12-29 | 2026-12-31 | 2027-01-02 | 2027-01-06 | 2027-01-06 | 2027-01-11 | 2027-01-11 | 2027-01-15 | 2027-01-15 | 2027-01-20 |  |  | 2027-01-21 | 2027-01-23 | 2027-01-25 | 2027-02-05 | 2027-02-05 | 163 | N/3 | Shaker | Chest,Stone | Thigh | white-3016 pcs 2 clr rub print HP rine stone and 1 clr flat emb |  |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -3016 | [11 empty] | 6 | Dec'3
OVS SPA | 48898 | 271SHR028-222 | 4104 | 274 | 2026-08-26 | 2026-09-04 | Halter nk Tank top | Tank Top |  |  | 2026-12-01 | 2026-12-08 | 2026-12-10 | 2026-12-22 |  |  | 2027-01-08 | 2027-01-04 | 2027-01-09 | 2027-01-11 | 2027-01-12 |  |  | 2027-01-13 | 2027-01-16 |  |  | 2027-01-18 | 2027-01-22 |  |  | 2027-01-23 | 2027-01-25 | 2027-01-27 | 2027-02-05 | 2027-02-05 | 163 | D1 | Shaker | Stone |  | white-4104 pcs 1 size rine stone HP |  |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -4104 | [11 empty] | 6 | Jan'2
OVS SPA | 48899 | 271TSH043-222 | 6108 | 1395 | 2026-08-26 | 2026-09-04 | SS o nk TS | TS |  |  | 2026-11-20 | 2026-11-30 | 2026-12-01 | 2026-12-14 |  |  | 2027-01-07 | 2027-01-01 | 2027-01-06 | 2027-01-07 | 2027-01-09 | 2027-01-11 | 2027-01-15 |  |  |  |  | 2027-01-15 | 2027-01-20 |  |  | 2027-01-21 | 2027-01-23 | 2027-01-25 | 2027-02-05 | 2027-02-05 | 163 | D1 | Shaker | Fr,Bk |  | white-6108 pcs frt back digital Photo print |  | Print sub plan need | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -6108 | [11 empty] | 6 | Jan'1
OVS SPA | 48900 | 271TSH044-222 | 3066 | 631 | 2026-08-26 | 2026-09-04 | SS o nk TS w gmts dye acid wash | TS |  |  | 2026-11-20 | 2026-11-30 | 2026-12-01 | 2026-12-15 |  |  | 2027-01-01 | 2026-12-21 | 51/27 | 2027-01-06 | 2027-01-07 | 2027-01-19 | 2027-01-23 | 2027-01-23 | 2027-01-28 |  |  | 2027-01-08 | 2027-01-11 | 2027-01-12 | 2027-01-19 | 2027-01-29 | 2027-01-30 | 2027-02-02 | 2027-02-05 | 2027-02-05 | 163 | D1 | Shaker | Chest,Stone |  | Lupine-3066 pcs 1 clr rub print and rine stone HP at edge of the artwork |  | Gms dye acid wash | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -3066 | [11 empty] | 6 | Jan'1
BS-ONL | 48158-Remake | 15368187 | 13992 | 2143 | 2026-06-24 | 2026-09-05 | SS v nk TS | TS |  |  | 2026-09-05 | 2026-09-08 | 2026-09-08 | 2026-09-12 |  |  | 2026-08-07 | 2026-08-07 | 2026-08-13 | 2026-09-12 | 2026-09-14 | 2026-09-14 | 2026-09-17 |  |  | 2026-09-16 | 2026-09-19 | 2026-09-18 | 2026-09-22 |  |  | 2026-09-22 | 2026-09-22 | 2026-09-22 | 2026-09-22 | 2026-09-24 | 90 | V | Mainul | Chest | Chest | black-6996 pcs,,c.dancer-6996 pcs all combo 3 clr rub and 1 clr lurex emb |  |  | NFL3 |  |  | Cut Ok | 0 | 0 | 0 | 0 | -13992 | [11 empty] | 39 | Sep'2 |  |  | 25.07.26
BS-NMT | 48979 | 13260940 | 3820 | 770 | 2026-09-07 | 2026-09-07 | Elasted legging w leg openning letus stich | Legging |  |  | 2026-09-26 | 2026-09-24 | 2026-09-28 | 2026-10-06 |  |  | 2026-10-08 | 2026-10-06 | 2026-10-08 | 2026-10-08 | 2026-10-10 | 2026-10-10 | 2026-10-12 |  |  |  |  | 2026-10-13 | 2026-10-15 |  |  | 2026-10-16 | 2026-10-17 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 42 | W1 | Jafar | Waist |  | 3 combo label print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3820 | [11 empty] | 43 | Oct'1
BS-ONS | 48199 4th | 22042193 | 22512 | 5619 | 2026-09-07 | 2026-09-11 | SS o nk TS w nk rib | TS |  |  | 2026-09-14 | 2026-09-21 | 2026-09-21 | 2026-10-08 |  |  | 2026-10-07 | 2026-10-02 |  | 2026-10-07 | 2026-10-13 | 2026-10-10 | 2026-10-15 |  |  |  |  | 2026-10-14 | 2026-10-22 |  |  | 2026-10-23 | 2026-10-24 | 2026-10-24 | 2026-10-26 | 2026-10-28 | 49 | ZA2 | Shovon | Heat Press/Heat Seal |  | 2 combo nk HP |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -22512 | [11 empty] | 44 | Oct'1
BS-ONL | 47488 2nd | 15369134 | 1700 | 349 | 2026-09-01 | 2026-09-05 | LS v nk TS | TS |  |  | 2026-09-15 | 2026-09-20 | 2026-09-25 | 2026-10-05 |  |  | 2026-10-03 | 2026-10-03 |  | 2026-10-08 | 2026-10-09 | [6 empty] | 2026-10-12 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 48 | L1 | Mainul | [5 empty] | NFL2 |  |  | CAD | 0 | 0 | 0 | 0 | -1700 | [11 empty] | 43 | Oct'1 |  |  | 16.09.26
BS-ONL | 48953 | 15400631 | 2400 | 544 | 2026-08-27 | 2026-09-07 | 3/4 Slve V nk TS | TS |  |  | 2026-09-05 | 2026-09-10 | 2026-09-12 | 2026-09-24 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-29 | 2026-10-01 | 2026-10-02 | [6 empty] | 2026-10-03 | 2026-10-05 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-12 | 2026-10-14 | 46 | L1 | Mainul | [5 empty] | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -2400 | [11 empty] | 42 | Oct'1
BS-ONL | 46748 17th | 15244714 | 3024 | 467 | 2026-09-03 | 2026-09-07 | SS o nk TS | TS |  |  | 2026-09-15 | 2026-09-21 | 2026-09-25 | 2026-10-05 |  |  | 2026-10-07 | 2026-10-03 |  | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 |  |  |  |  | 2026-10-13 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 46 | F | Imran | Chest |  | c.dan -3024 1 clr gltr print |  | Stock fab from 24508 92th | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -3024 | [11 empty] | 43 | Oct'1
BS-ONL | 46748 18th | 15244714 | 6048 | 939 | 2026-09-07 | 2026-09-11 | SS o nk TS | TS |  |  | 2026-09-18 | 2026-09-24 | 2026-10-01 | 2026-10-07 |  |  | 2026-10-08 | 2026-10-03 |  | 2026-10-08 | 2026-10-10 | 2026-10-10 | 2026-10-14 |  |  |  |  | 2026-10-15 | 2026-10-19 |  |  | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-26 | 2026-10-28 | 49 | F | Imran | Chest |  | black-3024 pcs,,night sky-3024 pcs all combo 1 clr gltr print |  |  | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -6048 | [11 empty] | 44 | Oct'1
BS-ONL | 41880 27th | 15062199 | 6000 | 2195 | 2026-09-04 | 2026-09-07 | HW legging Drawstring at leg opening | Legging |  |  | 2026-09-14 | 2026-09-24 | 2026-09-26 | 2026-10-06 |  |  | 2026-10-02 | 2026-10-02 |  | 2026-10-06 | 2026-10-08 | 2026-10-08 | 2026-10-10 |  |  |  |  | 2026-10-12 | 2026-10-15 |  |  | 2026-10-16 | 2026-10-17 | 2026-10-19 | 2026-10-19 | 2026-10-21 | 45 | H | Khalid | Waist |  | 1 combo waist lettering logo print |  |  | NFL1 |  |  | CAD | 0 | 0 | 0 | 0 | -6000 | [11 empty] | 43 | Oct'1 |  |  | 17.09.26
BS-ONL | 27204 69th | 15323159 | 11120 | 2660 | 2026-09-07 | 2026-09-07 | LS o nk TS | TS |  |  | 2026-09-18 | 2026-09-27 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-10 | 2026-10-10 |  | 2026-10-14 | 2026-10-17 | [6 empty] | 2026-10-17 | 2026-10-21 |  |  | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-26 | 2026-10-28 | 49 | F | Dalim | [5 empty] | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -11120 | [11 empty] | 44 | Oct'2
BS-ONL | 48833 1st | 15373005 | 1224 | 103 | 2026-08-24 | 2026-09-05 | Rib Tank top w gmts dye acid wash | Tank Top |  |  | 2026-09-10 | 2026-09-15 | 2026-09-18 | 2026-09-24 |  |  | 2026-09-24 | 2026-09-24 | 2026-10-01 | 2026-10-03 | 2026-10-03 |  |  |  |  | 2026-10-05 | 2026-10-16 | 2026-10-09 | 2026-10-10 | 2026-10-12 | 2026-12-14 | 2026-10-18 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-21 | 56 | M | Abid |  | Chest | c.dan no wash-888 pcs 1 clr flat all over emb ,,bel air blue wash -336 pcs 1 clr flat emb |  | bel air blue clr gmts dye acid wash | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -1224 | [11 empty] | 43 | Oct'1
BS-ONL | 48834 | 15373126 | 2772 | 872 | 2026-08-25 | 2026-09-07 | YD SS long fress w waist self fabric string and blind stitch | Dress | 2026-09-14 | 2026-09-21 | 2026-09-21 | 2026-09-28 | 2026-09-26 | 2026-10-05 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-06 | 2026-10-07 | 2026-10-08 | [6 empty] | 2026-10-09 | 2026-10-13 |  |  | 2026-10-14 | 2026-10-15 | 2026-10-17 | 2026-10-19 | 2026-10-21 | 55 | K | Abid |  |  |  | YD |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -2772 | [11 empty] | 43 | Oct'1
GBX-TM LEWIN | 44711 13th | 67936/67937/68213/68224 | 6625 | 1624 | 2026-09-03 | 2026-09-05 | MENS SS TS | TS |  |  | 2026-09-14 | 2026-09-22 | 2026-09-26 | 2026-10-10 |  |  | 2026-10-06 | 2026-10-06 |  | 2026-10-12 | 2026-10-15 | [6 empty] | 2026-10-14 | 2026-10-19 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-24 | 2026-10-28 | 2026-10-29 | 55 | N/1 | Shofi | [5 empty] | NCL |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -6625 | [11 empty] | 44 | Oct'2
GBX-TM LEWIN | 46696 5th | 68490/68491/68492/68591 | 2845 | 787 | 2026-09-03 | 2026-09-05 | SS o nk TS | TS |  |  | 2026-09-15 | 2026-09-19 | 2026-09-26 | 2026-10-10 |  |  | 2026-10-08 | 2026-10-08 |  | 2026-10-12 | 2026-10-13 | [6 empty] | 2026-10-15 | 2026-10-19 |  |  | 2026-10-21 | 2026-10-22 | 2026-10-24 | 2026-10-28 | 2026-10-29 | 55 | N/1 | Shofi | [5 empty] | NCL |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -2845 | [11 empty] | 44 | Oct'2
GBX-TM LEWIN | 44714 12th | 68245/68246/68247/68248 | 13075 | 4358 | 2026-09-03 | 2026-09-05 | MENS O NK TS W PLKT & BTN | TS |  |  | 2026-09-14 | 2026-06-26 | 2026-09-26 | 2026-10-10 |  |  | 2026-10-08 | 2026-10-07 |  | 2026-10-10 | 2026-10-14 | [6 empty] | 2026-10-12 | 2026-10-24 |  |  | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 55 | N/2 | Shofi | [5 empty] | NCL |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -13075 | [11 empty] | 44 | Oct'1
GBX-TM LEWIN | 44712 7th | 68239/68240/68241 | 1785 | 466 | 2026-09-03 | 2026-09-05 | SS TS W PLKT & BTN | TS |  |  | 2026-09-18 | 2026-09-23 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-10 | 2026-10-10 |  | 2026-10-16 | 2026-10-17 | [6 empty] | 2026-10-20 | 2026-10-23 |  |  | 2026-10-24 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 55 | N/2 | Shofi | [5 empty] | NCL |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1785 | [11 empty] | 44 | Oct'2
GBX-TM LEWIN | 44715 14th | 68166/68167/68400/68398/68401 | 5575 | 1857 | 2026-09-03 | 2026-09-07 | MENS LS TS | TS |  |  | 2026-09-17 | 2026-09-26 | 2026-10-01 | 2026-10-13 |  |  | 2026-10-10 | 2026-10-10 |  | 2026-10-14 | 2026-10-17 | [6 empty] | 2026-10-16 | 2026-10-20 |  |  | 2026-10-21 | 2026-10-22 | 2026-10-24 | 2026-10-28 | 2026-10-29 | 55 | N/1 | Shofi | [5 empty] | NCL |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -5575 | [11 empty] | 44 | Oct'2
GBX-TM LEWIN | 44374 10th | 68169 | 1575 | 403 | 2026-09-11 | 2026-09-12 | SS v nk TS | TS |  |  | 2026-09-22 | 2026-09-26 | 2026-10-01 | 2026-10-10 |  |  | 2026-10-10 | 2026-10-10 | 2026-10-16 | 2026-10-17 | 2026-10-19 | [6 empty] | 2026-10-21 | 2026-10-22 |  |  | 2026-10-23 | 2026-10-24 | 2026-10-26 | 2026-10-28 | 2026-10-28 | 47 | N/1 | Shofi | [5 empty] | NCL |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1575 | [11 empty] | 44 | Oct'2
BS-NMT | 48974 | 13264667 | 5385 | 1355 | 2026-09-04 | 2026-09-07 | YD SS contrast nk TS | TS | 2026-10-01 | 2026-10-08 | 2026-10-10 | 2026-10-20 | 2026-10-10 | 2026-10-26 |  |  | 2026-10-29 | 2026-10-29 | 2026-11-05 | 2026-11-07 | 2026-11-11 | [6 empty] | 2026-11-12 | 2026-11-17 |  |  | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-23 | 2026-11-25 | 80 | Y | Tomal |  |  |  | YD |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -5385 | [11 empty] | 48 | Nov'1
BS-NMT | 48976 | 13264758 | 10640 | 3046 | 2026-09-04 | 2026-09-07 | YD LS o nk TS | TS | 2026-09-21 | 2026-09-30 | 2026-09-28 | 2026-10-11 | 2026-10-08 | 2026-10-15 |  |  | 2026-10-12 | 2026-10-12 | 2026-10-17 | 2026-10-20 | 2026-10-24 | [6 empty] | 2026-10-23 | 2026-10-28 |  |  | 2026-10-30 | 2026-10-31 | 2026-11-02 | 2026-11-02 | 2026-11-04 | 59 | ZA1 | Tomal |  |  |  | YD |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -10640 | [11 empty] | 45 | Oct'2
BS-NMT | 48975 | 13264739 | 3747 | 1065 | 2026-09-04 | 2026-09-07 | YD LS o nk TS | TS | 2026-09-22 | 2026-09-28 | 2026-10-01 | 2026-10-10 | 2026-10-10 | 2026-10-16 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-20 | 2026-10-21 | 2026-10-22 | [6 empty] | 2026-10-23 | 2026-10-27 |  |  | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-11-02 | 2026-11-04 | 59 | Z | Tomal |  |  |  | YD |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -3747 | [11 empty] | 45 | Oct'3
BS-NMT | 48977 | 13270882 | 4740 | 1040 | 2026-09-05 | 2026-09-07 | YD LS boat nk TS | TS | 2026-10-01 | 2026-10-09 | 2026-10-10 | 2026-10-20 | 2026-10-15 | 2026-10-28 |  |  | 2026-10-29 | 2026-10-26 | 2026-11-05 | 2026-11-07 | 2026-11-10 | [6 empty] | 2026-11-11 | 2026-11-16 |  |  | 2026-11-17 | 2026-11-19 | 2026-11-20 | 2026-11-23 | 2026-11-25 | 79 | Y1 | Tomal |  |  |  | YD |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -4740 | [11 empty] | 48 | Nov'1
BS-NMT | 48749 | 13270214 | 810 | 117 | 2026-09-03 | 2026-09-07 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-09-18 | 2026-09-23 | 2026-10-01 | 2026-10-14 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-20 | 2026-10-22 | 2026-10-23 |  |  |  |  | 2026-10-26 | 2026-10-29 | 2026-11-02 | 2026-11-03 |  |  | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-09 | 2026-11-11 | 67 | T2 | Shamoly |  | Chest | chestnut-810 pcs far fabric attach emb |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -810 | [11 empty] | 46 | Oct'3
BS-NMT | 43330 12th | 13197665 | 2000 | 888 | 2026-09-02 | 2026-09-07 | LS Swt Zip hoodie w kangro pkt | Hoody |  |  | 2026-09-17 | 2026-09-23 | 2026-10-01 | 2026-10-13 |  |  | 2026-10-10 | 2026-10-10 |  | 2026-10-16 | 2026-10-17 | [6 empty] | 2026-10-20 | 2026-10-24 |  |  | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-11-02 | 2026-11-04 | 61 | S | Jafar | [5 empty] | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -2000 | [11 empty] | 45 | Oct'2
BS-NMT | 46491 9th | 13225095 | 2000 | 283 | 2026-09-07 | 2026-09-07 | YD LS o nk TS | TS | 2026-09-22 | 2026-09-28 | 2026-10-03 | 2026-10-12 | 2026-10-14 | 2026-10-20 |  |  | 2026-10-20 | 2026-10-20 |  | 2026-10-26 | 2026-10-27 | 2026-10-29 | 2026-10-30 |  |  |  |  | 2026-11-02 | 2026-11-04 |  |  | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-09 | 2026-11-11 | 63 | Z | Jafar | Chest,Nk |  | indigo-2000 pcs 1 clr puff print | YD |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -2000 | [11 empty] | 46 | Oct'3
BS-NMT | 43319 22th | 13238718 | 1020 | 233 | 2026-09-10 | 2026-09-12 | AOP LS Swt shirt | Swt Shirt |  |  | 2026-09-19 | 2026-09-24 | 2026-10-01 | 2026-10-10 | 2026-10-13 | 2026-10-19 | 2026-10-16 | 2026-10-16 |  | 2026-10-21 | 2026-10-22 | [6 empty] | 2026-10-23 | 2026-10-24 |  |  | 2026-10-27 | 2026-10-28 | 2026-10-30 | 2026-11-02 | 2026-11-04 | 53 | Z | Jafar |  |  |  | AOP |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1020 | [11 empty] | 45 | Oct'3
BS-NMT | 43325 16th | 13224921 | 1000 | 405 | 2026-09-09 | 2026-09-12 | LS Swt full Zip hoodie | Hoody |  |  | 2026-09-21 | 2026-09-25 | 2026-10-02 | 2026-10-14 |  |  | 2026-10-14 | 2026-10-14 |  | 2026-10-19 | 2026-10-20 | [6 empty] | 2026-10-22 | 2026-10-24 |  |  | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-11-02 | 2026-11-04 | 54 | S | Jafar | [5 empty] | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1000 | [11 empty] | 45 | Oct'2
BS-NMT | 46499 3rd | 13259554 | 3040 | 560 | 2026-09-09 | 2026-09-12 | LS AOP Dress | Dress |  |  | 2026-09-25 | 2026-09-29 | 2026-10-03 | 2026-10-15 | 2026-10-16 | 2026-10-22 | 2026-10-23 | 2026-10-23 |  | 2026-10-28 | 2026-10-29 | 2026-10-29 | 2026-11-02 |  |  |  |  | 2026-11-02 | 2026-11-05 |  |  | 2026-11-06 | 2026-11-07 | 2026-11-09 | 2026-11-09 | 2026-11-11 | 61 | Z | Jafar | Nk |  | 2 combo label print | AOP |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -3040 | [11 empty] | 46 | Oct'3
BS-ONS | 41626 28th | 22031973 | 2010 | 1321 | 2026-09-01 | 2026-09-05 | MENS LONG SWT PANT W SIDE & BK PKT | PANT |  |  | 2026-09-18 | 2026-09-24 | 2026-10-01 | 2026-10-12 |  |  | 2026-10-09 | 2026-10-09 |  | 2026-10-15 | 2026-10-16 | [6 empty] | 2026-10-19 | 2026-10-22 |  |  | 2026-10-24 | 2026-10-26 | 2026-10-28 | 2026-11-02 | 2026-11-04 | 62 | C | Shakel | [5 empty] | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -2010 | [11 empty] | 45 | Oct'2
BS-ONS | 45964 17th | 22039968 | 6000 | 4191 | 2026-09-06 | 2026-09-11 | LS High nk Haalf Zipp Swt shirt | Swt Shirt |  |  | 2026-09-28 | 2026-10-06 | 2026-10-09 | 2026-10-26 |  |  | 2026-10-24 | 2026-10-23 |  | 2026-10-28 | 2026-10-31 | [6 empty] | 2026-11-04 | 2026-11-11 |  |  | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-16 | 2026-11-18 | 71 | R | Shakel | [5 empty] | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -6000 | [11 empty] | 47 | Oct'3
BS-ONS | 48199 5th | 22042193 | 42332 | 10575 | 2026-09-07 | 2026-09-11 | SS o nk TS w nk rib | TS |  |  | 2026-09-18 | 2026-09-28 | 2026-09-25 | 2026-10-12 |  |  | 2026-10-12 | 2026-10-05 |  | 2026-10-10 | 2026-10-17 | 2026-10-13 | 2026-10-20 |  |  |  |  | 2026-10-17 | 2026-10-29 |  |  | 2026-10-30 | 2026-10-31 | 2026-11-02 | 2026-11-02 | 2026-11-04 | 56 | ZA1 | Shovon | Heat Press/Heat Seal |  | 7 combo nk HP |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -42332 | [11 empty] | 45 | Oct'1
BS-ONS | 47818 6th | 22041282 | 5877 | 2005 | 2026-09-07 | 2026-09-11 | SS TS w nk and arm hole contrast piping | TS |  |  | 2026-09-26 | 2026-10-06 | 2026-10-10 | 2026-10-26 |  |  | 2026-10-28 | 2026-10-28 |  | 2026-11-04 | 2026-11-06 | [6 empty] | 2026-11-09 | 2026-11-12 |  |  | 2026-11-14 | 2026-11-16 | 2026-11-18 | 2026-11-23 | 2026-11-25 | 77 | F | Shovon | [5 empty] | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -5877 | [11 empty] | 48 | Nov'1
BS-ONL | 30711 10th | 15209156 | 6210 | 1275 | 2026-09-07 | 2026-09-07 | LS o nk TS | TS |  |  | 2026-09-17 | 2026-09-26 | 2026-10-01 | 2026-10-17 |  |  | 2026-10-14 | 2026-10-14 |  | 2026-10-19 | 2026-10-21 | [6 empty] | 2026-10-23 | 2026-10-27 |  |  | 2026-10-28 | 2026-10-29 | 2026-10-31 | 2026-11-02 | 2026-11-04 | 56 | W2 | Mainul | [5 empty] | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -6210 | [11 empty] | 45 | Oct'2
BS-ONL | 30709 10th | 15209151 | 2790 | 559 | 2026-09-07 | 2026-09-07 | Legging | Legging |  |  | 2026-09-25 | 2026-09-30 | 2026-10-08 | 2026-10-20 |  |  | 2026-10-20 | 2026-10-20 |  | 2026-10-26 | 2026-10-27 | [6 empty] | 2026-11-02 | 2026-11-05 |  |  | 2026-11-06 | 2026-11-07 | 2026-11-09 | 2026-11-09 | 2026-11-11 | 63 | L2 | Mainul | [5 empty] | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -2790 | [11 empty] | 46 | Oct'3
BS-ONL | 44840 9th | 15318962 | 1204 | 741 | 2026-09-03 | 2026-09-07 | LDS LS HOOD SWT W DRAWSTING | HOODY | [8 empty] | 2026-10-10 | 2026-09-25 |  | 2026-10-03 | 2026-10-05 | 2026-10-08 | 2026-10-14 |  |  | 2026-10-16 | 2026-10-17 | 2026-10-20 | 2026-10-22 |  |  | 2026-10-24 | 2026-10-26 | 2026-10-28 | 2026-11-02 | 2026-11-04 | 60 | R | Imran | slv,Chest | Chest | C DANCER navy 1204 PCS 1 CLR PALCEMENT PRINT at chest and both slve and chest 1 CLR LURTEX EMB |  | stock fab from 44840 7th | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1204 | [11 empty] | 45 | Oct'1
BS-ONL | 44198 6th | 15337134 | 30100 | 11710 | 2026-09-07 | 2026-09-12 | YD LS o nk TS | TS | 2026-09-18 | 2026-09-30 | 2026-09-28 | 2026-10-12 | 2026-10-06 | 2026-10-16 |  |  | 2026-10-14 | 2026-10-09 |  | 2026-10-14 | 2026-10-20 | [6 empty] | 2026-10-17 | 2026-10-29 |  |  | 2026-10-31 | 2026-10-31 | 2026-11-02 | 2026-11-02 | 2026-11-04 | 56 | D | Imran |  |  |  | YD |  | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -30100 | [11 empty] | 45 | Oct'2
BS-ONL | 44198 7th | 15337134 | 36240 | 14159 | 2026-09-07 | 2026-09-12 | YD LS o nk TS | TS | 2026-09-28 | 2026-10-12 | 2026-10-10 | 2026-10-23 | 2026-10-15 | 2026-10-27 |  |  | 2026-10-20 | 2026-10-19 |  | 2026-10-24 | 2026-11-02 | [6 empty] | 2026-10-30 | 2026-11-12 |  |  | 2026-11-13 | 2026-11-13 | 2026-11-14 | 2026-11-16 | 2026-11-18 | 70 | D1 | Imran |  |  |  | YD |  | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -36240 | [11 empty] | 47 | Oct'3
BS-ONL | 48981 | 15345973 | 2412 | 1264 | 2026-09-10 | 2026-09-12 | LS YD O nk TS | TS | 2026-09-18 | 2026-09-26 | 2026-09-28 | 2026-10-05 | 2026-10-03 | 2026-10-09 |  |  | 2026-10-09 | 2026-10-09 | 2026-10-14 | 2026-10-16 | 2026-10-17 | [6 empty] | 2026-10-19 | 2026-10-22 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-24 | 2026-11-02 | 2026-11-04 | 53 | N1 | Zahirul |  |  |  | YD |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -2412 | [11 empty] | 45 | Oct'2
BS-ONL | 48964 | 15400703 | 21600 | 5058 | 2026-09-03 | 2026-09-05 | SS o nk TS w nk and arm hole hem picoting | TS |  |  | 2026-09-22 | 2026-10-02 | 2026-09-30 | 2026-10-13 |  |  | 2026-10-07 | 2026-10-07 | 2026-10-13 | 2026-10-15 | 2026-10-20 | [6 empty] | 2026-10-19 | 2026-10-27 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-02 | 2026-11-04 | 60 | G2 | Dalim | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -21600 | [11 empty] | 45 | Oct'2
BS-ONL | 43969 43th | 15270390 | 1801 | 310 | 2026-09-03 | 2026-09-05 | SS o nk TS | TS |  |  | 2026-09-22 | 2026-09-26 | 2026-10-02 | 2026-10-16 |  |  | 2026-10-15 | 2026-10-15 |  | 2026-10-20 | 2026-10-21 | [6 empty] | 2026-10-24 | 2026-10-26 |  |  | 2026-10-28 | 2026-10-30 | 2026-10-31 | 2026-11-16 | 2026-11-18 | 74 | Z | Dalim | [5 empty] | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1801 | [11 empty] | 47 | Oct'2
BS-ONL | 26030 25th | 15308926 | 1200 | 299 | 2026-09-03 | 2026-09-05 | SS TS W BK CUT & SEW & SIDE SLEET | TS |  |  | 2026-09-18 | 2026-09-24 | 2026-10-01 | 2026-10-10 |  |  | 2026-10-05 | 2026-10-05 |  | 2026-10-13 | 2026-10-14 | [6 empty] | 2026-10-16 | 2026-10-17 |  |  | 2026-10-19 | 2026-10-20 | 2026-10-25 | 2026-11-16 | 2026-11-18 | 74 | U | Dalim | [5 empty] | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1200 | [11 empty] | 47 | Oct'2
BS-ONL | 43969 44th | 15270390 | 6080 | 993 | 2026-09-03 | 2026-09-07 | SS o nk TS | TS |  |  | 2026-09-18 | 2026-09-24 | 2026-10-02 | 2026-10-14 |  |  | 2026-10-14 | 2026-10-14 |  | 2026-10-19 | 2026-10-22 | [6 empty] | 2026-10-22 | 2026-10-26 |  |  | 2026-10-28 | 2026-10-30 | 2026-10-31 | 2026-11-16 | 2026-11-18 | 74 | Z | Dalim | [5 empty] | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -6080 | [11 empty] | 47 | Oct'2
BS-ONL | 47709 4th | 15299770 | 3220 | 436 | 2026-09-07 | 2026-09-11 | LS o nk TS w blind hem | TS |  |  | 2026-10-02 | 2026-10-08 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-05 | 2026-11-05 |  | 2026-11-09 | 2026-11-10 | [6 empty] | 2026-11-12 | 2026-11-16 |  |  | 2026-11-17 | 2026-11-18 | 2026-11-20 | 2026-11-23 | 2026-11-25 | 77 | N1 | Abid | [5 empty] | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -3220 | [11 empty] | 48 | Nov'1
OVS SPA | 48961 | 271TSH043-6153 | 14195 | 2024 | 2026-09-03 | 2026-09-05 | SS o nk TS w side slit self fab bow attach | TS |  |  | 2026-09-25 | 2026-10-08 | 2026-10-10 | 2026-10-24 |  |  | 2026-11-02 | 2026-10-31 | 2026-11-04 | 2026-11-05 | 2026-11-10 | [6 empty] | 2026-11-09 | 2026-11-16 |  |  | 2026-11-17 | 2026-11-19 | 2026-11-21 | 2026-11-23 | 2026-11-23 | 81 | N1 | Sirajul | [5 empty] | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -14195 | [11 empty] | 48 | Nov'1
OVS SPA | 48962 | 271SHR012-6153 | 12012 | 2876 | 2026-09-03 | 2026-09-05 | Waist belt shorts w side pkt and drawstring | Shorts |  |  | 2026-09-21 | 2026-10-06 | 2026-10-07 | 2026-10-22 |  |  | 2026-10-30 | 2026-10-29 | 2026-11-03 | 2026-11-04 | 2026-11-09 | [6 empty] | 2026-11-07 | 2026-11-17 |  |  | 2026-11-18 | 2026-11-19 | 2026-11-21 | 2026-11-23 | 2026-11-23 | 81 | U | Sirajul | [5 empty] | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -12012 | [11 empty] | 48 | Nov'1
OVS SPA | 48472 | 271POLDUMAX-1014 | 18781 | 5561 | 2026-08-27 | 2026-09-05 | SS Polo shirt w flat knit collar placket btn and side slit | Polo | 2026-09-11 | 2026-09-19 | 2026-09-17 | 2026-10-10 | 2026-10-05 | 2026-10-24 |  |  | 2026-10-24 | 2026-10-24 | 2026-10-28 | 2026-10-29 | 2026-11-07 | [6 empty] | 2026-11-04 | 18/44 |  |  | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-23 | 2026-11-23 | 88 | J | Sirajul | [5 empty] | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -18781 | [11 empty] | 48 | Oct'3
OVS SPA | 48468 | 271SHRSHRSEER-1014 | 8076 | 1977 | 2026-08-27 | 2026-09-05 | Waist belt shorts w side pkt and drawstring | Shorts |  |  | 2026-09-17 | 2026-10-03 | 2026-10-01 | 2026-10-20 |  |  | 2026-10-30 | 2026-10-29 | 2026-11-03 | 2026-11-04 | 2026-11-07 | [6 empty] | 2026-11-09 | 2026-11-18 |  |  | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-23 | 2026-11-23 | 88 | U | Sirajul | [5 empty] | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -8076 | [11 empty] | 48 | Nov'1
OVS SPA | 48469 | 271POLPOLOSEER-1014 | 12480 | 2927 | 2026-08-27 | 2026-09-05 | SS Polo shirt w flat knit YD collar placket btn and side slit | Polo | 2026-09-12 | 2026-09-23 | 2026-09-21 | 2026-10-07 | 2026-10-05 | 2026-10-24 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-31 | 2026-11-02 | 2026-11-07 | [6 empty] | 2026-11-06 | 2026-11-17 |  |  | 2026-11-18 | 2026-11-19 | 2026-11-21 | 2026-11-23 | 2026-11-23 | 88 | V1 | Sirajul |  |  |  | YD |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -12480 | [11 empty] | 48 | Nov'1
OVS SPA | 48471 | 271SHRRAYAN-1014 | 14579 | 4802 | 2026-08-27 | 2026-09-05 | Waist belt shorts w side back pkt and drawstring | Shorts |  |  | 2026-09-15 | 2026-10-05 | 2026-10-01 | 2026-10-24 |  |  | 2026-10-28 | 2026-10-27 | 2026-11-02 | 2026-11-03 | 2026-11-09 | [6 empty] | 2026-11-07 | 2026-11-18 |  |  | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-23 | 2026-11-23 | 88 | N/3 | Sirajul | [5 empty] | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -14579 | [11 empty] | 48 | Nov'1
OVS SPA | 48478 | 271JOG018-226 | 37692 | 5685 | 2026-08-27 | 2026-09-07 | SS TS w shlder contrast tape and Shorts w contrast piping w side pkt drawstring | Top & BTM |  |  | 2026-09-17 | 2026-10-09 | 2026-10-05 | 2026-10-30 |  |  | 2026-11-02 | 2026-10-21 | 2026-10-27 | 2026-10-28 | 2026-10-09 | 2026-11-05 | 2026-11-14 |  |  |  |  | 2026-11-10 | 2026-11-24 |  |  | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-30 | 2026-11-30 | 95 | NFL1+NCL3 | Sirajul | Chest,Nk & Thigh |  | meneral top-5139 pcs,,meneral btm-5139 pcs ,,pageant-13707 pcs,,pageant btm-13707 pcs all combo top chest and btm thigh 3 clr pig print and top nk HP label |  |  | NFL1 | NFL2 | NFL3 | File Due | 0 | 0 | 0 | 0 | -37692 | [11 empty] | 49 | Oct'3
OVS SPA | 48474 | 271JOG004-223 | 37524 | 2284 | 2026-08-27 | 2026-09-07 | SS TS w shlder contrast nk and armhole piping and Shorts w contrast piping w side pkt drawstring | Top & BTM |  |  | 2026-09-17 | 2026-10-09 | 2026-10-05 | 2026-10-30 |  |  | 2026-11-02 | 2026-10-21 | 2026-10-27 | 2026-10-28 | 2026-11-09 | 2026-11-05 | 2026-11-14 |  |  |  |  | 2026-11-10 | 2026-11-24 |  |  | 2026-11-25 | 2026-11-26 | 2026-11-28 | 2026-11-30 | 2026-11-30 | 95 | NFL2+NCL2 | Sirajul | Chest,Nk & Thigh |  | yellow top-5856 pcs,naval top-12906 pcs both top 1 clr rub print and nk HP label,,,blue btm-5856 pcs,,oxford btm-12906 pcs both btm 1 clr rub print at thigh |  |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -37524 | [11 empty] | 49 | Oct'3
GBX-New Look | 48966 | 9697335 | 2729 | 968 | 2026-09-03 | 2026-09-07 | YD halter nk dress w inner layer | Dress | 2026-09-24 | 2026-09-29 | 2026-10-02 | 2026-10-09 | 2026-10-12 | 2026-10-17 |  |  | 2026-10-17 | 2026-10-17 | 2026-10-24 | 2026-10-27 | 2026-10-29 | [6 empty] | 2026-11-02 | 2026-11-05 |  |  | 2026-11-06 | 2026-11-06 | 2026-11-07 | 2026-11-07 | 2026-11-08 | 65 | N/3 | Sifat |  |  |  | YD |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -2729 | [11 empty] | 46 | Oct'3
GBX-Maurices | 48718 | 2592600/4259600 | 22609 | 5422 | 2026-09-02 | 2026-09-05 | SS crew nk TS w gmts pigment dye | TS |  |  | 2026-09-12 | 2026-09-26 | 2026-09-25 | 2026-10-04 |  |  | 2026-09-28 | 2026-09-28 | 2026-10-06 | 2026-10-08 | 2026-10-14 | 2026-10-18 | 2026-11-08 |  |  | 2026-10-10 | 2026-10-22 | 2026-10-20 | 2026-10-31 | 2026-10-24 | 2026-11-07 | 2026-11-09 | 2026-11-09 | 2026-11-10 | 2026-11-13 | 2026-11-13 | 72 | N/1 | Mannan | Heat Press/Heat Seal | Chest | della robia blue- core-14856 pcs,,plus-7753 pcs both nk HP and Lazer cut self fabric applique emb |  | Gmts dye pigment wash | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -22609 | [11 empty] | 46 | Oct'1
GBX-Miss Shelfridge | 48982 | INDOMS33594 | 1500 | 268 | 2026-09-10 | 2026-09-12 | LS v nk Half placket btn w nk Lace | TS |  |  | 2026-10-01 | 2026-10-08 | 2026-10-12 | 2026-10-24 |  |  | 2026-10-27 | 2026-10-27 | 2026-11-02 | 2026-11-05 | 2026-11-06 | [6 empty] | 2026-11-07 | 2026-11-09 |  |  | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-15 | 2026-11-15 | 66 | N/3 | Morad |  |  |  |  | Lace | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -1500 | [11 empty] | 47 | Nov'1
GBX-Miss Shelfridge | 48983 | INDOMS33574 | 1500 | 528 | 2026-09-10 | 2026-09-12 | Nk Lace trim LS wrap top | TS |  |  | 2026-09-25 | 2026-09-30 | 2026-10-05 | 2026-10-18 | 2026-10-19 | 2026-10-24 | 2026-10-24 | 2026-10-24 | 2026-10-30 | 2026-11-02 | 2026-11-03 | [6 empty] | 2026-11-05 | 2026-11-07 |  |  | 2026-11-09 | 2026-11-10 | 2026-11-12 | 2026-11-15 | 2026-11-15 | 66 | N/3 | Morad |  |  |  | AOP | Lace | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -1500 | [11 empty] | 47 | Nov'1
BS-NMT | 48914 | 13196052 | 1000 | 130 | 2026-08-19 | 2026-09-07 | LS Polo shirt w flat knit collar placket btn | Polo |  |  | 2026-10-21 | 2026-11-09 | 2026-11-10 | 2026-11-20 |  |  | 2026-11-28 | 2026-11-26 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-08 | 2026-12-09 |  |  |  |  | 2026-12-10 | 2026-12-12 |  |  | 2026-12-14 | 2026-12-17 | 2026-12-19 | 2026-12-21 | 2026-12-23 | 124 | S | Tomal | Nk |  | 1 combo nk Print |  |  | NFL3 |  |  | File Due | 0 | 0 | 0 | 0 | -1000 | [11 empty] | 52 | Dec'1
BS-ONS | 48283 4th | 22042341 | 4000 | 2782 | 2026-08-28 | 2026-09-05 | LS Swt shirt w cuff btm rib | Swt Shirt |  |  | 2026-09-25 | 2026-10-03 | 2026-10-06 | 2026-10-22 |  |  | 2026-10-26 | 2026-10-26 |  | 2026-11-02 | 2026-11-03 | 2026-11-05 | 2026-11-10 |  |  |  |  | 2026-11-12 | 2026-11-14 |  |  | 2026-11-17 | 2026-11-19 | 2026-11-20 | 2026-12-14 | 2026-12-16 | 108 | E | Shakel | Fr,Bk |  | black parks-2008 pcs,,vintage khaki-2008 pcs both combo frt 1 clr rub back 1 clr rub 1 clr puff |  |  | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -4000 | [11 empty] | 51 | Nov'1
BS-ONS | 48949 | 22041275 | 912 | 270 | 2026-08-25 | 2026-09-07 | SS O nk TS w frt half placket btn frt pkt and nk arm hem raw edge | TS |  |  | 2026-10-02 | 2026-10-08 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-05 | 2026-11-05 | 2026-11-11 | 2026-11-13 | 2026-11-14 | 2026-11-16 | 2026-11-17 |  |  |  |  | 2026-11-19 | 2026-11-21 | 2026-11-23 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-27 | 2026-12-05 | 2026-12-07 | 102 | C | Shovon | Nk |  | c.dan-456 pcs,,oak-456 pcs both nk patch label print |  | Trumble wash for raw edge | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -912 | [11 empty] | 50 | Nov'2
BS-ONS | 48199 6th | 22042193 | 11264 | 2811 | 2026-09-07 | 2026-09-11 | SS o nk TS w nk rib | TS |  |  | 2026-09-28 | 2026-10-06 | 2026-10-07 | 2026-10-24 |  |  | 2026-10-27 | 2026-10-27 |  | 2026-11-04 | 2026-11-09 | 2026-11-09 | 2026-11-13 |  |  |  |  | 2026-11-16 | 2026-11-20 |  |  | 2026-11-23 | 2026-11-25 | 2026-11-27 | 2026-11-30 | 2026-12-02 | 84 | W1 | Shovon | Heat Press/Heat Seal |  | 4 combo nk HP |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -11264 | [11 empty] | 49 | Nov'1
BS-ONS | 48950 | 22041488 | 630 | 368 | 2026-08-25 | 2026-09-07 | LS Swt hoody w cuff btm rib and kangaroo pkt | Hoody |  |  | 2026-10-03 | 2026-10-09 | 2026-10-15 | 2026-10-30 |  |  | 2026-11-11 | 2026-11-11 | 2026-11-17 | 2026-11-20 | 2026-11-21 | 2026-11-24 | 2026-11-27 |  |  |  |  | 2026-12-01 | 2026-12-02 |  |  | 2026-12-04 | 2026-12-07 | 2026-12-10 | 2026-12-21 | 2026-12-23 | 118 | C | Shovon | Fr,Bk |  | Ashey blue-630 pcs frt back 1 clr rub print |  |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -630 | [11 empty] | 52 | Nov'2
BS-ONL | 48965 | 15400705 | 18960 | 3950 | 2026-09-03 | 2026-09-05 | LS Cardigan w full placket btn | Cardigan |  |  | 2026-09-23 | 2026-10-08 | 2026-10-10 | 2026-10-27 |  |  | 2026-10-30 | 2026-10-30 | 2026-11-06 | 2026-11-09 | 2026-11-14 | [6 empty] | 2026-11-13 | 2026-11-21 |  |  | 2026-11-23 | 2026-11-25 | 2026-11-26 | 2026-11-30 | 2026-12-02 | 88 | D | Dalim | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -18960 | [11 empty] | 49 | Nov'1
BS-ONL | 41836 12th | 15343893 | 1400 | 269 | 2026-09-03 | 2026-09-05 | SS o nk TS | TS |  |  | 2026-10-01 | 2026-10-05 | 2026-10-13 | 2026-10-27 |  |  | 2026-11-04 | 2026-11-04 |  | 2026-11-10 | 2026-11-11 | [6 empty] | 2026-11-16 | 2026-11-17 |  |  | 2026-11-19 | 2026-11-21 | 2026-11-25 | 2026-12-21 | 2026-12-23 | 109 | ZA1 | Dalim | [5 empty] | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1400 | [11 empty] | 52 | Nov'1
BS-ONL | 48833 2nd | 15373005 | 7858 | 661 | 2026-08-24 | 2026-09-05 | Rib Tank top w gmts dye acid wash | Tank Top |  |  | 2026-09-28 | 2026-10-05 | 2026-10-14 | 2026-10-30 |  |  | 2026-11-04 | 2026-11-04 |  | 2026-11-10 | 2026-11-14 |  |  |  |  | 2026-11-15 | 2026-11-28 | 2026-11-27 | 2026-11-28 | 2026-11-27 | 2026-12-06 | 2026-12-15 | 2026-12-17 | 2026-12-18 | 2026-12-19 | 2026-12-21 | 117 | L2 | Abid |  | Chest | c.dan no wash-288 pcs 1 clr flat all over emb ,,bel air blue wash -1120 pcs 1 clr flat emb ,,snow wash-2094 pcs 1 clr flat emb,, purple wash-3024 pcs 1 clr flat emb,,night sky wash-1332 pcs 1 clr flat emb |  | all comb without c.dan clr gmts dye acid wash | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -7858 | [11 empty] | 52 | Nov'1
BS-ONL | 48850 | 15389920 | 1524 | 419 | 2026-08-24 | 2026-09-07 | SL Dress w bmt cut&sew double layer and Imp metal buckle | Dress |  |  | 2026-10-10 | 2026-10-15 | 2026-10-24 | 2026-10-10 |  |  | 2026-11-14 | 2026-11-14 | 2026-11-21 | 2026-11-25 | 2026-11-26 | [6 empty] | 2026-12-01 | 2026-12-03 |  |  | 2026-12-05 | 2026-12-09 | 2026-12-12 | 2026-12-21 | 2026-12-23 | 119 | J | Abid |  |  |  |  | Imp Metal buckle | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -1524 | [11 empty] | 52 | Nov'3
OVS SPA | 48524 | 271TNKFTT536-6172 | 4035 | 622 | 2026-09-02 | 2026-09-07 | Square nk Rib tank Top | Tank Top |  |  | 2026-10-17 | 2026-10-30 | 2026-11-02 | 2026-11-14 |  |  | 2026-11-21 | 2026-11-20 | 2026-11-25 | 2026-11-26 | 2026-11-28 | [6 empty] | 2026-12-01 | 2026-12-07 |  |  | 2026-12-08 | 2026-12-09 | 2026-12-11 | 2026-12-14 | 2026-12-14 | 103 | G1 | Shaker | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -4035 | [11 empty] | 51 | Nov'3
OVS SPA | 47858 | 271TSH033TS33-6198 | 25866 | 1090 | 2026-08-28 | 2026-09-07 | SS roll slve TS w frt pkt | TS |  |  | 2026-10-10 | 2026-10-30 | 2026-11-02 | 2026-11-21 |  |  | 2026-12-01 | 2026-11-25 | 2026-11-30 | 2026-12-01 | 2026-12-11 | [6 empty] | 2026-12-08 | 2026-12-24 |  |  | 2026-12-25 | 2026-12-26 | 2026-12-28 | 2026-12-29 | 2026-12-29 | 123 | F | Khairul | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -25866 | [11 empty] | 53 | Dec'1
OVS SPA | 48492 | 271TSH035TS35-6198 | 6668 | 1570 | 2026-08-27 | 2026-09-07 | YD SS o nk TS | TS | 2026-10-19 | 2026-10-31 | 2026-11-02 | 2026-11-12 | 2026-11-13 | 2026-11-21 |  |  | 2026-12-05 | 2026-12-04 | 2026-12-09 | 2026-12-10 | 2026-12-12 | [6 empty] | 2026-12-14 | 2026-12-19 |  |  | 2026-12-21 | 2026-12-23 | 2026-12-25 | 2026-12-29 | 2026-12-29 | 124 | G1 | Khairul |  |  |  | YD |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -6668 | [11 empty] | 53 | Dec'1
OVS SPA | 47859 | 271TSH088TS88-6198 | 15137 | 2745 | 2026-08-28 | 2026-09-07 | SS double nk TS | TS |  |  | 2026-10-20 | 2026-11-05 | 2026-11-06 | 2026-11-25 |  |  | 2026-12-01 | 2026-11-24 | 2026-11-30 | 2026-12-01 | 2026-12-07 |  |  |  |  | 2026-12-04 | 2026-12-12 | 2026-12-11 | 2026-12-19 |  |  | 2026-12-21 | 2026-12-23 | 2026-12-25 | 2026-12-29 | 2026-12-29 | 123 | G1 | Khairul |  | Nk | brush-3531 pcs,,black-3531 pcs,,yellow-3025 pcs,,sage-3025 pcs,,chestnut-2025 pcs all combo nk Line 1 clr flat emb |  |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -15137 | [11 empty] | 53 | Dec'1
OVS SPA | 47860 | 271TSH090TS90-6198 | 15137 | 2430 | 2026-08-28 | 2026-09-07 | SS V shape double nk TS | TS |  |  | 2026-10-15 | 2026-10-30 | 2026-11-02 | 2026-11-24 |  |  | 2026-12-01 | 2026-11-24 | 2026-11-30 | 2026-12-01 | 2026-12-07 | [6 empty] | 2026-12-08 | 2026-12-17 |  |  | 2026-12-18 | 2026-12-21 | 2026-12-23 | 2026-12-29 | 2026-12-29 | 123 | G2 | Khairul | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -15137 | [11 empty] | 53 | Dec'1
OVS SPA | 47843 | 271TSH190-6156 | 5866 | 1180 | 2026-08-31 | 2026-09-11 | SS o nk TS w side slit and back side printed label attach | TS |  |  | 2026-10-01 | 2026-10-10 | 2026-10-14 | 2026-10-28 |  |  | 2026-11-20 | 2026-11-11 | 2026-11-18 | 2026-11-19 | 2026-11-21 |  |  |  |  | 2026-11-25 | 2026-11-30 | 2026-12-01 | 2026-12-05 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-11 | 2026-12-14 | 2026-12-14 | 105 | D1 | Khairul |  | Chest | off white-5866 pcs fr 1 clr flat emb |  |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -5866 | [11 empty] | 51 | Nov'2
OVS SPA | 47847 | 271TSH191-6156 | 2674 | 470 | 2026-08-31 | 2026-09-11 | SS TS w double layer collar placket and side slit w front pkt w btn | TS |  |  | 2026-10-20 | 2026-10-30 | 2026-11-02 | 2026-11-13 |  |  | 2026-11-20 | 2026-11-14 | 2026-11-20 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-30 |  |  |  |  | 2026-12-01 | 2026-12-05 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-11 | 2026-12-14 | 2026-12-14 | 105 | N/2 | Khairul | Pkt |  | off white-2674 pcs 1 clr pig all over block wise placement print full pkt only |  |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -2674 | [11 empty] | 51 | Nov'3
OVS SPA | 47848 | 271TSH192-6156 | 4039 | 820 | 2026-08-31 | 2026-09-11 | YD SS o nk TS w contrast nk Tape | TS | 2026-10-01 | 2026-10-10 | 2026-10-12 | 2026-10-20 | 2026-10-26 | 2026-11-05 |  |  | 2026-11-20 | 2026-11-14 | 2026-11-20 | 2026-11-21 | 2026-11-24 |  |  |  |  | 2026-11-25 | 2026-11-30 | 2026-12-01 | 2026-12-05 |  |  | 2026-12-07 | 2026-12-09 | 2026-12-11 | 2026-12-14 | 2026-12-14 | 105 | F | Khairul |  | Slv | white/blue-4039 pcs 1 clr flat emb at one slve | YD |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -4039 | [11 empty] | 51 | Nov'3
GBX-Maurices | 48971 | 2598532/4258532 | 25226 | 7159 | 2026-09-10 | 2026-09-12 | SS Crew nk TS w btm Knot | TS |  |  | 2026-09-25 | 2026-10-18 | 2026-10-06 | 2026-10-24 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-28 | 2026-10-30 | 2026-11-06 | 2026-11-16 | 2026-12-02 |  |  | 2026-11-02 | 2026-11-14 | 2026-11-12 | 2026-11-30 |  |  | 2026-12-03 | 2026-12-05 | 2026-12-07 | 2026-12-10 | 2026-12-10 | 91 | N/1 | Mannan | Heat Press/Heat Seal | Chest | Thyme core-17658 pcs,,plus-7568 pcs both 1 clr cording emb and nk HP label |  |  | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -25226 | [11 empty] | 50 | Oct'3
GBX-Maurices | 48734 | 2521751/4701751 | 16485 | 4902 | 2026-09-10 | 2026-09-12 | SS reglan Slve TS w curve btm hem w bk btm cut&sew and gmts burn wash | TS | 2026-10-26: 2026-10-05; 2026-11-05: 2026-10-22 |  |  | 2026-10-26 | 2026-10-26 | 2026-11-06 | 2026-11-10 | 2026-11-15 | 2026-11-24 | 2026-12-03 |  |  |  |  | 2026-11-13 | 2026-11-26 | 2026-11-18 | 2026-11-30 | 2026-12-06 | 2026-12-07 | 2026-12-08 | 2026-12-10 | 2026-12-10 | 91 | N/1 | Mannan | Heat Press/Heat Seal |  | 1 combo nk HP label |  | Gmts burn wash | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -16485 | [11 empty] | 50 | Nov'1
BS-NMT | 48939 2nd | 13265710 | 2240 | 306 | 2026-09-02 | 2026-09-07 | SS O nk Dress w btm mesh | Dress |  |  | 2026-10-26 | 2026-10-30 | 2026-11-10 | 2026-11-24 |  |  | 2026-12-01 | 2026-12-01 |  | 2026-12-07 | 2026-12-09 | [6 empty] | 2026-12-12 | 2026-12-15 |  |  | 2026-12-18 | 2026-12-19 | 2026-12-24 | 2027-01-11 | 2027-01-13 | 131 | S | Jafar | [5 empty] | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -2240 | [11 empty] | 3 | Dec'1
BS-NMT | 44843 6th | 13251915 | 4560 | 460 | 2026-09-02 | 2026-09-07 | GIRLS SS TS | TS |  |  | 2026-10-10 | 2026-10-16 | 2026-10-25 | 2026-11-10 |  |  | 2026-11-18 | 2026-11-18 |  | 2026-11-25 | 2026-11-27 | 2026-12-01 | 2026-12-03 |  |  | 2026-12-01 | 2026-12-08 | 2026-12-10 | 2026-12-14 |  |  | 2026-12-17 | 2026-12-21 | 2026-12-24 | 2027-01-25 | 2027-01-27 | 145 | ZA2 | Jafar | Nk | Chest | blue-2040 pcs,,fairy-2520 pcs both combo chest 2 clr flat all over emb |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -4560 | [11 empty] | 5 | Nov'3
BS-NMT | 48938 2nd | 13265708 | 2100 | 184 | 2026-09-02 | 2026-09-07 | SS O nk Body w btm snap btn | Body |  |  | 2026-10-10 | 2026-10-15 | 2026-10-25 | 2026-11-07 |  |  | 2026-11-12 | 2026-11-12 |  | 2026-11-18 | 2026-11-20 | 2026-11-24 | 2026-11-26 |  |  | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-10 |  |  | 2026-12-12 | 2026-12-15 | 2026-12-20 | 2027-01-04 | 2027-01-06 | 124 | Y | Jafar | Nk | Chest | blue-2100 pcs 1 clr flat all over emb at chest |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -2100 | [11 empty] | 2 | Nov'2
BS-NMT | 48936 2nd | 13259417 | 2500 | 333 | 2026-09-02 | 2026-09-07 | SS boat nk wrap shlder TS w side seam gathering | TS |  |  | 2026-10-10 | 2026-10-15 | 2026-10-25 | 2026-11-10 |  |  | 2026-11-18 | 2026-11-18 |  | 2026-11-25 | 2026-11-27 | 2026-12-02 | 2026-12-04 |  |  |  |  | 2026-12-08 | 2026-12-11 |  |  | 2026-12-15 | 2026-12-18 | 2026-12-24 | 2027-01-11 | 2027-01-13 | 131 | Z | Jafar | Nk |  | 2 combo label print |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -2500 | [11 empty] | 3 | Nov'3
BS-NMT | 45576 6th | 13215107 | 9480 | 1265 | 2026-09-02 | 2026-09-07 | SS AOP capsl dress | Dress |  |  | 2026-10-10 | 2026-10-20 | 2026-11-02 | 2026-11-17 | 2026-11-18 | 2026-11-30 | 2026-12-08 | 2026-12-08 |  | 2026-12-14 | 2026-12-18 | 2026-12-18 | 2026-12-22 |  |  |  |  | 2026-12-24 | 2026-12-30 |  |  | 2027-01-03 | 2027-01-05 | 2027-01-10 | 2027-01-25 | 2027-01-27 | 145 | V | Jafar | Nk |  | 4 combo label print | AOP |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -9480 | [11 empty] | 5 | Dec'2
BS-NMT | 45586 4th | 13240424 | 1020 | 178 | 2026-09-02 | 2026-09-07 | Long Tank Top | Tank Top |  |  | 2026-11-15 | 2026-11-18 | 2026-12-01 | 2026-12-12 |  |  | 2026-12-15 | 2026-12-15 |  | 2026-12-22 | 2026-12-23 | 2026-12-25 | 2026-12-26 |  |  |  |  | 2027-01-01 | 2027-01-02 |  |  | 2027-01-04 | 2027-01-08 | 2027-01-15 | 2027-02-08 | 2027-02-10 | 159 | ZA1 | Jafar | Nk |  | 1 combo label print |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1020 | [11 empty] | 7 | Dec'3
BS-NMT | 45584 6th | 13236672 | 13260 | 1413 | 2026-09-02 | 2026-09-07 | Tank Top | Tank Top |  |  | 2026-10-22 | 2026-10-30 | 2026-11-13 | 2026-11-30 |  |  | 2026-12-10 | 2026-12-10 |  | 2026-12-18 | 2026-12-22 | 2026-12-24 | 2026-12-28 |  |  |  |  | 2027-01-01 | 2027-01-05 |  |  | 2027-01-08 | 2027-01-12 | 2027-01-17 | 2027-02-01 | 2027-02-03 | 152 | G1 | Jafar | NK |  | 5 combo label print |  |  | NFL1 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -13260 | [11 empty] | 6 | Dec'2
BS-NMT | 45581 6th | 13228199 | 12640 | 933 | 2026-09-02 | 2026-09-07 | Short Leggings | Legging |  |  | 2026-10-25 | 2026-10-30 | 2026-11-10 | 2026-11-28 |  |  | 2026-12-05 | 2026-12-05 |  | 2026-12-10 | 2026-12-14 | 2026-12-14 | 2026-12-18 |  |  |  |  | 2026-12-21 | 2026-12-26 |  |  | 2026-12-29 | 2027-01-02 | 2027-01-07 | 2027-02-01 | 2027-01-03 | 152 | W2 | Jafar | Waist |  | 5 combo label print |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -12640 | [11 empty] | 2 | Dec'1
BS-NMT | 45589 4th | 13241233 | 2040 | 323 | 2026-09-02 | 2026-09-07 | SS o nk TS w nk Rib Gmts dye acid wash | TS |  |  | 2026-10-15 | 2026-10-18 | 2026-11-02 | 2026-11-09 |  |  | 2026-11-12 | 2026-11-12 |  | 2026-11-19 | 2026-11-20 | 2026-12-09 | 2026-12-11 |  |  |  |  | 2026-11-24 | 2026-11-25 | 2026-12-05 | 2026-12-08 | 2026-12-15 | 2026-12-18 | 2026-12-25 | 2027-02-01 | 2027-02-03 | 152 | ZA2 | Jafar | Chest |  | blue-2040 pcs 2 clr HD print |  | Gmts dye acid wash | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -2040 | [11 empty] | 6 | Nov'2
BS-NMT | 45590 4th | 13241260 | 4320 | 1129 | 2026-09-02 | 2026-09-07 | Shorts pant w adj waist belt pocket drawstring gmts dye acid wash | Shorts |  |  | 2026-10-24 | 2026-10-30 | 2026-11-10 | 2026-11-20 |  |  | 2026-11-30 | 2026-11-27 |  | 2026-12-07 | 2026-12-10 | 2026-12-29 | 2027-01-05 |  |  |  |  | 2026-12-14 | 2026-12-19 | 2026-12-21 | 2026-12-31 | 2027-01-09 | 2027-01-11 | 2027-01-14 | 2027-02-01 | 2027-02-03 | 152 | X | Jafar | Thigh |  | blue-2820 pcs,,green-1500 pcs all combo 2 clr HD print |  | Gmts dye acid wash | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -4320 | [11 empty] | 6 | Dec'1
BS-NMT | 45574 5th | 13201014 | 4640 | 488 | 2026-09-02 | 2026-09-07 | Solid legging w waist elastic | Legging |  |  | 2026-11-02 | 2026-11-07 | 2026-11-13 | 2026-11-30 |  |  | 2026-12-08 | 2026-12-08 |  | 2026-12-14 | 2026-12-15 | 2026-12-19 | 2026-12-21 |  |  |  |  | 2026-12-24 | 2026-12-26 |  |  | 2026-12-29 | 2027-01-03 | 2027-01-08 | 2027-02-01 | 2027-02-03 | 152 | W2 | Jafar | Waist |  | 4 combo label print |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -4640 | [11 empty] | 6 | Dec'2
BS-NMT | 45596 3rd | 13258062 | 3220 | 728 | 2026-09-02 | 2026-09-07 | Long Tank top dress w side slit | Dress |  |  | 2026-10-20 | 2026-10-26 | 2026-11-05 | 2026-11-20 |  |  | 2026-12-03 | 2026-12-03 |  | 2026-12-11 | 2026-12-12 | 2026-12-15 | 2026-12-17 |  |  |  |  | 2026-12-21 | 2026-12-24 |  |  | 2026-12-28 | 2026-12-30 | 2027-01-05 | 2027-02-01 | 2027-02-03 | 152 | V | Jafar | Nk |  | 2 combo label print |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -3220 | [11 empty] | 6 | Dec'2
BS-NMT | 45573 6th | 13191810 | 13200 | 980 | 2026-09-02 | 2026-09-07 | Short Leggings w waist elatic | Legging |  |  | 2026-10-25 | 2026-10-30 | 2026-11-12 | 2026-11-30 |  |  | 2026-12-10 | 2026-12-10 |  | 2026-12-15 | 2026-12-18 | 2026-12-22 | 2026-12-26 |  |  |  |  | 2027-01-01 | 2027-01-05 |  |  | 2027-01-08 | 2027-01-12 | 2027-01-18 | 2027-02-08 | 2027-02-10 | 159 | W2 | Jafar | Waist |  | 76 combo label print |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -13200 | [11 empty] | 7 | Dec'2
BS-NMT | 48937 2nd | 13265705 | 1100 | 101 | 2026-09-02 | 2026-09-07 | SS O nk Body w btm snap btn | Body |  |  | 2026-11-05 | 2026-11-10 | 2026-11-18 | 2026-11-30 |  |  | 2026-12-11 | 2026-12-11 |  | 2026-12-17 | 2026-12-18 | 2026-12-23 | 2026-12-24 |  |  | 2026-12-22 | 2026-12-28 | 2027-01-01 | 2027-01-02 |  |  | 2027-01-07 | 2027-01-09 | 2027-01-15 | 2027-02-01 | 2027-02-03 | 152 | Y | Jafar | Nk | Chest | fairy-1100 pcs 1 clr flat all over emb at chest |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1100 | [11 empty] | 6 | Dec'2
BS-NMT | 48940 2nd | 13265711 | 3000 | 218 | 2026-09-02 | 2026-09-07 | Ealstic waist shorts w herringbone drawstring | Shorts |  |  | 2026-11-02 | 2026-11-07 | 2026-11-13 | 2026-11-28 |  |  | 2026-12-05 | 2026-12-05 |  | 2026-12-12 | 2026-12-15 | 2026-12-18 | 2026-12-21 |  |  | 2026-12-17 | 2026-12-26 | 2027-01-01 | 2027-01-03 |  |  | 2027-01-05 | 2027-01-09 | 2027-01-14 | 2027-02-01 | 2027-02-03 | 152 | W2 | Jafar | Waist | AOE | blue-1500 pcs,,fairy-1500 pcs both combo frt 2 part 2 clr flat all over emb |  |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -3000 | [11 empty] | 6 | Dec'2
BS-NMT | 45579 6th | 13218694 | 3060 | 679 | 2026-09-02 | 2026-09-07 | SS YD Dress w waist elastic | Dress | 2026-10-18 | 2026-10-26 | 2026-11-05 | 2026-11-17 | 2026-11-27 | 2026-11-30 |  |  | 2026-12-12 | 2026-12-12 |  | 2026-12-18 | 2026-12-22 | 2026-12-24 | 2026-12-26 |  |  |  |  | 2027-01-01 | 2027-01-03 |  |  | 2027-01-07 | 2027-01-10 | 2027-01-15 | 2027-02-15 | 2027-02-17 | 166 | V | Jafar | Nk |  | 3 combo label print | YD |  | NFL3 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -3060 | [11 empty] | 8 | Dec'2
BS-ONS | 48951 | 22041268 | 7538 | 1927 | 2026-08-25 | 2026-09-07 | Rib SS O nk TS | TS |  |  | 2026-10-10 | 2026-10-20 | 2026-11-02 | 2026-11-18 |  |  | 2026-11-24 | 2026-11-24 | 2026-12-01 | 2026-12-03 | 2026-12-08 | [6 empty] | 2026-12-08 | 2026-12-12 |  |  | 2026-12-15 | 2026-12-18 | 2026-12-22 | 2027-01-03 | 2027-01-05 | 131 | F | Shovon | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -7538 | [11 empty] | 2 | Dec'1
BS-ONL | 48960 | 15247717 | 15520 | 3862 | 2026-09-02 | 2026-09-07 | YD & AOP SS Long May dress w waist self fabric string | Dress | 2026-10-13 | 2026-10-22 | 2026-10-23 | 2026-11-08 | 2026-11-13 | 2026-11-28 | 2026-12-03 | 2026-12-10 | 2026-12-15 | 2026-12-15 | 2026-12-23 | 2026-12-26 | 2027-01-01 | [6 empty] | 2027-01-01 | 2027-01-12 |  |  | 2027-01-15 | 2027-01-18 | 2027-01-23 | 2027-02-08 | 2027-02-10 | 159 | Q | Mainul |  |  |  | YD & AOP |  | NFL2 |  |  | File Due | 0 | 0 | 0 | 0 | -15520 | [11 empty] | 7 | Dec'3
BS-ONL | 48229 2nd | 15325769 | 1840 | 331 | 2026-09-09 | 2026-09-12 | SS Long dresss w shlder Woven emb lace | Dress |  |  | 2026-10-17 | 2026-10-22 | 2026-11-05 | 2026-11-17 |  |  | 2026-11-20 | 2026-11-20 |  | 2026-11-25 | 2026-11-27 | [6 empty] | 2026-12-01 | 2026-12-03 |  |  | 2026-12-05 | 2026-12-08 | 2026-12-11 | 2027-01-11 | 2027-01-13 | 124 | K | Abid |  |  |  |  | Lace | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1840 | [11 empty] | 3 | Nov'3
BS-ONL | 48225 2nd | 15374431 | 1560 | 195 | 2026-09-09 | 2026-09-12 | Tank Top | Tank Top |  |  | 2026-10-16 | 2026-10-20 | 2026-11-02 | 2026-11-14 |  |  | 2026-11-20 | 2026-11-20 |  | 2026-11-26 | 2026-11-27 | [6 empty] | 2026-12-01 | 2026-12-02 |  |  | 2026-12-04 | 2026-12-07 | 2026-12-14 | 2027-01-11 | 2027-01-13 | 124 | O1 | Abid | [5 empty] | NFL2 |  |  | Po Sheet Due | 0 | 0 | 0 | 0 | -1560 | [11 empty] | 3 | Nov'3
OVS SPA | 48521 | 271TNKFTT539-6172 | 9099 | 1744 | 2026-09-02 | 2026-09-07 | Rib Tank top | Tank Top |  |  | 2026-11-02 | 2026-11-13 | 2026-11-14 | 2026-11-30 |  |  | 2026-12-15 | 2026-12-14 | 2026-12-19 | 2026-12-21 | 2026-12-23 | [6 empty] | 2026-12-24 | 2026-12-31 |  |  | 2027-01-01 | 2027-01-04 | 2027-01-06 | 2027-01-12 | 2027-01-12 | 132 | G1 | Shaker | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -9099 | [11 empty] | 3 | Dec'3
OVS SPA | 48522 | 271TNKFTT429-6172 | 4839 | 1228 | 2026-09-02 | 2026-09-07 | YD Rib Tank top | Tank Top | 2026-11-02 | 2026-11-12 | 2026-11-13 | 2026-11-21 | 2026-11-23 | 2026-12-03 |  |  | 2026-12-18 | 2026-12-17 | 2026-12-22 | 2026-12-23 | 2026-12-25 | [6 empty] | 2026-12-26 | 2026-12-31 |  |  | 2027-01-01 | 2027-01-04 | 2027-01-06 | 2027-01-12 | 2027-01-12 | 132 | G2 | Shaker |  |  |  | YD |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -4839 | [11 empty] | 3 | Dec'3
OVS SPA | 48523 | 271TNKFTT541-6172 | 3639 | 485 | 2026-09-02 | 2026-09-07 | Rib Tank top w frt placket btn and nk lace attach | Tank Top |  |  | 2026-11-02 | 2026-11-12 | 2026-11-14 | 2026-11-28 |  |  | 2026-12-22 | 2026-12-21 | 2026-12-25 | 2026-12-26 | 2026-12-28 | [6 empty] | 2026-12-29 | 2027-01-05 |  |  | 2027-01-06 | 2027-01-07 | 2027-01-09 | 2027-01-12 | 2027-01-12 | 132 | A | Shaker |  |  |  |  | Lace | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -3639 | [11 empty] | 3 | Dec'3
OVS SPA | 48579 | 271MBW006TANKMB-6116 | 14165 | 4556 | 2026-08-28 | 2026-09-07 | SL V nk Maxi tank top Dress | Dress |  |  | 2026-11-10 | 2026-11-26 | 2026-11-27 | 2026-12-17 |  |  | 2026-12-31 | 2026-12-30 | 2027-01-04 | 2027-01-05 | 2027-01-12 | [6 empty] | 2027-01-11 | 2027-01-25 |  |  | 2027-01-26 | 2027-01-28 | 2027-01-30 | 2027-02-05 | 2027-02-05 | 161 | A | Basir | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -14165 | [11 empty] | 6 | Jan'1
OVS SPA | 48581 | 271MBW018PIQ1-6116 | 9671 | 3812 | 2026-08-28 | 2026-09-07 | SS o nk Beachwear Dress | Dress |  |  | 2026-11-10 | 2026-11-25 | 2026-11-26 | 2026-12-14 |  |  | 2026-12-31 | 2027-01-01 | 2027-01-05 | 2027-01-06 | 2027-01-13 | [6 empty] | 2027-01-11 | 2027-01-22 |  |  | 2027-01-23 | 2027-01-26 | 2027-01-28 | 2027-02-05 | 2027-02-05 | 161 | C | Basir | [5 empty] | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -9671 | [11 empty] | 6 | Jan'1
OVS SPA | 48580 | 271MBW007TANKM-6116 | 7833 | 2043 | 2026-08-28 | 2026-09-07 | SL V nk Maxi beachwear tank top Dress | Dress |  |  | 2026-11-10 | 2026-11-23 | 2026-12-01 | 2026-12-17 |  |  | 2026-12-31 | 2027-01-01 | 2027-01-05 | 2027-01-06 | 2027-01-13 | [6 empty] | 2027-01-11 | 2027-01-22 |  |  | 2027-01-23 | 2027-01-26 | 2027-01-28 | 2027-02-05 | 2027-02-05 | 161 | N/3 | Basir | [5 empty] | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -7833 | [11 empty] | 6 | Jan'1
OVS SPA | 48930 | 271MBW016AMZIC-6116 | 13635 | 2954 | 2026-08-28 | 2026-09-07 | SL V nk TS Dress w sequin Lace at nk | Dress |  |  | 2026-11-16 | 2026-11-30 | 2026-12-01 | 2026-12-17 |  |  | 2026-12-31 | 2027-01-01 | 2027-01-05 | 2027-01-06 | 2027-01-13 | [6 empty] | 2027-01-11 | 2027-01-22 |  |  | 2027-01-23 | 2027-01-26 | 2027-01-28 | 2027-02-05 | 2027-02-05 | 161 | N/2 | Basir |  |  |  |  | Lace | NCL |  |  | File Due | 0 | 0 | 0 | 0 | -13635 | [11 empty] | 6 | Jan'1
OVS SPA | 48582 | 271MBW017AMZ1P-6116 | 13735 | 3022 | 2026-08-28 | 2026-09-07 | SS V nk Night dress | Dress |  |  | 2026-11-16 | 2026-11-30 | 2026-12-01 | 2026-12-17 |  |  | 2027-01-04 | 2026-12-25 | 2027-01-02 | 2027-01-04 | 2027-01-08 | 2027-01-07 | 2027-01-15 |  |  |  |  | 2027-01-14 | 2027-01-26 |  |  | 2027-01-27 | 2027-01-29 | 2027-02-01 | 2027-02-12 | 2027-02-12 | 168 | E | Basir | Panel Print |  | black-3507 pcs,,peatch-3407 pcs,,green-2307 pcs,,brown-2307 pcs,,storm-2207 pcs all combo 1 clr puff print at front nk panel |  |  | NFL1 |  |  | File Due | 0 | 0 | 0 | 0 | -13735 | [11 empty] | 7 | Jan'1
Formulas:
Week = WEEKNUM([Cargo Closing Date],1)

## Summary (hidden)
Order | Fabrics Summary |  |  | Garment Division Summary
No Of Job | Require | Dyeing Delivery | Dyeing Delivery Bal | Order Qty | Cutting Qty | Cutting Bal | Print/Embr. Req Qty | Print/Embr. Send Qty | Print/Embr. Recv Qty | Print/Embr. Rcv Bal | Sewing Input Qty | Sewing Input Bal | Sewing Qty | Sewing Bal | Packing Qty | Packing Bal | Ship Qty | Ship Balance
182 | 168262 | 167435 | 827 | 911006 | 1001856 | -90850 |  | 970272 | -31584 | 1001856 | -545402 | 1456408 | -803697 | 1714703 | -820817 | 1731823 | 0 | 911006
Job No. | Finish Fabric Req (Kg) | Fabric Recv(kg) | Fabric Bal(Kg) | Order Qty | Print/Embr. Send | Print/Embro Recv | Print/Embro Recv Bal | Sewing Qty | Sewing Bal | Packing Qty | Packing Bal | Shipment Qty | Shipment Bal | Sum of Priority
22997 | 743 | 743 | 0 | 887 | 0 | 0 | 0 | 0 | -887 | 0 | -887 | 0 | -887
22998 | 2056 | 2056 | 0 | 2555 | 0 | 0 | 0 | 0 | -2555 | 0 | -2555 | 0 | -2555 | 0
23000 | 3209 | 3201 | -8 | 4159 | 0 | 0 | 0 | 0 | -4159 | 0 | -4159 | 0 | -4159 | 0
23001 | 848 | 848 | 0 | 1073 | 0 | 0 | 0 | 0 | -1073 | 0 | -1073 | 0 | -1073
23004 | 720 | 720 | 0 | 1686 | 3484 | 3484 | 0 | 1700 | 14 | 500 | -1186 | 710 | -976 | 0
23005 | 1844 | 1843 | -1 | 2454 | 5078 | 5070 | -8 | 0 | -2454 | 0 | -2454 | 0 | -2454 | 0
23009 | 4920 | 4863 | -57 | 18324 | 0 | 0 | 0 | 17018 | -1306 | 0 | -18324 | 0 | -18324 | 0
23011 | 376 | 376 | 0 | 4786 | 0 | 0 | 0 | 0 | -4786 | 0 | -4786 | 0 | -4786
23012 | 326 | 326 | 0 | 4786 | 0 | 0 | 0 | 0 | -4786 | 0 | -4786 | 0 | -4786
23013 | 178 | 178 | 0 | 2370 | 0 | 0 | 0 | 0 | -2370 | 0 | -2370 | 0 | -2370
23014 | 152 | 152 | 0 | 1875 | 0 | 0 | 0 | 0 | -1875 | 0 | -1875 | 0 | -1875
23015 | 268 | 268 | 0 | 3030 | 0 | 0 | 0 | 0 | -3030 | 0 | -3030 | 0 | -3030
23016 | 430 | 429 | -1 | 3600 | 0 | 0 | 0 | 0 | -3600 | 0 | -3600 | 0 | -3600
23017 | 213 | 213 | 0 | 2400 | 0 | 0 | 0 | 0 | -2400 | 0 | -2400 | 0 | -2400
23018 | 345 | 345 | 0 | 2400 | 0 | 0 | 0 | 0 | -2400 | 0 | -2400 | 0 | -2400
23019 | 148 | 148 | 0 | 2040 | 0 | 0 | 0 | 0 | -2040 | 0 | -2040 | 0 | -2040
23020 | 1073 | 1073 | 0 | 11700 | 0 | 0 | 0 | 0 | -11700 | 0 | -11700 | 0 | -11700
23021 | 399 | 399 | 0 | 4469 | 9216 | 9028 | -188 | 0 | -4469 | 0 | -4469 | 0 | -4469 | 0
23022 | 351 | 341 | -10 | 2649 | 5518 | 5396 | -122 | 2834 | 185 | 2692 | 43 | 2649 | 0
23023 | 280 | 272 | -8 | 2871 | 5976 | 5930 | -46 | 2938 | 67 | 2930 | 59 | 2881 | 10
23024 | 374 | 366 | -8 | 3349 | 6934 | 6832 | -102 | 3396 | 47 | 3349 | 0 | 3349 | 0
23025 | 617 | 617 | 0 | 6329 | 13150 | 13148 | -2 | 6505 | 176 | 6329 | 0 | 6329 | 0
23026 | 273 | 268 | -5 | 4305 | 8844 | 8792 | -52 | 0 | -4305 | 0 | -4305 | 0 | -4305
23027 | 97 | 97 | 0 | 1020 | 2128 | 2104 | -24 | 0 | -1020 | 0 | -1020 | 0 | -1020
23039 | 564 | 564 | 0 | 2862 | 0 | 0 | 0 | 3045 | 183 | 2862 | 0 | 2862 | 0 | 0
23040 | 444 | 444 | 0 | 2423 | 0 | 0 | 0 | 0 | -2423 | 0 | -2423 | 0 | -2423 | 0
23041 | 533 | 514 | -19 | 3504 | 7398 | 7398 | 0 | 0 | -3504 | 0 | -3504 | 0 | -3504
23042 | 182 | 182 | 0 | 1385 | 2824 | 2824 | 0 | 0 | -1385 | 0 | -1385 | 0 | -1385
23043 | 152 | 152 | 0 | 1500 | 0 | 0 | 0 | 1515 | 15 | 1500 | 0 | 1500 | 0
23044 | 232 | 232 | 0 | 870 | 0 | 0 | 0 | 880 | 10 | 870 | 0 | 870 | 0 | 0
23045 | 177 | 170 | -7 | 810 | 0 | 0 | 0 | 0 | -810 | 0 | -810 | 0 | -810 | 0
23046 | 339 | 339 | 0 | 1938 | 0 | 0 | 0 | 0 | -1938 | 0 | -1938 | 0 | -1938
23047 | 276 | 276 | 0 | 1092 | 0 | 0 | 0 | 0 | -1092 | 0 | -1092 | 0 | -1092
23048 | 494 | 494 | 0 | 1926 | 0 | 0 | 0 | 0 | -1926 | 0 | -1926 | 0 | -1926
23049 | 434 | 434 | 0 | 1005 | 0 | 0 | 0 | 0 | -1005 | 0 | -1005 | 0 | -1005
23050 | 222 | 222 | 0 | 705 | 0 | 0 | 0 | 0 | -705 | 0 | -705 | 0 | -705
23051 | 894 | 894 | 0 | 5220 | 0 | 0 | 0 | 0 | -5220 | 0 | -5220 | 0 | -5220
23052 | 995 | 985 | -10 | 5850 | 0 | 0 | 0 | 0 | -5850 | 0 | -5850 | 0 | -5850
23053 | 660 | 641 | -19 | 2370 | 0 | 0 | 0 | 0 | -2370 | 0 | -2370 | 0 | -2370
23054 | 165 | 165 | 0 | 600 | 0 | 0 | 0 | 0 | -600 | 0 | -600 | 0 | -600
23056 | 244 | 244 | 0 | 1536 | 0 | 0 | 0 | 0 | -1536 | 0 | -1536 | 0 | -1536
23057 | 256 | 253 | -3 | 1420 | 0 | 0 | 0 | 0 | -1420 | 0 | -1420 | 0 | -1420
23058 | 520 | 520 | 0 | 1365 | 0 | 0 | 0 | 1370 | 5 | 1365 | 0 | 1365 | 0 | 0
23059 | 525 | 525 | 0 | 1395 | 0 | 0 | 0 | 0 | -1395 | 0 | -1395 | 0 | -1395 | 0
23064 | 2065 | 2059 | -6 | 22230 | 33376 | 33344 | -32 | 8306 | -13924 | 5500 | -16730 | 0 | -22230 | 0
23066 | 455 | 455 | 0 | 4044 | 0 | 0 | 0 | 0 | -4044 | 0 | -4044 | 0 | -4044
23067 | 828 | 828 | 0 | 6990 | 0 | 0 | 0 | 0 | -6990 | 0 | -6990 | 0 | -6990
23070 | 534 | 534 | 0 | 2016 | 0 | 0 | 0 | 0 | -2016 | 0 | -2016 | 0 | -2016
23071 | 579 | 579 | 0 | 3024 | 0 | 0 | 0 | 0 | -3024 | 0 | -3024 | 0 | -3024
23072 | 1057 | 1057 | 0 | 3492 | 0 | 0 | 0 | 0 | -3492 | 0 | -3492 | 0 | -3492
23073 | 1444 | 1443 | -1 | 6951 | 0 | 0 | 0 | 0 | -6951 | 0 | -6951 | 0 | -6951
23074 | 652 | 652 | 0 | 5160 | 0 | 0 | 0 | 0 | -5160 | 0 | -5160 | 0 | -5160
23075 | 596 | 596 | 0 | 5112 | 0 | 0 | 0 | 0 | -5112 | 0 | -5112 | 0 | -5112
23077 | 1075 | 1074 | -1 | 9153 | 0 | 0 | 0 | 0 | -9153 | 0 | -9153 | 0 | -9153
23078 | 360 | 360 | 0 | 2010 | 0 | 0 | 0 | 0 | -2010 | 0 | -2010 | 0 | -2010
23080 | 739 | 739 | 0 | 4290 | 0 | 0 | 0 | 0 | -4290 | 0 | -4290 | 0 | -4290
23081 | 1125 | 1125 | 0 | 6168 | 0 | 0 | 0 | 0 | -6168 | 0 | -6168 | 0 | -6168
23082 | 657 | 653 | -4 | 4130 | 0 | 0 | 0 | 0 | -4130 | 0 | -4130 | 0 | -4130
23084 | 208 | 208 | 0 | 1608 | 0 | 0 | 0 | 0 | -1608 | 0 | -1608 | 0 | -1608
23086 | 600 | 600 | 0 | 5064 | 0 | 0 | 0 | 0 | -5064 | 0 | -5064 | 0 | -5064
23087 | 710 | 710 | 0 | 3819 | 0 | 0 | 0 | 0 | -3819 | 0 | -3819 | 0 | -3819
23088 | 916 | 914 | -2 | 2400 | 0 | 0 | 0 | 0 | -2400 | 0 | -2400 | 0 | -2400
23089 | 528 | 528 | 0 | 3096 | 0 | 0 | 0 | 0 | -3096 | 0 | -3096 | 0 | -3096
23090 | 605 | 605 | 0 | 4749 | 0 | 0 | 0 | 0 | -4749 | 0 | -4749 | 0 | -4749
23091 | 667 | 667 | 0 | 2163 | 0 | 0 | 0 | 0 | -2163 | 0 | -2163 | 0 | -2163
23092 | 559 | 558 | -1 | 3288 | 0 | 0 | 0 | 0 | -3288 | 0 | -3288 | 0 | -3288
23093 | 670 | 664 | -6 | 3654 | 7574 | 7566 | -8 | 3762 | 108 | 3702 | 48 | 3702 | 48
23094 | 1192 | 1192 | 0 | 4626 | 0 | 0 | 0 | 3510 | -1116 | 3000 | -1626 | 1566 | -3060
23096 | 363 | 362 | -1 | 1854 | 3826 | 3780 | -46 | 1908 | 54 | 1854 | 0 | 1854 | 0
23097 | 2645 | 2635 | -10 | 6594 | 13686 | 13616 | -70 | 6762 | 168 | 6594 | 0 | 6594 | 0
23098 | 670 | 659 | -11 | 3567 | 0 | 0 | 0 | 3712 | 145 | 3567 | 0 | 3567 | 0
23099 | 607 | 592 | -15 | 3585 | 0 | 0 | 0 | 0 | -3585 | 0 | -3585 | 0 | -3585
23100 | 540 | 521 | -19 | 2640 | 5372 | 5358 | -14 | 0 | -2640 | 0 | -2640 | 0 | -2640
23101 | 564 | 564 | 0 | 2520 | 5220 | 5128 | -92 | 2653 | 133 | 2520 | 0 | 2520 | 0
23102 | 551 | 551 | 0 | 2118 | 4386 | 4346 | -40 | 2162 | 44 | 2118 | 0 | 2118 | 0
23103 | 786 | 786 | 0 | 6048 | 12824 | 12482 | -342 | 6286 | 238 | 6048 | 0 | 6048 | 0
23104 | 234 | 234 | 0 | 4626 | 0 | 0 | 0 | 0 | -4626 | 0 | -4626 | 0 | -4626
23105 | 553 | 552 | -1 | 4590 | 9474 | 9374 | -100 | 0 | -4590 | 0 | -4590 | 0 | -4590
23106 | 428 | 428 | 0 | 4590 | 5234 | 5228 | -6 | 0 | -4590 | 0 | -4590 | 0 | -4590
23113 | 368 | 358 | -10 | 3066 | 6376 | 6272 | -104 | 3167 | 101 | 3066 | 0 | 1056 | -2010
23193 | 2900 | 2887 | -13 | 23198 | 47404 | 47220 | -184 | 23348 | 150 | 6500 | -16698 | 0 | -23198 | 0
23194 | 3559 | 3373 | -186 | 27120 | 55892 | 55888 | -4 | 25873 | -1247 | 0 | -27120 | 0 | -27120 | 0
23281 | 808 | 800 | -8 | 2736 | 0 | 0 | 0 | 0 | -2736 | 0 | -2736 | 0 | -2736
23282 | 933 | 927 | -6 | 4608 | 0 | 0 | 0 | 0 | -4608 | 0 | -4608 | 0 | -4608
23289 | 691 | 691 | 0 | 2982 | 0 | 0 | 0 | 0 | -2982 | 0 | -2982 | 0 | -2982
23293 | 212 | 212 | 0 | 2006 | 0 | 0 | 0 | 0 | -2006 | 0 | -2006 | 0 | -2006
23311 | 3765 | 3724 | -41 | 17770 | 35058 | 34998 | -60 | 18494 | 724 | 0 | -17770 | 0 | -17770 | 0
23313 | 4104 | 4064 | -40 | 19704 | 40118 | 40110 | -8 | 20233 | 529 | 0 | -19704 | 0 | -19704 | 0
23674 | 24345 | 24345 | 0 | 93967 | 193030 | 191126 | -1904 | 81618 | -12349 | 0 | -93967 | 0 | -93967 | 0
23677 | 364 | 364 | 0 | 3000 | 0 | 0 | 0 | 0 | -3000 | 0 | -3000 | 0 | -3000
19398 3rd | 0 | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | -3750 | 0 | -3750 | 0 | -3750
19398 4th | 0 | 0 | 0 | 12080 | 0 | 0 | 0 | 12378 | 298 | 12150 | 70 | 10728 | -1352
23030 | 728 | 728 | 0 | 6447 | 0 | 0 | 0 | 0 | -6447 | 0 | -6447 | 0 | -6447
23033 | 493 | 493 | 0 | 4194 | 0 | 0 | 0 | 0 | -4194 | 0 | -4194 | 0 | -4194
23029 | 163 | 163 | 0 | 1500 | 0 | 0 | 0 | 0 | -1500 | 0 | -1500 | 0 | -1500
23037 | 802 | 802 | 0 | 3540 | 0 | 0 | 0 | 0 | -3540 | 0 | -3540 | 0 | -3540
23036 | 381 | 381 | 0 | 1848 | 0 | 0 | 0 | 0 | -1848 | 0 | -1848 | 0 | -1848
23032 | 1022 | 1022 | 0 | 8544 | 0 | 0 | 0 | 0 | -8544 | 0 | -8544 | 0 | -8544
23031 | 132 | 132 | 0 | 1080 | 0 | 0 | 0 | 1095 | 15 | 0 | -1080 | 0 | -1080
23034 | 711 | 708 | -3 | 7080 | 0 | 0 | 0 | 0 | -7080 | 0 | -7080 | 0 | -7080
23035 | 548 | 548 | 0 | 5580 | 0 | 0 | 0 | 0 | -5580 | 0 | -5580 | 0 | -5580
23028 | 74 | 74 | 0 | 1230 | 0 | 0 | 0 | 0 | -1230 | 0 | -1230 | 0 | -1230
23095 | 614 | 614 | 0 | 3153 | 6538 | 6396 | -142 | 3253 | 100 | 3153 | 0 | 3153 | 0
23287 | 810 | 789 | -21 | 2400 | 0 | 0 | 0 | 0 | -2400 | 0 | -2400 | 0 | -2400
23279 | 840 | 831 | -9 | 4752 | 0 | 0 | 0 | 0 | -4752 | 0 | -4752 | 0 | -4752
23285 | 482 | 482 | 0 | 2496 | 0 | 0 | 0 | 0 | -2496 | 0 | -2496 | 0 | -2496
23288 | 812 | 812 | 0 | 5940 | 0 | 0 | 0 | 0 | -5940 | 0 | -5940 | 0 | -5940
23848 | 1462 | 1462 | 0 | 11570 | 0 | 0 | 0 | 0 | -11570 | 0 | -11570 | 0 | -11570 | 0
23849 | 1384 | 1383 | -1 | 7005 | 0 | 0 | 0 | 7252 | 247 | 7005 | 0 | 6705 | -300 | 0
23786 | 612 | 612 | 0 | 7725 | 15660 | 15652 | -8 | 7798 | 73 | 7795 | 70 | 7725 | 0
24029 | 1046 | 1044 | -2 | 2904 | 0 | 0 | 0 | 2158 | -746 | 0 | -2904 | 0 | -2904 | 0
24030 | 215 | 213 | -2 | 1005 | 2048 | 2040 | -8 | 0 | -1005 | 0 | -1005 | 0 | -1005 | 0
24035 | 469 | 465 | -4 | 3936 | 8100 | 8100 | 0 | 4052 | 116 | 0 | -3936 | 0 | -3936 | 0
24033 | 193 | 193 | 0 | 1005 | 2100 | 2100 | 0 | 0 | -1005 | 0 | -1005 | 0 | -1005 | 0
24028 | 998 | 998 | 0 | 2952 | 0 | 0 | 0 | 0 | -2952 | 0 | -2952 | 0 | -2952 | 0
23883 | 1196 | 1196 | 0 | 8996 | 18270 | 18244 | -26 | 0 | -8996 | 0 | -8996 | 0 | -8996 | 0
23918 | 1054 | 1053 | -1 | 3354 | 7042 | 6974 | -68 | 0 | -3354 | 0 | -3354 | 0 | -3354 | 0
23919 | 1412 | 1403 | -9 | 4115 | 8498 | 8494 | -4 | 0 | -4115 | 0 | -4115 | 0 | -4115 | 0
23855 | 967 | 967 | 0 | 6653 | 13600 | 0 | -13600 | 0 | -6653 | 0 | -6653 | 0 | -6653
23784 | 633 | 633 | 0 | 1167 | 0 | 0 | 0 | 0 | -1167 | 0 | -1167 | 0 | -1167 | 0
23830 | 1511 | 1511 | 0 | 4344 | 9000 | 8908 | -92 | 0 | -4344 | 0 | -4344 | 0 | -4344 | 0
23841 | 463 | 463 | 0 | 1820 | 3778 | 3778 | 0 | 0 | -1820 | 0 | -1820 | 0 | -1820 | 0
23894 | 295 | 295 | 0 | 2667 | 2668 | 2660 | -8 | 0 | -2667 | 0 | -2667 | 0 | -2667
23878 | 296 | 293 | -3 | 1656 | 3424 | 3414 | -10 | 0 | -1656 | 0 | -1656 | 0 | -1656 | 0
23879 | 724 | 721 | -3 | 3738 | 7708 | 7692 | -16 | 0 | -3738 | 0 | -3738 | 0 | -3738 | 0
23877 | 538 | 538 | 0 | 3177 | 6488 | 6460 | -28 | 0 | -3177 | 0 | -3177 | 0 | -3177 | 0
23886 | 373 | 373 | 0 | 2199 | 4592 | 4586 | -6 | 0 | -2199 | 0 | -2199 | 0 | -2199 | 0
23887 | 562 | 562 | 0 | 4194 | 8582 | 8576 | -6 | 0 | -4194 | 0 | -4194 | 0 | -4194 | 0
23885 | 274 | 274 | 0 | 1992 | 4112 | 3894 | -218 | 0 | -1992 | 0 | -1992 | 0 | -1992 | 0
23881 | 1289 | 1278 | -11 | 6720 | 13806 | 13772 | -34 | 0 | -6720 | 0 | -6720 | 0 | -6720 | 0
23892 | 728 | 725 | -3 | 4014 | 1662 | 1644 | -18 | 0 | -4014 | 0 | -4014 | 0 | -4014
23889 | 1043 | 1043 | 0 | 2514 | 5142 | 5136 | -6 | 0 | -2514 | 0 | -2514 | 0 | -2514 | 0
23891 | 437 | 437 | 0 | 2406 | 0 | 0 | 0 | 0 | -2406 | 0 | -2406 | 0 | -2406 | 0
23895 | 1894 | 1869 | -25 | 8985 | 0 | 0 | 0 | 0 | -8985 | 0 | -8985 | 0 | -8985 | 0
23853 | 275 | 275 | 0 | 1500 | 3072 | 3020 | -52 | 0 | -1500 | 0 | -1500 | 0 | -1500 | 0
23852 | 405 | 403 | -2 | 1953 | 0 | 0 | 0 | 0 | -1953 | 0 | -1953 | 0 | -1953 | 0
23851 | 565 | 563 | -2 | 2725 | 0 | 0 | 0 | 0 | -2725 | 0 | -2725 | 0 | -2725 | 0
23850 | 637 | 635 | -2 | 5199 | 10636 | 10616 | -20 | 0 | -5199 | 0 | -5199 | 0 | -5199 | 0
23854 | 264 | 262 | -2 | 1500 | 3046 | 3028 | -18 | 0 | -1500 | 0 | -1500 | 0 | -1500 | 0
23799 | 930 | 924 | -6 | 8904 | 0 | 0 | 0 | 0 | -8904 | 0 | -8904 | 0 | -8904 | 0
23800 | 823 | 823 | 0 | 7523 | 10356 | 10314 | -42 | 0 | -7523 | 0 | -7523 | 0 | -7523 | 0
23790 | 466 | 464 | -2 | 6986 | 14272 | 14272 | 0 | 0 | -6986 | 0 | -6986 | 0 | -6986 | 0
23794 | 82 | 80 | -2 | 810 | 866 | 866 | 0 | 0 | -810 | 0 | -810 | 0 | -810 | 0
23795 | 81 | 80 | -1 | 840 | 888 | 884 | -4 | 0 | -840 | 0 | -840 | 0 | -840 | 0
23694 2nd | 585 | 585 | 0 | 4500 | 9256 | 9248 | -8 | 3874 | -626 | 0 | -4500 | 0 | -4500 | 0
24012 | 705 | 704 | -1 | 3557 | 7368 | 7346 | -22 | 0 | -3557 | 0 | -3557 | 0 | -3557 | 0
24009 | 1472 | 1472 | 0 | 8580 | 17708 | 17708 | 0 | 0 | -8580 | 0 | -8580 | 0 | -8580 | 0
24014 | 625 | 623 | -2 | 1866 | 3828 | 1632 | -2196 | 0 | -1866 | 0 | -1866 | 0 | -1866 | 0
24011 | 4302 | 4302 | 0 | 10689 | 21776 | 21458 | -318 | 0 | -10689 | 0 | -10689 | 0 | -10689 | 0
24006 | 1030 | 1030 | 0 | 3000 | 0 | 0 | 0 | 0 | -3000 | 0 | -3000 | 0 | -3000 | 0
23917 | 3463 | 3356 | -107 | 13696 | 0 | 0 | 0 | 9087 | -4609 | 0 | -13696 | 0 | -13696 | 0
23923 | 1607 | 1605 | -2 | 2554 | 5436 | 5302 | -134 | 0 | -2554 | 0 | -2554 | 0 | -2554 | 0
23924 | 1291 | 1277 | -14 | 5670 | 11670 | 11598 | -72 | 0 | -5670 | 0 | -5670 | 0 | -5670 | 0
24037 | 1190 | 1190 | 0 | 3500 | 7176 | 0 | -7176 | 0 | -3500 | 0 | -3500 | 0 | -3500
23903 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | -1500 | 0 | -1500 | 0 | -1500
24107 | 516 | 510 | -6 | 5160 | 10576 | 10484 | -92 | 5262 | 102 | 5160 | 0 | 5160 | 0
24108 | 394 | 394 | 0 | 3000 | 6100 | 6100 | 0 | 0 | -3000 | 0 | -3000 | 0 | -3000 | 0
24101 | 1266 | 1266 | 0 | 5148 | 0 | 0 | 0 | 5200 | 52 | 5180 | 32 | 5178 | 30 | 0
24127 | 197 | 197 | 0 | 824 | 0 | 0 | 0 | 0 | -824 | 0 | -824 | 0 | -824 | 0
23899 | 678 | 678 | 0 | 4596 | 9392 | 9372 | -20 | 0 | -4596 | 0 | -4596 | 0 | -4596
24023 | 393 | 393 | 0 | 1296 | 2694 | 0 | -2694 | 0 | -1296 | 0 | -1296 | 0 | -1296
23904 | 1466 | 1465 | -1 | 8520 | 17060 | 16980 | -80 | 0 | -8520 | 0 | -8520 | 0 | -8520
23912 | 1226 | 1225 | -1 | 11106 | 22656 | 22374 | -282 | 0 | -11106 | 0 | -11106 | 0 | -11106
23916 | 1091 | 1082 | -9 | 5097 | 4170 | 4128 | -42 | 0 | -5097 | 0 | -5097 | 0 | -5097
23905 | 232 | 232 | 0 | 1152 | 3620 | 3618 | -2 | 0 | -1152 | 0 | -1152 | 0 | -1152
23903 1st | 369 | 369 | 0 | 1500 | 0 | 0 | 0 | 0 | -1500 | 0 | -1500 | 0 | -1500
24128 | 190 | 190 | 0 | 721 | 0 | 0 | 0 | 0 | -721 | 0 | -721 | 0 | -721 | 0
23925 | 1030 | 1030 | 0 | 2719 | 5672 | 5642 | -30 | 2808 | 89 | 0 | -2719 | 0 | -2719 | 0
23791 | 483 | 483 | 0 | 6108 | 12542 | 12372 | -170 | 6201 | 93 | 0 | -6108 | 0 | -6108 | 0
23792 | 258 | 258 | 0 | 3254 | 6660 | 6640 | -20 | 0 | -3254 | 0 | -3254 | 0 | -3254 | 0
23793 | 318 | 315 | -3 | 4013 | 8292 | 8230 | -62 | 4075 | 62 | 0 | -4013 | 0 | -4013 | 0
23796 | 1083 | 1083 | 0 | 8561 | 11206 | 11182 | -24 | 0 | -8561 | 0 | -8561 | 0 | -8561 | 0
23797 | 1124 | 1112 | -12 | 8885 | 12746 | 12718 | -28 | 7695 | -1190 | 0 | -8885 | 0 | -8885 | 0
22037 2nd | 710 | 710 | 0 | 20000 | 0 | 0 | 0 | 18096 | -1904 | 0 | -20000 | 0 | -20000 | 0
24161 | 702 | 702 | 0 | 1980 | 4076 | 4060 | -16 | 0 | -1980 | 0 | -1980 | 0 | -1980 | 0
24165 | 672 | 669 | -3 | 1998 | 4136 | 4110 | -26 | 0 | -1998 | 0 | -1998 | 0 | -1998 | 0
24169 | 315 | 315 | 0 | 1560 | 3198 | 3178 | -20 | 0 | -1560 | 0 | -1560 | 0 | -1560 | 0
24170 | 434 | 434 | 0 | 1515 | 3118 | 3078 | -40 | 0 | -1515 | 0 | -1515 | 0 | -1515 | 0
23697 1st | 1306 | 1306 | 0 | 4197 | 0 | 0 | 0 | 4319 | 122 | 0 | -4197 | 0 | -4197 | 0
23697 2nd | 1142 | 1142 | 0 | 3673 | 0 | 0 | 0 | 0 | -3673 | 0 | -3673 | 0 | -3673 | 0
24008 | 1347 | 1342 | -5 | 7845 | 16046 | 16046 | 0 | 8006 | 161 | 0 | -7845 | 0 | -7845 | 0
24265 | 483 | 476 | -7 | 4080 | 8324 | 8306 | -18 | 0 | -4080 | 0 | -4080 | 0 | -4080 | 0
Grand Total | 168262 | 167435 | -827 | 911006 | 1001856 | 970272 | -31584 | 365604 | -545402 | 107309 | -803697 | 90189 | -820817 | 0
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Sew-1 (hidden)
[20 empty] | IFERROR(VLOOKUP(B3,'\\192.168.100.54\dyeing & finishing\Dyeing\Bulk\Report\Daily Report\Finish Fabric Plan & Execution Status\[Finish Fabric Plan & Execution Status.xlsx]Tracking Sheet'!$B$2:$E$20000,2,0),0) | IFERROR(VLOOKUP(B3,'\\192.168.100.54\dyeing & finishing\Dyeing\Bulk\Report\Daily Report\Finish Fabric Plan & Execution Status\[Finish Fabric Plan & Execution Status.xlsx]Tracking Sheet'!$B$2:$E$20000,3,0),0) |  | IFERROR(VLOOKUP(B3,'\\192.168.100.54\cutting\Report\Daily Report\2022\Cutting T & A\[Cutting, Print & Input Summary.xls]Tracking Sheet'!$B$2:$F$10000,2,0),0) |  |  | IFERROR(VLOOKUP(B3,'\\192.168.100.54\cutting\Report\Daily Report\2022\Cutting T & A\[Cutting, Print & Input Summary.xls]Tracking Sheet'!$B$2:$F$10000,3,0),0) | IFERROR(VLOOKUP(B3,'\\192.168.100.54\cutting\Report\Daily Report\2022\Cutting T & A\[Cutting, Print & Input Summary.xls]Tracking Sheet'!$B$2:$F$10000,4,0),0) |  | IFERROR(VLOOKUP(B3,'\\192.168.100.54\cutting\Report\Daily Report\2022\Cutting T & A\[Cutting, Print & Input Summary.xls]Tracking Sheet'!$B$2:$F$10000,5,0),0) |  | IFERROR(VLOOKUP(B3,'\\192.168.100.54\mis\Report\Daily Report\Daily Production Summary\[Production Summary.xlsx]Tracking Sheet'!$B$2:$E$5000,2,0),0)
Line | Buyer | Job | Style | Order Qty | Item Description | Dyeing-Finishing T & A End | All Over Print T & A End | Trims & Accessories T & A End | Production & Other File Handover Date | Cutting T & A Start | Sewing T & A Start | Ex-Factory Date | Cargo Closing Date | Merchandiser Name | Print Position | Embriodary Position | Print & Emb Description | Remarks | PRESENT STATUS | Fabric Req. (in Kg) | Fabric Received | Fabric Balance | Cutting Qty | Cutting Balance | Print Send | Print rcvd | Recv balance | Sewing input | Sewing input Balance | Sewing Qty | Sew Bala | Priority | Trims Due Status | Remarks
A | OVS SPA | 23366 | 231TRO236 | 17766 | Pant W Fr PKT B | 2022-08-05 |  | 2022-08-11 | 2022-08-11 | 2022-05-17 | 2022-09-01 | 2022-09-28 | 2022-09-28 | Khairul |  |  | P.Orange-3618,GM-2544,Navy B-4116,Daphne-1134,N.Iron-3114,T.Turquoise-2040,Riverside-1200 all cmb 1 clr pig |  | Cut Run | 2568 | 1642 | -926 | 5784 | -11982 | 5784 | 3680 | -2104 | 0 | -17766 | 0 | -17766 | 9-1 | Elastic-125 roll due( white-3.5cm),Hang tag due
A | BS-NMT | 24160 | 13216547 | 1980 | LS Swt Hoody | 2022-08-30 |  | 2022-09-02 | 2022-09-02 | 2022-09-09 | 2022-09-19 | 2022-09-30 | 2022-10-05 | Shamoly | Chest |  | A.Green-990 2 clr rub,D.Sapphire-990 2 clr rub |  | File Due | 0 | 0 | 0 | 0 | -1980 | 0 | 0 | 0 | 0 | -1980 | 0 | -1980 | 9-2 | #N/A
A | BS-NMT | 24164 | 13216822 | 1992 | LS Swt Hoody | 2022-08-30 |  | 2022-09-02 | 2022-09-02 | 2022-09-08 | 2022-09-16 | 2022-09-30 | 2022-10-05 | Shamoly | Chest |  | P.Whip-996 ,D.Sapphire-996 bth cmb 1 clr glit |  | File Due | 0 | 0 | 0 | 0 | -1992 | 0 | 0 | 0 | 0 | -1992 | 0 | -1992 | 9-3 | #N/A
A | OVS SPA | 23728 | 22TSH008 | 12535 | SS TS W Side Ruched | 2022-08-12 | 2022-08-27 | 2022-09-02 | 2022-09-02 | 2022-09-10 | 2022-09-20 | 2022-10-10 | 2022-10-10 | Alamin | Nk |  |  |  | File Due | 2016 | 0 | -2016 | 0 | -12535 | 0 | 0 | 0 | 0 | -12535 | 0 | -12535 | 9-4 | #N/A
B | GBX ( New Look) | 24084 | 8393452 | 10301 | Legging W Revet | 2022-08-25 |  | 2022-08-20 | 2022-08-20 | 2022-08-27 | 2022-09-01 | 2022-09-17 | 2022-09-18 | Shofi |  |  |  |  | Need Cut FB | 0 | 0 | 0 | 0 | -10301 | 0 | 0 | 0 | 0 | -10301 | 0 | -10301 | 9-1 | Poly, Rivet due
B | GBX ( New Look) | 23678 | 8341320 | 6615 | SS Polo Shirt | 2022-08-25 |  | 2022-09-05 | 2022-09-05 | 2022-08-29 | 2022-09-16 | 2022-10-08 | 2022-10-10 | Morad |  |  |  |  | File Due | 1172 | 1136 | -36 | 0 | -6615 | 0 | 0 | 0 | 0 | -6615 | 0 | -6615 | 9-2 | #N/A
B | GBX ( New Look) | 23679 | 8341581 | 6826 | SS Polo Shirt | 2022-08-26 |  | 2022-09-07 | 2022-09-07 | 2022-09-02 | 2022-09-20 | 2022-10-08 | 2022-10-10 | Morad |  |  |  |  | File Due | 1337 | 1329 | -8 | 0 | -6826 | 0 | 0 | 0 | 0 | -6826 | 0 | -6826 | 9-3 | #N/A
B | BS-ONS | 24062 | 22026023 | 1680 | SS Polo Shirt | 2022-08-27 |  | 2022-09-12 | 2022-09-12 | 2022-09-20 | 2022-09-24 | 2022-10-03 | 2022-10-05 | Shohag |  |  |  |  | File Due | 425 | 0 | -425 | 0 | -1680 | 0 | 0 | 0 | 0 | -1680 | 0 | -1680 | 9-4 | #N/A
C1 | BS-ONS | 23932 2nd | 22002973 | 6080 | SS TS | 2022-08-23 |  | 2022-08-23 | 2022-08-23 | 2022-08-27 | 2022-09-01 | 2022-09-19 | 2022-09-21 | Shohag |  |  |  |  | File Due | 0 | 0 | 0 | 0 | -6080 | 0 | 0 | 0 | 0 | -6080 | 0 | -6080 | 9-1 | #N/A
C1+D1 | OVS SPA | 23688 | 231PJA110 | 13190 | LS TS W Cuff & Payjama W cuff | 2022-08-25 |  | 2022-09-03 | 2022-09-03 | 2022-09-12 | 2022-09-21 | 2022-10-15 | 2022-10-15 | Alamin | Chest,Nk |  | Lt. Blue T-6595 3 clr pig Nk heat press. Blue-6595 NA |  | File Due | 2698 | 2677 | -21 | 0 | -13190 | 0 | 0 | 0 | 0 | -13190 | 0 | -13190 | 9-2+6 | #N/A
C1+D1 | OVS SPA | 23689 | 231TSH175 | 17472 | LS TS W Cuff & Payjama W cuff | 2022-08-25 |  | 2022-09-03 | 2022-09-03 | 2022-09-10 | 2022-09-17 | 2022-10-15 | 2022-10-15 | Alamin | Chest,Nk |  | Blue-8736 4 clr pig |  | File Due | 4026 | 2850 | -1176 | 0 | -17472 | 0 | 0 | 0 | 0 | -17472 | 0 | -17472 | 9-3+7 | #N/A
C2 | GBX ( New Look) | 24120 | 8450988 | 11905 | SS TS | 2022-08-24 |  | 2022-08-25 | 2022-08-25 | 2022-09-02 | 2022-09-08 | 2022-09-24 | 2022-09-24 | Morad | Nk |  | 3 clr pig |  | File Due | 2422 | 0 | -2422 | 0 | -11905 | 0 | 0 | 0 | 0 | -11905 | 0 | -11905 | 9-1 | #N/A
C2 | BS-ONS | 23299 | 22026019 | 4016 | SS TS YD | 2022-08-09 |  | 2022-09-01 | 2022-09-01 | 2022-09-07 | 2022-09-13 | 2022-10-02 | 2022-10-05 | Shohag |  |  |  |  | File Due | 1034 | 0 | -1034 | 0 | -4016 | 0 | 0 | 0 | 0 | -4016 | 0 | -4016 | 9-2 | #N/A
C2 | BS-ONL | 21833 5th | 15209156 | 17280 | Lds O Nk Top | 2022-08-28 |  | 2022-09-06 | 2022-09-06 | 2022-09-10 | 2022-09-14 | 2022-10-17 | 2022-10-19 | Imran |  |  |  |  | Cut Run | 3701 | 3370 | -331 | 6341 | -10939 | 0 | 0 | 0 | 0 | -17280 | 0 | -17280 | 9-3 | #N/A
D1 | BS-ONL | 23979 | 15287574 | 807 | SS TS | 2022-08-12 |  | 2022-08-17 | 2022-08-17 | 2022-08-24 | 2022-09-06 | 2022-09-27 | 2022-09-29 | Subarno | Chest | Seq | B.White BRANCH-807 UC 8 clr pig 1 clr deq |  | CAD | 124 | 124 | 0 | 0 | -807 | 0 | 0 | 0 | 0 | -807 | 0 | -807 | 9-1 | Ok
D1 | BS-ONL | 23980 | 15293033 | 2471 | SS TS | 2022-08-10 |  | 2022-08-16 | 2022-08-13 | 2022-08-23 | 2022-09-07 | 2022-09-26 | 2022-10-31 | Subarno | Chest | Seq | B.White Giraf-832 UC 3 clr glit 1 clr seq 1clr stone sticker attach ,B.white Giraffe CRAZY-807 3 clr glit 1 clr seq 1clr stone sticker attach, B.white PANDA-832 UC 3 clr glit 1 clr seq |  | File Due | 372 | 367 | -5 | 0 | -2471 | 0 | 0 | 0 | 0 | -2471 | 0 | -2471 | 9-2 | Ok
D1 | GBX ( New Look) | 24079 1st |  | 1260 | Tank Top | 2022-08-24 |  | 2022-09-01 | 2022-09-01 | 2022-09-07 | 2022-09-13 | 2022-09-24 | 2022-09-25 | Morad | Nk |  |  |  | File Due | 272 | 0 | -272 | 0 | -1260 | 0 | 0 | 0 | 0 | -1260 | 0 | -1260 | 9-3 | #N/A
D1 | GBX ( New Look) | 24080 |  | 2310 | Tank Top | 2022-08-22 |  | 2022-08-26 | 2022-08-26 | 2022-09-03 | 2022-09-10 | 2022-09-17 | 2022-09-25 | Morad |  | Logo | L.Green-1155,Indigo-1155 all cmb 1 clr thrd Emb |  | File Due | 478 | 0 | -478 | 0 | -2310 | 0 | 0 | 0 | 0 | -2310 | 0 | -2310 | 9-4 | #N/A
D1 | BS-ONL | 24001 | 15298416 | 6200 | SS TS | 2022-08-26 |  | 2022-09-02 | 2022-09-02 | 2022-09-09 | 2022-09-14 | 2022-09-26 | 2022-09-28 | Atiq |  |  |  |  | File Due | 863 | 529 | -334 | 0 | -6200 | 0 | 0 | 0 | 0 | -6200 | 0 | -6200 | 9-5 | #N/A
D2 | BS-NMT | 24031 | 13217320 | 21836 | SS TS | 2022-08-16 |  | 2022-08-20 | 2022-08-20 | 2022-08-26 | 2022-09-05 | 2022-09-30 | 2022-10-05 | Shamoly | Chest,Nk |  | B.Orchre-5444 4 clr rub,D.Supphire-6539 4 clr rub,Jet Stream-4603 2 clr rub,W.Iron-5250 3clr rub |  | CAD | 2402 | 2340 | -62 | 0 | -21836 | 0 | 0 | 0 | 0 | -21836 | 0 | -21836 | 9-1 | Sew thrd-Wrought Iron,Price sticker due
D2 | OVS SPA | 23331 | 231TSH004 | 12601 | SL TS | 2022-09-02 |  | 2022-09-07 | 2022-09-07 | 2022-09-16 | 2022-09-20 | 2022-10-07 | 2022-10-11 | Khairul |  |  |  |  | Need Cut | 1873 | 1361 | -512 | 0 | -12601 | 0 | 0 | 0 | 0 | -12601 | 0 | -12601 | 9-2 | #N/A
E | UTG (Bonprix) | 19904 4th | BPB0084 | 3000 | LS V NK TS W NK Lace | - |  | 2022-09-01 | 2022-09-01 | 2022-08-12 | 2022-09-10 | 2022-09-25 | 2022-09-25 | Tuhin |  |  |  |  | Need Cut | 640 | 534 | -106 | 0 | -3000 | 0 | 0 | 0 | 0 | -3000 | 0 | -3000 | 9-1 | #N/A
E | BS-ONL | 23779 | 15280421 | 1209 | LS Swt Shirt | 2022-08-26 |  | 2022-09-01 | 2022-09-01 | 2022-09-02 | 2022-09-16 | 2022-10-03 | 2022-10-05 | Faisal | Chest |  | LGM AMOUR-1209 1 clr rub |  | File Due | 647 | 0 | -647 | 0 | -1209 | 0 | 0 | 0 | 0 | -1209 | 0 | -1209 | 9-2 | #N/A
E | BS-NMT | 24162 | 13214308 | 6580 | SS TS | 2022-09-26 |  | 2022-09-01 | 2022-09-01 | 2022-09-07 | 2022-09-17 | 2022-09-30 | 2022-10-05 | Shamoly | Chest,Nk |  | C.Dancer-3276 1 clr pig,D.Sapphire-3304 1 clr rub |  | File Due | 0 | 0 | 0 | 0 | -6580 | 0 | 0 | 0 | 0 | -6580 | 0 | -6580 | 9-3 | #N/A
E | BS-NMT | 24163 | 13216819 | 1998 | SS TS | 2022-09-02 |  | 2022-09-07 | 2022-09-07 | 2022-09-14 | 2022-09-22 | 2022-09-30 | 2022-10-05 | Shamoly | Chest,Nk |  | D.Sapphire-999 1 clr rub 2 clr glit,P.Nectar-999 2 clr ub |  | File Due | 0 | 0 | 0 | 0 | -1998 | 0 | 0 | 0 | 0 | -1998 | 0 | -1998 | 9-4 | #N/A
E | BS-NMT | 24168 | 13216817 | 1992 | SS TS | 2022-08-29 |  | 2022-09-03 | 2022-09-03 | 2022-09-12 | 2022-09-21 | 2022-09-30 | 2022-10-05 | Shamoly | Chest,Nk |  | B.White-996,P.Nectar-996 bth cmb 4 clr rub |  | File Due | 0 | 0 | 0 | 0 | -1992 | 0 | 0 | 0 | 0 | -1992 | 0 | -1992 | 9-5 | #N/A
E | BS-NMT | 24167 | 13216816 | 1992 | SS TS | 2022-08-27 |  | 2022-09-03 | 2022-09-03 | 2022-09-12 | 2022-09-22 | 2022-09-30 | 2022-10-05 | Shamoly | Chest,Nk |  | LGM-996,P.Nectar-996 both 1 clr glitter |  | File Due | 0 | 0 | 0 | 0 | -1992 | 0 | 0 | 0 | 0 | -1992 | 0 | -1992 | 9-6 | #N/A
F | BS-ONL | 23301 2nd | 15209156 | 17280 | LS TS 3Pk | 2022-08-13 |  | 2022-08-22 | 2022-08-22 |  | 2022-09-01 | 2022-09-26 | 2022-09-28 | Imran |  |  |  |  | Cut Run | 3631 | 3630 | -1 | 15938 | -1342 | 0 | 0 | 0 | 0 | -17280 | 0 | -17280 | 9-1 | #N/A
F | GBX ( New Look) | 24121 | 8451088 | 2591 | SS TS | 2022-08-26 |  | 2022-09-01 | 2022-09-01 | 2022-09-07 | 2022-09-14 | 2022-09-24 | 2022-09-24 | Morad | Nk |  | 1 clr pig |  | File Due | 501 | 0 | -501 | 0 | -2591 | 0 | 0 | 0 | 0 | -2591 | 0 | -2591 | 9-2 | #N/A
F | GBX ( New Look) | 24122 | 8451102 | 6008 | SS TS | 2022-08-25 |  | 2022-08-29 | 2022-08-29 | 2022-09-06 | 2022-09-14 | 2022-09-24 | 2022-09-24 | Morad | Nk |  | 2 clr pig |  | File Due | 1390 | 0 | -1390 | 0 | -6008 | 0 | 0 | 0 | 0 | -6008 | 0 | -6008 | 9-3 | #N/A
F | BS-ONS | 23927 | 22024741 | 20255 | YD SS TS | 2022-09-02 |  | 2022-09-01 | 2022-09-01 | 2022-09-08 | 2022-09-17 | 2022-10-10 | 2022-10-12 | Shohag | Chest |  | B.White-8331,D.Navy-7686,B.White STRIPE-1026,D.Navy STRIPE-1126 all cmb UC 1 clr THRD LOGO |  | File Due | 5774 | 0 | -5774 | 0 | -20255 | 0 | 0 | 0 | 0 | -20255 | 0 | -20255 | 9-4 | #N/A
G | BS-ONL | 23988 | 15279486 | 2376 | YD LS TS Rib VC | 2022-08-17 |  | 2022-08-22 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-19 | 2022-10-05 | Atiq | Nk |  | 1 clr foil |  | Ready Test Cut | 657 | 212 | -445 | 0 | -2376 | 0 | 0 | 0 | 0 | -2376 | 0 | -2376 | 9-1 | #N/A
G | BS-ONL | 23990 | 15279575 | 780 | YD LS TS W All hem Letuce Rib VC | 2022-08-16 |  | 2022-08-20 | 2022-08-20 | 2022-08-29 | 2022-09-05 | 2022-09-19 | 2022-10-05 | Atiq | Nk |  | 1 clr foil |  | CAD | 221 | 0 | -221 | 0 | -780 | 0 | 0 | 0 | 0 | -780 | 0 | -780 | 9-2 | Ok
G | BS-NMT | 23898 | 13212372 | 2655 | LS TS | 2022-09-15 |  | 2022-09-21 | 2022-09-21 | 2022-09-30 | 2022-10-11 | 2022-10-30 | 2022-11-02 | Kamruzzaman | Chest,Nk |  | Black-884 2 clr rub,Pink Yarrow-959 2 clr rub 1 clr glit,W.Allyssum-812 2 clr rub 1 clr glit |  | CAD | 452 | 302 | -150 | 0 | -2655 | 0 | 0 | 0 | 0 | -2655 | 0 | -2655 | 9-3 | #N/A
G | BS-ONL | 23943 | 15283138 | 3348 | YD LS TS | 2022-08-16 |  | 2022-08-19 | 2022-08-19 | 2022-08-26 | 2022-09-07 | 2022-09-19 | 2022-09-28 | Maruf | Chest |  | Bonbon SATURDAY-1220,First FRIDAY-1244,Phantom SUNDAY-884 all cmb 1 clr HD |  | Size Set Run | 544 | 342 | -202 | 0 | -3348 | 0 | 0 | 0 | 0 | -3348 | 0 | -3348 | 9-4 | Herringbone tape due
G | BS-ONL | 23945 | 15283140 | 1296 | YD LS TS | 2022-08-20 |  | 2022-08-24 | 2022-08-24 | 2022-09-02 | 2022-09-10 | 2022-09-19 | 2022-09-28 | Maruf | Chest |  | Bonbon SATURDAY-600,First FRIDAY-696 all cmb 1 clr HD |  | Size Set Run | 160 | 73 | -87 | 0 | -1296 | 0 | 0 | 0 | 0 | -1296 | 0 | -1296 | 9-5 | #N/A
G | BS-ONL | 22696 3rd | 15209153 | 23400 | SS TS | 2022-08-22 |  | 2022-09-01 | 2022-09-01 | 2022-09-06 | 2022-09-12 | 2022-10-10 | 2022-10-12 | Imarn |  |  |  |  | Cut Run | 3842 | 3840 | -2 | 8019 | -15381 | 0 | 0 | 0 | 0 | -23400 | 0 | -23400 | 9-6 | #N/A
H1 | BS-ONL | 21813 3rd | 15266481 | 30102 | SS TS | 2022-08-16 |  | 2022-08-17 | 2022-08-17 | 2022-08-20 | 2022-09-01 | 2022-10-17 | 2022-10-19 | Subarno | Chest |  | Blushing Bride-6966,C.dancer-7109,M.F=Green-7175,Provence-7224 all cmb 1 clr glitter |  | Need Cut | 3461 | 3315 | -146 | 7369 | -22733 | 8010 | 2477 | -5533 | 0 | -30102 | 0 | -30102 | 9-1 | Ok
H1 | BS-ONS | 23300 | 22026021 | 8816 | SS TS | 2022-08-22 |  | 2022-09-05 | 2022-09-05 | 2022-09-13 | 2022-09-16 | 2022-10-02 | 2022-10-19 | Shohag |  |  |  |  | File Due | 2590 | 2581 | -9 | 0 | -8816 | 0 | 0 | 0 | 0 | -8816 | 0 | -8816 | 9-2 | #N/A
H1 | BS-ONS | 23298 | 22026020 | 5016 | SS TS | 2022-08-22 |  | 2022-09-01 | 2022-09-01 | 2022-09-08 | 2022-09-19 | 2022-10-02 | 2022-10-19 | Shohag | FR & Bk |  | Black-2508 1 clr rub,Black BUTTERFLY-2508 FR 4 clr rub, Bk 4 clr rub BIG ARTW |  | File Due | 1360 | 1347 | -13 | 0 | -5016 | 0 | 0 | 0 | 0 | -5016 | 0 | -5016 | 9-3 | #N/A
H2 | OVS SPA | 22983 | 231SWT024 | 11902 | LS Reglan Swt Shir | 2022-07-25 | - | 2022-08-01 | 2022-08-01 | 2022-08-03 | 2022-08-17 | 2022-09-10 | 2022-09-20 | Salam | Chest |  | White -2965,Fuchsia-8937all cmb 6 clr rub |  | Cut Ok | 1805 | 1786 | -19 | 11839 | -63 | 11839 | 11679 | -160 | 0 | -11902 | 0 | -11902 | 8-2+9-1 | ok
H2 | OVS SPA | 23236 | 231SWT011 | 20720 | Boys Swt Shirt | 2022-08-02 |  | 2022-08-09 | 2022-08-09 | 2022-05-27 | 2022-09-01 | 2022-09-27 | 2022-09-30 | Basir | Chest |  | Bright white 8030 pcs, Black beauty 7010 pcs , Gray Mel 5680 pcs all combo 2 clr rubber print |  | Cut Run | 8210 | 8185 | -25 | 15870 | -4850 | 11170 | 0 | -11170 | 0 | -20720 | 0 | -20720 | 9-2 | #N/A
H2 | OVS SPA | OVS 23751 | 231TSH257 | 6576 |  |  |  |  | 2022-09-12 | 2022-09-19 |  | 2022-10-02 | 2022-10-05 | Khairul |  |  |  |  | Need Test Cut | 0 | 0 | 0 | 0 | -6576 | 0 | 0 | 0 | 0 | -6576 | 0 | -6576 | 9-3 | #N/A
H2 | BS-ONS | 23938 | 22026120 | 1980 | LS Swt Shirt | 2022-08-23 | 2022-09-07 | 2022-09-12 | 2022-09-12 | 2022-09-20 | 2022-09-23 | 2022-10-03 | 2022-10-05 | Shohag |  |  |  |  | File Due | 1434 | 234 | -1200 | 0 | -1980 | 0 | 0 | 0 | 0 | -1980 | 0 | -1980 | 9-4 | #N/A

## Sew-2 (hidden)
Buyer | Job | Style | Order Qty | Item Description | Dyeing-Finishing T & A End | All Over Print T & A End | Trims & Accessories T & A End | Production & Other File Handover Date | Cutting T & A Start | Sewing T & A Start | Ex-Factory Date | Cargo Closing Date | Line | Merchandiser Name | Print Position | Embriodary Position | Print & Emb Description | Floor | PRESENT STATUS | Fabric Req. (in Kg) | Fabric Received | Fabric Balance | Cutting Qty | Cutting Balance | Print Send | Print rcvd | Recv balance | Sewing input | Sewing input Balance | Sewing Qty | Priority | Trims Due Details
OVS SPA | 22978 | 231MMP202 | 6528 | LS TS W lace ,PLK | 2022-08-08 |  | 2022-08-17 | 2022-08-17 | 2022-05-31 | 2022-09-01 | 2022-09-30 | 2022-09-30 | J | Salam |  |  |  | NFL 2 | Cut Ok | 1697 | 1635 | -62 | 6616 | 88 | 6616 | 2176 | -4440 | 0 | -6528 | 0 | 9-1 | Hang tag due-25.08
OVS SPA | 22969 | 231NDG291 | 4580 | LS TS W Lace at CLR & PLKt | 2022-07-26 | 2022-08-18 | 2022-08-23 | 2022-08-23 | 2022-09-02 | 2022-09-08 | 2022-09-30 | 2022-09-30 | J | Salam |  |  |  | NFL 2 | Cut Run | 1763 | 1559 | -204 | 3958 | -622 | 0 | 0 | 0 | 0 | -4580 | 0 | 9-2 | #N/A
OVS SPA | 22970 | 231NDG292 | 4947 | LS TS W Lace & Full PLKt | 2022-07-28 | 2022-08-16 | 2022-08-22 | 2022-08-22 | 2022-09-01 | 2022-09-06 | 2022-09-30 | 2022-09-30 | J | Salam |  |  |  | NFL 2 | File Due | 2061 | 2061 | 0 | 0 | -4947 | 0 | 0 | 0 | 0 | -4947 | 0 | 9-3 | #N/A
BS-ONL | 23816 | 15279401 | 804 | LS Maternity Hoody B | 2022-08-31 |  | 2022-09-08 | 2022-09-08 | 2022-09-16 | 2022-09-20 | 2022-10-03 | 2022-10-05 | J | Masud Rana |  |  |  | NFL 2 | CAD | 427 | 427 | 0 | 0 | -804 | 0 | 0 | 0 | 0 | -804 | 0 | 9-5
BS-ONL | 23818 | 15279428 | 996 | LS Wrap Dress | 2022-08-31 |  | 2022-09-05 | 2022-09-05 | 2022-09-15 | 2022-09-19 | 2022-10-02 | 2022-10-05 | J | Masud Rana |  |  |  | NFL 2 | File Due | 333 | 0 | -333 | 0 | -996 | 0 | 0 | 0 | 0 | -996 | 0 | 9-6
BS-ONL | 23785 | 15280781 | 1620 | C&S LS Hoody W DRST | 2022-08-25 |  | 2022-09-02 | 2022-09-02 | 2022-09-09 | 2022-09-20 | 2022-10-02 | 2022-10-05 | J | Faisal |  | Chest | Hunter green-810,Moonlight Ocean-810 bth 1 clr thrd Letter Emb 15000 Stc | NFL 2 | File Due | 1002 | 0 | -1002 | 0 | -1620 | 0 | 0 | 0 | 0 | -1620 | 0 | 9-7 | #N/A
BS-ONL | 23781 | 15281534 | 1830 | LS Hoody Jacket W Cangaroo PKT | 2022-08-27 |  | 2022-09-03 | 2022-09-03 | 2022-09-10 | 2022-09-20 | 2022-10-03 | 2022-10-05 | J | Faisal |  | Chest | Black LOGO-1830 UC 1 clr Lurex trd Emb | NFL 2 | Need Test Cut | 994 | 0 | -994 | 0 | -1830 | 0 | 0 | 0 | 0 | -1830 | 0 | 9-8 | #N/A
OVS SPA | 23729 | 22SWT008 | 7035 | LS Swt Shirt W Smock at BTM,Cuff | 2022-08-25 |  | 2022-08-26 | 2022-08-26 | 2022-09-03 | 2022-09-23 | 2022-10-10 | 2022-10-10 | J | Alamin | Chest |  | Lt. Lilac-6515 1 clr oig 2 clr thrd Flower EMB | NFL 2 | File Due | 3083 | 0 | -3083 | 0 | -7035 | 0 | 0 | 0 | 0 | -7035 | 0 | 9-9 | #N/A
OVS SPA | 22968 | 231PJA290 | 8972 | LS TS W Lace | 2022-08-04 | 2022-08-23 | 2022-08-28 | 2022-08-28 | 2022-09-06 | 2022-09-10 | 2022-09-30 | 2022-09-30 | J+O | Salam |  |  |  | NFL 2 | Cut Ok | 2691 | 2691 | 0 | 5785 | -3187 | 0 | 0 | 0 | 0 | -8972 | 0 | 9-4+7 | #N/A
BS-ONL | 23947 | 15266550 | 2368 | LS TS | 2022-08-10 |  | 2022-08-17 | 2022-08-17 | 2022-08-25 | 2022-09-05 | 2022-09-26 | 2022-10-19 | K1 | Maruf | Chest |  | M.Green-660,Provence-636,R.Smoke-1072 all cmb 1 clr glit | NFL 2 | Need Cut | 174 | 174 | 0 | 0 | -2368 | 0 | 0 | 0 | 0 | -2368 | 0 | 9-1 | Ok
OVS SPA | 23344 | 231TNK112 | 4800 | SL TS | 2022-08-30 |  | 2022-09-07 | 2022-09-07 | 2022-09-16 | 2022-09-22 | 2022-10-15 | 2022-10-14 | K1 | Khairul | Sticker |  | Stone Sticker attach at NK,SLV, Body Hem | NFL 2 | File Due | 689 | 456 | -233 | 0 | -4800 | 0 | 0 | 0 | 0 | -4800 | 0 | 9-10 | #N/A
BS-ONL | 23948 | 15250807 | 1224 | SS TS | 2022-08-12 |  | 2022-08-18 | 2022-08-18 | 2022-08-26 | 2022-09-05 | 2022-09-19 | 2022-10-19 | K1 | Maruf | Chest |  | C.Blue SILVER ONLY-612,P.Rose SILVER ONLY-612 all cmb 1 clr glit | NFL 2 | Size Set Run | 80 | 80 | 0 | 0 | -1224 | 0 | 0 | 0 | 0 | -1224 | 0 | 9-2 | Strechable Elastic tape due
BS-ONL | 23946 | 15249924 | 5808 | SS TS | 2022-08-09 |  | 2022-08-12 | 2022-08-12 | 2022-08-20 | 2022-09-01 | 2022-09-19 | 2022-10-26 | K1 | Maruf | Chest |  | C.Blue SILVER ONLY-3000,P.Rose SILVER ONLY-2808 all cmb 1 clr glit | NFL 2 | Size Set Run | 615 | 606 | -9 | 0 | -5808 | 0 | 0 | 0 | 0 | -5808 | 0 | 9-3 | Strechable Elastic tape due
BS-ONL | 23975 | 15282703 | 4276 | SS TS W Acid Wash | 2022-08-16 |  | 2022-08-20 | 2022-08-18 | 2022-08-30 | 2022-09-07 | 2022-09-27 | 2022-09-29 | K1 | Subarno | Chest |  | C.Dancer INSPIRE-1888,D.Blue INSTINCT-2388 bth cmb 4 clr rub Acid Wash | NFL 2 | Need Cut | 911 | 911 | 0 | 0 | -4276 | 0 | 0 | 0 | 0 | -4276 | 0 | 9-4 | Ok
BS-ONL | 23944 | 15282016 | 1648 | LS TS | 2022-08-12 |  | 2022-08-18 | 2022-08-18 | 2022-08-26 | 2022-09-08 | 2022-09-19 | 2022-09-28 | K1 | Maruf | Chest | Seq | Black TOI-516 UC 1 clr rub 1 clr seq then Beads Attch,B.White PETIT-1132 FR Part All over Tpe 1 clr rub 1 clr seq then Hand Emb. Beads attch, | NFL 2 | Size Set Run | 228 | 228 | 0 | 0 | -1648 | 0 | 0 | 0 | 0 | -1648 | 0 | 9-5 | Herringbone tape due
BS-ONL | 23973 | 15282143 | 4296 | SS TS | 2022-08-08 |  | 2022-08-10 | 2022-08-10 | 2022-08-18 | 2022-09-08 | 2022-09-19 | 2022-09-21 | K1 | Subarno | Chest |  | Baltic JOYFUL-1432 1 clr rub 1 pcs Hand embellish attach,Black Fabulous-1432 no print 9 pcs Hand embellish attach CRITICAL Hand Embellishment T&A- 24.08-6.09 | NFL 2 | Cut Ok | 636 | 636 | 0 | 4444 | 148 | 4444 | 1291 | -3153 | 0 | -4296 | 0 | 9-6 | #N/A
BS-ONL | 23978 | 15283023 | 4581 | YD SS TS | 2022-08-20 |  | 2022-08-25 | 2022-08-25 | 2022-09-01 | 2022-09-09 | 2022-09-19 | 2022-09-27 | K1 | Subarno | Chest |  | LGM LOVE-1280,Provence LOVE-1125,Pimice stone HAPPY-947,V.Green HAPPY-1229 All cmb UC 1 clr HD | NFL 2 | Need Cut FB | 714 | 0 | -714 | 0 | -4581 | 0 | 0 | 0 | 0 | -4581 | 0 | 9-7 | #N/A
OVS SPA | 23335 | 231TSH112 | 4296 | SL TS | 2022-08-31 |  | 2022-09-07 | 2022-09-07 | 2022-09-15 | 2022-09-20 | 2022-10-10 | 2022-10-10 | K1 | Khairul | Sticker |  | Stone Sticker attach at NK,SLV, Body Hem | NFL 2 | File Due | 619 | 611 | -8 | 0 | -4296 | 0 | 0 | 0 | 0 | -4296 | 0 | 9-8 | #N/A
BS-ONL | 24061 | 15265543 | 4800 | LS Swt Shirt | 2022-08-23 |  | 2022-08-29 | 2022-08-29 | 2022-08-23 | 2022-09-14 | 2022-09-26 | 2022-09-28 | K1 | Iftekher | Chest |  | Allure NEW YORK-1200,N.Sky PARIS-1200,Pastel LOS ANGELES-1200,Phantom BOSTON-1200 all cmb 1 clr rub | NFL 2 | File Due | 2104 | 351 | -1753 | 0 | -4800 | 0 | 0 | 0 | 0 | -4800 | 0 | 9-8 | #N/A
BS-ONL | 24071 | 15286563 | 6426 | SS TS | 2022-08-25 |  | 2022-09-01 | 2022-09-01 | 2022-09-08 | 2022-09-16 | 2022-09-26 | 2022-09-30 | K2 | Iftekhar | Chest |  | P.Blue-3388,Sun Coral-3046 bth cmb 1 clr rub | NFL 2 | Size Set Run | 1109 | 525 | -584 | 0 | -6426 | 0 | 0 | 0 | 0 | -6426 | 0 | 9-1 | #N/A
BS-ONL | 24072 | 15281107 | 7644 | SS TS | 2022-08-22 |  | 2022-08-25 | 2022-08-25 | 2022-09-03 | 2022-09-12 | 2022-09-26 | 2022-09-30 | K2 | Iftekhar | Chest |  | Blue Night PLAY-7648 4 clr rub | NFL 2 | Cut Run | 1230 | 961 | -269 | 5856 | -1788 | 5828 | 5819 | -9 | 0 | -7644 | 0 | 9-2 | #N/A
BS-ONL | 23963 | 15283992 | 3600 | SS TS | 2022-08-25 |  | 2022-09-01 | 2022-09-01 | 2022-09-08 | 2022-09-17 | 2022-10-03 | 2022-10-05 | K2 | Imran | Chest,Nk |  | C.Dancer SQUARE-1800,Pink Yarraw HAHAHA-1800 all cmb 1 clr rub | NFL 2 | File Due | 506 | 506 | 0 | 0 | -3600 | 0 | 0 | 0 | 0 | -3600 | 0 | 9-3 | #N/A
BS-ONL | 24086 | 15283350 | 5952 | SS TS | 2022-08-30 |  | 2022-09-06 | 2022-09-06 | 2022-09-14 | 2022-09-26 | 2022-10-17 | 2022-10-19 | K2 | Maruf | Chest |  | Kalamata AMOUR-2964 1 clr rub,Misty Rose GOLD GLITTER-2988 1 clr glit | NFL 2 | File Due | 592 | 589 | -3 | 0 | -5952 | 0 | 0 | 0 | 0 | -5952 | 0 | 9-4
BS-ONL | 23831 | 15281089 | 6072 | Pant W FR PKT, FR Dirt,Panel & DRST B | 2022-08-20 |  | 2022-08-24 | 2022-08-24 | 2022-08-31 | 2022-09-09 | 2022-09-19 | 2022-09-21 | L | Faisal |  | Terry | Black R-1356,Bonbon R-1092,First Tee R-3624 all cmb 1 leg 1 clr thrd Applique typr Letter Terry 8000 Stc Dev. By Design mode | NFL 2 | File Due | 2328 | 573 | -1755 | 0 | -6072 | 0 | 0 | 0 | 0 | -6072 | 0 | 9-1 | #N/A
BS-ONL | 23832 | 15292461 | 2424 | Pant W FR PKT, FR Dirt,Panel & DRST B | 2022-08-20 |  | 2022-08-25 | 2022-08-25 | 2022-09-02 | 2022-09-12 | 2022-09-19 | 2022-09-21 | L | Faisal |  | Terry | Black R-796,Bonbon R-472,First Tee R-1156 all cmb 1 leg 1 clr thrd Applique typr Letter Terry 8000 Stc Dev. By Design mode | NFL 2 | File Due | 931 | 230 | -701 | 0 | -2424 | 0 | 0 | 0 | 0 | -2424 | 0 | 9-2 | #N/A
BS-ONL | 23820 | 15281090 | 612 | Pant W FR PKT, FR Dirt,Panel & DRST B | 2022-08-23 |  | 2022-08-27 | 2022-08-27 | 2022-09-05 | 2022-09-13 | 2022-09-19 | 2022-09-21 | L | Faisal |  | Terry | Bonbon R-312,First Tee R-300 all cmb 1 leg 1 clr thrd Applique typr Letter Terry 8000 Stc Dev. By Design mode | NFL 2 | File Due | 128 | 72 | -56 | 0 | -612 | 0 | 0 | 0 | 0 | -612 | 0 | 9-3 | #N/A
BS-ONL | 23821 | 15292458 | 636 | LS Swt shirt W Slv dble Panel | 2022-08-20 |  | 2022-08-25 | 2022-08-25 | 2022-09-03 | 2022-09-13 | 2022-09-19 | 2022-09-21 | L | Faisal |  | Terry | Bonbon R-324,First R-312 all cmb UC Applique type terry Emb 8000 stc Dev. By Design mode | NFL 2 | File Due | 135 | 128 | -7 | 0 | -636 | 0 | 0 | 0 | 0 | -636 | 0 | 9-4 | #N/A
BS-ONL | 23783 | 15280428 | 2760 | Pant W FR PKT, FR Dirt,Panel & DRST B | 2022-08-20 |  | 2022-08-23 | 2022-08-23 | 2022-09-01 | 2022-09-04 | 2022-09-26 | 2022-09-28 | L | Faisal |  | Terry | Black R-624,First R-2136 all cmb 1 leg 1 clr thrd Applique typr Letter Terry 8000 Stc Dev. By Design mode | NFL 2 | Need Test Cut | 1073 | 85 | -988 | 0 | -2760 | 0 | 0 | 0 | 0 | -2760 | 0 | 9-5 | #N/A
BS-ONL | 23828 | 15281092 | 600 | LS Swt Shirt W Elastane Slv, Hem | 2022-08-26 |  | 2022-09-02 | 2022-09-02 | 2022-09-08 | 2022-09-16 | 2022-09-26 | 2022-09-28 | L | Faisal | Chest |  | Provence TODAY-1800 1b clr Letter Foil | NFL 2 | File Due | 86 | 6 | -80 | 0 | -600 | 0 | 0 | 0 | 0 | -600 | 0 | 9-6 | #N/A
BS-ONL | 23985 | 15258567 | 1728 | SS TS W Gmts Acid Wash | 2022-08-25 |  | 2022-09-02 | 2022-09-02 | 2022-09-13 | 2022-09-16 | 2022-10-03 | 2022-10-05 | L | Atiq |  |  |  | NFL 2 | File Due | 720 | 396 | -324 | 0 | -1728 | 0 | 0 | 0 | 0 | -1728 | 0 | 9-7 | #N/A
BS-ONL | BSONL 23770 | 15280443 | 1008 | YD LS TS | 2022-08-27 |  | 2022-09-05 | 2022-09-05 | 2022-09-13 | 2022-09-16 | 2022-10-03 | 2022-10-05 | L | Masud Rana |  |  |  | NFL 2 | File Due | 0 | 0 | 0 | 0 | -1008 | 0 | 0 | 0 | 0 | -1008 | 0 | 9-7 | #N/A
BS-ONL | 23842 | 15246790 | 4758 | LS Swt Shirt B | 2022-09-03 |  | 2022-09-07 | 2022-09-07 | 2022-09-14 | 2022-09-23 | 2022-10-10 | 2022-10-12 | M1 | Faisal | Chest |  | Bonbon BETTER-2048,Provence BETTER-1226,P.Rose BETTER-1484 all cmb 1 clr rub | NFL 2 | File Due | 1202 | 74 | -1128 | 0 | -4758 | 0 | 0 | 0 | 0 | -4758 | 0 | 9-10 | #N/A
BS-ONL | 23824 | 15281459 | 1460 | LS Swt Shirt B | 2022-09-03 |  | 2022-09-09 | 2022-09-09 | 2022-09-17 | 2022-09-26 | 2022-10-10 | 2022-10-12 | M1 | Faisal |  | Chest | M.Green LOGO-760,ProvenceLOGO-700 UC 4 clr thrd logo Emb | NFL 2 | File Due | 276 | 0 | -276 | 0 | -1460 | 0 | 0 | 0 | 0 | -1460 | 0 | 9-11 | #N/A
BS-ONL | 23834 | 15281087 | 6266 | LS Swt shirt W Slv dble Panel | 2022-08-21 |  | 2022-08-25 | 2022-08-25 | 2022-09-01 | 2022-09-10 | 2022-09-26 | 2022-09-28 | M1 | Faisal |  | Terry | Black R-1308,Bonbon R-1224,First R-3734 all cmb UC Applique type terry Emb 8000 stc Dev. By Design mode | NFL 2 | File Due | 1963 | 514 | -1449 | 0 | -6266 | 0 | 0 | 0 | 0 | -6266 | 0 | 9-2 | #N/A
BS-ONL | 23833 | 15292460 | 2676 | LS Swt shirt W Slv dble Panel | 2022-08-22 |  | 2022-08-26 | 2022-08-26 | 2022-09-03 | 2022-09-13 | 2022-09-24 | 2022-09-28 | M1 | Faisal |  | Terry | Black R-848,Bonbon R-324,First R-313 all cmb UC Applique type terry Emb 8000 stc Dev. By Design mode | NFL 2 | File Due | 844 | 252 | -592 | 0 | -2676 | 0 | 0 | 0 | 0 | -2676 | 0 | 9-3 | #N/A
BS-ONL | 23822 | 15292457 | 636 | LS Swt shirt W Slv dble Panel | 2022-09-27 |  | 2022-09-01 | 2022-09-01 | 2022-09-08 | 2022-09-15 | 2022-09-24 | 2022-09-28 | M1 | Faisal |  | Terry | Bonbon R-324,First R-312 all cmb UC Applique type terry Emb 8000 stc Dev. By Design mode | NFL 2 | File Due | 128 | 69 | -59 | 0 | -636 | 0 | 0 | 0 | 0 | -636 | 0 | 9-4 | #N/A
BS-ONL | 23782 | 15280427 | 2472 | LS Swt shirt W Slv dble Panel | 2022-08-26 |  | 2022-08-29 | 2022-08-29 | 2022-09-06 | 2022-09-16 | 2022-09-26 | 2022-09-28 | M1 | Faisal |  | Terry | Black R-816,First Tee R-1656 all cmb UC Applique type terry Emb 8000 stc Dev. By Design mode | NFL 2 | Size Set Run | 1129 | 100 | -1029 | 0 | -2472 | 0 | 0 | 0 | 0 | -2472 | 0 | 9-5 | #N/A
BS-ONL | 23823 | 1528088 | 600 | LS Swt shirt W Slv dble Panel | 2022-08-27 |  | 2022-09-01 | 2022-09-01 | 2022-09-08 | 2022-09-15 | 2022-09-19 | 2022-09-24 | M1 | Faisal |  | Terry | Bonbon R-300,First R-300 all cmb UC Applique type terry Emb 8000 stc Dev. By Design mode | NFL 2 | File Due | 112 | 59 | -53 | 0 | -600 | 0 | 0 | 0 | 0 | -600 | 0 | 9-5 | #N/A
BS-ONL | 23777 | 15285854 | 810 | C&S LS Swt Shirt | 2022-09-05 |  | 2022-09-09 | 2022-09-09 | 2022-09-17 | 2022-09-19 | 2022-09-26 | 2022-09-28 | M1 | Faisal |  |  |  | NFL 2 | File Due | 437 | 12 | -425 | 0 | -810 | 0 | 0 | 0 | 0 | -810 | 0 | 9-6 | #N/A
BS-ONL | 23776 | 15280807 | 1305 | C&S LS Swt Shirt | 2022-09-03 |  | 2022-09-08 | 2022-09-08 | 2022-09-15 | 2022-09-20 | 2022-09-26 | 2022-09-28 | M1 | Faisal |  |  |  | NFL 2 | File Due | 590 | 16 | -574 | 0 | -1305 | 0 | 0 | 0 | 0 | -1305 | 0 | 9-7 | #N/A
BS-ONL | 23844 | 15282628 | 852 | C&S LS Swt Shirt | 2022-08-20 |  | 2022-08-24 | 2022-08-24 | 2022-09-02 | 2022-09-17 | 2022-09-26 | 2022-09-28 | M1 | Faisal | Chest |  | Moonbeam L.BROWN-852 C&S Letter ambush | NFL 2 | File Due | 316 | 0 | -316 | 0 | -852 | 0 | 0 | 0 | 0 | -852 | 0 | 9-8 | #N/A
BS-ONL | 24102 | 15293785 | 18480 | YD LS TS | 2022-08-22 |  | 2022-08-20 | 2022-08-20 | 2022-08-27 | 2022-09-01 | 2022-09-12 | 2022-09-14 | M1+M2 | Iftekher |  |  |  | NFL 2 | Need Cut FB | 4120 | 3 | -4117 | 0 | -18480 | 0 | 0 | 0 | 0 | -18480 | 0 | 9-1+1 | Ok
BS-ONL | 23774 | 15282988 | 3060 | Tank Top | 2022-08-18 |  | 2022-08-22 | 2022-08-22 | 2022-08-29 | 2022-09-01 | 2022-09-08 | 2022-09-08 | N1 | Masud Rana |  |  |  | NFL 2 | File Due | 618 | 618 | 0 | 0 | -3060 | 0 | 0 | 0 | 0 | -3060 | 0 | 9-1 | #N/A
OVS SPA | 23278 | 22TSH007 | 3005 | YD LS TS | 2022-08-13 |  | 2022-08-22 | 2022-08-22 | 2022-08-30 |  | 2022-09-20 | 2022-09-20 | N1 | Alamain |  |  |  | NFL 2 | Need Test Cut | 706 | 0 | -706 | 0 | -3005 | 0 | 0 | 0 | 0 | -3005 | 0 | 9-5 | #N/A
OVS SPA | 22976 | 231MMP200 | 5615 | LS TS | 2022-07-30 | 2022-08-21 | 2022-08-28 | 2022-08-28 | 2022-09-07 | 2022-09-12 | 2022-09-30 | 2022-09-30 | N1 | Salam |  |  |  | NFL 2 | Need Cut | 1521 | 1521 | 0 | 0 | -5615 | 0 | 0 | 0 | 0 | -5615 | 0 | 9-6 | #N/A
OVS SPA | 22977 | 231MMP201 | 6488 | LS TS | 2022-08-10 |  | 2022-08-19 | 2022-08-19 | 2022-05-16 | 2022-09-07 | 2022-09-30 | 2022-09-30 | N1 | Salam | Chest |  | DGM-6488 5 CLR Flock | NFL 2 | Cut Ok | 1725 | 1725 | 0 | 6598 | 110 | 6598 | 0 | -6598 | 0 | -6488 | 0 | 9-7 | Hang tag due
OVS SPA | 23690 | 231PJA510 | 24066 | LS TS W All Hem Letuce & Payjama W Cuff Letuce | 2022-08-05 | 2022-08-24 | 2022-09-01 | 2022-09-01 | 2022-08-23 | 2022-09-19 | 2022-10-15 | 2022-10-15 | N1+N2 | Alamin | Nk |  |  | NFL 2 | File Due | 2999 | 0 | -2999 | 0 | -24066 | 0 | 0 | 0 | 0 | -24066 | 0 | 9-8+9 | #N/A
OVS SPA | 23314 | 231PJA505BK | 2646 | LS TS W All Hem Letuce & Payjama W Cuff Letuce | 2022-08-09 | 2022-08-26 | 2022-09-05 | 2022-09-05 | 2022-08-23 | 2022-09-24 | 2022-10-12 | 2022-10-12 | N1+N2 | Alamin | Chest |  | Pink-2646 Top 3 clr pig 1 clr glit | NFL 2 | File Due | 672 | 660 | -12 | 0 | -2646 | 0 | 0 | 0 | 0 | -2646 | 0 | 9-9+9 | #N/A
OVS SPA | 22945 | 231PJA006 | 5300 | LS TS W PLKT & Plazu | 2022-07-04 | 2022-07-30 | 2022-08-09 | 2022-08-09 | 2022-08-18 | 2022-09-01 | 2022-09-17 | 2022-09-18 | N1+O | Basir | Chest |  | 14-3905 tpg-2400 1 clr glitter 4 clr rub | NFL 2 | Size Set Run | 2480 | 2414 | -66 | 0 | -5300 | 0 | 0 | 0 | 0 | -5300 | 0 | 9-2+1 | all ok
OVS SPA | 22946 | 231PJA007 | 5300 | LS TS W PLKT & Plazu | 2022-07-04 | 2022-07-30 | 2022-08-09 | 2022-08-09 | 2022-11-17 | 2022-09-01 | 2022-09-17 | 2022-09-18 | N1+O | Basir | Chest |  | Coarsage-2900 1 clr glitter 4 clr rub | NFL 2 | Cut Ok | 2462 | 2417 | -45 | 10798 | 5498 | 2971 | 2964 | -7 | 0 | -5300 | 0 | 9-3+2 | #N/A
OVS SPA | 22947 | 231PJA00PD3 | 2320 | LS Dress W Lace at SF cuff,Btm | 2022-09-16 |  | 2022-09-24 | 2022-09-24 | 2022-10-04 | 2022-10-08 | 2022-10-25 | 2022-10-25 | N1+O | Basir |  |  |  | NFL 2 | Cut Ok | 1424 | 1409 | -15 | 3087 | 767 | 0 | 0 | 0 | 0 | -2320 | 0 | 9-4+3 | #N/A
BS-ONL | 23772 | 15281451 | 1164 | SS TS | 2022-08-08 |  | 2022-08-13 | 2022-08-13 | 2022-08-22 | 2022-09-01 | 2022-09-07 | 2022-09-07 | N2 | Masud Rana | Chest Flock |  | First tee1164 pcs 1 clr letteing flock print | NFL 2 | Cut Ok | 251 | 251 | 0 | 1202 | 38 | 0 | 0 | 0 | 0 | -1164 | 0 | 9-1 | #N/A
BS-ONL | 23163 | 15274730 15286828 | 1704 | LS TS | 2022-08-04 |  | 2022-08-10 | 2022-08-10 | 2022-08-18 | 2022-09-01 | 2022-09-26 | 2022-09-28 | N2 | Iftekhar | Chest |  | B.Night-1062,B.Blue-642 bth cmb 1 clr rub | NFL 2 | Cut Ok | 352 | 352 | 0 | 1770 | 66 | 1770 | 1768 | -2 | 0 | -1704 | 0 | 9-2 | #N/A
BS-ONL | 23192 | 15282069 | 732 | LS TS | 2022-08-04 |  | 2022-08-14 | 2022-08-14 | 2022-08-23 | 2022-09-03 | 2022-09-20 | 2022-09-28 | N2 | Iftekhar | Chest |  | B.Blue-732 1 clr rub | NFL 2 | Need Cut | 98 | 98 | 0 | 0 | -732 | 0 | 0 | 0 | 0 | -732 | 0 | 9-3 | Price sticker due.
BS-ONL | 23166 | 15279358 | 588 | SS TS | 2022-08-08 |  | 2022-08-16 | 2022-08-16 | 2022-08-24 | 2022-09-06 | 2022-09-19 | 2022-09-28 | N2 | Iftekhar | Chest |  | Whisper White-588 | NFL 2 | Cut Ok | 83 | 83 | 0 | 588 | 0 | 606 | 555 | -51 | 0 | -588 | 0 | 9-4 | Ok
BS-ONL | 23974 | 13282153 | 4992 | SS TS | 2022-08-03 |  | 2022-08-02 | 2022-08-02 | 2022-08-10 | 2022-08-16 | 2022-09-27 | 2022-09-29 | N2 | Subarno | Chest | Seq | Black TOI-1712 UC 2 clr rub 1 clr seq,B.White PT-1712 2 clr Pig 1 clr seq ,Pumice Stone FLEUR-1568 front part all ove type 2 clr pig 1clr seq | NFL 2 | Cut Ok | 747 | 743 | -4 | 5174 | 182 | 5174 | 0 | -5174 | 0 | -4992 | 0 | 9-5 | #N/A
OVS SPA | 23203 | 223TSHFTT82 | 4304 | SS TS | 2022-07-28 |  | 2022-08-09 | 2022-08-09 | 2022-08-18 | 2022-09-01 | 2022-09-20 | 2022-09-20 | N2 | Momin | Chest |  | Blue-2800,TBC-1504 bth Cmb 1 cr HD & 1 clr gliter | NFL 2 | Size Set Run | 601 | 360 | -241 | 0 | -4304 | 0 | 0 | 0 | 0 | -4304 | 0 | 9-6 | #N/A
OVS SPA | 23210 | 223TSHFTT64 | 4902 | SL TS | 2022-08-12 |  | 2022-08-20 | 2022-08-20 | 2022-06-29 | 2022-09-12 | 2022-09-30 | 2022-10-05 | N2 | Momin | Chest |  | White-2400,Navy-1500,TBC-1=1002 all cmb 2 clr pig | NFL 2 | Cut Ok | 873 | 426 | -447 | 0 | -4902 | 0 | 0 | 0 | 0 | -4902 | 0 | 9-7 | All due
OVS SPA | 22979 | 231MMP203 | 7453 | Pant W SF Cuff & BTN | 2022-07-28 | 2022-08-19 | 2022-08-29 | 2022-08-29 | 2022-09-07 | 2022-09-13 | 2022-09-30 | 2022-09-30 | O | Salam |  |  |  | NFL 2 | Need Cut | 2248 | 2201 | -47 | 0 | -7453 | 0 | 0 | 0 | 0 | -7453 | 0 | 9-4 | #N/A
OVS SPA | 22980 | 231MMP204 | 6296 | Pant W SF Cuff & BTN | 2022-08-16 |  | 2022-08-22 | 2022-08-22 | 2022-09-02 | 2022-09-06 | 2022-09-30 | 2022-09-30 | O | Salam |  |  |  | NFL 2 | Cut Run | 1684 | 1684 | 0 | 3514 | -2782 | 0 | 0 | 0 | 0 | -6296 | 0 | 9-5 | #N/A
OVS SPA | 22981 | 231MMP205 | 7411 | Pant W SF Cuff & BTN | 2022-07-28 | 2022-08-16 | 2022-08-25 | 2022-08-25 | 2022-09-02 | 2022-09-06 | 2022-09-30 | 2022-09-30 | O | Salam |  |  |  | NFL 2 | Cut Run | 2038 | 1928 | -110 | 1400 | -6011 | 0 | 0 | 0 | 0 | -7411 | 0 | 9-6 | #N/A
BS-ONL | 23771 | 15281415 | 801 | Swt T Shirt | 2022-08-25 |  | 2022-09-03 | 2022-09-03 | 2022-09-12 | 2022-09-22 | 2022-10-03 | 2022-10-05 | O | Masud Rana |  | Terry | Black-801 pcs lettering arrey emb | NFL 2 | File Due | 578 | 578 | 0 | 0 | -801 | 0 | 0 | 0 | 0 | -801 | 0 | 9-8 | #N/A
BS-ONL | 23189 | 15282064 | 1348 | Pant W Fr PKT & Metal DRST | 2022-07-30 |  | 2022-08-10 | 2022-08-10 | 2022-08-19 | 2022-09-01 | 2022-09-26 | 2022-09-28 | P | Iftekhar | Thigh |  | Black-762,B.Blue-586 bth cmb 1 clr rub | NFL 2 | Cut Ok | 511 | 511 | 0 | 1398 | 50 | 1392 | 1225 | -167 | 0 | -1348 | 0 | 9-1 | Drawstring,Price sticker due
BS-ONL | 23171 | 15274729 15274733 | 1776 | HW Legging W SF C&S | 2022-08-05 |  | 2022-08-14 | 2022-08-14 | 2022-08-21 | 2022-09-03 | 2022-09-20 | 2022-09-28 | P | Iftekhar | Waist Band,Bth leg |  | Blue Night-1776 1 clr rub bth leg and waist | NFL 2 | Cut Ok | 461 | 461 | 0 | 1836 | 60 | 1836 | 1216 | -620 | 0 | -1776 | 0 | 9-2 | Ok
OVS SPA | 23206 | 231TROFTB48 | 4200 | Pant W FR PKT & Pleat At FR Part DRST | 2022-08-08 |  | 2022-08-20 | 2022-08-20 | 2022-09-02 | 2022-09-06 | 2022-09-26 | 2022-10-01 | P | Momin |  |  |  | NFL 2 | CAD | 1983 | 1931 | -52 | 0 | -4200 | 0 | 0 | 0 | 0 | -4200 | 0 | 9-3 | Sewing thread,Care label,Drawstring,Hang tag,Poly due
OVS SPA | 23205 | 231TROFTB36 | 4606 | Pant W FR PKT & Pleat At FR Part DRST | 2022-08-10 |  | 2022-08-20 | 2022-08-20 | 2022-08-31 | 2022-09-09 | 2022-09-27 | 2022-10-01 | P | Momin |  | Thigh | Navy-2002,Green-1603,TBC-1001 all cmb 1 clr rub | NFL 2 | File Due | 2336 | 890 | -1446 | 0 | -4606 | 0 | 0 | 0 | 0 | -4606 | 0 | 9-4 | All due
BS-ONL | 23840 | 15281093 | 1362 | Pant W Elasten SF Cuff & DRST | 2022-08-27 |  | 2022-09-02 | 2022-09-02 | 2022-09-10 | 2022-09-14 | 2022-09-26 | 2022-09-28 | P | Faisal |  |  |  | NFL 2 | File Due | 333 | 0 | -333 | 0 | -1362 | 0 | 0 | 0 | 0 | -1362 | 0 | 9-5 | #N/A
BS-ONL | 23780 | 15281539 | 1305 | Pant W Lurex Waist Belt | 2022-08-26 |  | 2022-09-02 | 2022-09-02 | 2022-09-09 | 2022-09-26 | 2022-09-26 | 2022-09-28 | P | Faisal |  | Thigh | Black LOGO-1305 1 clr lurex trd EMB | NFL 2 | Size Set Run | 588 | 0 | -588 | 0 | -1305 | 0 | 0 | 0 | 0 | -1305 | 0 | 9-6 | #N/A
BS-ONL | 23837 | 15281480 | 600 | Pant W Cuff & Waist Belt | 2022-08-27 |  | 2022-09-05 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-09-28 | P | Faisal |  | Thigh | Oatmeal Melange-600 1 clr Lurex thrd EMB | NFL 2 | File Due | 218 | 0 | -218 | 0 | -600 | 0 | 0 | 0 | 0 | -600 | 0 | 9-6 | #N/A
BS-ONL | 23827 | 15281094 | 600 | Pant W Elasten SF Cuff & DRST | 2022-08-31 |  | 2022-09-08 | 2022-09-08 | 2022-09-16 | 2022-09-19 | 2022-09-26 | 2022-09-28 | P | Faisal |  |  |  | NFL 2 | File Due | 95 | 0 | -95 | 0 | -600 | 0 | 0 | 0 | 0 | -600 | 0 | 9-7 | #N/A
BS-ONL | 23826 | 15281473 | 612 | Pant W Frill at FR PKT | 2022-08-31 |  | 2022-09-06 | 2022-09-06 | 2022-09-14 | 2022-09-19 | 2022-10-03 | 2022-10-05 | P | Faisal |  |  |  | NFL 2 | File Due | 134 | 0 | -134 | 0 | -612 | 0 | 0 | 0 | 0 | -612 | 0 | 9-8 | #N/A
BS-ONL | 23839 | 15281471 | 612 | Pant W Frill at FR PKT | 2022-09-02 |  | 2022-09-07 | 2022-09-07 | 2022-09-15 | 2022-09-19 | 2022-10-03 | 2022-10-05 | P | Faisal |  |  |  | NFL 2 | File Due | 212 | 0 | -212 | 0 | -612 | 0 | 0 | 0 | 0 | -612 | 0 | 9-9 | #N/A
BS-ONL | 23190 | 15282066 | 1356 | LS Reglan Swt Shirt | 2022-08-05 |  | 2022-08-14 | 2022-08-14 | 2022-05-13 | 2022-09-01 | 2022-09-26 | 2022-09-28 | Q | Iftekhar | Chest |  | Black-872,B.Blue-484 bth cmb 1 clr rub | NFL 2 | Cut Ok | 407 | 407 | 0 | 1404 | 48 | 1404 | 1403 | -1 | 0 | -1356 | 0 | 9-1 | Herringbone tape-Black, Brilliant Blue, Price sticker due
OVS SPA | 23244 | 30TSH008 | 11641 | SS TS | 2022-07-29 |  | 2022-08-01 | 2022-08-01 | 2022-05-21 | 2022-09-05 | 2022-09-30 | 2022-10-05 | Q | Momin | Chest,Stone |  | Off White-6307,Peach-4004 all cmb 7 clr rub 1 then Stone stiker attach | NFL 2 | File Due | 1066 | 1060 | -6 | 0 | -11641 | 0 | 0 | 0 | 0 | -11641 | 0 | 9-2 | #N/A
OVS SPA | 23362 | 231TSH232 | 6306 | SS TS W FR PKT | 2022-08-20 |  | 2022-08-24 | 2022-08-24 | 2022-05-20 | 2022-09-07 | 2022-09-25 | 2022-09-25 | Q | Momin |  |  |  | NFL 2 | Ready Test Cut | 537 | 537 | 0 | 0 | -6306 | 0 | 0 | 0 | 0 | -6306 | 0 | 9-3 | #N/A
OVS SPA | 23245 | 30TSH009 | 9016 | LS Reglan TS | 2022-08-10 |  | 2022-08-19 | 2022-08-19 | 2022-08-29 | 2022-09-08 | 2022-09-30 | 2022-10-05 | Q | Momin |  | Chest | Dk Coral-6874,Dk Lemon-2142 bth cmb 1 clr thrd Letter HD EMB | NFL 2 | File Due | 1993 | 1505 | -488 | 0 | -9016 | 0 | 0 | 0 | 0 | -9016 | 0 | 9-5 | Sewing thread,Hang tag,Hanger due
OVS SPA | OVS 23358 | 231TSH038 | 5826 | SS T Shirt W Btn | 2022-08-22 |  | 2022-09-01 | 2022-09-01 | 2022-05-10 | 2022-09-14 | 2022-09-24 | 2022-09-25 | Q | Momin |  |  |  | NFL 2 | File Due | 0 | 0 | 0 | 0 | -5826 | 0 | 0 | 0 | 0 | -5826 | 0 | 9-5 | #N/A
OVS SPA | OVS 23200 | 223TSHFTT66 | 2796 | Lds Jumsuit | 2022-08-05 |  | 2022-08-16 | 2022-08-16 |  | 2022-09-01 | 2022-09-20 | 2022-09-20 | R | Momin |  |  |  | NFL 2 | Size Set Run | 0 | 0 | 0 | 0 | -2796 | 0 | 0 | 0 | 0 | -2796 | 0 | 9-1 | Sewing thread,Care label,Button,Hanger loop,Hang tag due
OVS SPA | 23204 | 2223SWTFTT84 | 3400 | LS Hoody Cardigan W DRST,2 FR PKT and Full PLK& SNP BTN | 2022-08-10 |  | 2022-08-19 | 2022-08-19 |  | 2022-09-05 | 2022-09-23 | 2022-09-25 | R | Momin |  |  |  | NFL 2 | CAD | 1949 | 1938 | -11 | 0 | -3400 | 0 | 0 | 0 | 0 | -3400 | 0 | 9-2 | Sewing thread,Care label,Hang tag,Poly,Drawstring due
OVS SPA | 23274 | 22LJK004 | 5970 | LS C&S Swt Cardigan W Fr PKT & YD Collor,Cuff,BTM | 2022-08-03 |  | 2022-08-08 | 2022-08-08 | 2022-08-24 | 2022-09-03 | 2022-09-20 | 2022-09-20 | R | Alamain |  | Chest | Fuxia/White=5970, Patch make, 1 clr thrd arry,3 clr thrd EMB CRITICAL | NFL 2 | Size Set Run | 2601 | 2600 | -1 | 0 | -5970 | 0 | 0 | 0 | 0 | -5970 | 0 | 9-3 | #N/A
OVS SPA | 23208 | 231SWTFTT61 | 5196 | LS Hoody W DRST | 2022-08-06 |  | 2022-08-13 | 2022-08-13 | 2022-06-30 | 2022-09-10 | 2022-10-05 | 2022-10-05 | R | Momin | Chest | Chest | White-1998,Navy-1398,TBC-1=1002,TBC-2=798 all cmb 2 clr pig 1 clr thrd Letter 3D Emb | NFL 2 | Cut Ok | 2772 | 1282 | -1490 | 0 | -5196 | 0 | 0 | 0 | 0 | -5196 | 0 | 9-3 | #N/A
OVS SPA | 23209 | 231SWTFTT63 | 3186 | LS Hoody Jacket | 2022-08-09 |  | 2022-08-17 | 2022-08-17 | 2022-06-23 | 2022-09-12 | 2022-09-29 | 2022-10-01 | R | Momin |  | Chest | Blue -1986,Green-1200 all cmb upper chest 1 clr thrd Emb 3000 stc | NFL 2 | Cut Ok | 1744 | 0 | -1744 | 0 | -3186 | 0 | 0 | 0 | 0 | -3186 | 0 | 9-4 | #N/A
OVS SPA | 23360 | 231SWT230 | 6852 | LS Cardigan | 2022-08-20 |  | 2022-08-24 | 2022-08-24 | 2022-10-07 | 2022-09-12 | 2022-09-30 | 2022-09-30 | R | Khairul | Chest |  | N.Blazer-3684,S.Glade-1968,Riverside-1200 all cmb 1 clr rub | NFL 2 | File Due | 1365 | 872 | -493 | 0 | -6852 | 0 | 0 | 0 | 0 | -6852 | 0 | 9-4 | #N/A
OVS SPA | 23361 | 231SWT231 | 6084 | LS Hoody JKt | 2022-08-04 | 2022-08-22 | 2022-09-02 | 2022-09-02 | 2022-10-01 | 2022-09-14 | 2022-09-30 | 2022-09-30 | R | Khairul |  |  |  | NFL 2 | File Due | 1454 | 425 | -1029 | 0 | -6084 | 0 | 0 | 0 | 0 | -6084 | 0 | 9-7 | #N/A

## S-3 (hidden)
Buyer | Job | Style | Order Qty | Item Description | Dyeing-Finishing T & A End | All Over Print T & A End | Trims & Accessories T & A End | Production & Other File Handover Date | Cutting T & A Start | Sewing T & A Start | Ex-Factory Date | Cargo Closing Date | Line | Merchandiser Name | Print Position | Embriodary Position | Print & Emb Description | Remarks | Floor | PRESENT STATUS | Fabric Req. (in Kg) | Fabric Received | Fabric Balance | Cutting Qty | Cutting Balance | Print/Embr. Require | Print Send | Print rcvd | Recv balance | Sewing input | Sewing input Balance | Sewing Qty | Priority | Trims Due Details
GBX ( New Look) | 24101 | 8471859 | 5148 | Lds Playsuit | 2022-08-21 |  | 2022-08-20 | 2022-08-20 | 2022-08-29 | 2022-09-01 | 2022-09-10 | 2022-09-11 | S | Shofi |  |  |  |  | NFL 3 | File Due | 1266 | 0 | -1266 | 0 | -5148 |  | 0 | 0 | 0 | 0 | -5148 | 0 | 9-1 | Ok
BS-NMT | 24011 | 13212489 | 10689 | C&S LS Hoody | 2022-08-25 |  | 2022-08-30 | 2022-08-29 | 2022-09-06 | 2022-09-13 | 2022-10-03 | 2022-10-05 | S | Tomal | Chest |  | D.Sapphire-5592,GM-5079 both combo cut & Sew 1 clr rubber |  | NFL 3 | File Due | 4302 | 4233 | -69 | 0 | -10689 |  | 0 | 0 | 0 | 0 | -10689 | 0 | 9-10 | #N/A
BS-NMT | 23889 | 13212215 | 2514 | C&S LS Hoody | 2022-08-19 |  | 2022-08-24 | 2022-08-24 | 2022-09-02 | 2022-09-13 | 2022-10-03 | 2022-10-05 | S | Kamruzzaman | Chest |  | O.Chiffon-1311 ,L.wreath-1203 bth cmb 2 clr rub |  | NFL 3 | File Due | 1043 | 394 | -649 | 0 | -2514 |  | 0 | 0 | 0 | 0 | -2514 | 0 | 9-11 | #N/A
GBX ( New Look) | 24127 | 8471859 | 824 | Lds Playsuit | 2022-08-20 |  | 2022-08-24 | 2022-08-24 | 2022-09-02 | 2022-09-05 | 2022-09-10 | 2022-09-11 | S | Shofi |  |  |  |  | NFL 3 | File Due | 197 | 0 | -197 | 0 | -824 |  | 0 | 0 | 0 | 0 | -824 | 0 | 9-2 | #N/A
GBX ( New Look) | 24128 | 8471859 | 721 | Lds Playsuit | 2022-08-20 |  | 2022-08-24 | 2022-08-24 | 2022-09-02 | 2022-09-05 | 2022-09-10 | 2022-09-11 | S | Shofi |  |  |  |  | NFL 3 | File Due | 190 | 0 | -190 | 0 | -721 |  | 0 | 0 | 0 | 0 | -721 | 0 | 9-3 | #N/A
BS-ONL | 23841 | 15281091 | 1820 | LS Hoody PB W Hood Inner Tapeta Fabric & Etasen Hem | 2022-08-22 |  | 2022-08-25 | 2022-08-25 | 2022-09-02 | 2022-09-10 | 2022-09-19 | 2022-09-21 | S | Faisal | Chest |  | Provence TODAY-1800 1b clr Letter Foil |  | NFL 3 | File Due | 463 | 0 | -463 | 0 | -1820 |  | 0 | 0 | 0 | 0 | -1820 | 0 | 9-4 | #N/A
BS-ONL | 23830 | 15221787 | 4344 | LS Hoody PB W Hood Inner Tapeta Fabric | 2022-08-22 |  | 2022-08-25 | 2022-08-25 | 2022-09-01 | 2022-09-02 | 2022-09-26 | 2022-09-28 | S | Faisal | Chest |  | C.Blue ONLY-2556, P.Rose ONLY-1788 all cmb 1 clr Letter Glit |  | NFL 3 | File Due | 1511 | 0 | -1511 | 0 | -4344 |  | 0 | 0 | 0 | 0 | -4344 | 0 | 9-5 | #N/A
BS-ONL | 23835 | 15281424 | 2958 | C&S LS Hoody | 2022-09-02 |  | 2022-09-05 | 2022-09-05 | 2022-09-12 | 2022-09-15 | 2022-09-26 | 2022-09-28 | S | Faisal |  |  |  |  | NFL 3 | File Due | 1355 | 0 | -1355 | 0 | -2958 |  | 0 | 0 | 0 | 0 | -2958 | 0 | 9-6 | #N/A
BS-ONL | 23843 | 15282660 | 804 | C&S LS Hoody | 2022-08-27 |  | 2022-09-02 | 2022-09-02 | 2022-09-09 | 2022-09-19 | 2022-09-26 | 2022-09-28 | S | Faisal | MP |  | Moonstruck BLUE BLIZZARD-804 C&S UC & Btm 1 clr HD 1cl Rub |  | NFL 3 | File Due | 363 | 0 | -363 | 0 | -804 |  | 0 | 0 | 0 | 0 | -804 | 0 | 9-7 | #N/A
BS-ONL | 23784 | 15280427 | 1167 | C&S LS Hoody | 2022-08-20 | 2022-08-31 | 2022-09-05 | 2022-09-05 | 2022-09-12 | 2022-09-15 | 2022-09-26 | 2022-09-28 | S | Faisal |  |  |  |  | NFL 3 | Ready Test Cut | 633 | 156 | -477 | 0 | -1167 |  | 0 | 0 | 0 | 0 | -1167 | 0 | 9-8 | #N/A
BS-ONL | 23775 | 15280806 | 1620 | C&S LS Hoody W DRST | 2022-08-31 |  | 2022-09-05 | 2022-09-05 | 2022-09-12 | 2022-09-15 | 2022-09-26 | 2022-09-28 | S | Faisal |  | Terry | C Dancer-810,N.Sky-810 all cmb UC Applique type terry Emb 8000 stc Dev. By Design mode |  | NFL 3 | File Due | 702 | 82 | -620 | 0 | -1620 |  | 0 | 0 | 0 | 0 | -1620 | 0 | 9-9 | #N/A
OVS SPA | 23674 | 231TRO006 | 93967 | Pant W Fr PKT & DRST | 2022-08-03 |  | 2022-08-01 | 2022-07-26 | 2022-08-03 | 2022-08-12 | 2022-09-20 | 2022-09-20 | S+U+X1+U+X | Sirajul | Chest |  | Dress Blue-26316,O.Blue-18540,G.Kiwi-3038,D.Mint-7541,P.Black-16800,D.Gray-16788 all cmb 1 clr rub |  | NFL 3 | Cut Run | 24345 | 24250 | -95 | 34382 | -59585 |  | 37954 | 30542 | -7412 | 10752 | -83215 | 3475 | 8+9-4+2+1+1+1 | Drawstring Partial Due
BS-NMT | 24108 | 13205791 | 3000 | Legging | 2022-08-11 | 2022-08-17 | 2022-08-17 | 2022-08-17 | 2022-08-23 | 2022-09-01 | 2022-09-12 | 2022-09-14 | T | Kamruzzaman | Waist |  |  |  | NFL 3 | Cut Run | 394 | 394 | 0 | 1522 | -1478 |  | 1522 | 1522 | 0 | 0 | -3000 | 0 | 9-1 | Price Sticker due
BS-NMT | 23853 | 13217547 | 1500 | LS Swt Shirt B | 2022-08-25 |  | 2022-09-03 | 2022-09-03 | 2022-09-10 | 2022-09-20 | 2022-10-10 | 2022-10-12 | T | Sadia | Chest |  | Deco Rose-3 clr rub 1 clr glit |  | NFL 3 | File Due | 275 | 275 | 0 | 0 | -1500 |  | 0 | 0 | 0 | 0 | -1500 | 0 | 9-10 | #N/A
BS-NMT | 23791 | 13212757 | 6108 | [5 empty] | 2022-08-29 |  | 2022-10-10 | 2022-10-12 | T | Mahmud | Chest,Nk |  |  |  | NFL 3 | Need Cut | 483 | 483 | 0 | 0 | -6108 |  | 0 | 0 | 0 | 0 | -6108 | 0 | 9-2 | #N/A
BS-NMT | 23792 | 13212658 | 3254 | [5 empty] | 2022-08-30 |  | 2022-10-10 | 2022-10-12 | T | Mahmud | Chest,Nk |  |  |  | NFL 3 | Need Cut | 258 | 258 | 0 | 0 | -3254 |  | 0 | 0 | 0 | 0 | -3254 | 0 | 9-3 | #N/A
BS-NMT | 23793 | 13212746 | 4013 | [7 empty] | 2022-10-10 | 2022-10-12 | T | Mahmud | Chest,Nk |  |  |  | NFL 3 | Cut Run | 318 | 315 | -3 | 1888 | -2125 |  | 0 | 0 | 0 | 0 | -4013 | 0 | 9-4 | #N/A
BS-NMT | 23694 2nd | 13204840 | 4500 | LS TS W Lace at Slv,Nk | 2022-08-26 |  | 2022-09-01 | 2022-09-01 | 2022-05-12 | 2022-09-14 | 2022-10-03 | 2022-10-05 | T | Tomal | Nk |  |  |  | NFL 3 | File Due | 585 | 195 | -390 | 0 | -4500 |  | 0 | 0 | 0 | 0 | -4500 | 0 | 9-7 | #N/A
BS-NMT | 23796 | 13212668 | 8561 | [5 empty] | 2022-09-06 |  | 2022-09-26 | 2022-10-10 | T | Mahmud | Chest |  |  |  | NFL 3 | Need Cut | 1083 | 808 | -275 | 0 | -8561 |  | 0 | 0 | 0 | 0 | -8561 | 0 | 9-8 | #N/A
BS-NMT | 23797 | 13212747 | 8885 | [5 empty] | 2022-09-05 |  | 2022-10-10 | 2022-10-12 | T | Mahmud | Chest |  |  |  | NFL 3 | Need Cut | 1124 | 879 | -245 | 0 | -8885 |  | 0 | 0 | 0 | 0 | -8885 | 0 | 9-9 | #N/A
BS-NMT | 23794 | 13217992 | 810 | SWT AOP Legging & LS TS W SH PLKT | 2022-08-17 | 2022-08-27 | 2022-09-03 | 2022-09-03 | 2022-09-09 | 2022-09-15 | 2022-10-10 | 2022-10-12 | T+W | Mahmud | Chest,Nk |  | Rose smoke-405 4 clr rub,Deco Rose-405 NA |  | NFL 3 | Size Set Run | 82 | 52 | -30 | 0 | -810 |  | 0 | 0 | 0 | 0 | -810 | 0 | 9-5+6 | #N/A
BS-NMT | 23795 | 13217990 | 840 | LS TS W SH PLKT & Swt pant W FR Fake PKT | 2022-08-25 |  | 2022-09-02 | 2022-09-02 | 2022-09-08 | 2022-09-13 | 2022-10-10 | 2022-10-12 | T+W | Mahmud | Chest,Nk |  | W.Allysum-420 2 clrm rub 2 clr puff,B.Blue-420 NA |  | NFL 3 | Size Set Run | 81 | 48 | -33 | 0 | -840 |  | 0 | 0 | 0 | 0 | -840 | 0 | 9-6+5 | #N/A
BS-NMT | 24166 | 13216826 | 2010 | C&S Swt Pant B W Fr PKT & DRST | 2022-08-27 |  | 2022-09-03 | 2022-09-03 | 2022-09-10 | 2022-09-19 | 2022-09-30 | 2022-10-05 | U | Shamoly | Chest |  | D.Sapphire-996,P.Whip-996 both combo pant cut & Sew 1 clr rubber |  | NFL 3 | File Due | 0 | 0 | 0 | 0 | -2010 |  | 0 | 0 | 0 | 0 | -2010 | 0 | 9-2 | #N/A
BS-NMT | 23852 | 13212808 | 1953 | Swt Pant w FR PKT & FR Pleat B | 2022-08-27 |  | 2022-09-06 | 2022-09-06 | 2022-09-14 | 2022-09-19 | 2022-10-10 | 2022-10-12 | U | Sadia |  |  |  |  | NFL 3 | File Due | 405 | 0 | -405 | 0 | -1953 |  | 0 | 0 | 0 | 0 | -1953 | 0 | 9-3 | #N/A
BS-NMT | 24006 | 13204808 | 3000 | Pant W FR PKT, Bone PKT W DRST | 2022-08-27 |  | 2022-09-05 | 2022-09-05 | 2022-09-13 | 2022-09-17 | 2022-10-03 | 2022-10-05 | U | Tomal |  |  |  |  | NFL 3 | File Due | 1030 | 0 | -1030 | 0 | -3000 |  | 0 | 0 | 0 | 0 | -3000 | 0 | 9-4 | #N/A
BS-NMT | 23891 | 13212531 | 2406 | Pant W FR PKT & Bk Bone PKT | 2022-08-18 | 2022-09-03 | 2022-09-08 | 2022-09-08 | 2022-09-16 | 2022-09-17 | 2022-10-08 | 2022-10-10 | U | Kamruzzaman |  |  |  |  | NFL 3 | File Due | 437 | 70 | -367 | 0 | -2406 |  | 0 | 0 | 0 | 0 | -2406 | 0 | 9-5 | #N/A
BS-NMT | 23798 | 13212751 | 4332 | LS Hood Night Suit W 1 slv spike | 2022-09-13 | 2022-09-27 | 2022-09-02 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-10-10 | 2022-10-12 | U | Mahmud | Chest,Nk |  | B.Blue-3336 3 clr rub,T.Coconut-996 NA |  | NFL 3 | File Due | 1018 | 823 | -195 | 0 | -4332 |  | 0 | 0 | 0 | 0 | -4332 | 0 | 9-5
BS-ONS | 23918 | 22024752 | 3354 | SS TS W PKT | 2022-08-16 |  | 2022-08-19 | 2022-08-19 | 2022-08-26 | 2022-09-08 | 2022-09-23 | 2022-09-28 | V | Shohag | MP |  | Moonstruck-1594,P.Ash-1824 bth cmb FR part UC 3 clr rub ,BK 4 clr rub BIG ART Nk patch |  | NFL 3 | File Due | 1054 | 1053 | -1 | 0 | -3354 |  | 0 | 0 | 0 | 0 | -3354 | 0 | 9-1 | File Due
BS-NMT | 24010 | 13212480 | 8577 | LS Hoody | 2022-07-16 | 2022-08-29 | 2022-09-01 | 2022-09-01 | 2022-09-07 | 2022-09-15 | 2022-10-03 | 2022-10-05 | V | Tomal | Chest |  | D.Sapphire-4773,GM-3804 both combo 1 clr glitter |  | NFL 3 | File Due | 3757 | 348 | -3409 | 0 | -8577 |  | 0 | 0 | 0 | 0 | -8577 | 0 | 9-10 | #N/A
BS-NMT | 24014 | 13213156 | 1866 | LS Swt Shirt B | 2022-08-26 |  | 2022-09-01 | 2022-09-01 | 2022-09-07 | 2022-09-20 | 2022-10-03 | 2022-10-05 | V | Tomal |  | Terry | L.Wreath-1068,O Chiffon-798 both combo 2 clr thraed emb and 1 clr lettring emb |  | NFL 3 | File Due | 625 | 3 | -622 | 0 | -1866 |  | 0 | 0 | 0 | 0 | -1866 | 0 | 9-11 | #N/A
BS-ONS | 23919 | 22024783 | 4115 | SS TS | 2022-08-16 |  | 2022-08-19 | 2022-08-19 | 2022-08-27 | 2022-09-05 | 2022-09-17 | 2022-09-21 | V | Shohag | Chest |  | Black-1013,Dachhund-1888 all cmb UC 1 clr rub |  | NFL 3 | File Due | 1412 | 765 | -647 | 0 | -4115 |  | 0 | 0 | 0 | 0 | -4115 | 0 | 9-2 | File Due
BS-ONS | 23923 | 22024751 | 2554 | LS Swt Shirt B | 2022-08-18 |  | 2022-08-20 | 2022-08-20 | 2022-08-29 | 2022-09-08 | 2022-09-19 | 2022-09-21 | V | Shohag | MP |  | Black-1358 FR Part UC 1 clr rub BK Part 1 clr rub BIG ART ,C.Dancer-1264 FR Part 1 clr rub BK Part 1 clr rub BIG ART , 1 Slv 1 clr rub |  | NFL 3 | File Due | 1607 | 774 | -833 | 0 | -2554 |  | 0 | 0 | 0 | 0 | -2554 | 0 | 9-3 | File Due
BS-NMT | 24161 | 13216549 | 1980 | LS Swt Shirt | 2022-08-30 |  | 2022-08-30 | 2022-08-30 | 2022-09-05 | 2022-09-13 | 2022-09-30 | 2022-10-05 | V | Shamoly | Chest |  | A.Green-999,D.Sapphire-231 all combo 1 clr rubber |  | NFL 3 | File Due | 0 | 0 | 0 | 0 | -1980 |  | 0 | 0 | 0 | 0 | -1980 | 0 | 9-4 | #N/A
BS-NMT | 24165 | 13216824 | 1998 | LS Swt Shirt | 2022-08-30 |  | 2022-08-31 | 2022-08-31 | 2022-09-06 | 2022-09-15 | 2022-09-30 | 2022-10-05 | V | Shamoly | Chest |  | D.Sapphire-96,Lgrey-903,P.Whip-903,P.Nectar-96 all combo 1 clr glitter |  | NFL 3 | File Due | 0 | 0 | 0 | 0 | -1998 |  | 0 | 0 | 0 | 0 | -1998 | 0 | 9-5 | #N/A
BS-NMT | 24169 | 13220206 | 1560 | LS Dress W Btm double part W Mesh | 2022-08-25 | 2022-09-03 | 2022-09-06 | 2022-09-06 | 2022-09-12 | 2022-09-17 | 2022-09-26 | 2022-09-28 | V | Shamoly | NK |  |  |  | NFL 3 | File Due | 0 | 0 | 0 | 0 | -1560 |  | 0 | 0 | 0 | 0 | -1560 | 0 | 9-6 | #N/A
BS-NMT | 23851 | 13212807 | 2725 | LS Swt Shirt W Fr Founce B | 2022-08-25 |  | 2022-09-03 | 2022-09-03 | 2022-09-12 | 2022-09-15 | 2022-10-10 | 2022-10-12 | V | Sadia |  |  |  |  | NFL 3 | File Due | 565 | 0 | -565 | 0 | -2725 |  | 0 | 0 | 0 | 0 | -2725 | 0 | 9-8 | #N/A
BS-NMT | 24170 | 13220207 | 1515 | LS Dress W Btm double part W Mesh | 2022-08-25 | 2022-09-03 | 2022-09-06 | 2022-09-06 | 2022-09-12 |  | 2022-09-23 | 2022-09-26 | V | Shamoly | NK |  |  |  | NFL 3 | File Due | 0 | 0 | 0 | 0 | -1515 |  | 0 | 0 | 0 | 0 | -1515 | 0 | 9-7 | #N/A
BS-NMT | 24029 | 13213219 | 2904 | LS Swt Shirt W Patch label | 2022-08-30 |  | 2022-09-07 | 2022-09-07 | 2022-09-14 | 2022-09-17 | 2022-09-30 | 2022-10-05 | V | Shamoly |  |  |  |  | NFL 3 | CAD | 1046 | 1039 | -7 | 0 | -2904 |  | 0 | 0 | 0 | 0 | -2904 | 0 | 9-9 | #N/A
Sainsbury | 23697 1st | SS23 | 4197 | LS Dress | 2022-08-26 |  | 2022-08-30 | 2022-08-26 | 2022-08-30 | 2022-09-01 | 2022-09-10 | 2022-09-14 | W | Mannan |  |  |  |  | NFL 3 | File Due | 0 | 0 | 0 | 0 | -4197 |  | 0 | 0 | 0 | 0 | -4197 | 0 | 9-1 | #N/A
Sainsbury | 23697 2nd | SS23 | 3673 | LS Dress | 2022-08-27 |  | 2022-08-30 | 2022-08-26 | 2022-09-01 | 2022-09-05 | 2022-09-24 | 2022-09-24 | W | Mannan |  |  |  |  | NFL 3 |  | 0 | 0 | 0 | 0 | -3673 |  | 0 | 0 | 0 | 0 | -3673 | 0 | 9-2
BS-NMT | 23799 | 13212748 | 8904 | SWT Pant W Fake FR PKT & Side Tri angle teeth shape | 2022-08-16 | 2022-08-29 | 2022-09-03 | 2022-09-03 | 2022-09-10 | 2022-09-14 | 2022-10-10 | 2022-10-12 | W | Mahmud |  |  |  |  | NFL 3 | Size Set Run | 930 | 92 | -838 | 0 | -8904 |  | 0 | 0 | 0 | 0 | -8904 | 0 | 9-3 | #N/A
BS-NMT | 23800 | 13212666 | 7523 | HW Pant | 2022-08-10 | 2022-08-23 | 2022-08-25 | 2022-08-25 | 2022-09-01 | 2022-09-09 | 2022-10-10 | 2022-10-12 | W | Mahmud | Thigh |  | Butter cream-5079 3 clr rib 1 clr glit ,Deco Rose- NA |  | NFL 3 | Size Set Run | 823 | 668 | -155 | 0 | -7523 |  | 0 | 0 | 0 | 0 | -7523 | 0 | 9-4 | #N/A
BS-NMT | 23854 | 13217548 | 1500 | HW Pant | 2022-08-25 |  | 2022-09-02 | 2022-09-02 | 2022-09-09 | 2022-09-17 | 2022-10-10 | 2022-10-12 | W | Sadia | Thigh |  | Deco Rose-3 clr rub 1 clr glit |  | NFL 3 | File Due | 264 | 262 | -2 | 0 | -1500 |  | 0 | 0 | 0 | 0 | -1500 | 0 | 9-7 | #N/A
BS-NMT | 24028 | 13213215 | 2952 | Pant W FR PKT, Elastane Cuff | 2022-08-30 |  | 2022-09-06 | 2022-09-06 | 2022-09-14 | 2022-09-19 | 2022-09-30 | 2022-10-05 | W | Shamoly |  |  |  |  | NFL 3 | File Due | 998 | 998 | 0 | 0 | -2952 |  | 0 | 0 | 0 | 0 | -2952 | 0 | 9-8 | #N/A
GUESS | 24037 | Q3GQ08KBEKO | 9172 | LS Swt Hoody W Woven Slv Panel | imported 12.09 |  | 2022-09-14 | 2022-09-16 | 2022-09-24 | 2022-09-28 | 2022-10-13 | 2022-10-13 | W | Mannan |  |  |  |  | NFL 3 |  | 1190 | 133 | -1057 | 0 | -9172 |  | 0 | 0 | 0 | 0 | -9172 | 0 | 9-9 | #N/A
BS-NMT | 23895 | 13212251 | 5154 | pant W FR PKT & Side Cargoo PKT | 2022-08-25 |  | 2022-09-02 | 2022-09-02 | 2022-09-12 | 2022-09-15 | 2022-10-03 | 2022-10-06 | X | Kamruzzaman |  |  |  |  | NFL 3 | File Due | 1894 | 0 | -1894 | 0 | -5154 |  | 0 | 0 | 0 | 0 | -5154 | 0 | 9-2 | #N/A
BS-NMT | 23880 | 13212251 | 8985 | pant W FR PKT & Side Cargoo PKT | 2022-08-27 |  | 2022-09-05 | 2022-09-05 | 2022-09-14 | 2022-09-19 | 2022-10-04 | 2022-10-10 | X | Kamruzzaman |  |  |  |  | NFL 3 | File Due | 1226 | 0 | -1226 | 0 | -8985 |  | 0 | 0 | 0 | 0 | -8985 | 0 | 9-3 | #N/A
BS-ONS | 23917 | 22024773 22025947 | 13696 | SS TS | 2022-08-12 | 2022-08-22 | 2022-08-22 | 2022-08-22 | 2022-08-29 | 2022-09-01 | 2022-09-26 | 2022-09-28 | Y1 | Shohag |  |  |  |  | NFL 3 | File Due | 3346 | 146 | -3200 | 0 | -13696 |  | 0 | 0 | 0 | 0 | -13696 | 0 | 9-1 | #N/A
BS-ONL | 19398 5th | 15256046 | 12920 | LS HNK TS Rib | 2022-06-15 |  | 1900-01-15 02:10 | 1900-01-15 02:10 | 2022-09-24 | 2022-10-10 | 2022-10-24 | 2022-10-26 | Y1 | Iftekhar |  |  |  |  | NFL 3 | File Due | 0 | 0 | 0 | 0 | -12920 |  | 0 | 0 | 0 | 0 | -12920 | 0 | 9-2 | Ok
BS-NMT | 23886 | 13212258 | 2199 | LS TS | 2022-08-25 |  | 2022-09-01 | 2022-09-01 | 2022-09-07 | 2022-09-16 | 2022-10-03 | 2022-10-05 | Y1 | Kamruzzaman | Chest,Nk |  | B.Blue-795 upper chest 3 clr rub 1clr glit,Buttercream-1404 5 clr rub |  | NFL 3 | Size Set Run | 373 | 238 | -135 | 0 | -2199 |  | 0 | 0 | 0 | 0 | -2199 | 0 | 9-3 | #N/A
BS-NMT | 23877 | 13212266 | 3177 | LS TS | 2022-08-25 |  | 2022-08-29 | 2022-08-29 | 2022-09-06 | 2022-09-15 | 2022-10-02 | 2022-10-05 | Y1 | Kamruzzaman | Chest,Nk |  | Buttercream-205 4 clr rub,Eventide-1152 3 clr rub 1 clr glit |  | NFL 3 | Cut Ok | 538 | 538 | 0 | 3268 | 91 |  | 3244 | 3230 | -14 | 0 | -3177 | 0 | 9-4 | #N/A
BS-NMT | 23879 | 132122021 | 3738 | LS TS | 2022-08-25 |  | 2022-08-29 | 2022-08-29 | 2022-09-06 | 2022-09-17 | 2022-10-03 | 2022-10-05 | Y1 | Kamruzzaman | Chest,Nk |  | B.Blue-1445 2 clr rub,F.Biome-1445 3 clr rub,O.Chiffon-848 4 clr urb |  | NFL 3 | Size Set Run | 724 | 713 | -11 | 0 | -3738 |  | 0 | 0 | 0 | 0 | -3738 | 0 | 9-5 | #N/A
BS-NMT | 23878 | 13212211 | 1656 | LS TS W FR PKT | 2022-08-25 |  | 2022-09-01 | 2022-09-01 | 2022-09-08 | 2022-09-19 | 2022-10-03 | 2022-10-05 | Y1 | Kamruzzaman | Nk |  | B.Blue-828,L.Wreath-828 |  | NFL 3 | File Due | 296 | 0 | -296 | 0 | -1656 |  | 0 | 0 | 0 | 0 | -1656 | 0 | 9-6 | #N/A
BS-NMT | 23887 | 13212199 | 4194 | LS TS | 2022-08-25 |  | 2022-08-29 | 2022-08-29 | 2022-09-05 | 2022-09-14 | 2022-10-03 | 2022-10-05 | Y1 | Kamruzzaman | Chest,Nk |  | B.Blue-1695,F.Biome-1695,O.Chiffon-804 all cmb 3 clr rub |  | NFL 3 | Size Set Run | 562 | 335 | -227 | 0 | -4194 |  | 0 | 0 | 0 | 0 | -4194 | 0 | 9-7 | #N/A
BS-NMT | 23881 | 13212200 13217282 | 6720 | LS TS | 2022-08-22 |  | 2022-08-27 | 2022-08-27 | 2022-09-05 | 2022-09-13 | 2022-10-03 | 2022-10-05 | Y1 | Kamruzzaman | Chest,Nk |  | D.Sapphire-2632 5 clr rub,Tigerly-1036 3 clr rub ,W.Alyssum-3052 2 clr rub |  | NFL 3 | Size Set Run | 1289 | 1278 | -11 | 0 | -6720 |  | 0 | 0 | 0 | 0 | -6720 | 0 | 9-8 | #N/A
BS-NMT | 23885 | 13217283 | 1992 | LS TS | 2022-08-25 |  | 2022-09-03 | 2022-09-03 | 2022-09-09 | 2022-09-19 | 2022-10-03 | 2022-10-05 | Y1 | Kamruzzaman | Chest,Nk |  | B.Blue-996,Buttercream-996 ll cmb 5 clr rub |  | NFL 3 | Size Set Run | 274 | 137 | -137 | 0 | -1992 |  | 0 | 0 | 0 | 0 | -1992 | 0 | 9-9 | #N/A
BS-ONS | 23925 | 22024756 | 2719 | SS TS | 2022-08-13 |  | 2022-08-16 | 2022-08-16 | 2022-08-22 | 2022-09-01 | 2022-09-16 | 2022-09-19 | Y2 | Shohag | MP |  | C.Dancer-1655,Teak-1080 bth cmb FR 1 clr Rub Big ArTW 1 slv 1 clr rub |  | NFL 3 | File Due | 1030 | 1030 | 0 | 0 | -2719 |  | 0 | 0 | 0 | 0 | -2719 | 0 | 9-1 | File Due
BS-ONS | 23924 | 22024742 | 5670 | SS TS | 2022-08-23 |  | 2022-08-16 | 2022-08-16 | 2022-08-23 | 2022-09-05 | 2022-09-16 | 2022-09-19 | Y2 | Shohag | Chest |  | Black-1978,B.White-2158,P.Ash-1558 all cmb Photo |  | NFL 3 | File Due | 1291 | 1277 | -14 | 0 | -5670 |  | 0 | 0 | 0 | 0 | -5670 | 0 | 9-2 | File Due
BS-NMT | 24009 | 13212477 | 8580 | LS TS | 2022-08-20 |  | 2022-08-23 | 2022-08-23 | 2022-09-01 | 2022-09-12 | 2022-10-03 | 2022-10-05 | Y2 | Tomal | Chest,Nk | Seq | Pink Yarrow-2145 only neck print and 4 clr seq,S.Verbena-2145 only neck print and 4 clr seq,GM-2145 1 clr rubber 2 clr seq,D.Sapphire-2145 1 clr rubber 2 clr seq |  | NFL 3 | File Due | 1472 | 1084 | -388 | 0 | -8580 |  | 0 | 0 | 0 | 0 | -8580 | 0 | 9-3 | #N/A
BS-NMT | 24008 | 13212466 | 7845 | [5 empty] | 2022-09-06 |  | 2022-10-03 | 2022-10-05 | Y2 | Tomal | Nk | Seq |  |  | NFL 3 | Need Cut | 1347 | 1342 | -5 | 1300 | -6545 |  | 2600 | 0 | -2600 | 0 | -7845 | 0 | 9-4
BS-NMT | 24012 | 13213141 | 3557 | LS TS | 2022-08-24 |  | 2022-09-01 | 2022-09-01 | 2022-09-07 | 2022-09-17 | 2022-10-03 | 2022-10-05 | Y2 | Tomal | MP |  | D.Sapphire-1969, Forest Biome-1588 both combo 1 slv 3 clr rubber, Upper chest 2 clr rubber, back part 4 clr rubber |  | NFL 3 | File Due | 705 | 704 | -1 | 0 | -3557 |  | 0 | 0 | 0 | 0 | -3557 | 0 | 9-5 | #N/A
BS-NMT | 24035 | 13213305 | 3936 | LS TS W All hem letuce | 2022-08-26 |  | 2022-09-02 | 2022-09-02 | 2022-09-08 | 2022-09-16 | 2022-09-30 | 2022-10-05 | Y2 | Shamoly | Nk | Chest | D.Sapphire-2256,Foxglove-1680 all cmb 2 clr emb |  | NFL 3 | CAD | 469 | 465 | -4 | 0 | -3936 |  | 0 | 0 | 0 | 0 | -3936 | 0 | 9-6 | #N/A
BS-NMT | 24033 | 13213291 | 1005 | LS TS W All hem letuce | 2022-08-25 |  | 2022-09-03 | 2022-09-03 | 2022-09-10 | 2022-09-19 | 2022-09-30 | 2022-10-05 | Y2 | Shamoly | Nk | Chest | D.Sapphire-1005 UC 2 clr emb |  | NFL 3 | CAD | 193 | 193 | 0 | 0 | -1005 |  | 0 | 0 | 0 | 0 | -1005 | 0 | 9-7 | #N/A
BS-NMT | 24030 | 13213222 | 1005 | LS TS W Cuff | 2022-08-27 |  | 2022-09-03 | 2022-09-03 | 2022-09-10 | 2022-09-19 | 2022-09-30 | 2022-10-05 | Y2 | Shamoly | Chest,Nk |  | W.Iron-1005 1 clr rub |  | NFL 3 | CAD | 215 | 213 | -2 | 0 | -1005 |  | 0 | 0 | 0 | 0 | -1005 | 0 | 9-8 | #N/A
BS-NMT | 23850 | 13212816 | 2148 | LS TS W Slv Cap gathering | 2022-08-24 |  | 2022-08-30 | 2022-08-30 | 2022-09-06 | 2022-09-15 | 2022-10-08 | 2022-10-12 | Y2 | Sadia | Chest,Nk |  | Buttercream-1713,Eventide-3486 all cmb 6 clr pig 1 clr glit |  | NFL 3 | File Due | 637 | 621 | -16 | 0 | -2148 |  | 0 | 0 | 0 | 0 | -2148 | 0 | 9-9 | #N/A
BS-NMT | 23876 | 13195885 | 8358 | Swt Legging | 2022-08-19 |  | 2022-08-22 | 2022-08-22 | 2022-08-29 | 2022-09-01 | 2022-09-19 | 2022-09-21 | Z | Kamruzzaman |  |  |  |  | NFL 3 | Cut Run | 1601 | 1568 | -33 | 8017 | -341 |  | 0 | 0 | 0 | 0 | -8358 | 8662 | 9-1 | #N/A
BS-NMT | 23883 | 13205791 | 8996 | Legging | 2022-08-13 | 2022-08-25 | 2022-08-27 | 2022-08-27 | 2022-09-05 | 2022-09-13 | 2022-10-03 | 2022-10-05 | Z | Kamruzzaman | Waist |  |  |  | NFL 3 | Cut Run | 1196 | 585 | -611 | 4617 | -4379 |  | 4573 | 4572 | -1 | 0 | -8996 | 0 | 9-2 | #N/A
BS-NMT | 24265 | 13180124 | 4080 | [5 empty] | 2022-09-03 |  | 2022-09-26 | 2022-09-28 | Z | Kamruzzaman | Waist |  |  |  | NFL 3 | Need Cut | 0 | 0 | 0 | 0 | -4080 |  | 0 | 0 | 0 | 0 | -4080 | 0 | 9-3 | #N/A
BS-NMT | 23790 | 13212742 | 6986 | Legging W Lace at cuff | 2022-09-03 |  | 2022-09-08 | 2022-09-08 | 2022-09-15 | 2022-09-19 | 2022-10-10 | 2022-10-12 | Z | Mahmud | Waist |  |  |  | NFL 3 | File Due | 466 | 464 | -2 | 0 | -6986 |  | 0 | 0 | 0 | 0 | -6986 | 0 | 9-4 | #N/A
BS-NMT | 23897 | 13212535 | 2766 | Legging | 2022-08-13 | 2022-08-29 | 2022-09-03 | 2022-09-03 | 2022-09-10 | 2022-09-19 | 2022-10-10 | 2022-10-12 | Z | Kamruzzaman | Waist |  |  |  | NFL 3 | File Due | 274 | 0 | -274 | 0 | -2766 |  | 0 | 0 | 0 | 0 | -2766 | 0 | 9-5 | #N/A
BS-NMT | 23888 | 13212336 | 1896 | Legging | 2022-08-13 | 2022-08-29 | 2022-09-03 | 2022-09-03 | 2022-09-10 | 2022-09-20 | 2022-10-01 | 2022-10-05 | Z | Kamruzzaman | Waist |  |  |  | NFL 3 | File Due | 289 | 0 | -289 | 0 | -1896 |  | 0 | 0 | 0 | 0 | -1896 | 0 | 9-6 | #N/A
BS-NMT | 23890 | 13212532 | 2160 | Legging | 2022-09-03 |  | 2022-09-09 | 2022-09-09 | 2022-09-16 | 2022-09-20 | 2022-10-10 | 2022-10-12 | Z | Kamruzzaman | Waist |  |  |  | NFL 3 | File Due | 261 | 0 | -261 | 0 | -2160 |  | 0 | 0 | 0 | 0 | -2160 | 0 | 9-7 | #N/A
BS-NMT | 24013 | 13213143 | 2121 | SS TS | 2022-08-03 |  | 2022-08-24 | 2022-08-24 | 2022-09-01 | 2022-09-10 | 2022-10-03 |  | Z | Tomal | Chest,Nk |  | GM-1305,L.Wreath-816 both combo 6 clr rubber |  | NFL 3 | File Due | 301 | 185 | -116 | 0 | -2121 |  | 0 | 0 | 0 | 0 | -2121 | 0 | 9-8 | #N/A
BS-NMT | 24007 | 13208644 | 6000 | LS HNK TS Rib | 2022-08-10 |  | 2022-09-02 | 2022-09-02 | 2022-09-09 | 2022-09-17 | 2022-10-03 |  | Z | Tomal | Nk |  |  |  | NFL 3 | File Due | 980 | 321 | -659 | 0 | -6000 |  | 0 | 0 | 0 | 0 | -6000 | 0 | 9-9 | #N/A
BS-ONL | 21814 4th | 15267765 | 17808 | LS Hoody Jacket | 2022-08-16 |  | 2022-08-17 | 2022-08-17 | 2022-08-23 | 2022-09-01 | 2022-10-17 | 2022-11-09 | ZA | Imran |  | Chest | Black MULTICOL LOGO-1140, Blushing Bride MULTICOL LOGO-3300,M.Green MULTICOL LOGO-8334, R.Smoke MULTICOL LOGO-1827 all cmb 4clr thrd letter EMB 2000 stc, Hole Emb | NOOS | NFL 3 | Cut Run | 7117 | 1634 | -5483 | 3348 | -14460 |  | 3277 | 3277 | 0 | 0 | -17808 | 0 | 9-2 | Ok
BS-NMT | 23787 | 13212624 | 4493 | LS Body W CLR Lace & BK PLKT,BTN | 2022-08-30 |  | 2022-09-03 | 2022-09-03 | 2022-09-09 | 2022-09-17 | 2022-10-11 | 2022-10-12 | ZA | Mahmud | Nk |  |  |  | NFL 3 | Cut Run | 341 | 186 | -155 | 2480 | -2013 |  | 2480 | 0 | -2480 | 0 | -4493 | 0 | 9-4 | Lace
BS-NMT | 23789 | 13212741 | 4493 | LS Body W CLR Lace & BK PLKT,BTN | 2022-08-26 |  | 2022-09-01 | 2022-09-01 | 2022-09-08 | 2022-09-16 | 2022-10-10 | 2022-10-12 | ZA | Mahmud | Nk |  |  |  | NFL 3 |  | 407 | 0 | -407 | 0 | -4493 |  | 0 | 0 | 0 | 0 | -4493 | 0 | 9-6
BS-NMT | 24036 | 13213329 13217541 | 26157 | SS TS | 2022-08-11 |  | 2022-08-13 | 2022-08-13 | 2022-08-22 | 2022-09-01 | 2022-09-30 | 2022-10-05 | ZA1 | Shamoly | Chest,Nk |  | Cyclamen--7325 4 clr rub 1 clr glit,D.Sapphire-7480 2 clr rub 1clr glit,Jet Stream-7739 3 clr rub 1 clr glit, Puple heather-3613 5 clr rub 1 clr glit |  | NFL 3 | CAD | 1896 | 1878 | -18 | 0 | -26157 |  | 0 | 0 | 0 | 0 | -26157 | 0 | 9-1 | Price Sticker due
BS-NMT | 23060 | 13211097 | 1956 | C & S LS Hoody | 2022-07-26 |  | 2022-08-05 | 2022-08-04 | 2022-08-10 | 2022-08-17 | 2022-09-05 | 2022-09-07 | ZA | Tomal | Chest |  | Turtledove-1956 2 clr rub |  | NFL 3 | File Due | 1086 | 1086 | 0 | 0 | -1956 |  | 0 | 0 | 0 | 0 | -1956 | 0 | 9-1 | Ok
BS-NMT | 24034 | 13213295 | 21836 | SS TS | 2022-08-20 | - | 2022-08-22 | 2022-08-22 | 2022-08-29 | 2022-09-10 | 2022-09-30 | 2022-10-05 | ZA1 | Shamoly | Chest,Nk |  | Cyclamen--5079 2 clr rub 1 clr glit,D.Sapphire-3615 2 clr rub 1 clr glit, Jet stram-4608 2 clr rub 1 clr glit, Purple heather-3988 4 clr rub 1 clr glit |  | NFL 3 | CAD | 1815 | 1796 | -19 | 0 | -21836 |  | 0 | 0 | 0 | 0 | -21836 | 0 | 9-2 | #N/A
GBX ( New Look) | 24073 |  | 3360 | SS POlo Shirt W PKT Tipped/YD CLR,Cuff | 2022-08-31 |  | 2022-09-05 | 2022-09-05 | 2022-09-13 | 2022-09-16 | 2022-10-01 | 2022-10-02 | ZA | Morad |  |  |  |  | NFL 3 |  | 777 | 0 | -777 | 0 | -3360 |  | 0 | 0 | 0 | 0 | -3360 | 0 | 9-3

## Sheet2 (hidden)
Row Labels | Sum of Order Qty
Grand Total
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Line Execution (hidden)
Sewing Line Plan Execution
Line | Job | Style | Item | No of M/C | O.Qty | Plan qty | Fab Req. | Fab Del. | Fab Bal. | Pre Production Status | Present Status | Cutting Qty | Cutting Bal. | Print Position | Embriodary Position | Print & Emb Description | Ex-factory Date | Merchant Name | Trims & Accessories Status
A | 23366 | [7 empty] | 0 |  |  |  | 0
A | 24160 | [7 empty] | 0 |  |  |  | 0
A | 24164 | [7 empty] | 0 |  |  |  | 0
A | 23728 | [7 empty] | 0 |  |  |  | 0
B | 24084 | [7 empty] | 0 |  |  |  | 0
B | 23678 | [7 empty] | 0 |  |  |  | 0
B | 23679 | [7 empty] | 0 |  |  |  | 0
B | 24062 | [7 empty] | 0 |  |  |  | 0
C1 | 23932 2nd | [7 empty] | 0 |  |  |  | 0
C1 | 23688 | [7 empty] | 0 |  |  |  | 0
C1 | 23689 | [7 empty] | 0 |  |  |  | 0
C2 | 24120 | [7 empty] | 0 |  |  |  | 0
C2 | 23299 | [7 empty] | 0 |  |  |  | 0
C2 | 21833 5th | [7 empty] | 0 |  |  |  | 0
D1 | 23979 | [7 empty] | 0 |  |  |  | 0
D1 | 23980 | [7 empty] | 0 |  |  |  | 0
D1 | 23981 | [7 empty] | 0 |  |  |  | 0
D1 | 24079 1st | [7 empty] | 0 |  |  |  | 0
D1 | 24080 | [7 empty] | 0 |  |  |  | 0
D1 | 24001 | [7 empty] | 0 |  |  |  | 0
D1 | 23688 | [7 empty] | 0 |  |  |  | 0
D1 | 23689 | [7 empty] | 0 |  |  |  | 0
D2 | 24031 | [7 empty] | 0 |  |  |  | 0
D2 | 23331 | [7 empty] | 0 |  |  |  | 0
E | 19904 4th | [7 empty] | 0 |  |  |  | 0
E | 23779 | [7 empty] | 0 |  |  |  | 0
E | 24162 | [7 empty] | 0 |  |  |  | 0
E | 24163 | [7 empty] | 0 |  |  |  | 0
E | 24168 | [7 empty] | 0 |  |  |  | 0
E | 24167 | [7 empty] | 0 |  |  |  | 0
F | 23301 2nd | [7 empty] | 0 |  |  |  | 0
F | 24121 | [7 empty] | 0 |  |  |  | 0
F | 24122 | [7 empty] | 0 |  |  |  | 0
F | 23927 | [7 empty] | 0 |  |  |  | 0
G | 23988 | [7 empty] | 0 |  |  |  | 0
G | 23990 | [7 empty] | 0 |  |  |  | 0
G | 23898 | [7 empty] | 0 |  |  |  | 0
G | 23943 | [7 empty] | 0 |  |  |  | 0
G | 23945 | [7 empty] | 0 |  |  |  | 0
G | 22696 3rd | [7 empty] | 0 |  |  |  | 0
H1 | 21813 3rd | [7 empty] | 0 |  |  |  | 0
H1 | 23300 | [7 empty] | 0 |  |  |  | 0
H1 | 23298 | [7 empty] | 0 |  |  |  | 0
H2 | 22983 | [7 empty] | 0 |  |  |  | 0
H2 | 23236 | [7 empty] | 0 |  |  |  | 0
H2 | 23751 | [7 empty] | 0 |  |  |  | 0
H2 | 23938 | [7 empty] | 0 |  |  |  | 0
J | 22978 | [7 empty] | 0 |  |  |  | 0
J | 23969 | [7 empty] | 0 |  |  |  | 0
J | 22970 | [7 empty] | 0 |  |  |  | 0
J | 22968 | [7 empty] | 0 |  |  |  | 0
J | 23816 | [7 empty] | 0 |  |  |  | 0
J | 23818 | [7 empty] | 0 |  |  |  | 0
J | 23785 | [7 empty] | 0 |  |  |  | 0
J | 23781 | [7 empty] | 0 |  |  |  | 0
J | 23729 | [7 empty] | 0 |  |  |  | 0
K1 | 23947 | [7 empty] | 0 |  |  |  | 0
K1 | 23948 | [7 empty] | 0 |  |  |  | 0
K1 | 23946 | [7 empty] | 0 |  |  |  | 0
K1 | 23975 | [7 empty] | 0 |  |  |  | 0
K1 | 23944 | [7 empty] | 0 |  |  |  | 0
K1 | 23973 | [7 empty] | 0 |  |  |  | 0
K1 | 23978 | [7 empty] | 0 |  |  |  | 0
K1 | 24061 | [7 empty] | 0 |  |  |  | 0
K1 | 23335 | [7 empty] | 0 |  |  |  | 0
K1 | 23344 | [7 empty] | 0 |  |  |  | 0
K2 | 24071 | [7 empty] | 0 |  |  |  | 0
K2 | 24072 | [7 empty] | 0 |  |  |  | 0
K2 | 23963 | [7 empty] | 0 |  |  |  | 0
K2 | 24086 | [7 empty] | 0 |  |  |  | 0
L | 23831 | [7 empty] | 0 |  |  |  | 0
L | 23832 | [7 empty] | 0 |  |  |  | 0
L | 23820 | [7 empty] | 0 |  |  |  | 0
L | 23821 | [7 empty] | 0 |  |  |  | 0
L | 23783 | [7 empty] | 0 |  |  |  | 0
L | 23828 | [7 empty] | 0 |  |  |  | 0
L | 23985 | [7 empty] | 0 |  |  |  | 0
L | 23770 | [7 empty] | 0 |  |  |  | 0
M1 | 24102 | [7 empty] | 0 |  |  |  | 0
M1 | 23834 | [7 empty] | 0 |  |  |  | 0
M1 | 23833 | [7 empty] | 0 |  |  |  | 0
M1 | 23822 | [7 empty] | 0 |  |  |  | 0
M1 | 23823 | [7 empty] | 0 |  |  |  | 0
M1 | 23782 | [7 empty] | 0 |  |  |  | 0
M1 | 23777 | [7 empty] | 0 |  |  |  | 0
M1 | 27776 | [7 empty] | 0 |  |  |  | 0
M1 | 23844 | [7 empty] | 0 |  |  |  | 0
M1 | 23842 | [7 empty] | 0 |  |  |  | 0
M1 | 23824 | [7 empty] | 0 |  |  |  | 0
M2 | 24102 | [7 empty] | 0 |  |  |  | 0
N1 | 23774 | [7 empty] | 0 |  |  |  | 0
N1 | 22945 | [7 empty] | 0 |  |  |  | 0
N1 | 22946 | [7 empty] | 0 |  |  |  | 0
N1 | 22947 | [7 empty] | 0 |  |  |  | 0
N1 | 22976 | [7 empty] | 0 |  |  |  | 0
N1 | 22977 | [7 empty] | 0 |  |  |  | 0
N1 | 23690 | [7 empty] | 0 |  |  |  | 0
N1 | 23314 | [7 empty] | 0 |  |  |  | 0
N2 | 23772 | [7 empty] | 0 |  |  |  | 0
N2 | 23163 | [7 empty] | 0 |  |  |  | 0
N2 | 23192 | [7 empty] | 0 |  |  |  | 0
N2 | 23166 | [7 empty] | 0 |  |  |  | 0
N2 | 23974 | [7 empty] | 0 |  |  |  | 0
N2 | 23203 | [7 empty] | 0 |  |  |  | 0
N2 | 23210 | [7 empty] | 0 |  |  |  | 0
N2 | 23690 | [7 empty] | 0 |  |  |  | 0
N2 | 23314 | [7 empty] | 0 |  |  |  | 0
O | 22945 | [7 empty] | 0 |  |  |  | 0
O | 22946 | [7 empty] | 0 |  |  |  | 0
O | 22947 | [7 empty] | 0 |  |  |  | 0
O | 22979 | [7 empty] | 0 |  |  |  | 0
O | 22980 | [7 empty] | 0 |  |  |  | 0
O | 22981 | [7 empty] | 0 |  |  |  | 0
O | 22968 | [7 empty] | 0 |  |  |  | 0
O | 23771 | [7 empty] | 0 |  |  |  | 0
P | 23189 | [7 empty] | 0 |  |  |  | 0
P | 23171 | [7 empty] | 0 |  |  |  | 0
P | 23206 | [7 empty] | 0 |  |  |  | 0
P | 23205 | [7 empty] | 0 |  |  |  | 0
P | 23840 | [7 empty] | 0 |  |  |  | 0
P | 23780 | [7 empty] | 0 |  |  |  | 0
P | 23837 | [7 empty] | 0 |  |  |  | 0
P | 23827 | [7 empty] | 0 |  |  |  | 0
P | 23826 | [7 empty] | 0 |  |  |  | 0
P | 23839 | [7 empty] | 0 |  |  |  | 0
Q | 23190 | [7 empty] | 0 |  |  |  | 0
Q | 23244 | [7 empty] | 0 |  |  |  | 0
Q | 23362 | [7 empty] | 0 |  |  |  | 0
Q | 23245 | [7 empty] | 0 |  |  |  | 0
Q | 23358 | [7 empty] | 0 |  |  |  | 0
R | 23200 | [7 empty] | 0 |  |  |  | 0
R | 23204 | [7 empty] | 0 |  |  |  | 0
R | 23274 | [7 empty] | 0 |  |  |  | 0
R | 23360 | [7 empty] | 0 |  |  |  | 0
R | 23208 | [7 empty] | 0 |  |  |  | 0
R | 23209 | [7 empty] | 0 |  |  |  | 0
R | 23361 | [7 empty] | 0 |  |  |  | 0
S | 24101 | [7 empty] | 0 |  |  |  | 0
S | 24127 | [7 empty] | 0 |  |  |  | 0
S | 24128 | [7 empty] | 0 |  |  |  | 0
S | 23841 | [7 empty] | 0 |  |  |  | 0
S | 23830 | [7 empty] | 0 |  |  |  | 0
S | 23835 | [7 empty] | 0 |  |  |  | 0
S | 23843 | [7 empty] | 0 |  |  |  | 0
S | 23784 | [7 empty] | 0 |  |  |  | 0
S | 23775 | [7 empty] | 0 |  |  |  | 0
S | 24011 | [7 empty] | 0 |  |  |  | 0
S | 23889 | [7 empty] | 0 |  |  |  | 0
T | 24108 | [7 empty] | 0 |  |  |  | 0
T | 23791 | [7 empty] | 0 |  |  |  | 0
T | 23792 | [7 empty] | 0 |  |  |  | 0
T | 23793 | [7 empty] | 0 |  |  |  | 0
T | 23794 | [7 empty] | 0 |  |  |  | 0
T | 23795 | [7 empty] | 0 |  |  |  | 0
T | 23694 2nd | [7 empty] | 0 |  |  |  | 0
T | 23796 | [7 empty] | 0 |  |  |  | 0
T | 23797 | [7 empty] | 0 |  |  |  | 0
T | 23853 | [7 empty] | 0 |  |  |  | 0
U | 23674 | [7 empty] | 0 |  |  |  | 0
U | 24166 | [7 empty] | 0 |  |  |  | 0
U | 23852 | [7 empty] | 0 |  |  |  | 0
U | 24006 | [7 empty] | 0 |  |  |  | 0
U | 23891 | [7 empty] | 0 |  |  |  | 0
U | 23798 | [7 empty] | 0 |  |  |  | 0
V | 23918 | [7 empty] | 0 |  |  |  | 0
V | 23919 | [7 empty] | 0 |  |  |  | 0
V | 23923 | [7 empty] | 0 |  |  |  | 0
V | 24161 | [7 empty] | 0 |  |  |  | 0
V | 24165 | [7 empty] | 0 |  |  |  | 0
V | 24169 | [7 empty] | 0 |  |  |  | 0
V | 24170 | [7 empty] | 0 |  |  |  | 0
V | 23851 | [7 empty] | 0 |  |  |  | 0
V | 24029 | [7 empty] | 0 |  |  |  | 0
V | 24010 | [7 empty] | 0 |  |  |  | 0
V | 24014 | [7 empty] | 0 |  |  |  | 0
W | 23697 1st | [7 empty] | 0 |  |  |  | 0
W | 23697 2nd | [7 empty] | 0 |  |  |  | 0
W | 23799 | [7 empty] | 0 |  |  |  | 0
W | 23800 | [7 empty] | 0 |  |  |  | 0
W | 23795 | [7 empty] | 0 |  |  |  | 0
W | 23794 | [7 empty] | 0 |  |  |  | 0
W | 23854 | [7 empty] | 0 |  |  |  | 0
W | 24028 | [7 empty] | 0 |  |  |  | 0
W | 24037 | [7 empty] | 0 |  |  |  | 0
X | 23674 | [7 empty] | 0 |  |  |  | 0
X | 23895 | [7 empty] | 0 |  |  |  | 0
X | 23880 | [7 empty] | 0 |  |  |  | 0
Y1 | 23917 | [7 empty] | 0 |  |  |  | 0
Y1 | 19398 5th | [7 empty] | 0 |  |  |  | 0
Y1 | 23886 | [7 empty] | 0 |  |  |  | 0
Y1 | 23877 | [7 empty] | 0 |  |  |  | 0
Y1 | 23879 | [7 empty] | 0 |  |  |  | 0
Y1 | 23878 | [7 empty] | 0 |  |  |  | 0
Y1 | 23887 | [7 empty] | 0 |  |  |  | 0
Y1 | 23881 | [7 empty] | 0 |  |  |  | 0
Y1 | 23885 | [7 empty] | 0 |  |  |  | 0
Y2 | 23925 | [7 empty] | 0 |  |  |  | 0
Y2 | 23924 | [7 empty] | 0 |  |  |  | 0
Y2 | 24009 | [7 empty] | 0 |  |  |  | 0
Y2 | 24008 | [7 empty] | 0 |  |  |  | 0
Y2 | 24012 | [7 empty] | 0 |  |  |  | 0
Y2 | 24035 | [7 empty] | 0 |  |  |  | 0
Y2 | 24033 | [7 empty] | 0 |  |  |  | 0
Y2 | 24030 | [7 empty] | 0 |  |  |  | 0
Y2 | 23850 | [7 empty] | 0 |  |  |  | 0
[9 empty] | 0 |  |  |  | 0
Z | 23876 | [7 empty] | 0 |  |  |  | 0
Z | 23883 | [7 empty] | 0 |  |  |  | 0
Z | 24265 | [7 empty] | 0 |  |  |  | 0
Z | 23790 | [7 empty] | 0 |  |  |  | 0
Z | 23897 | [7 empty] | 0 |  |  |  | 0
Z | 23888 | [7 empty] | 0 |  |  |  | 0
Z | 23890 | [7 empty] | 0 |  |  |  | 0
Z | 24013 | [7 empty] | 0 |  |  |  | 0
Z | 24007 | [7 empty] | 0 |  |  |  | 0
ZA | 23060 | [7 empty] | 0 |  |  |  | 0
ZA | 21814 4th | [7 empty] | 0 |  |  |  | 0
ZA | 24073 | [7 empty] | 0 |  |  |  | 0
ZA | 23787 | [7 empty] | 0 |  |  |  | 0
ZA | 23789 | [7 empty] | 0 |  |  |  | 0
ZA1 | 24036 | [7 empty] | 0 |  |  |  | 0
ZA1 | 24034 | [7 empty] | 0 |  |  |  | 0